## Read_Me
GU Zhan (Sam)
17 March 2019
Convert to NLP-Solver to support iss-vm

## Project_Facts_(User_Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula

Vlookup Index	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60	61	62	63
					Required Effort (Person-Day)					Required Effort (Person-Day)					Required Effort (Person-Day)					Required Effort (Person-Day)					Required Effort (Person-Day)					Required Effort (Person-Day)
				Resource Allocation / Full Time Employee (FTEs)					Plan Phase	Plan Phase	Plan Total / (Person-Day)	Plan Total / (Calendar-Day)		Development Phase	Development Phase	Development Total / (Person-Day)	Development Total / (Calendar-Day)		SIT Phase	SIT Phase	SIT Total / (Person-Day)	SIT Total / (Calendar-Day)		UAT Phase	UAT Phase	UAT Total / (Person-Day)	UAT Total / (Calendar-Day)		NFT Phase	NFT Phase	NFT Total / (Person-Day)	NFT Total / (Calendar-Day)		Production Phase	Production Phase	Production Total / (Person-Day)	Production Total / (Calendar-Day)					Benchmark Reference / (Theoretically Perfect Project Make-Span without constraints)
Project Name		Code Base Version		Knowledge / Engineer	Software / Engineer	Project Manager / (Future work)	Admin / (Future work)		Knowledge / Engineer	Software / Engineer				Knowledge / Engineer	Software / Engineer				Knowledge / Engineer	Software / Engineer				Knowledge / Engineer	Software / Engineer				Knowledge / Engineer	Software / Engineer				Knowledge / Engineer	Software / Engineer				Total Project Effort / (Person-Days)	Total Project Span / (Calendar-Days)	Project Cost / (Total Project Effort x $500/Person-Day)		Project Priority		Total Project Effort - KE / (Person-Days)	Total Project Effort - SE / (Person-Days)		Perfect Project Span - KE / (Calendar-Days)	Perfect Project Span - SE / (Calendar-Days)	Perfect Project Span / (Calendar-Days)
Project-A01		v001		0.30	1.53				17.00	17.76	34.76	56.85		4.08	74.00	78.08	48.21		4.08	17.76	21.84	13.64		4.08	17.76	21.84	13.64		4.08	17.76	21.84	13.64		4.08	17.76	21.84	13.64		200.20	159.64	$100,100		0.06		37.40	162.80		125.08	106.07	125.08
Project-A02		v002		0.33	1.26				15.00	19.20	34.20	44.87		3.60	80.00	83.60	63.72		3.60	19.20	22.80	15.29		3.60	19.20	22.80	15.29		3.60	19.20	22.80	15.29		3.60	19.20	22.80	15.29		209.00	169.77	$104,500		0.06		33.00	176.00		98.72	140.19	140.19					E
Project-A03		v003		0.63	2.14				16.00	6.48	22.48	25.32		3.84	27.00	30.84	12.62		3.84	6.48	10.32	6.08		3.84	6.48	10.32	6.08		3.84	6.48	10.32	6.08		3.84	6.48	10.32	6.08		94.60	62.25	$47,300		0.03		35.20	59.40		55.71	27.77	55.71					N
Project-A04		v004		0.68	1.69				35.00	4.32	39.32	51.73		8.40	18.00	26.40	12.42		8.40	4.32	12.72	12.42		8.40	4.32	12.72	12.42		8.40	4.32	12.72	12.42		8.40	4.32	12.72	12.42		116.60	113.81	$58,300		0.03		77.00	39.60		113.81	23.46	113.81					D
Project-A05		v002		0.29	1.52				6.00	19.20	25.20	20.83		1.44	80.00	81.44	52.52		1.44	19.20	20.64	12.60		1.44	19.20	20.64	12.60		1.44	19.20	20.64	12.60		1.44	19.20	20.64	12.60		189.20	123.77	$94,600		0.05		13.20	176.00		45.83	115.54	115.54
Project-A06		v003		0.69	1.85				52.00	10.56	62.56	75.23		12.48	44.00	56.48	23.83		12.48	10.56	23.04	18.06		12.48	10.56	23.04	18.06		12.48	10.56	23.04	18.06		12.48	10.56	23.04	18.06		211.20	171.28	$105,600		0.06		114.40	96.80		165.50	52.42	165.50					O
Project-A07		v005		0.50	3.79				93.00	19.92	112.92	187.45		22.32	83.00	105.32	44.99		22.32	19.92	42.24	44.99		22.32	19.92	42.24	44.99		22.32	19.92	42.24	44.99		22.32	19.92	42.24	44.99		387.20	412.38	$193,600		0.11		204.60	182.60		412.38	48.16	412.38					F
Project-A08		v006		0.37	1.06				5.00	2.64	7.64	13.67		1.20	11.00	12.20	10.37		1.20	2.64	3.84	3.28		1.20	2.64	3.84	3.28		1.20	2.64	3.84	3.28		1.20	2.64	3.84	3.28		35.20	37.17	$17,600		0.01		11.00	24.20		30.08	22.82	30.08
Project-A09		v003		0.51	1.53				49.00	20.64	69.64	95.41		11.76	86.00	97.76	56.35		11.76	20.64	32.40	22.90		11.76	20.64	32.40	22.90		11.76	20.64	32.40	22.90		11.76	20.64	32.40	22.90		297.00	243.36	$148,500		0.08		107.80	189.20		209.91	123.97	209.91					T
Project-A10		v001		0.63	1.20				36.00	20.88	56.88	57.17		8.64	87.00	95.64	72.59		8.64	20.88	29.52	17.42		8.64	20.88	29.52	17.42		8.64	20.88	29.52	17.42		8.64	20.88	29.52	17.42		270.60	199.44	$135,300		0.08		79.20	191.40		125.77	159.69	159.69					H
Project-A11		v002		1.20	2.24				63.00	19.20	82.20	52.52		15.12	80.00	95.12	35.72		15.12	19.20	34.32	12.60		15.12	19.20	34.32	12.60		15.12	19.20	34.32	12.60		15.12	19.20	34.32	12.60		314.60	138.66	$157,300		0.09		138.60	176.00		115.54	78.58	115.54					I
Project-A12		v004		0.46	1.40				65.00	21.84	86.84	142.56		15.60	91.00	106.60	64.95		15.60	21.84	37.44	34.21		15.60	21.84	37.44	34.21		15.60	21.84	37.44	34.21		15.60	21.84	37.44	34.21		343.20	344.36	$171,600		0.10		143.00	200.20		313.62	142.90	313.62					S
Project-A13		v007		0.62	1.30				96.00	9.60	105.60	156.00		23.04	40.00	63.04	37.44		23.04	9.60	32.64	37.44		23.04	9.60	32.64	37.44		23.04	9.60	32.64	37.44		23.04	9.60	32.64	37.44		299.20	343.20	$149,600		0.08		211.20	88.00		343.20	67.70	343.20
Project-A14		v006		0.46	0.56				39.00	12.72	51.72	85.54		9.36	53.00	62.36	93.88		9.36	12.72	22.08	22.53		9.36	12.72	22.08	22.53		9.36	12.72	22.08	22.53		9.36	12.72	22.08	22.53		202.40	269.54	$101,200		0.06		85.80	116.60		188.19	206.53	206.53					W
Project-A15		v008		0.31	0.59				72.00	23.76	95.76	234.04		17.28	99.00	116.28	167.45		17.28	23.76	41.04	56.17		17.28	23.76	41.04	56.17		17.28	23.76	41.04	56.17		17.28	23.76	41.04	56.17		376.20	626.16	$188,100		0.11		158.40	217.80		514.88	368.39	514.88					O
					R
					K
		Average		0.53	1.58				43.93	15.25	59.18	86.61		10.54	63.53	74.08	53.14		10.54	15.25	25.79	21.98		10.54	15.25	25.79	21.98		10.54	15.25	25.79	21.98		10.54	15.25	25.79	21.98		236.43	227.65	$118,213		0.07		96.65	139.77	Average	190.55	112.28	201.44					S
		Total		7.96	23.66				659.00	228.72	887.72	1299.18		158.16	953.00	1111.16	797.06		158.16	228.72	386.88	329.64		158.16	228.72	386.88	329.64		158.16	228.72	386.88	329.64		158.16	228.72	386.88	329.64		3546.40	3414.79	$1,773,200		1.00		1449.80	2096.60	Total	2858.21	1684.21	3021.66					H
					E
		Available FTE		8	24					E
					T

		END	OF	THIS	WORKSHEET

## Project_Release_Optimizer_(GA)
Legend:		Fitness Control Dashboard
Chromosome		Fitness Breakdown		Fitness Priority	Formula		Value					Benchmark
Constraint (Hard)		Proj Make-Span (Overall)		Medium	=AW15		1213.38		<- To shorten entire projects span (ALL projects)					Perfect AVG Project Span
Constraint (Soft)		Average Proj Make-Span (Individual)		Medium	=AV32		476.59		<- To shorten average individual project span				<---------->	201.444118006
Fitness		Priority-Weighted Plan-Lead		Low	=AT32		189.05		<- To schedule important projects to start earlier
User Inputs		Code-Base Violation x Weight		High	='Code Base Violation Constraint'!E13*20		0.00		<- Heuristic Weight (Hard -> Soft constraint):			50
Formula		Integrated Fitness - To Min()		N.A.	=SUM(I4:I7)		1879.02		<- To Minimize
		Code-Base constraint satisfied ?		TRUE

Vlookup Index	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	38	39	49	50	51	52	53	54	55	56	57	58	59	60	61	62

		Resource Allocation / Full Time Employee (FTEs)					Plan Phase (Calendar-Day)				Development Phase (Calendar-Day)				SIT Phase (Calendar-Day)				UAT Phase (Calendar-Day)				NFT Phase (Calendar-Day)				Prod Phase (Calendar-Day)					Fitness - Lead / Idle Time (Days) prior to:					Fitness - Project Make-Sapn (Days) / (Without Plan-Lead)			Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name		Knowledge / Engineer	Software / Engineer	Project Manager / (Future work)	Admin / (Future work)		Initial Date		Lead prior to Plan / (Calendar-Day)	Start Date	End Date		Lead prior to Development / (Calendar-Day)	Start Date	End Date		Lead prior to SIT / (Calendar-Day)	Start Date	End Date		Lead prior to UAT / (Calendar-Day)	Start Date	End Date		Lead prior to NFT / (Calendar-Day)	Start Date	End Date		Lead prior to Prod / (Calendar-Day)	Start Date	End Date		Code Base Version		Project Priority		Plan	Development	SIT	UAT	NFT	Prod	Total	Priority-Weighted Plan-Lead		Individual	Overall		Refer to worksheet: Code Base Violation Constraint
Project-A01		0.30	1.53				01-Jan-2014		14	16-Jan-2014	13-Mar-2014		0	14-Mar-2014	02-May-2014		0	03-May-2014	16-May-2014		4	21-May-2014	04-Jun-2014		17	22-Jun-2014	05-Jul-2014		32	07-Aug-2014	21-Aug-2014		v001		0.06		14	0	0	4	17	32	67	11.85		217.64	1213.38					E
Project-A02		0.33	1.26				01-Jan-2014		335	03-Dec-2014	16-Jan-2015		0	17-Jan-2015	22-Mar-2015		0	23-Mar-2015	07-Apr-2015		13	21-Apr-2015	07-May-2015		354	26-Apr-2016	11-May-2016		1	13-May-2016	28-May-2016		v002		0.06		335	0	0	13	354	1	703	296.14		542.77					N
Project-A03		0.63	2.14				01-Jan-2014		12	14-Jan-2014	08-Feb-2014		0	09-Feb-2014	21-Feb-2014		0	22-Feb-2014	01-Mar-2014		143	23-Jul-2014	29-Jul-2014		109	16-Nov-2014	22-Nov-2014		45	07-Jan-2015	13-Jan-2015		v003		0.03		12	0	0	143	109	45	309	4.80		364.25					D
Project-A04		0.68	1.69				01-Jan-2014		129	11-May-2014	01-Jul-2014		0	02-Jul-2014	15-Jul-2014		0	16-Jul-2014	28-Jul-2014		72	09-Oct-2014	21-Oct-2014		129	28-Feb-2015	13-Mar-2015		9	23-Mar-2015	04-Apr-2015		v004		0.03		129	0	0	72	129	9	339	63.62		328.81
Project-A05		0.29	1.52				01-Jan-2014		14	16-Jan-2014	05-Feb-2014		0	06-Feb-2014	31-Mar-2014		0	01-Apr-2014	13-Apr-2014		363	12-Apr-2015	25-Apr-2015		160	03-Oct-2015	16-Oct-2015		37	23-Nov-2015	05-Dec-2015		v002		0.05		14	0	0	363	160	37	574	11.20		688.77					O
Project-A06		0.69	1.85				01-Jan-2014		314	12-Nov-2014	26-Jan-2015		0	27-Jan-2015	20-Feb-2015		0	21-Feb-2015	11-Mar-2015		117	07-Jul-2015	25-Jul-2015		165	07-Jan-2016	25-Jan-2016		0	26-Jan-2016	13-Feb-2016		v003		0.06		314	0	0	117	165	0	596	280.50		458.28					F
Project-A07		0.50	3.79				01-Jan-2014		355	23-Dec-2014	28-Jun-2015		0	29-Jun-2015	13-Aug-2015		0	14-Aug-2015	28-Sep-2015		360	23-Sep-2016	07-Nov-2016		18	26-Nov-2016	10-Jan-2017		66	18-Mar-2017	02-May-2017		v005		0.11		355	0	0	360	18	66	799	581.39		861.38
Project-A08		0.37	1.06				01-Jan-2014		3	05-Jan-2014	18-Jan-2014		0	19-Jan-2014	30-Jan-2014		0	31-Jan-2014	03-Feb-2014		6	10-Feb-2014	13-Feb-2014		28	14-Mar-2014	17-Mar-2014		2	20-Mar-2014	24-Mar-2014		v006		0.01		3	0	0	6	28	2	39	0.45		78.17					T
Project-A09		0.51	1.53				01-Jan-2014		15	17-Jan-2014	22-Apr-2014		0	23-Apr-2014	18-Jun-2014		0	19-Jun-2014	12-Jul-2014		39	21-Aug-2014	13-Sep-2014		45	29-Oct-2014	21-Nov-2014		21	13-Dec-2014	05-Jan-2015		v003		0.08		15	0	0	39	45	21	120	18.84		353.36					H
Project-A10		0.63	1.20				01-Jan-2014		4	06-Jan-2014	04-Mar-2014		0	05-Mar-2014	16-May-2014		0	17-May-2014	04-Jun-2014		4	09-Jun-2014	26-Jun-2014		3	30-Jun-2014	18-Jul-2014		61	18-Sep-2014	05-Oct-2014		v001		0.08		4	0	0	4	3	61	72	4.58		272.44					I
Project-A11		1.20	2.24				01-Jan-2014		210	31-Jul-2014	21-Sep-2014		0	22-Sep-2014	28-Oct-2014		0	29-Oct-2014	10-Nov-2014		265	03-Aug-2015	16-Aug-2015		38	24-Sep-2015	07-Oct-2015		11	19-Oct-2015	31-Oct-2015		v002		0.09		210	0	0	265	38	11	524	279.44		457.66					S
Project-A12		0.46	1.40				01-Jan-2014		340	08-Dec-2014	29-Apr-2015		0	30-Apr-2015	04-Jul-2015		0	05-Jul-2015	08-Aug-2015		208	04-Mar-2016	07-Apr-2016		33	11-May-2016	15-Jun-2016		9	25-Jun-2016	29-Jul-2016		v004		0.10		340	0	0	208	33	9	590	493.55		599.36
Project-A13		0.62	1.30				01-Jan-2014		56	27-Feb-2014	02-Aug-2014		0	03-Aug-2014	09-Sep-2014		0	10-Sep-2014	17-Oct-2014		12	30-Oct-2014	07-Dec-2014		349	22-Nov-2015	29-Dec-2015		54	22-Feb-2016	31-Mar-2016		v007		0.08		56	0	0	12	349	54	471	70.87		763.20					W
Project-A14		0.46	0.56				01-Jan-2014		200	21-Jul-2014	14-Oct-2014		0	15-Oct-2014	17-Jan-2015		0	18-Jan-2015	09-Feb-2015		9	19-Feb-2015	14-Mar-2015		149	11-Aug-2015	03-Sep-2015		20	24-Sep-2015	16-Oct-2015		v006		0.06		200	0	0	9	149	20	378	171.22		452.54					O
Project-A15		0.31	0.59				01-Jan-2014		344	12-Dec-2014	03-Aug-2015		0	04-Aug-2015	18-Jan-2016		0	19-Jan-2016	15-Mar-2016		50	05-May-2016	30-Jun-2016		20	21-Jul-2016	15-Sep-2016		9	25-Sep-2016	21-Nov-2016		v008		0.11		344	0	0	50	20	9	423	547.37		710.16					R
							K
							S
Average		0.53	1.58					156				0				0				111				108				25					0.07		156	0	0	111	108	25	400	189.05	Average	476.59					H
Total		7.96	23.66					2345				0				0				1665				1617				377					1.00		2345	0	0	1665	1617	377	6004	2835.81	Total	7148.79					E
		<=	<=					E
Available FTE		8	24					Priority Factor					T
							15.00

		END	OF	THIS	WORKSHEET

## Code_Base_Violation_Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula

Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) / Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.

Total - Violation / (SIT/UAT/NFT/Prod)	Count:	0
	Days:	0.00

					E
					N
SIT - Violation	Count:	0			Compare Roll Project against Column Project, to check violation.					D
	Days:	0.00
					Count					Days (Overlap) simplified rough formula					O
Project Name	Start Date	End Date	Code Base Version		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15					F
Project-A01	03-May-2014	16-May-2014	v001			0	0	0	0	0	0	0	0	0	0	0	0	0	0			0	0	0	0	0	0	0	0	0	0	0	0	0	0
Project-A02	23-Mar-2015	07-Apr-2015	v002				0	0	0	0	0	0	0	0	0	0	0	0	0				0	0	0	0	0	0	0	0	0	0	0	0	0					T
Project-A03	22-Feb-2014	01-Mar-2014	v003					0	0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0	0					H
Project-A04	16-Jul-2014	28-Jul-2014	v004					0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0					I
Project-A05	01-Apr-2014	13-Apr-2014	v002					0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0					S
Project-A06	21-Feb-2015	11-Mar-2015	v003					0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0
Project-A07	14-Aug-2015	28-Sep-2015	v005					0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0					W
Project-A08	31-Jan-2014	03-Feb-2014	v006					0	0	0	0	0	0	0					0	0	0	0	0	0	0					O
Project-A09	19-Jun-2014	12-Jul-2014	v003					0	0	0	0	0	0					0	0	0	0	0	0					R
Project-A10	17-May-2014	04-Jun-2014	v001					0	0	0	0	0					0	0	0	0	0					K
Project-A11	29-Oct-2014	10-Nov-2014	v002					0	0	0	0					0	0	0	0					S
Project-A12	05-Jul-2015	08-Aug-2015	v004					0	0	0					0	0	0					H
Project-A13	10-Sep-2014	17-Oct-2014	v007					0	0					0	0					E
Project-A14	18-Jan-2015	09-Feb-2015	v006					0					0					E
Project-A15	19-Jan-2016	15-Mar-2016	v008					T

UAT - Violation	Count:	0			Compare Roll Project against Column Project, to check violation.
	Days:	0.00
					Count					Days (Overlap) simplified rough formula
Project Name	Start Date	End Date	Code Base Version		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15
Project-A01	21-May-2014	04-Jun-2014	v001			0	0	0	0	0	0	0	0	0	0	0	0	0	0			0	0	0	0	0	0	0	0	0	0	0	0	0	0
Project-A02	21-Apr-2015	07-May-2015	v002				0	0	0	0	0	0	0	0	0	0	0	0	0				0	0	0	0	0	0	0	0	0	0	0	0	0
Project-A03	23-Jul-2014	29-Jul-2014	v003					0	0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0	0
Project-A04	09-Oct-2014	21-Oct-2014	v004					0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0
Project-A05	12-Apr-2015	25-Apr-2015	v002					0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0
Project-A06	07-Jul-2015	25-Jul-2015	v003					0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0
Project-A07	23-Sep-2016	07-Nov-2016	v005					0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0
Project-A08	10-Feb-2014	13-Feb-2014	v006					0	0	0	0	0	0	0					0	0	0	0	0	0	0
Project-A09	21-Aug-2014	13-Sep-2014	v003					0	0	0	0	0	0					0	0	0	0	0	0
Project-A10	09-Jun-2014	26-Jun-2014	v001					0	0	0	0	0					0	0	0	0	0
Project-A11	03-Aug-2015	16-Aug-2015	v002					0	0	0	0					0	0	0	0
Project-A12	04-Mar-2016	07-Apr-2016	v004					0	0	0					0	0	0
Project-A13	30-Oct-2014	07-Dec-2014	v007					0	0					0	0
Project-A14	19-Feb-2015	14-Mar-2015	v006					0					0
Project-A15	05-May-2016	30-Jun-2016	v008

NFT - Violation	Count:	0			Compare Roll Project against Column Project, to check violation.
	Days:	0.00
					Count					Days (Overlap) simplified rough formula
Project Name	Start Date	End Date	Code Base Version		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15
Project-A01	22-Jun-2014	05-Jul-2014	v001			0	0	0	0	0	0	0	0	0	0	0	0	0	0			0	0	0	0	0	0	0	0	0	0	0	0	0	0
Project-A02	26-Apr-2016	11-May-2016	v002				0	0	0	0	0	0	0	0	0	0	0	0	0				0	0	0	0	0	0	0	0	0	0	0	0	0
Project-A03	16-Nov-2014	22-Nov-2014	v003					0	0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0	0
Project-A04	28-Feb-2015	13-Mar-2015	v004					0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0
Project-A05	03-Oct-2015	16-Oct-2015	v002					0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0
Project-A06	07-Jan-2016	25-Jan-2016	v003					0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0
Project-A07	26-Nov-2016	10-Jan-2017	v005					0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0
Project-A08	14-Mar-2014	17-Mar-2014	v006					0	0	0	0	0	0	0					0	0	0	0	0	0	0
Project-A09	29-Oct-2014	21-Nov-2014	v003					0	0	0	0	0	0					0	0	0	0	0	0
Project-A10	30-Jun-2014	18-Jul-2014	v001					0	0	0	0	0					0	0	0	0	0
Project-A11	24-Sep-2015	07-Oct-2015	v002					0	0	0	0					0	0	0	0
Project-A12	11-May-2016	15-Jun-2016	v004					0	0	0					0	0	0
Project-A13	22-Nov-2015	29-Dec-2015	v007					0	0					0	0
Project-A14	11-Aug-2015	03-Sep-2015	v006					0					0
Project-A15	21-Jul-2016	15-Sep-2016	v008

Prod - Violation	Count:	0			Compare Roll Project against Column Project, to check violation.
	Days:	0.00
					Count					Days (Overlap) simplified rough formula
Project Name	Start Date	End Date	Code Base Version		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15
Project-A01	07-Aug-2014	21-Aug-2014	v001			0	0	0	0	0	0	0	0	0	0	0	0	0	0			0	0	0	0	0	0	0	0	0	0	0	0	0	0
Project-A02	13-May-2016	28-May-2016	v002				0	0	0	0	0	0	0	0	0	0	0	0	0				0	0	0	0	0	0	0	0	0	0	0	0	0
Project-A03	07-Jan-2015	13-Jan-2015	v003					0	0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0	0
Project-A04	23-Mar-2015	04-Apr-2015	v004					0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0
Project-A05	23-Nov-2015	05-Dec-2015	v002					0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0
Project-A06	26-Jan-2016	13-Feb-2016	v003					0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0
Project-A07	18-Mar-2017	02-May-2017	v005					0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0
Project-A08	20-Mar-2014	24-Mar-2014	v006					0	0	0	0	0	0	0					0	0	0	0	0	0	0
Project-A09	13-Dec-2014	05-Jan-2015	v003					0	0	0	0	0	0					0	0	0	0	0	0
Project-A10	18-Sep-2014	05-Oct-2014	v001					0	0	0	0	0					0	0	0	0	0
Project-A11	19-Oct-2015	31-Oct-2015	v002					0	0	0	0					0	0	0	0
Project-A12	25-Jun-2016	29-Jul-2016	v004					0	0	0					0	0	0
Project-A13	22-Feb-2016	31-Mar-2016	v007					0	0					0	0
Project-A14	24-Sep-2015	16-Oct-2015	v006					0					0
Project-A15	25-Sep-2016	21-Nov-2016	v008

	END	OF	THIS	WORKSHEET

## Random_Number
Random	x100	Interger
0.4019161149	40.1916114872	40
0.881930662	88.1930661954	88
0.354782845	35.4782844986	35
0.0091527496	0.9152749633	0
0.906447353	90.6447352952	90
0.6634989937	66.3498993687	66
0.9210775011	92.1077501063	92
0.6782024028	67.8202402794	67
0.6253226267	62.5322626704	62
0.0714446041	7.1444604101	7
0.8798241975	87.9824197474	87
0.5233053765	52.3305376489	52
0.5456751538	54.5675153755	54
0.270699153	27.0699153014	27
0.6829421515	68.2942151508	68
0.9839454455	98.394544546	98
0.0103783406	1.0378340557	1
0.6664572375	66.6457237461	66
0.555422534	55.5422533973	55
0.070947152	7.0947152041	7
0.1476899359	14.7689935865	14
0.6329378175	63.2937817472	63
0.0791346098	7.9134609757	7
0.7611092769	76.110927691	76
0.0818469244	8.1846924412	8
0.9179337779	91.7933777926	91
0.7839423351	78.3942335116	78
0.2552139276	25.5213927649	25
0.4037684046	40.3768404576	40
0.211469353	21.1469352972	21
0.3758361463	37.5836146295	37
0.8444261265	84.4426126485	84
0.9053348334	90.5334833365	90
0.9942354043	99.4235404324	99
0.1012647883	10.1264788268	10
0.0809696988	8.096969875	8
0.1543556194	15.4355619438	15
0.8479095168	84.7909516799	84
0.2253183284	22.5318328367	22

## _PalUtilTempWorksheet
0

## ev_HiddenInfo
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize	1879.02				MACROS			Compatibility with Old Versions (4 trips pre-v5 versions)	4		RISKOpt Tag	TRUE		Out. Stats
Goal (Type, Target Value)	1	0			Start (enabled, macro)	FALSE		Formula Conversion Cell (not used in v5)			#Iterations (Sim Stopping)			Mean			Creation Version	5.5.0		Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count)	FALSE	5000000000000			Before Recalc (enabled, macro)	FALSE		Number Formatting Cell (introduced in v5)	365		Sim. Stopping Mode, Tolerance			Std. Dev.			Required Version	5.0.0		Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count)	TRUE	10	2		After Recalc (enabled, macro)	FALSE					Same Seed Each Simulation			Min			Recommended Version	4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent)	FALSE	1000000000	1E-10	TRUE	After Storage (enabled, macro)	FALSE					Sampling Type			Max			Last Modified by Version	5.5.0
Formula Stopping (enabled, formula)	FALSE	0			Finish (enabled, macro)	FALSE					Macro Before Simulation (enabled, macro)
Population Size	500										Macro After Simulation (enabled, macro)
UNUSED	UNUSED				Seed (Is Auto, Value)	TRUE	1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5)	3				Minimize Excel on Startup	FALSE
Stop on Errors (before v5: Pause on Errors)	FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting)	FALSE
Ev4/RO1: Graph Progress	FALSE				Show Excel Recalcs (replaces "Update Display" used before v5)	2

# Chromosomes	1																		# Constraints	2
Method + #Operators	Mutation Rate	Crossover Rate	Description	# Time Blocks/All Groups Must Be Present	Constraint Range	#Ranges	Adj. Range	Min Val or Range	Max Val Or Range	Flags									HARD CONSTRAINT DEV	CONSTRAINT SOLVER	ROFUNC	RISKOPT	SOFT CONSTRAINT DEV	EVAL (True/False or penalty)	Type (Hard/Soft)	Entry Mode	Formula	Description	Left Val Or Range	Left Operator	Constrained Cells	Right Operator	Right Val Or Range	Penalty Function	RO Eval Time (Iter/Sim)	RO Statistic to Constrain	RO Statistic Parameter
RECIPE11	0.5	0.5				2	#VALUE!	0.25	5	False,False,False									2	1		Max 8 KE FTEs	0	6	7.96	2	8
DEFAULT PARENT SELECTION							Err:509	0	365	True,False,False									2	1		Max 24 SE FTEs	0	6	23.66	2	24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH

## Project_Release_Optimizer_(NLP-Solver)
Legend:		Fitness Control Dashboard
Chromosome		Fitness Breakdown		Fitness Priority	Formula		Value					Benchmark
Constraint (Hard)		Proj Make-Span (Overall)		Medium	'=Project_Release_Optimizer_(GA).AW15		1213.38		<- To shorten entire projects span (ALL projects)					Perfect AVG Project Span
Constraint (Soft)		Average Proj Make-Span (Individual)		Medium	'=Project_Release_Optimizer_(GA).AV32		476.59		<- To shorten average individual project span				<---------->	201.44
Fitness		Priority-Weighted Plan-Lead		Low	'=Project_Release_Optimizer_(GA).AT32		189.05		<- To schedule important projects to start earlier
User Inputs		Code-Base Violation x Weight		High	'='Code Base Violation Constraint'!E13*20		0.00		<- Heuristic Weight (Hard -> Soft constraint):			50
Formula		Integrated Fitness - To Min()		N.A.	'=Project_Release_Optimizer_(GA).SUM(I4:I7)		1879.02		<- To Minimize
		Code-Base constraint satisfied ?		TRUE

Vlookup Index	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	38	39	49	50	51	52	53	54	55	56	57	58	59	60	61	62

		Resource Allocation / Full Time Employee (FTEs)
Project Name		Knowledge / Engineer	Software Engineer	Lead prior to Plan / (Calendar-Day)	Lead prior to UAT / (Calendar-Day)	Lead prior to NFT / (Calendar-Day)	Lead prior to Prod / (Calendar-Day)
Project-A01		0.30	1.53	14	4	17	32
Project-A02		0.33	1.26	335	13	354	1
Project-A03		0.63	2.14	12	143	109	45
Project-A04		0.68	1.69	129	72	129	9
Project-A05		0.29	1.52	14	363	160	37
Project-A06		0.69	1.85	314	117	165	0
Project-A07		0.50	3.79	355	360	18	66
Project-A08		0.37	1.06	3	6	28	2
Project-A09		0.51	1.53	15	39	45	21
Project-A10		0.63	1.20	4	4	3	61
Project-A11		1.20	2.24	210	265	38	11
Project-A12		0.46	1.40	340	208	33	9
Project-A13		0.62	1.30	56	12	349	54
Project-A14		0.46	0.56	200	9	149	20
Project-A15		0.31	0.59	344	50	20	9

Average		0.53	1.58	156	111	108	25
Total		7.96	23.66	2345	1665	1617	377
		<=	<=
Available FTE		8	24

		END	OF	THIS	WORKSHEET