## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.50909 | 0.28768 |  |  |  | 17 | 17.76 | 34.76 | 61.7363 |  | 4.08 | 74 | 78.08 | 257.2344 |  | 4.08 | 17.76 | 21.84 | 61.7363 |  | 4.08 | 17.76 | 21.84 | 61.7363 |  | 4.08 | 17.76 | 21.84 | 61.7363 |  | 4.08 | 17.76 | 21.84 | 61.7363 |  | 200.2 | 565.9156 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 73.464 | 565.9156 | 565.9156
Project-A02 |  | v002 |  | 0.50215 | 1.5156 |  |  |  | 15 | 19.2 | 34.2 | 29.8714 |  | 3.6 | 80 | 83.6 | 52.7844 |  | 3.6 | 19.2 | 22.8 | 12.6683 |  | 3.6 | 19.2 | 22.8 | 12.6683 |  | 3.6 | 19.2 | 22.8 | 12.6683 |  | 3.6 | 19.2 | 22.8 | 12.6683 |  | 209 | 133.3288 | 104500 |  | 0.058933 |  | 33 | 176 |  | 65.717 | 116.1257 | 116.1257 | [12 empty] | E
Project-A03 |  | v003 |  | 0.52935 | 3.675 |  |  |  | 16 | 6.48 | 22.48 | 30.2259 |  | 3.84 | 27 | 30.84 | 7.347 |  | 3.84 | 6.48 | 10.32 | 7.2542 |  | 3.84 | 6.48 | 10.32 | 7.2542 |  | 3.84 | 6.48 | 10.32 | 7.2542 |  | 3.84 | 6.48 | 10.32 | 7.2542 |  | 94.6 | 66.5898 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 66.497 | 16.1634 | 66.497 | [12 empty] | N
Project-A04 |  | v004 |  | 0.507 | 1.5023 |  |  |  | 35 | 4.32 | 39.32 | 69.0337 |  | 8.4 | 18 | 26.4 | 16.5681 |  | 8.4 | 4.32 | 12.72 | 16.5681 |  | 8.4 | 4.32 | 12.72 | 16.5681 |  | 8.4 | 4.32 | 12.72 | 16.5681 |  | 8.4 | 4.32 | 12.72 | 16.5681 |  | 116.6 | 151.8742 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 151.8742 | 26.3588 | 151.8742 | [12 empty] | D
Project-A05 |  | v002 |  | 0.51634 | 1.7136 |  |  |  | 6 | 19.2 | 25.2 | 11.6203 |  | 1.44 | 80 | 81.44 | 46.6855 |  | 1.44 | 19.2 | 20.64 | 11.2045 |  | 1.44 | 19.2 | 20.64 | 11.2045 |  | 1.44 | 19.2 | 20.64 | 11.2045 |  | 1.44 | 19.2 | 20.64 | 11.2045 |  | 189.2 | 103.1239 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 25.5646 | 102.7081 | 102.7081
Project-A06 |  | v003 |  | 0.52814 | 1.5009 |  |  |  | 52 | 10.56 | 62.56 | 98.4585 |  | 12.48 | 44 | 56.48 | 29.3155 |  | 12.48 | 10.56 | 23.04 | 23.63 |  | 12.48 | 10.56 | 23.04 | 23.63 |  | 12.48 | 10.56 | 23.04 | 23.63 |  | 12.48 | 10.56 | 23.04 | 23.63 |  | 211.2 | 222.2942 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 216.6087 | 64.4941 | 216.6087 | [12 empty] | O
Project-A07 |  | v005 |  | 0.2597 | 1.5361 |  |  |  | 93 | 19.92 | 112.92 | 358.1033 |  | 22.32 | 83 | 105.32 | 85.9448 |  | 22.32 | 19.92 | 42.24 | 85.9448 |  | 22.32 | 19.92 | 42.24 | 85.9448 |  | 22.32 | 19.92 | 42.24 | 85.9448 |  | 22.32 | 19.92 | 42.24 | 85.9448 |  | 387.2 | 787.8273 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 787.8273 | 118.8741 | 787.8273 | [12 empty] | F
Project-A08 |  | v006 |  | 0.50094 | 1.9669 |  |  |  | 5 | 2.64 | 7.64 | 9.9813 |  | 1.2 | 11 | 12.2 | 5.5926 |  | 1.2 | 2.64 | 3.84 | 2.3955 |  | 1.2 | 2.64 | 3.84 | 2.3955 |  | 1.2 | 2.64 | 3.84 | 2.3955 |  | 1.2 | 2.64 | 3.84 | 2.3955 |  | 35.2 | 25.156 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 21.9588 | 12.3038 | 21.9588
Project-A09 |  | v003 |  | 0.50826 | 1.5012 |  |  |  | 49 | 20.64 | 69.64 | 96.4072 |  | 11.76 | 86 | 97.76 | 57.2871 |  | 11.76 | 20.64 | 32.4 | 23.1377 |  | 11.76 | 20.64 | 32.4 | 23.1377 |  | 11.76 | 20.64 | 32.4 | 23.1377 |  | 11.76 | 20.64 | 32.4 | 23.1377 |  | 297 | 246.2453 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 212.0959 | 126.0316 | 212.0959 | [12 empty] | T
Project-A10 |  | v001 |  | 0.52746 | 1.5233 |  |  |  | 36 | 20.88 | 56.88 | 68.251 |  | 8.64 | 87 | 95.64 | 57.1135 |  | 8.64 | 20.88 | 29.52 | 16.3802 |  | 8.64 | 20.88 | 29.52 | 16.3802 |  | 8.64 | 20.88 | 29.52 | 16.3802 |  | 8.64 | 20.88 | 29.52 | 16.3802 |  | 270.6 | 190.8854 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 150.1522 | 125.6497 | 150.1522 | [12 empty] | H
Project-A11 |  | v002 |  | 0.52437 | 1.4908 |  |  |  | 63 | 19.2 | 82.2 | 120.1445 |  | 15.12 | 80 | 95.12 | 53.6642 |  | 15.12 | 19.2 | 34.32 | 28.8347 |  | 15.12 | 19.2 | 34.32 | 28.8347 |  | 15.12 | 19.2 | 34.32 | 28.8347 |  | 15.12 | 19.2 | 34.32 | 28.8347 |  | 314.6 | 289.1473 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 264.3178 | 118.0612 | 264.3178 | [12 empty] | I
Project-A12 |  | v004 |  | 0.49431 | 1.5027 |  |  |  | 65 | 21.84 | 86.84 | 131.496 |  | 15.6 | 91 | 106.6 | 60.5589 |  | 15.6 | 21.84 | 37.44 | 31.559 |  | 15.6 | 21.84 | 37.44 | 31.559 |  | 15.6 | 21.84 | 37.44 | 31.559 |  | 15.6 | 21.84 | 37.44 | 31.559 |  | 343.2 | 318.2911 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 289.2912 | 133.2297 | 289.2912 | [12 empty] | S
Project-A13 |  | v007 |  | 0.5396 | 2.0233 |  |  |  | 96 | 9.6 | 105.6 | 177.9109 |  | 23.04 | 40 | 63.04 | 42.6986 |  | 23.04 | 9.6 | 32.64 | 42.6986 |  | 23.04 | 9.6 | 32.64 | 42.6986 |  | 23.04 | 9.6 | 32.64 | 42.6986 |  | 23.04 | 9.6 | 32.64 | 42.6986 |  | 299.2 | 391.4039 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 391.4039 | 43.4931 | 391.4039
Project-A14 |  | v006 |  | 0.54853 | 2.0107 |  |  |  | 39 | 12.72 | 51.72 | 71.0985 |  | 9.36 | 53 | 62.36 | 26.3596 |  | 9.36 | 12.72 | 22.08 | 17.0636 |  | 9.36 | 12.72 | 22.08 | 17.0636 |  | 9.36 | 12.72 | 22.08 | 17.0636 |  | 9.36 | 12.72 | 22.08 | 17.0636 |  | 202.4 | 165.7126 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 156.4166 | 57.9911 | 156.4166 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0048 | 0.25009 |  |  |  | 72 | 23.76 | 95.76 | 95.0058 |  | 17.28 | 99 | 116.28 | 395.8574 |  | 17.28 | 23.76 | 41.04 | 95.0058 |  | 17.28 | 23.76 | 41.04 | 95.0058 |  | 17.28 | 23.76 | 41.04 | 95.0058 |  | 17.28 | 23.76 | 41.04 | 95.0058 |  | 376.2 | 870.8862 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 157.6507 | 870.8862 | 870.8862 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 95.2896 |  | 10.544 | 63.5333 | 74.0773 | 79.6674 |  | 10.544 | 15.248 | 25.792 | 31.7388 |  | 10.544 | 15.248 | 25.792 | 31.7388 |  | 10.544 | 15.248 | 25.792 | 31.7388 |  | 10.544 | 15.248 | 25.792 | 31.7388 |  | 236.4267 | 301.9121 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 202.056 | 166.5524 | 290.9386 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1429.3445 |  | 158.16 | 953 | 1111.16 | 1195.0116 |  | 158.16 | 228.72 | 386.88 | 476.0814 |  | 158.16 | 228.72 | 386.88 | 476.0814 |  | 158.16 | 228.72 | 386.88 | 476.0814 |  | 158.16 | 228.72 | 386.88 | 476.0814 |  | 3546.4 | 4528.6816 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3030.8401 | 2498.2863 | 4364.0793 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 953.8862 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 331.3788 |  | <- To shorten average individual project span |  |  |  | <----------> | 290.9386
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 31.6743 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 1323.1358 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 2640.0751 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.50909 | 0.28768 |  |  |  | 2014-01-01 |  | 1 | 2014-01-03 | 2014-03-05 17:40 |  | 0 | 2014-03-06 17:40 | 2014-11-18 23:18 |  | 0 | 2014-11-19 23:18 | 2015-01-20 16:58 |  | 0 | 2015-01-21 16:58 | 2015-03-24 10:38 |  | 0 | 2015-03-25 10:38 | 2015-05-26 04:18 |  | 0 | 2015-05-27 04:18 | 2015-07-27 21:59 |  | v001 |  | 0.056452 |  | 1 | 0 | 0 | 0 | 0 | 0 | 1 | 0.84677 |  | 570.9156 | 953.8862 | [14 empty] | E
Project-A02 |  | 0.50215 | 1.5156 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-31 20:55 |  | 0 | 2014-02-01 20:55 | 2014-03-26 15:44 |  | 0 | 2014-03-27 15:44 | 2014-04-09 07:47 |  | 0 | 2014-04-10 07:47 | 2014-04-22 23:49 |  | 0 | 2014-04-23 23:49 | 2014-05-06 15:51 |  | 0 | 2014-05-07 15:51 | 2014-05-20 07:53 |  | v002 |  | 0.058933 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 138.3288 | [15 empty] | N
Project-A03 |  | 0.52935 | 3.675 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-01 05:25 |  | 0 | 2014-02-02 05:25 | 2014-02-09 13:45 |  | 0 | 2014-02-10 13:45 | 2014-02-17 19:51 |  | 0 | 2014-02-18 19:51 | 2014-02-26 01:57 |  | 0 | 2014-02-27 01:57 | 2014-03-06 08:03 |  | 0 | 2014-03-07 08:03 | 2014-03-14 14:09 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 71.5898 | [15 empty] | D
Project-A04 |  | 0.507 | 1.5023 |  |  |  | 2014-01-01 |  | 35 | 2014-02-06 | 2014-04-16 00:49 |  | 0 | 2014-04-17 00:49 | 2014-05-03 14:27 |  | 0 | 2014-05-04 14:27 | 2014-05-21 04:05 |  | 0 | 2014-05-22 04:05 | 2014-06-07 17:43 |  | 0 | 2014-06-08 17:43 | 2014-06-25 07:21 |  | 0 | 2014-06-26 07:21 | 2014-07-12 20:59 |  | v004 |  | 0.032878 |  | 35 | 0 | 0 | 0 | 0 | 0 | 35 | 17.2612 |  | 156.8742
Project-A05 |  | 0.51634 | 1.7136 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-13 14:53 |  | 0 | 2014-01-14 14:53 | 2014-03-02 07:20 |  | 0 | 2014-03-03 07:20 | 2014-03-14 12:15 |  | 0 | 2014-03-15 12:15 | 2014-03-26 17:09 |  | 0 | 2014-03-27 17:09 | 2014-04-07 22:04 |  | 0 | 2014-04-08 22:04 | 2014-04-20 02:58 |  | v002 |  | 0.05335 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 108.1239 | [15 empty] | O
Project-A06 |  | 0.52814 | 1.5009 |  |  |  | 2014-01-01 |  | 59 | 2014-03-02 | 2014-06-08 11:00 |  | 0 | 2014-06-09 11:00 | 2014-07-08 18:35 |  | 0 | 2014-07-09 18:35 | 2014-08-02 09:42 |  | 0 | 2014-08-03 09:42 | 2014-08-27 00:49 |  | 0 | 2014-08-28 00:49 | 2014-09-20 15:56 |  | 0 | 2014-09-21 15:56 | 2014-10-15 07:04 |  | v003 |  | 0.059553 |  | 59 | 0 | 0 | 0 | 0 | 0 | 59 | 52.7047 |  | 227.2942 | [15 empty] | F
Project-A07 |  | 0.2597 | 1.5361 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-12-26 02:29 |  | 0 | 2014-12-27 02:29 | 2015-03-23 01:09 |  | 0 | 2015-03-24 01:09 | 2015-06-17 23:50 |  | 0 | 2015-06-18 23:50 | 2015-09-12 22:30 |  | 0 | 2015-09-13 22:30 | 2015-12-08 21:11 |  | 0 | 2015-12-09 21:11 | 2016-03-04 19:51 |  | v005 |  | 0.10918 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 792.8273
Project-A08 |  | 0.50094 | 1.9669 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 23:33 |  | 0 | 2014-01-12 23:33 | 2014-01-18 13:46 |  | 0 | 2014-01-19 13:46 | 2014-01-21 23:16 |  | 0 | 2014-01-22 23:16 | 2014-01-25 08:46 |  | 0 | 2014-01-26 08:46 | 2014-01-28 18:15 |  | 0 | 2014-01-29 18:15 | 2014-02-01 03:45 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30.156 | [15 empty] | T
Project-A09 |  | 0.50826 | 1.5012 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-04-20 09:46 |  | 0 | 2014-04-21 09:46 | 2014-06-17 16:40 |  | 0 | 2014-06-18 16:40 | 2014-07-11 19:58 |  | 2 | 2014-07-14 19:58 | 2014-08-06 23:17 |  | 365 | 2015-08-07 23:17 | 2015-08-31 02:35 |  | 0 | 2015-09-01 02:35 | 2015-09-24 05:53 |  | v003 |  | 0.083747 |  | 12 | 0 | 0 | 2 | 365 | 0 | 379 | 15.0744 |  | 618.2453 | [15 empty] | H
Project-A10 |  | 0.52746 | 1.5233 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-04-03 06:01 |  | 0 | 2014-04-04 06:01 | 2014-05-31 08:45 |  | 0 | 2014-06-01 08:45 | 2014-06-17 17:52 |  | 0 | 2014-06-18 17:52 | 2014-07-05 03:00 |  | 0 | 2014-07-06 03:00 | 2014-07-22 12:07 |  | 0 | 2014-07-23 12:07 | 2014-08-08 21:15 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 26.3244 |  | 195.8854 | [15 empty] | I
Project-A11 |  | 0.52437 | 1.4908 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-06-05 03:28 |  | 0 | 2014-06-06 03:28 | 2014-07-29 19:24 |  | 0 | 2014-07-30 19:24 | 2014-08-28 15:26 |  | 0 | 2014-08-29 15:26 | 2014-09-27 11:28 |  | 0 | 2014-09-28 11:28 | 2014-10-27 07:30 |  | 0 | 2014-10-28 07:30 | 2014-11-26 03:32 |  | v002 |  | 0.08871 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 45.2419 |  | 294.1473 | [15 empty] | S
Project-A12 |  | 0.49431 | 1.5027 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-06-27 11:54 |  | 0 | 2014-06-28 11:54 | 2014-08-28 01:19 |  | 0 | 2014-08-29 01:19 | 2014-09-29 14:44 |  | 0 | 2014-09-30 14:44 | 2014-11-01 04:09 |  | 0 | 2014-11-02 04:09 | 2014-12-03 17:34 |  | 0 | 2014-12-04 17:34 | 2015-01-05 06:59 |  | v004 |  | 0.096774 |  | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 65.3226 |  | 323.2911
Project-A13 |  | 0.5396 | 2.0233 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-08-23 21:52 |  | 0 | 2014-08-24 21:52 | 2014-10-06 14:38 |  | 0 | 2014-10-07 14:38 | 2014-11-19 07:24 |  | 0 | 2014-11-20 07:24 | 2015-01-02 00:10 |  | 0 | 2015-01-03 00:10 | 2015-02-14 16:56 |  | 0 | 2015-02-15 16:56 | 2015-03-30 09:42 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 396.4039 | [15 empty] | W
Project-A14 |  | 0.54853 | 2.0107 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-20 02:22 |  | 0 | 2014-05-21 02:22 | 2014-06-16 11:00 |  | 0 | 2014-06-17 11:00 | 2014-07-04 12:31 |  | 0 | 2014-07-05 12:31 | 2014-07-22 14:03 |  | 0 | 2014-07-23 14:03 | 2014-08-09 15:35 |  | 0 | 2014-08-10 15:35 | 2014-08-27 17:06 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 57.3573 |  | 170.7126 | [15 empty] | O
Project-A15 |  | 1.0048 | 0.25009 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-06-24 00:08 |  | 0 | 2014-06-25 00:08 | 2015-07-25 20:43 |  | 0 | 2015-07-26 20:43 | 2015-10-29 20:51 |  | 0 | 2015-10-30 20:51 | 2016-02-02 21:00 |  | 0 | 2016-02-03 21:00 | 2016-05-08 21:08 |  | 0 | 2016-05-09 21:08 | 2016-08-12 21:16 |  | v008 |  | 0.10608 |  | 78 | 0 | 0 | 0 | 0 | 0 | 78 | 124.1129 |  | 875.8862 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 27.3333 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.13333 |  |  |  | 24.3333 |  |  |  | 0 | [5 empty] | 0.066667 |  | 27.3333 | 0 | 0 | 0.13333 | 24.3333 | 0 | 51.8 | 31.6743 | Average | 331.3788 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 410 |  |  |  | 0 |  |  |  | 0 |  |  |  | 2 |  |  |  | 365 |  |  |  | 0 | [5 empty] | 1 |  | 410 | 0 | 0 | 2 | 365 | 0 | 777 | 475.1148 | Total | 4970.6816 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 4
| Days: | 26.4627
E
N
SIT - Violation | Count: | 3 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 18.7094
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-11-19 23:18 | 2015-01-20 16:58 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-27 15:44 | 2014-04-09 07:47 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-10 13:45 | 2014-02-17 19:51 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-04 14:27 | 2014-05-21 04:05 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-03-03 07:20 | 2014-03-14 12:15 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-09 18:35 | 2014-08-02 09:42 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 2.5954 | 0 | 0 | 0 | 0
Project-A07 | 2015-03-24 01:09 | 2015-06-17 23:50 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-19 13:46 | 2014-01-21 23:16 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-18 16:40 | 2014-07-11 19:58 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 15.8274 | 0 | R
Project-A10 | 2014-06-01 08:45 | 2014-06-17 17:52 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0.28665 | 0 | K
Project-A11 | 2014-07-30 19:24 | 2014-08-28 15:26 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-29 01:19 | 2014-09-29 14:44 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-07 14:38 | 2014-11-19 07:24 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-17 11:00 | 2014-07-04 12:31 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2015-07-26 20:43 | 2015-10-29 20:51 | v008 | [31 empty] | T
UAT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 7.7533
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-01-21 16:58 | 2015-03-24 10:38 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-10 07:47 | 2014-04-22 23:49 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-18 19:51 | 2014-02-26 01:57 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-22 04:05 | 2014-06-07 17:43 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-15 12:15 | 2014-03-26 17:09 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-03 09:42 | 2014-08-27 00:49 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-06-18 23:50 | 2015-09-12 22:30 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-22 23:16 | 2014-01-25 08:46 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-14 19:58 | 2014-08-06 23:17 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 7.7533 | 0
Project-A10 | 2014-06-18 17:52 | 2014-07-05 03:00 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-08-29 15:26 | 2014-09-27 11:28 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-30 14:44 | 2014-11-01 04:09 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-11-20 07:24 | 2015-01-02 00:10 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-05 12:31 | 2014-07-22 14:03 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-10-30 20:51 | 2016-02-02 21:00 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-03-25 10:38 | 2015-05-26 04:18 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-23 23:49 | 2014-05-06 15:51 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-27 01:57 | 2014-03-06 08:03 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-08 17:43 | 2014-06-25 07:21 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-27 17:09 | 2014-04-07 22:04 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-28 00:49 | 2014-09-20 15:56 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-09-13 22:30 | 2015-12-08 21:11 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-26 08:46 | 2014-01-28 18:15 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-08-07 23:17 | 2015-08-31 02:35 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-06 03:00 | 2014-07-22 12:07 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-28 11:28 | 2014-10-27 07:30 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-02 04:09 | 2014-12-03 17:34 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-03 00:10 | 2015-02-14 16:56 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-23 14:03 | 2014-08-09 15:35 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-02-03 21:00 | 2016-05-08 21:08 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-05-27 04:18 | 2015-07-27 21:59 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-07 15:51 | 2014-05-20 07:53 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-07 08:03 | 2014-03-14 14:09 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-26 07:21 | 2014-07-12 20:59 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-08 22:04 | 2014-04-20 02:58 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-21 15:56 | 2014-10-15 07:04 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-12-09 21:11 | 2016-03-04 19:51 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-29 18:15 | 2014-02-01 03:45 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-09-01 02:35 | 2015-09-24 05:53 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-23 12:07 | 2014-08-08 21:15 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-28 07:30 | 2014-11-26 03:32 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-04 17:34 | 2015-01-05 06:59 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-02-15 16:56 | 2015-03-30 09:42 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-10 15:35 | 2014-08-27 17:06 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-05-09 21:08 | 2016-08-12 21:16 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.18127 | 18.127 | 18
0.51678 | 51.6781 | 51
0.4034 | 40.3401 | 40
0.77922 | 77.9222 | 77
0.70329 | 70.329 | 70
0.046568 | 4.6568 | 4
0.36551 | 36.5513 | 36
0.027573 | 2.7573 | 2
0.60273 | 60.2731 | 60
0.26379 | 26.3791 | 26
0.084899 | 8.4899 | 8
0.25142 | 25.1416 | 25
0.94659 | 94.659 | 94
0.85548 | 85.5483 | 85
0.87333 | 87.3333 | 87
0.38203 | 38.203 | 38
0.43805 | 43.8051 | 43
0.31036 | 31.0358 | 31
0.14522 | 14.5216 | 14
0.88666 | 88.6663 | 88
0.68946 | 68.9464 | 68
0.99876 | 99.8757 | 99
0.50817 | 50.8166 | 50
0.08269 | 8.269 | 8
0.69654 | 69.6537 | 69
0.31129 | 31.1289 | 31
0.67078 | 67.0777 | 67
0.70662 | 70.6625 | 70
0.21087 | 21.087 | 21
0.22363 | 22.3627 | 22
0.15165 | 15.1652 | 15
0.23 | 23 | 23
0.34921 | 34.9206 | 34
0.31731 | 31.7313 | 31
0.64632 | 64.632 | 64
0.0073902 | 0.73902 | 0
0.78798 | 78.7976 | 78
0.5415 | 54.1504 | 54
0.21146 | 21.1461 | 21

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 2640.0751 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.9 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH