## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.52699 | 0.2611 |  |  |  | 17 | 17.76 | 34.76 | 68.0209 |  | 4.08 | 74 | 78.08 | 283.4203 |  | 4.08 | 17.76 | 21.84 | 68.0209 |  | 4.08 | 17.76 | 21.84 | 68.0209 |  | 4.08 | 17.76 | 21.84 | 68.0209 |  | 4.08 | 17.76 | 21.84 | 68.0209 |  | 200.2 | 623.5246 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 70.969 | 623.5246 | 623.5246
Project-A02 |  | v002 |  | 0.49555 | 1.4821 |  |  |  | 15 | 19.2 | 34.2 | 30.2695 |  | 3.6 | 80 | 83.6 | 53.9772 |  | 3.6 | 19.2 | 22.8 | 12.9545 |  | 3.6 | 19.2 | 22.8 | 12.9545 |  | 3.6 | 19.2 | 22.8 | 12.9545 |  | 3.6 | 19.2 | 22.8 | 12.9545 |  | 209 | 136.0649 | 104500 |  | 0.058933 |  | 33 | 176 |  | 66.593 | 118.7499 | 118.7499 | [12 empty] | E
Project-A03 |  | v003 |  | 0.49345 | 4.9998 |  |  |  | 16 | 6.48 | 22.48 | 32.4246 |  | 3.84 | 27 | 30.84 | 7.7819 |  | 3.84 | 6.48 | 10.32 | 7.7819 |  | 3.84 | 6.48 | 10.32 | 7.7819 |  | 3.84 | 6.48 | 10.32 | 7.7819 |  | 3.84 | 6.48 | 10.32 | 7.7819 |  | 94.6 | 71.334 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 71.334 | 11.8804 | 71.334 | [12 empty] | N
Project-A04 |  | v004 |  | 0.51578 | 1.4965 |  |  |  | 35 | 4.32 | 39.32 | 67.8579 |  | 8.4 | 18 | 26.4 | 16.2859 |  | 8.4 | 4.32 | 12.72 | 16.2859 |  | 8.4 | 4.32 | 12.72 | 16.2859 |  | 8.4 | 4.32 | 12.72 | 16.2859 |  | 8.4 | 4.32 | 12.72 | 16.2859 |  | 116.6 | 149.2873 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 149.2873 | 26.4609 | 149.2873 | [12 empty] | D
Project-A05 |  | v002 |  | 0.5135 | 0.25103 |  |  |  | 6 | 19.2 | 25.2 | 76.4838 |  | 1.44 | 80 | 81.44 | 318.6826 |  | 1.44 | 19.2 | 20.64 | 76.4838 |  | 1.44 | 19.2 | 20.64 | 76.4838 |  | 1.44 | 19.2 | 20.64 | 76.4838 |  | 1.44 | 19.2 | 20.64 | 76.4838 |  | 189.2 | 701.1017 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 25.7062 | 701.1017 | 701.1017
Project-A06 |  | v003 |  | 0.52593 | 1.5208 |  |  |  | 52 | 10.56 | 62.56 | 98.8731 |  | 12.48 | 44 | 56.48 | 28.9323 |  | 12.48 | 10.56 | 23.04 | 23.7295 |  | 12.48 | 10.56 | 23.04 | 23.7295 |  | 12.48 | 10.56 | 23.04 | 23.7295 |  | 12.48 | 10.56 | 23.04 | 23.7295 |  | 211.2 | 222.7235 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 217.5207 | 63.6511 | 217.5207 | [12 empty] | O
Project-A07 |  | v005 |  | 0.52106 | 1.5217 |  |  |  | 93 | 19.92 | 112.92 | 178.4823 |  | 22.32 | 83 | 105.32 | 54.5435 |  | 22.32 | 19.92 | 42.24 | 42.8358 |  | 22.32 | 19.92 | 42.24 | 42.8358 |  | 22.32 | 19.92 | 42.24 | 42.8358 |  | 22.32 | 19.92 | 42.24 | 42.8358 |  | 387.2 | 404.3688 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 392.6611 | 119.9957 | 392.6611 | [12 empty] | F
Project-A08 |  | v006 |  | 0.53907 | 3.2503 |  |  |  | 5 | 2.64 | 7.64 | 9.2752 |  | 1.2 | 11 | 12.2 | 3.3843 |  | 1.2 | 2.64 | 3.84 | 2.226 |  | 1.2 | 2.64 | 3.84 | 2.226 |  | 1.2 | 2.64 | 3.84 | 2.226 |  | 1.2 | 2.64 | 3.84 | 2.226 |  | 35.2 | 21.5637 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 20.4054 | 7.4455 | 20.4054
Project-A09 |  | v003 |  | 0.49691 | 1.566 |  |  |  | 49 | 20.64 | 69.64 | 98.6088 |  | 11.76 | 86 | 97.76 | 54.9176 |  | 11.76 | 20.64 | 32.4 | 23.6661 |  | 11.76 | 20.64 | 32.4 | 23.6661 |  | 11.76 | 20.64 | 32.4 | 23.6661 |  | 11.76 | 20.64 | 32.4 | 23.6661 |  | 297 | 248.1909 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 216.9394 | 120.8188 | 216.9394 | [12 empty] | T
Project-A10 |  | v001 |  | 0.52098 | 1.6071 |  |  |  | 36 | 20.88 | 56.88 | 69.1003 |  | 8.64 | 87 | 95.64 | 54.1351 |  | 8.64 | 20.88 | 29.52 | 16.5841 |  | 8.64 | 20.88 | 29.52 | 16.5841 |  | 8.64 | 20.88 | 29.52 | 16.5841 |  | 8.64 | 20.88 | 29.52 | 16.5841 |  | 270.6 | 189.5716 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 152.0206 | 119.0972 | 152.0206 | [12 empty] | H
Project-A11 |  | v002 |  | 0.53631 | 0.28568 |  |  |  | 63 | 19.2 | 82.2 | 117.4704 |  | 15.12 | 80 | 95.12 | 280.0376 |  | 15.12 | 19.2 | 34.32 | 67.209 |  | 15.12 | 19.2 | 34.32 | 67.209 |  | 15.12 | 19.2 | 34.32 | 67.209 |  | 15.12 | 19.2 | 34.32 | 67.209 |  | 314.6 | 666.3441 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 258.4348 | 616.0828 | 616.0828 | [12 empty] | I
Project-A12 |  | v004 |  | 0.51334 | 1.5119 |  |  |  | 65 | 21.84 | 86.84 | 126.622 |  | 15.6 | 91 | 106.6 | 60.1894 |  | 15.6 | 21.84 | 37.44 | 30.3893 |  | 15.6 | 21.84 | 37.44 | 30.3893 |  | 15.6 | 21.84 | 37.44 | 30.3893 |  | 15.6 | 21.84 | 37.44 | 30.3893 |  | 343.2 | 308.3685 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 278.5683 | 132.4168 | 278.5683 | [12 empty] | S
Project-A13 |  | v007 |  | 0.55088 | 1.9827 |  |  |  | 96 | 9.6 | 105.6 | 174.2682 |  | 23.04 | 40 | 63.04 | 41.8244 |  | 23.04 | 9.6 | 32.64 | 41.8244 |  | 23.04 | 9.6 | 32.64 | 41.8244 |  | 23.04 | 9.6 | 32.64 | 41.8244 |  | 23.04 | 9.6 | 32.64 | 41.8244 |  | 299.2 | 383.3901 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 383.3901 | 44.3831 | 383.3901
Project-A14 |  | v006 |  | 0.26328 | 1.983 |  |  |  | 39 | 12.72 | 51.72 | 148.1286 |  | 9.36 | 53 | 62.36 | 35.5509 |  | 9.36 | 12.72 | 22.08 | 35.5509 |  | 9.36 | 12.72 | 22.08 | 35.5509 |  | 9.36 | 12.72 | 22.08 | 35.5509 |  | 9.36 | 12.72 | 22.08 | 35.5509 |  | 202.4 | 325.8829 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 325.8829 | 58.7985 | 325.8829 | [12 empty] | W
Project-A15 |  | v008 |  | 0.98696 | 0.25 |  |  |  | 72 | 23.76 | 95.76 | 95.0397 |  | 17.28 | 99 | 116.28 | 395.9986 |  | 17.28 | 23.76 | 41.04 | 95.0397 |  | 17.28 | 23.76 | 41.04 | 95.0397 |  | 17.28 | 23.76 | 41.04 | 95.0397 |  | 17.28 | 23.76 | 41.04 | 95.0397 |  | 376.2 | 871.1969 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 160.4922 | 871.1969 | 871.1969 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.598 |  |  |  | 43.9333 | 15.248 | 59.1813 | 92.7283 |  | 10.544 | 63.5333 | 74.0773 | 112.6441 |  | 10.544 | 15.248 | 25.792 | 37.3721 |  | 10.544 | 15.248 | 25.792 | 37.3721 |  | 10.544 | 15.248 | 25.792 | 37.3721 |  | 10.544 | 15.248 | 25.792 | 37.3721 |  | 236.4267 | 354.8609 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 186.0137 | 242.3736 | 342.5777 | [12 empty] | S
|  | Total |  | 8 | 23.9699 |  |  |  | 659 | 228.72 | 887.72 | 1390.9251 |  | 158.16 | 953 | 1111.16 | 1689.6615 |  | 158.16 | 228.72 | 386.88 | 560.5817 |  | 158.16 | 228.72 | 386.88 | 560.5817 |  | 158.16 | 228.72 | 386.88 | 560.5817 |  | 158.16 | 228.72 | 386.88 | 560.5817 |  | 3546.4 | 5322.9135 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2790.205 | 3635.6038 | 5138.6656 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 1319.1969 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 409.1942 |  | <- To shorten average individual project span |  |  |  | <----------> | 342.5777
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 38.044 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 2708.6805 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 4475.1157 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.52699 | 0.2611 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-11 00:30 |  | 0 | 2014-03-12 00:30 | 2014-12-20 10:35 |  | 0 | 2014-12-21 10:35 | 2015-02-27 11:05 |  | 0 | 2015-02-28 11:05 | 2015-05-07 11:35 |  | 0 | 2015-05-08 11:35 | 2015-07-15 12:05 |  | 0 | 2015-07-16 12:05 | 2015-09-22 12:35 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 628.5246 | 1319.1969 | [14 empty] | E
Project-A02 |  | 0.49555 | 1.4821 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-01 06:28 |  | 0 | 2014-02-02 06:28 | 2014-03-28 05:55 |  | 0 | 2014-03-29 05:55 | 2014-04-11 04:50 |  | 0 | 2014-04-12 04:50 | 2014-04-25 03:44 |  | 0 | 2014-04-26 03:44 | 2014-05-09 02:39 |  | 0 | 2014-05-10 02:39 | 2014-05-23 01:33 |  | v002 |  | 0.058933 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 141.0649 | [15 empty] | N
Project-A03 |  | 0.49345 | 4.9998 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-03 10:11 |  | 0 | 2014-02-04 10:11 | 2014-02-12 04:57 |  | 0 | 2014-02-13 04:57 | 2014-02-20 23:43 |  | 0 | 2014-02-21 23:43 | 2014-03-01 18:29 |  | 0 | 2014-03-02 18:29 | 2014-03-10 13:15 |  | 0 | 2014-03-11 13:15 | 2014-03-19 08:01 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 76.334 | [15 empty] | D
Project-A04 |  | 0.51578 | 1.4965 |  |  |  | 2014-01-01 |  | 36 | 2014-02-07 | 2014-04-15 20:35 |  | 0 | 2014-04-16 20:35 | 2014-05-03 03:27 |  | 0 | 2014-05-04 03:27 | 2014-05-20 10:19 |  | 0 | 2014-05-21 10:19 | 2014-06-06 17:10 |  | 0 | 2014-06-07 17:10 | 2014-06-24 00:02 |  | 0 | 2014-06-25 00:02 | 2014-07-11 06:54 |  | v004 |  | 0.032878 |  | 36 | 0 | 0 | 0 | 0 | 0 | 36 | 17.7543 |  | 154.2873
Project-A05 |  | 0.5135 | 0.25103 |  |  |  | 2014-01-01 |  | 46 | 2014-02-17 | 2014-05-04 11:37 |  | 0 | 2014-05-05 11:37 | 2015-03-20 04:00 |  | 0 | 2015-03-21 04:00 | 2015-06-05 15:36 |  | 0 | 2015-06-06 15:36 | 2015-08-22 03:13 |  | 0 | 2015-08-23 03:13 | 2015-11-07 14:50 |  | 0 | 2015-11-08 14:50 | 2016-01-24 02:26 |  | v002 |  | 0.05335 |  | 46 | 0 | 0 | 0 | 0 | 0 | 46 | 36.8114 |  | 706.1017 | [15 empty] | O
Project-A06 |  | 0.52593 | 1.5208 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-06-05 20:57 |  | 0 | 2014-06-06 20:57 | 2014-07-05 19:20 |  | 0 | 2014-07-06 19:20 | 2014-07-30 12:50 |  | 0 | 2014-07-31 12:50 | 2014-08-24 06:21 |  | 0 | 2014-08-25 06:21 | 2014-09-17 23:51 |  | 0 | 2014-09-18 23:51 | 2014-10-12 17:22 |  | v003 |  | 0.059553 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 50.0248 |  | 227.7235 | [15 empty] | F
Project-A07 |  | 0.52106 | 1.5217 |  |  |  | 2014-01-01 |  | 68 | 2014-03-11 | 2014-09-05 11:35 |  | 0 | 2014-09-06 11:35 | 2014-10-31 00:37 |  | 0 | 2014-11-01 00:37 | 2014-12-13 20:41 |  | 1 | 2014-12-15 20:41 | 2015-01-27 16:44 |  | 1 | 2015-01-29 16:44 | 2015-03-13 12:48 |  | 0 | 2015-03-14 12:48 | 2015-04-26 08:51 |  | v005 |  | 0.10918 |  | 68 | 0 | 0 | 1 | 1 | 0 | 70 | 111.3648 |  | 411.3688
Project-A08 |  | 0.53907 | 3.2503 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 06:36 |  | 0 | 2014-01-12 06:36 | 2014-01-15 15:50 |  | 0 | 2014-01-16 15:50 | 2014-01-18 21:15 |  | 0 | 2014-01-19 21:15 | 2014-01-22 02:41 |  | 0 | 2014-01-23 02:41 | 2014-01-25 08:06 |  | 0 | 2014-01-26 08:06 | 2014-01-28 13:32 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 26.5637 | [15 empty] | T
Project-A09 |  | 0.49691 | 1.566 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-04-22 14:37 |  | 0 | 2014-04-23 14:37 | 2014-06-17 12:38 |  | 0 | 2014-06-18 12:38 | 2014-07-12 04:37 |  | 0 | 2014-07-13 04:37 | 2014-08-05 20:37 |  | 0 | 2014-08-06 20:37 | 2014-08-30 12:36 |  | 0 | 2014-08-31 12:36 | 2014-09-24 04:35 |  | v003 |  | 0.083747 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 15.0744 |  | 253.1909 | [15 empty] | H
Project-A10 |  | 0.52098 | 1.6071 |  |  |  | 2014-01-01 |  | 25 | 2014-01-27 | 2014-04-06 02:24 |  | 0 | 2014-04-07 02:24 | 2014-05-31 05:39 |  | 0 | 2014-06-01 05:39 | 2014-06-17 19:40 |  | 0 | 2014-06-18 19:40 | 2014-07-05 09:41 |  | 0 | 2014-07-06 09:41 | 2014-07-22 23:42 |  | 0 | 2014-07-23 23:42 | 2014-08-09 13:43 |  | v001 |  | 0.076303 |  | 25 | 0 | 0 | 0 | 0 | 0 | 25 | 28.6135 |  | 194.5716 | [15 empty] | I
Project-A11 |  | 0.53631 | 0.28568 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-06-02 11:17 |  | 0 | 2014-06-03 11:17 | 2015-03-10 12:12 |  | 0 | 2015-03-11 12:12 | 2015-05-17 17:13 |  | 0 | 2015-05-18 17:13 | 2015-07-24 22:14 |  | 0 | 2015-07-25 22:14 | 2015-10-01 03:15 |  | 0 | 2015-10-02 03:15 | 2015-12-08 08:16 |  | v002 |  | 0.08871 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 45.2419 |  | 671.3441 | [15 empty] | S
Project-A12 |  | 0.51334 | 1.5119 |  |  |  | 2014-01-01 |  | 47 | 2014-02-18 | 2014-06-24 14:56 |  | 0 | 2014-06-25 14:56 | 2014-08-24 19:28 |  | 0 | 2014-08-25 19:28 | 2014-09-25 04:49 |  | 4 | 2014-09-30 04:49 | 2014-10-30 14:10 |  | 1 | 2014-11-01 14:10 | 2014-12-01 23:30 |  | 2 | 2014-12-04 23:30 | 2015-01-04 08:51 |  | v004 |  | 0.096774 |  | 47 | 0 | 0 | 4 | 1 | 2 | 54 | 68.2258 |  | 320.3685
Project-A13 |  | 0.55088 | 1.9827 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-08-20 06:26 |  | 0 | 2014-08-21 06:26 | 2014-10-02 02:13 |  | 0 | 2014-10-03 02:13 | 2014-11-13 22:00 |  | 0 | 2014-11-14 22:00 | 2014-12-26 17:47 |  | 364 | 2015-12-26 17:47 | 2016-02-06 13:35 |  | 0 | 2016-02-07 13:35 | 2016-03-20 09:22 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 364 | 0 | 420 | 70.8685 |  | 752.3901 | [15 empty] | W
Project-A14 |  | 0.26328 | 1.983 |  |  |  | 2014-01-01 |  | 3 | 2014-01-05 | 2014-06-02 03:05 |  | 0 | 2014-06-03 03:05 | 2014-07-08 16:18 |  | 0 | 2014-07-09 16:18 | 2014-08-14 05:32 |  | 2 | 2014-08-17 05:32 | 2014-09-21 18:45 |  | 0 | 2014-09-22 18:45 | 2014-10-28 07:58 |  | 0 | 2014-10-29 07:58 | 2014-12-03 21:11 |  | v006 |  | 0.057072 |  | 3 | 0 | 0 | 2 | 0 | 0 | 5 | 2.5682 |  | 332.8829 | [15 empty] | O
Project-A15 |  | 0.98696 | 0.25 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-06-24 00:57 |  | 0 | 2014-06-25 00:57 | 2015-07-26 00:55 |  | 0 | 2015-07-27 00:55 | 2015-10-30 01:52 |  | 0 | 2015-10-31 01:52 | 2016-02-03 02:49 |  | 365 | 2017-02-03 02:49 | 2017-05-09 03:46 |  | 0 | 2017-05-10 03:46 | 2017-08-13 04:43 |  | v008 |  | 0.10608 |  | 78 | 0 | 0 | 0 | 365 | 0 | 443 | 124.1129 |  | 1241.1969 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.598 | [5 empty] | 30.7333 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.46667 |  |  |  | 48.7333 |  |  |  | 0.13333 | [5 empty] | 0.066667 |  | 30.7333 | 0 | 0 | 0.46667 | 48.7333 | 0.13333 | 80.0667 | 38.044 | Average | 409.1942 | [15 empty] | H
Total |  | 8 | 23.9699 | [5 empty] | 461 |  |  |  | 0 |  |  |  | 0 |  |  |  | 7 |  |  |  | 731 |  |  |  | 2 | [5 empty] | 1 |  | 461 | 0 | 0 | 7 | 731 | 2 | 1201 | 570.6607 | Total | 6137.9135 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 5
| Days: | 54.1736
E
N
SIT - Violation | Count: | 3 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 36.2597
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-12-21 10:35 | 2015-02-27 11:05 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-29 05:55 | 2014-04-11 04:50 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-13 04:57 | 2014-02-20 23:43 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-04 03:27 | 2014-05-20 10:19 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2015-03-21 04:00 | 2015-06-05 15:36 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-06 19:20 | 2014-07-30 12:50 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20.8555 | 0
Project-A07 | 2014-11-01 00:37 | 2014-12-13 20:41 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 1; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 12.8911 | 0 | 0 | W
Project-A08 | 2014-01-16 15:50 | 2014-01-18 21:15 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-18 12:38 | 2014-07-12 04:37 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 2.5131 | 0 | R
Project-A10 | 2014-06-01 05:39 | 2014-06-17 19:40 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2015-03-11 12:12 | 2015-05-17 17:13 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-25 19:28 | 2014-09-25 04:49 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-03 02:13 | 2014-11-13 22:00 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-07-09 16:18 | 2014-08-14 05:32 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2015-07-27 00:55 | 2015-10-30 01:52 | v008 | [31 empty] | T
UAT - Violation | Count: | 2 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 17.9139
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-02-28 11:05 | 2015-05-07 11:35 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-12 04:50 | 2014-04-25 03:44 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-21 23:43 | 2014-03-01 18:29 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-21 10:19 | 2014-06-06 17:10 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-06-06 15:36 | 2015-08-22 03:13 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-07-31 12:50 | 2014-08-24 06:21 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.0341 | 0
Project-A07 | 2014-12-15 20:41 | 2015-01-27 16:44 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 1; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 10.8797 | 0 | 0
Project-A08 | 2014-01-19 21:15 | 2014-01-22 02:41 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-13 04:37 | 2014-08-05 20:37 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-18 19:40 | 2014-07-05 09:41 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-05-18 17:13 | 2015-07-24 22:14 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-30 04:49 | 2014-10-30 14:10 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-11-14 22:00 | 2014-12-26 17:47 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-17 05:32 | 2014-09-21 18:45 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-10-31 01:52 | 2016-02-03 02:49 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-05-08 11:35 | 2015-07-15 12:05 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-26 03:44 | 2014-05-09 02:39 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-02 18:29 | 2014-03-10 13:15 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-07 17:10 | 2014-06-24 00:02 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-08-23 03:13 | 2015-11-07 14:50 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-25 06:21 | 2014-09-17 23:51 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-01-29 16:44 | 2015-03-13 12:48 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-23 02:41 | 2014-01-25 08:06 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-06 20:37 | 2014-08-30 12:36 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-06 09:41 | 2014-07-22 23:42 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-07-25 22:14 | 2015-10-01 03:15 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-01 14:10 | 2014-12-01 23:30 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-12-26 17:47 | 2016-02-06 13:35 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-09-22 18:45 | 2014-10-28 07:58 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2017-02-03 02:49 | 2017-05-09 03:46 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-07-16 12:05 | 2015-09-22 12:35 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-10 02:39 | 2014-05-23 01:33 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-11 13:15 | 2014-03-19 08:01 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-25 00:02 | 2014-07-11 06:54 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-11-08 14:50 | 2016-01-24 02:26 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-18 23:51 | 2014-10-12 17:22 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-03-14 12:48 | 2015-04-26 08:51 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-26 08:06 | 2014-01-28 13:32 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-31 12:36 | 2014-09-24 04:35 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-23 23:42 | 2014-08-09 13:43 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-10-02 03:15 | 2015-12-08 08:16 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-04 23:30 | 2015-01-04 08:51 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2016-02-07 13:35 | 2016-03-20 09:22 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-10-29 07:58 | 2014-12-03 21:11 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2017-05-10 03:46 | 2017-08-13 04:43 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.60587 | 60.5866 | 60
0.28724 | 28.724 | 28
0.78194 | 78.1941 | 78
0.08114 | 8.114 | 8
0.14172 | 14.1717 | 14
0.19739 | 19.7393 | 19
0.11681 | 11.6807 | 11
0.83682 | 83.6817 | 83
0.068663 | 6.8663 | 6
0.4879 | 48.7898 | 48
0.097758 | 9.7758 | 9
0.018427 | 1.8427 | 1
0.25388 | 25.3877 | 25
0.43554 | 43.5537 | 43
0.18466 | 18.466 | 18
0.86 | 86.0002 | 86
0.78619 | 78.619 | 78
0.94174 | 94.1742 | 94
0.028397 | 2.8397 | 2
0.91625 | 91.6246 | 91
0.97091 | 97.0911 | 97
0.069036 | 6.9036 | 6
0.82001 | 82.0011 | 82
0.031963 | 3.1963 | 3
0.33197 | 33.1971 | 33
0.075082 | 7.5082 | 7
0.053059 | 5.3059 | 5
0.047187 | 4.7187 | 4
0.2235 | 22.3501 | 22
0.86784 | 86.7845 | 86
0.73743 | 73.7429 | 73
0.20269 | 20.2687 | 20
0.70648 | 70.6479 | 70
0.93896 | 93.8959 | 93
0.82916 | 82.9159 | 82
0.84185 | 84.1849 | 84
0.21518 | 21.5185 | 21
0.023845 | 2.3845 | 2
0.48223 | 48.2228 | 48

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 4475.1157 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.9 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 23.9699 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH