## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.52144 | 0.27288 |  |  |  | 17 | 17.76 | 34.76 | 65.0824 |  | 4.08 | 74 | 78.08 | 271.1769 |  | 4.08 | 17.76 | 21.84 | 65.0824 |  | 4.08 | 17.76 | 21.84 | 65.0824 |  | 4.08 | 17.76 | 21.84 | 65.0824 |  | 4.08 | 17.76 | 21.84 | 65.0824 |  | 200.2 | 596.5891 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 71.7246 | 596.5891 | 596.5891
Project-A02 |  | v002 |  | 0.51852 | 3.2577 |  |  |  | 15 | 19.2 | 34.2 | 28.9287 |  | 3.6 | 80 | 83.6 | 24.5572 |  | 3.6 | 19.2 | 22.8 | 6.9429 |  | 3.6 | 19.2 | 22.8 | 6.9429 |  | 3.6 | 19.2 | 22.8 | 6.9429 |  | 3.6 | 19.2 | 22.8 | 6.9429 |  | 209 | 81.2575 | 104500 |  | 0.058933 |  | 33 | 176 |  | 63.6432 | 54.0258 | 63.6432 | [12 empty] | E
Project-A03 |  | v003 |  | 0.48804 | 1.7264 |  |  |  | 16 | 6.48 | 22.48 | 32.7839 |  | 3.84 | 27 | 30.84 | 15.6396 |  | 3.84 | 6.48 | 10.32 | 7.8681 |  | 3.84 | 6.48 | 10.32 | 7.8681 |  | 3.84 | 6.48 | 10.32 | 7.8681 |  | 3.84 | 6.48 | 10.32 | 7.8681 |  | 94.6 | 79.896 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 72.1245 | 34.4071 | 72.1245 | [12 empty] | N
Project-A04 |  | v004 |  | 0.49928 | 1.6893 |  |  |  | 35 | 4.32 | 39.32 | 70.1015 |  | 8.4 | 18 | 26.4 | 16.8244 |  | 8.4 | 4.32 | 12.72 | 16.8244 |  | 8.4 | 4.32 | 12.72 | 16.8244 |  | 8.4 | 4.32 | 12.72 | 16.8244 |  | 8.4 | 4.32 | 12.72 | 16.8244 |  | 116.6 | 154.2234 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 154.2234 | 23.4415 | 154.2234 | [12 empty] | D
Project-A05 |  | v002 |  | 0.48695 | 1.5683 |  |  |  | 6 | 19.2 | 25.2 | 12.3215 |  | 1.44 | 80 | 81.44 | 51.01 |  | 1.44 | 19.2 | 20.64 | 12.2424 |  | 1.44 | 19.2 | 20.64 | 12.2424 |  | 1.44 | 19.2 | 20.64 | 12.2424 |  | 1.44 | 19.2 | 20.64 | 12.2424 |  | 189.2 | 112.3011 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 27.1074 | 112.222 | 112.222
Project-A06 |  | v003 |  | 0.55816 | 1.5344 |  |  |  | 52 | 10.56 | 62.56 | 93.1641 |  | 12.48 | 44 | 56.48 | 28.6756 |  | 12.48 | 10.56 | 23.04 | 22.3594 |  | 12.48 | 10.56 | 23.04 | 22.3594 |  | 12.48 | 10.56 | 23.04 | 22.3594 |  | 12.48 | 10.56 | 23.04 | 22.3594 |  | 211.2 | 211.2771 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 204.9609 | 63.0863 | 204.9609 | [12 empty] | O
Project-A07 |  | v005 |  | 0.27587 | 1.522 |  |  |  | 93 | 19.92 | 112.92 | 337.1213 |  | 22.32 | 83 | 105.32 | 80.9091 |  | 22.32 | 19.92 | 42.24 | 80.9091 |  | 22.32 | 19.92 | 42.24 | 80.9091 |  | 22.32 | 19.92 | 42.24 | 80.9091 |  | 22.32 | 19.92 | 42.24 | 80.9091 |  | 387.2 | 741.6669 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 741.6669 | 119.9746 | 741.6669 | [12 empty] | F
Project-A08 |  | v006 |  | 0.54129 | 1.5029 |  |  |  | 5 | 2.64 | 7.64 | 9.2372 |  | 1.2 | 11 | 12.2 | 7.3192 |  | 1.2 | 2.64 | 3.84 | 2.2169 |  | 1.2 | 2.64 | 3.84 | 2.2169 |  | 1.2 | 2.64 | 3.84 | 2.2169 |  | 1.2 | 2.64 | 3.84 | 2.2169 |  | 35.2 | 25.4241 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 20.3219 | 16.1022 | 20.3219
Project-A09 |  | v003 |  | 0.56248 | 1.478 |  |  |  | 49 | 20.64 | 69.64 | 87.1146 |  | 11.76 | 86 | 97.76 | 58.1849 |  | 11.76 | 20.64 | 32.4 | 20.9075 |  | 11.76 | 20.64 | 32.4 | 20.9075 |  | 11.76 | 20.64 | 32.4 | 20.9075 |  | 11.76 | 20.64 | 32.4 | 20.9075 |  | 297 | 228.9295 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 191.652 | 128.0069 | 191.652 | [12 empty] | T
Project-A10 |  | v001 |  | 0.51345 | 1.5714 |  |  |  | 36 | 20.88 | 56.88 | 70.1141 |  | 8.64 | 87 | 95.64 | 55.3644 |  | 8.64 | 20.88 | 29.52 | 16.8274 |  | 8.64 | 20.88 | 29.52 | 16.8274 |  | 8.64 | 20.88 | 29.52 | 16.8274 |  | 8.64 | 20.88 | 29.52 | 16.8274 |  | 270.6 | 192.788 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 154.2509 | 121.8017 | 154.2509 | [12 empty] | H
Project-A11 |  | v002 |  | 0.50156 | 1.5213 |  |  |  | 63 | 19.2 | 82.2 | 125.6093 |  | 15.12 | 80 | 95.12 | 52.5865 |  | 15.12 | 19.2 | 34.32 | 30.1462 |  | 15.12 | 19.2 | 34.32 | 30.1462 |  | 15.12 | 19.2 | 34.32 | 30.1462 |  | 15.12 | 19.2 | 34.32 | 30.1462 |  | 314.6 | 298.7807 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 276.3404 | 115.6903 | 276.3404 | [12 empty] | I
Project-A12 |  | v004 |  | 0.48114 | 1.5215 |  |  |  | 65 | 21.84 | 86.84 | 135.0962 |  | 15.6 | 91 | 106.6 | 59.8112 |  | 15.6 | 21.84 | 37.44 | 32.4231 |  | 15.6 | 21.84 | 37.44 | 32.4231 |  | 15.6 | 21.84 | 37.44 | 32.4231 |  | 15.6 | 21.84 | 37.44 | 32.4231 |  | 343.2 | 324.5996 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 297.2116 | 131.5846 | 297.2116 | [12 empty] | S
Project-A13 |  | v007 |  | 0.5387 | 2.2127 |  |  |  | 96 | 9.6 | 105.6 | 178.2056 |  | 23.04 | 40 | 63.04 | 42.7693 |  | 23.04 | 9.6 | 32.64 | 42.7693 |  | 23.04 | 9.6 | 32.64 | 42.7693 |  | 23.04 | 9.6 | 32.64 | 42.7693 |  | 23.04 | 9.6 | 32.64 | 42.7693 |  | 299.2 | 392.0523 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 392.0523 | 39.7704 | 392.0523
Project-A14 |  | v006 |  | 0.50377 | 2.3652 |  |  |  | 39 | 12.72 | 51.72 | 77.4163 |  | 9.36 | 53 | 62.36 | 22.4083 |  | 9.36 | 12.72 | 22.08 | 18.5799 |  | 9.36 | 12.72 | 22.08 | 18.5799 |  | 9.36 | 12.72 | 22.08 | 18.5799 |  | 9.36 | 12.72 | 22.08 | 18.5799 |  | 202.4 | 174.1443 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 170.3159 | 49.2982 | 170.3159 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0094 | 0.25599 |  |  |  | 72 | 23.76 | 95.76 | 92.8164 |  | 17.28 | 99 | 116.28 | 386.7349 |  | 17.28 | 23.76 | 41.04 | 92.8164 |  | 17.28 | 23.76 | 41.04 | 92.8164 |  | 17.28 | 23.76 | 41.04 | 92.8164 |  | 17.28 | 23.76 | 41.04 | 92.8164 |  | 376.2 | 850.8168 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 156.9298 | 850.8168 | 850.8168 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 94.3409 |  | 10.544 | 63.5333 | 74.0773 | 78.2648 |  | 10.544 | 15.248 | 25.792 | 31.261 |  | 10.544 | 15.248 | 25.792 | 31.261 |  | 10.544 | 15.248 | 25.792 | 31.261 |  | 10.544 | 15.248 | 25.792 | 31.261 |  | 236.4267 | 297.6498 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 199.635 | 163.7878 | 286.5595 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1415.1131 |  | 158.16 | 953 | 1111.16 | 1173.9714 |  | 158.16 | 228.72 | 386.88 | 468.9155 |  | 158.16 | 228.72 | 386.88 | 468.9155 |  | 158.16 | 228.72 | 386.88 | 468.9155 |  | 158.16 | 228.72 | 386.88 | 468.9155 |  | 3546.4 | 4464.7464 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2994.5257 | 2456.8174 | 4298.3918 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 943.8168 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 306.0498 |  | <- To shorten average individual project span |  |  |  | <----------> | 286.5595
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 62.1563 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 2097.0113 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 3409.0342 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.52144 | 0.27288 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-08 01:59 |  | 0 | 2014-03-09 01:59 | 2014-12-05 06:13 |  | 0 | 2014-12-06 06:13 | 2015-02-09 08:12 |  | 0 | 2015-02-10 08:12 | 2015-04-16 10:11 |  | 0 | 2015-04-17 10:11 | 2015-06-21 12:10 |  | 0 | 2015-06-22 12:10 | 2015-08-26 14:08 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 601.5891 | 943.8168 | [14 empty] | E
Project-A02 |  | 0.51852 | 3.2577 |  |  |  | 2014-01-01 |  | 20 | 2014-01-22 | 2014-02-19 22:17 |  | 0 | 2014-02-20 22:17 | 2014-03-17 11:40 |  | 0 | 2014-03-18 11:40 | 2014-03-25 10:17 |  | 0 | 2014-03-26 10:17 | 2014-04-02 08:55 |  | 0 | 2014-04-03 08:55 | 2014-04-10 07:33 |  | 0 | 2014-04-11 07:33 | 2014-04-18 06:11 |  | v002 |  | 0.058933 |  | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 17.6799 |  | 86.2575 | [15 empty] | N
Project-A03 |  | 0.48804 | 1.7264 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-03 18:49 |  | 0 | 2014-02-04 18:49 | 2014-02-20 10:10 |  | 0 | 2014-02-21 10:10 | 2014-03-01 07:00 |  | 0 | 2014-03-02 07:00 | 2014-03-10 03:50 |  | 0 | 2014-03-11 03:50 | 2014-03-19 00:40 |  | 0 | 2014-03-20 00:40 | 2014-03-27 21:30 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 84.896 | [15 empty] | D
Project-A04 |  | 0.49928 | 1.6893 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-13 02:26 |  | 0 | 2014-03-14 02:26 | 2014-03-30 22:13 |  | 0 | 2014-03-31 22:13 | 2014-04-17 18:00 |  | 0 | 2014-04-18 18:00 | 2014-05-05 13:48 |  | 0 | 2014-05-06 13:48 | 2014-05-23 09:35 |  | 0 | 2014-05-24 09:35 | 2014-06-10 05:22 |  | v004 |  | 0.032878 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 159.2234
Project-A05 |  | 0.48695 | 1.5683 |  |  |  | 2014-01-01 |  | 59 | 2014-03-02 | 2014-03-14 07:43 |  | 0 | 2014-03-15 07:43 | 2014-05-05 07:57 |  | 0 | 2014-05-06 07:57 | 2014-05-18 13:46 |  | 0 | 2014-05-19 13:46 | 2014-05-31 19:36 |  | 0 | 2014-06-01 19:36 | 2014-06-14 01:25 |  | 0 | 2014-06-15 01:25 | 2014-06-27 07:14 |  | v002 |  | 0.05335 |  | 59 | 0 | 0 | 0 | 0 | 0 | 59 | 47.2146 |  | 117.3011 | [15 empty] | O
Project-A06 |  | 0.55816 | 1.5344 |  |  |  | 2014-01-01 |  | 61 | 2014-03-04 | 2014-06-05 03:56 |  | 0 | 2014-06-06 03:56 | 2014-07-04 20:09 |  | 0 | 2014-07-05 20:09 | 2014-07-28 04:47 |  | 16 | 2014-08-14 04:47 | 2014-09-05 13:24 |  | 0 | 2014-09-06 13:24 | 2014-09-28 22:02 |  | 3 | 2014-10-02 22:02 | 2014-10-25 06:39 |  | v003 |  | 0.059553 |  | 61 | 0 | 0 | 16 | 0 | 3 | 80 | 54.4913 |  | 235.2771 | [15 empty] | F
Project-A07 |  | 0.27587 | 1.522 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-12-05 02:55 |  | 0 | 2014-12-06 02:55 | 2015-02-25 00:44 |  | 0 | 2015-02-26 00:44 | 2015-05-17 22:33 |  | 0 | 2015-05-18 22:33 | 2015-08-07 20:22 |  | 0 | 2015-08-08 20:22 | 2015-10-28 18:11 |  | 0 | 2015-10-29 18:11 | 2016-01-18 16:00 |  | v005 |  | 0.10918 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 746.6669
Project-A08 |  | 0.54129 | 1.5029 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 05:42 |  | 0 | 2014-01-12 05:42 | 2014-01-19 13:21 |  | 0 | 2014-01-20 13:21 | 2014-01-22 18:34 |  | 0 | 2014-01-23 18:34 | 2014-01-25 23:46 |  | 0 | 2014-01-26 23:46 | 2014-01-29 04:58 |  | 1 | 2014-01-31 04:58 | 2014-02-02 10:11 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 31.4241 | [15 empty] | T
Project-A09 |  | 0.56248 | 1.478 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-30 02:45 |  | 0 | 2014-03-31 02:45 | 2014-05-28 07:11 |  | 0 | 2014-05-29 07:11 | 2014-06-19 04:58 |  | 0 | 2014-06-20 04:58 | 2014-07-11 02:45 |  | 0 | 2014-07-12 02:45 | 2014-08-02 00:32 |  | 6 | 2014-08-09 00:32 | 2014-08-29 22:18 |  | v003 |  | 0.083747 |  | 0 | 0 | 0 | 0 | 0 | 6 | 6 | 0 |  | 239.9295 | [15 empty] | H
Project-A10 |  | 0.51345 | 1.5714 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-03-13 02:44 |  | 0 | 2015-03-14 02:44 | 2015-05-08 11:29 |  | 0 | 2015-05-09 11:29 | 2015-05-26 07:20 |  | 0 | 2015-05-27 07:20 | 2015-06-13 03:12 |  | 0 | 2015-06-14 03:12 | 2015-06-30 23:03 |  | 0 | 2015-07-01 23:03 | 2015-07-18 18:55 |  | v001 |  | 0.076303 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 417.7574 |  | 197.788 | [15 empty] | I
Project-A11 |  | 0.50156 | 1.5213 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-06-10 14:37 |  | 0 | 2014-06-11 14:37 | 2014-08-03 04:42 |  | 0 | 2014-08-04 04:42 | 2014-09-03 08:12 |  | 8 | 2014-09-12 08:12 | 2014-10-12 11:43 |  | 0 | 2014-10-13 11:43 | 2014-11-12 15:14 |  | 0 | 2014-11-13 15:14 | 2014-12-13 18:44 |  | v002 |  | 0.08871 |  | 34 | 0 | 0 | 8 | 0 | 0 | 42 | 45.2419 |  | 311.7807 | [15 empty] | S
Project-A12 |  | 0.48114 | 1.5215 |  |  |  | 2014-01-01 |  | 53 | 2014-02-24 | 2014-07-09 02:18 |  | 0 | 2014-07-10 02:18 | 2014-09-07 21:47 |  | 0 | 2014-09-08 21:47 | 2014-10-11 07:56 |  | 8 | 2014-10-20 07:56 | 2014-11-21 18:05 |  | 0 | 2014-11-22 18:05 | 2014-12-25 04:14 |  | 0 | 2014-12-26 04:14 | 2015-01-27 14:23 |  | v004 |  | 0.096774 |  | 53 | 0 | 0 | 8 | 0 | 0 | 61 | 76.9355 |  | 337.5996
Project-A13 |  | 0.5387 | 2.2127 |  |  |  | 2014-01-01 |  | 59 | 2014-03-02 | 2014-08-27 04:56 |  | 0 | 2014-08-28 04:56 | 2014-10-09 23:24 |  | 0 | 2014-10-10 23:24 | 2014-11-22 17:52 |  | 0 | 2014-11-23 17:52 | 2015-01-05 12:20 |  | 0 | 2015-01-06 12:20 | 2015-02-18 06:47 |  | 1 | 2015-02-20 06:47 | 2015-04-04 01:15 |  | v007 |  | 0.084367 |  | 59 | 0 | 0 | 0 | 0 | 1 | 60 | 74.665 |  | 398.0523 | [15 empty] | W
Project-A14 |  | 0.50377 | 2.3652 |  |  |  | 2014-01-01 |  | 70 | 2014-03-13 | 2014-05-29 10:00 |  | 0 | 2014-05-30 10:00 | 2014-06-21 19:47 |  | 0 | 2014-06-22 19:47 | 2014-07-11 09:43 |  | 7 | 2014-07-19 09:43 | 2014-08-06 23:38 |  | 0 | 2014-08-07 23:38 | 2014-08-26 13:33 |  | 0 | 2014-08-27 13:33 | 2014-09-15 03:28 |  | v006 |  | 0.057072 |  | 70 | 0 | 0 | 7 | 0 | 0 | 77 | 59.9256 |  | 186.1443 | [15 empty] | O
Project-A15 |  | 1.0094 | 0.25599 |  |  |  | 2014-01-01 |  | 87 | 2014-03-30 | 2014-06-30 19:36 |  | 0 | 2014-07-01 19:36 | 2015-07-23 13:14 |  | 0 | 2015-07-24 13:14 | 2015-10-25 08:49 |  | 0 | 2015-10-26 08:49 | 2016-01-27 04:25 |  | 0 | 2016-01-28 04:25 | 2016-04-30 00:01 |  | 1 | 2016-05-02 00:01 | 2016-08-02 19:36 |  | v008 |  | 0.10608 |  | 87 | 0 | 0 | 0 | 0 | 1 | 88 | 138.4336 |  | 856.8168 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 53.8667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 2.6 |  |  |  | 0 |  |  |  | 0.8 | [5 empty] | 0.066667 |  | 53.8667 | 0 | 0 | 2.6 | 0 | 0.8 | 57.2667 | 62.1563 | Average | 306.0498 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 808 |  |  |  | 0 |  |  |  | 0 |  |  |  | 39 |  |  |  | 0 |  |  |  | 12 | [5 empty] | 1 |  | 808 | 0 | 0 | 39 | 0 | 12 | 859 | 932.3449 | Total | 4590.7464 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 5
| Days: | 41.9402
E
N
SIT - Violation | Count: | 3 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 14.3815
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-12-06 06:13 | 2015-02-09 08:12 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-18 11:40 | 2014-03-25 10:17 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-21 10:10 | 2014-03-01 07:00 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-03-31 22:13 | 2014-04-17 18:00 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-05-06 07:57 | 2014-05-18 13:46 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-05 20:09 | 2014-07-28 04:47 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.5649 | 0
Project-A07 | 2015-02-26 00:44 | 2015-05-17 22:33 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 1; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 8.4611 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-20 13:21 | 2014-01-22 18:34 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-05-29 07:11 | 2014-06-19 04:58 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2015-05-09 11:29 | 2015-05-26 07:20 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-08-04 04:42 | 2014-09-03 08:12 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-09-08 21:47 | 2014-10-11 07:56 | v004 |  | Count P-A13: 1; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0.35548 | 0 | 0 | H
Project-A13 | 2014-10-10 23:24 | 2014-11-22 17:52 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-22 19:47 | 2014-07-11 09:43 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2015-07-24 13:14 | 2015-10-25 08:49 | v008 | [31 empty] | T
UAT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 25.1936
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-02-10 08:12 | 2015-04-16 10:11 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-26 10:17 | 2014-04-02 08:55 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-02 07:00 | 2014-03-10 03:50 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-04-18 18:00 | 2014-05-05 13:48 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-19 13:46 | 2014-05-31 19:36 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-14 04:47 | 2014-09-05 13:24 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-05-18 22:33 | 2015-08-07 20:22 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 1; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 25.1936 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-23 18:34 | 2014-01-25 23:46 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-06-20 04:58 | 2014-07-11 02:45 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-05-27 07:20 | 2015-06-13 03:12 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-12 08:12 | 2014-10-12 11:43 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-20 07:56 | 2014-11-21 18:05 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-11-23 17:52 | 2015-01-05 12:20 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-19 09:43 | 2014-08-06 23:38 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-10-26 08:49 | 2016-01-27 04:25 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-04-17 10:11 | 2015-06-21 12:10 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-03 08:55 | 2014-04-10 07:33 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-11 03:50 | 2014-03-19 00:40 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-06 13:48 | 2014-05-23 09:35 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-06-01 19:36 | 2014-06-14 01:25 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-06 13:24 | 2014-09-28 22:02 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-08 20:22 | 2015-10-28 18:11 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-26 23:46 | 2014-01-29 04:58 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-12 02:45 | 2014-08-02 00:32 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-06-14 03:12 | 2015-06-30 23:03 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-13 11:43 | 2014-11-12 15:14 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-22 18:05 | 2014-12-25 04:14 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-06 12:20 | 2015-02-18 06:47 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-07 23:38 | 2014-08-26 13:33 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-01-28 04:25 | 2016-04-30 00:01 | v008
Prod - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 2.3651
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-06-22 12:10 | 2015-08-26 14:08 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-11 07:33 | 2014-04-18 06:11 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-20 00:40 | 2014-03-27 21:30 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-24 09:35 | 2014-06-10 05:22 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-06-15 01:25 | 2014-06-27 07:14 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-10-02 22:02 | 2014-10-25 06:39 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-29 18:11 | 2016-01-18 16:00 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-31 04:58 | 2014-02-02 10:11 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-09 00:32 | 2014-08-29 22:18 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 2.3651 | 0
Project-A10 | 2015-07-01 23:03 | 2015-07-18 18:55 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-11-13 15:14 | 2014-12-13 18:44 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-26 04:14 | 2015-01-27 14:23 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-02-20 06:47 | 2015-04-04 01:15 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-27 13:33 | 2014-09-15 03:28 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-05-02 00:01 | 2016-08-02 19:36 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.9336 | 93.3596 | 93
0.10636 | 10.6358 | 10
0.42261 | 42.261 | 42
0.71842 | 71.8421 | 71
0.23704 | 23.7043 | 23
0.58956 | 58.9562 | 58
0.96408 | 96.408 | 96
0.97328 | 97.3276 | 97
0.66221 | 66.2209 | 66
0.80549 | 80.549 | 80
0.44223 | 44.2229 | 44
0.45878 | 45.8776 | 45
0.25835 | 25.8347 | 25
0.20143 | 20.1428 | 20
0.67063 | 67.0629 | 67
0.97474 | 97.4741 | 97
0.6749 | 67.4896 | 67
0.59947 | 59.9468 | 59
0.14702 | 14.7019 | 14
0.41647 | 41.6469 | 41
0.35356 | 35.3557 | 35
0.984 | 98.4001 | 98
0.57948 | 57.9475 | 57
0.80674 | 80.6742 | 80
0.90376 | 90.3763 | 90
0.12701 | 12.701 | 12
0.83588 | 83.5883 | 83
0.49439 | 49.439 | 49
0.16193 | 16.1934 | 16
0.020199 | 2.0199 | 2
0.18364 | 18.3637 | 18
0.15688 | 15.6884 | 15
0.12269 | 12.2688 | 12
0.69036 | 69.0365 | 69
0.37126 | 37.1261 | 37
0.79965 | 79.9647 | 79
0.91266 | 91.2664 | 91
0.73845 | 73.8447 | 73
0.64905 | 64.905 | 64

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 3409.0342 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.9 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH