## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.50085 | 1.5393 |  |  |  | 17 | 17.76 | 34.76 | 33.9421 |  | 4.08 | 74 | 78.08 | 48.073 |  | 4.08 | 17.76 | 21.84 | 11.5375 |  | 4.08 | 17.76 | 21.84 | 11.5375 |  | 4.08 | 17.76 | 21.84 | 11.5375 |  | 4.08 | 17.76 | 21.84 | 11.5375 |  | 200.2 | 128.1651 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 74.6726 | 105.7605 | 105.7605
Project-A02 |  | v002 |  | 0.51845 | 1.5316 |  |  |  | 15 | 19.2 | 34.2 | 28.9324 |  | 3.6 | 80 | 83.6 | 52.2346 |  | 3.6 | 19.2 | 22.8 | 12.5363 |  | 3.6 | 19.2 | 22.8 | 12.5363 |  | 3.6 | 19.2 | 22.8 | 12.5363 |  | 3.6 | 19.2 | 22.8 | 12.5363 |  | 209 | 131.3122 | 104500 |  | 0.058933 |  | 33 | 176 |  | 63.6512 | 114.9161 | 114.9161 | [12 empty] | E
Project-A03 |  | v003 |  | 0.4987 | 1.5774 |  |  |  | 16 | 6.48 | 22.48 | 32.0834 |  | 3.84 | 27 | 30.84 | 17.1168 |  | 3.84 | 6.48 | 10.32 | 7.7 |  | 3.84 | 6.48 | 10.32 | 7.7 |  | 3.84 | 6.48 | 10.32 | 7.7 |  | 3.84 | 6.48 | 10.32 | 7.7 |  | 94.6 | 80.0003 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 70.5835 | 37.6569 | 70.5835 | [12 empty] | N
Project-A04 |  | v004 |  | 0.50682 | 1.5511 |  |  |  | 35 | 4.32 | 39.32 | 69.0576 |  | 8.4 | 18 | 26.4 | 16.5738 |  | 8.4 | 4.32 | 12.72 | 16.5738 |  | 8.4 | 4.32 | 12.72 | 16.5738 |  | 8.4 | 4.32 | 12.72 | 16.5738 |  | 8.4 | 4.32 | 12.72 | 16.5738 |  | 116.6 | 151.9268 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 151.9268 | 25.5296 | 151.9268 | [12 empty] | D
Project-A05 |  | v002 |  | 0.50285 | 1.5443 |  |  |  | 6 | 19.2 | 25.2 | 12.4331 |  | 1.44 | 80 | 81.44 | 51.8045 |  | 1.44 | 19.2 | 20.64 | 12.4331 |  | 1.44 | 19.2 | 20.64 | 12.4331 |  | 1.44 | 19.2 | 20.64 | 12.4331 |  | 1.44 | 19.2 | 20.64 | 12.4331 |  | 189.2 | 113.9699 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 26.2506 | 113.9699 | 113.9699
Project-A06 |  | v003 |  | 0.49851 | 1.5889 |  |  |  | 52 | 10.56 | 62.56 | 104.3105 |  | 12.48 | 44 | 56.48 | 27.6922 |  | 12.48 | 10.56 | 23.04 | 25.0345 |  | 12.48 | 10.56 | 23.04 | 25.0345 |  | 12.48 | 10.56 | 23.04 | 25.0345 |  | 12.48 | 10.56 | 23.04 | 25.0345 |  | 211.2 | 232.1408 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 229.4831 | 60.9229 | 229.4831 | [12 empty] | O
Project-A07 |  | v005 |  | 0.50473 | 1.5056 |  |  |  | 93 | 19.92 | 112.92 | 184.256 |  | 22.32 | 83 | 105.32 | 55.1263 |  | 22.32 | 19.92 | 42.24 | 44.2214 |  | 22.32 | 19.92 | 42.24 | 44.2214 |  | 22.32 | 19.92 | 42.24 | 44.2214 |  | 22.32 | 19.92 | 42.24 | 44.2214 |  | 387.2 | 416.2682 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 405.3633 | 121.2779 | 405.3633 | [12 empty] | F
Project-A08 |  | v006 |  | 0.56574 | 1.5224 |  |  |  | 5 | 2.64 | 7.64 | 8.838 |  | 1.2 | 11 | 12.2 | 7.2256 |  | 1.2 | 2.64 | 3.84 | 2.1211 |  | 1.2 | 2.64 | 3.84 | 2.1211 |  | 1.2 | 2.64 | 3.84 | 2.1211 |  | 1.2 | 2.64 | 3.84 | 2.1211 |  | 35.2 | 24.5481 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 19.4437 | 15.8963 | 19.4437
Project-A09 |  | v003 |  | 0.54548 | 0.28961 |  |  |  | 49 | 20.64 | 69.64 | 89.829 |  | 11.76 | 86 | 97.76 | 296.9546 |  | 11.76 | 20.64 | 32.4 | 71.2691 |  | 11.76 | 20.64 | 32.4 | 71.2691 |  | 11.76 | 20.64 | 32.4 | 71.2691 |  | 11.76 | 20.64 | 32.4 | 71.2691 |  | 297 | 671.86 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 197.6237 | 653.3001 | 653.3001 | [12 empty] | T
Project-A10 |  | v001 |  | 0.51702 | 1.5104 |  |  |  | 36 | 20.88 | 56.88 | 69.6298 |  | 8.64 | 87 | 95.64 | 57.6009 |  | 8.64 | 20.88 | 29.52 | 16.7111 |  | 8.64 | 20.88 | 29.52 | 16.7111 |  | 8.64 | 20.88 | 29.52 | 16.7111 |  | 8.64 | 20.88 | 29.52 | 16.7111 |  | 270.6 | 194.0753 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 153.1855 | 126.722 | 153.1855 | [12 empty] | H
Project-A11 |  | v002 |  | 0.26133 | 1.4658 |  |  |  | 63 | 19.2 | 82.2 | 241.0702 |  | 15.12 | 80 | 95.12 | 57.8569 |  | 15.12 | 19.2 | 34.32 | 57.8569 |  | 15.12 | 19.2 | 34.32 | 57.8569 |  | 15.12 | 19.2 | 34.32 | 57.8569 |  | 15.12 | 19.2 | 34.32 | 57.8569 |  | 314.6 | 530.3545 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 530.3545 | 120.0681 | 530.3545 | [12 empty] | I
Project-A12 |  | v004 |  | 0.49832 | 1.4891 |  |  |  | 65 | 21.84 | 86.84 | 130.4391 |  | 15.6 | 91 | 106.6 | 61.109 |  | 15.6 | 21.84 | 37.44 | 31.3054 |  | 15.6 | 21.84 | 37.44 | 31.3054 |  | 15.6 | 21.84 | 37.44 | 31.3054 |  | 15.6 | 21.84 | 37.44 | 31.3054 |  | 343.2 | 316.7695 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 286.9659 | 134.4397 | 286.9659 | [12 empty] | S
Project-A13 |  | v007 |  | 0.54309 | 2.0634 |  |  |  | 96 | 9.6 | 105.6 | 176.7666 |  | 23.04 | 40 | 63.04 | 42.424 |  | 23.04 | 9.6 | 32.64 | 42.424 |  | 23.04 | 9.6 | 32.64 | 42.424 |  | 23.04 | 9.6 | 32.64 | 42.424 |  | 23.04 | 9.6 | 32.64 | 42.424 |  | 299.2 | 388.8864 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 388.8864 | 42.6477 | 388.8864
Project-A14 |  | v006 |  | 0.51934 | 2.0699 |  |  |  | 39 | 12.72 | 51.72 | 75.0949 |  | 9.36 | 53 | 62.36 | 25.6053 |  | 9.36 | 12.72 | 22.08 | 18.0228 |  | 9.36 | 12.72 | 22.08 | 18.0228 |  | 9.36 | 12.72 | 22.08 | 18.0228 |  | 9.36 | 12.72 | 22.08 | 18.0228 |  | 202.4 | 172.7913 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 165.2087 | 56.3316 | 165.2087 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0188 | 2.7511 |  |  |  | 72 | 23.76 | 95.76 | 70.674 |  | 17.28 | 99 | 116.28 | 35.9852 |  | 17.28 | 23.76 | 41.04 | 16.9618 |  | 17.28 | 23.76 | 41.04 | 16.9618 |  | 17.28 | 23.76 | 41.04 | 16.9618 |  | 17.28 | 23.76 | 41.04 | 16.9618 |  | 376.2 | 174.5062 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 155.4828 | 79.1674 | 155.4828 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 88.4904 |  | 10.544 | 63.5333 | 74.0773 | 56.8922 |  | 10.544 | 15.248 | 25.792 | 25.7806 |  | 10.544 | 15.248 | 25.792 | 25.7806 |  | 10.544 | 15.248 | 25.792 | 25.7806 |  | 10.544 | 15.248 | 25.792 | 25.7806 |  | 236.4267 | 248.505 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 194.6055 | 120.5738 | 236.3221 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1327.3566 |  | 158.16 | 953 | 1111.16 | 853.3826 |  | 158.16 | 228.72 | 386.88 | 386.7088 |  | 158.16 | 228.72 | 386.88 | 386.7088 |  | 158.16 | 228.72 | 386.88 | 386.7088 |  | 158.16 | 228.72 | 386.88 | 386.7088 |  | 3546.4 | 3727.5746 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2919.0825 | 1808.6068 | 3544.8309 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 966.1408 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 304.6383 |  | <- To shorten average individual project span |  |  |  | <----------> | 236.3221
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 94.678 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 294.0098 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1659.467 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.50085 | 1.5393 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-04 22:37 |  | 0 | 2014-02-05 22:37 | 2014-03-26 00:22 |  | 0 | 2014-03-27 00:22 | 2014-04-07 13:16 |  | 4 | 2014-04-12 13:16 | 2014-04-24 02:10 |  | 6 | 2014-05-01 02:10 | 2014-05-12 15:04 |  | 0 | 2014-05-13 15:04 | 2014-05-25 03:58 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 4 | 6 | 0 | 10 | 0 |  | 143.1651 | 966.1408 | [14 empty] | E
Project-A02 |  | 0.51845 | 1.5316 |  |  |  | 2014-01-01 |  | 16 | 2014-01-18 | 2014-02-15 22:23 |  | 0 | 2014-02-16 22:23 | 2014-04-10 04:00 |  | 0 | 2014-04-11 04:00 | 2014-04-23 16:53 |  | 2 | 2014-04-26 16:53 | 2014-05-09 05:45 |  | 0 | 2014-05-10 05:45 | 2014-05-22 18:37 |  | 0 | 2014-05-23 18:37 | 2014-06-05 07:30 |  | v002 |  | 0.058933 |  | 16 | 0 | 0 | 2 | 0 | 0 | 18 | 14.1439 |  | 138.3122 | [15 empty] | N
Project-A03 |  | 0.4987 | 1.5774 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-03 02:00 |  | 0 | 2014-02-04 02:00 | 2014-02-21 04:48 |  | 0 | 2014-02-22 04:48 | 2014-03-01 21:36 |  | 0 | 2014-03-02 21:36 | 2014-03-10 14:24 |  | 0 | 2014-03-11 14:24 | 2014-03-19 07:12 |  | 2 | 2014-03-22 07:12 | 2014-03-30 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 |  | 87.0003 | [15 empty] | D
Project-A04 |  | 0.50682 | 1.5511 |  |  |  | 2014-01-01 |  | 35 | 2014-02-06 | 2014-04-16 01:23 |  | 0 | 2014-04-17 01:23 | 2014-05-03 15:09 |  | 0 | 2014-05-04 15:09 | 2014-05-21 04:56 |  | 0 | 2014-05-22 04:56 | 2014-06-07 18:42 |  | 0 | 2014-06-08 18:42 | 2014-06-25 08:28 |  | 0 | 2014-06-26 08:28 | 2014-07-12 22:15 |  | v004 |  | 0.032878 |  | 35 | 0 | 0 | 0 | 0 | 0 | 35 | 17.2612 |  | 156.9268
Project-A05 |  | 0.50285 | 1.5443 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-02-28 10:24 |  | 0 | 2014-03-01 10:24 | 2014-04-22 05:42 |  | 0 | 2014-04-23 05:42 | 2014-05-05 16:06 |  | 0 | 2014-05-06 16:06 | 2014-05-19 02:29 |  | 0 | 2014-05-20 02:29 | 2014-06-01 12:53 |  | 0 | 2014-06-02 12:53 | 2014-06-14 23:17 |  | v002 |  | 0.05335 |  | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 36.0112 |  | 118.9699 | [15 empty] | O
Project-A06 |  | 0.49851 | 1.5889 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-04-16 07:27 |  | 0 | 2015-04-17 07:27 | 2015-05-15 00:04 |  | 0 | 2015-05-16 00:04 | 2015-06-10 00:54 |  | 362 | 2016-06-07 00:54 | 2016-07-02 01:43 |  | 0 | 2016-07-03 01:43 | 2016-07-28 02:33 |  | 2 | 2016-07-31 02:33 | 2016-08-25 03:23 |  | v003 |  | 0.059553 |  | 365 | 0 | 0 | 362 | 0 | 2 | 729 | 326.0546 |  | 601.1408 | [15 empty] | F
Project-A07 |  | 0.50473 | 1.5056 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-07-05 06:09 |  | 0 | 2015-07-06 06:09 | 2015-08-30 09:11 |  | 0 | 2015-08-31 09:11 | 2015-10-14 14:30 |  | 0 | 2015-10-15 14:30 | 2015-11-28 19:48 |  | 0 | 2015-11-29 19:48 | 2016-01-13 01:07 |  | 3 | 2016-01-17 01:07 | 2016-03-01 06:26 |  | v005 |  | 0.10918 |  | 365 | 0 | 0 | 0 | 0 | 3 | 368 | 597.7667 |  | 424.2682
Project-A08 |  | 0.56574 | 1.5224 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-10 20:07 |  | 0 | 2014-01-11 20:07 | 2014-01-19 01:32 |  | 0 | 2014-01-20 01:32 | 2014-01-22 04:26 |  | 0 | 2014-01-23 04:26 | 2014-01-25 07:20 |  | 0 | 2014-01-26 07:20 | 2014-01-28 10:15 |  | 2 | 2014-01-31 10:15 | 2014-02-02 13:09 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 |  | 31.5481 | [15 empty] | T
Project-A09 |  | 0.54548 | 0.28961 |  |  |  | 2014-01-01 |  | 14 | 2014-01-16 | 2014-04-15 19:54 |  | 0 | 2014-04-16 19:54 | 2015-02-07 18:48 |  | 0 | 2015-02-08 18:48 | 2015-04-21 01:16 |  | 0 | 2015-04-22 01:16 | 2015-07-02 07:43 |  | 0 | 2015-07-03 07:43 | 2015-09-12 14:11 |  | 1 | 2015-09-14 14:11 | 2015-11-24 20:38 |  | v003 |  | 0.083747 |  | 14 | 0 | 0 | 0 | 0 | 1 | 15 | 17.5868 |  | 677.86 | [15 empty] | H
Project-A10 |  | 0.51702 | 1.5104 |  |  |  | 2014-01-01 |  | 24 | 2014-01-26 | 2014-04-05 15:07 |  | 0 | 2014-04-06 15:07 | 2014-06-03 05:32 |  | 0 | 2014-06-04 05:32 | 2014-06-20 22:36 |  | 0 | 2014-06-21 22:36 | 2014-07-08 15:40 |  | 0 | 2014-07-09 15:40 | 2014-07-26 08:44 |  | 5 | 2014-08-01 08:44 | 2014-08-18 01:48 |  | v001 |  | 0.076303 |  | 24 | 0 | 0 | 0 | 0 | 5 | 29 | 27.469 |  | 204.0753 | [15 empty] | I
Project-A11 |  | 0.26133 | 1.4658 |  |  |  | 2014-01-01 |  | 42 | 2014-02-13 | 2014-10-12 01:41 |  | 0 | 2014-10-13 01:41 | 2014-12-09 22:15 |  | 0 | 2014-12-10 22:15 | 2015-02-06 18:49 |  | 0 | 2015-02-07 18:49 | 2015-04-06 15:23 |  | 0 | 2015-04-07 15:23 | 2015-06-04 11:57 |  | 2 | 2015-06-07 11:57 | 2015-08-04 08:30 |  | v002 |  | 0.08871 |  | 42 | 0 | 0 | 0 | 0 | 2 | 44 | 55.8871 |  | 537.3545 | [15 empty] | S
Project-A12 |  | 0.49832 | 1.4891 |  |  |  | 2014-01-01 |  | 47 | 2014-02-18 | 2014-06-28 10:32 |  | 0 | 2014-06-29 10:32 | 2014-08-29 13:09 |  | 0 | 2014-08-30 13:09 | 2014-09-30 20:29 |  | 0 | 2014-10-01 20:29 | 2014-11-02 03:49 |  | 0 | 2014-11-03 03:49 | 2014-12-04 11:08 |  | 2 | 2014-12-07 11:08 | 2015-01-07 18:28 |  | v004 |  | 0.096774 |  | 47 | 0 | 0 | 0 | 0 | 2 | 49 | 68.2258 |  | 323.7695
Project-A13 |  | 0.54309 | 2.0634 |  |  |  | 2014-01-01 |  | 58 | 2014-03-01 | 2014-08-24 18:24 |  | 0 | 2014-08-25 18:24 | 2014-10-07 04:34 |  | 0 | 2014-10-08 04:34 | 2014-11-19 14:45 |  | 0 | 2014-11-20 14:45 | 2015-01-02 00:55 |  | 0 | 2015-01-03 00:55 | 2015-02-14 11:06 |  | 0 | 2015-02-15 11:06 | 2015-03-29 21:16 |  | v007 |  | 0.084367 |  | 58 | 0 | 0 | 0 | 0 | 0 | 58 | 73.3995 |  | 393.8864 | [15 empty] | W
Project-A14 |  | 0.51934 | 2.0699 |  |  |  | 2014-01-01 |  | 69 | 2014-03-12 | 2014-05-26 02:17 |  | 0 | 2014-05-27 02:17 | 2014-06-21 16:48 |  | 0 | 2014-06-22 16:48 | 2014-07-10 17:21 |  | 0 | 2014-07-11 17:21 | 2014-07-29 17:54 |  | 0 | 2014-07-30 17:54 | 2014-08-17 18:27 |  | 364 | 2015-08-17 18:27 | 2015-09-04 18:59 |  | v006 |  | 0.057072 |  | 69 | 0 | 0 | 0 | 0 | 364 | 433 | 59.0695 |  | 541.7913 | [15 empty] | O
Project-A15 |  | 1.0188 | 2.7511 |  |  |  | 2014-01-01 |  | 80 | 2014-03-23 | 2014-06-01 16:11 |  | 0 | 2014-06-02 16:11 | 2014-07-08 15:49 |  | 0 | 2014-07-09 15:49 | 2014-07-26 14:54 |  | 7 | 2014-08-03 14:54 | 2014-08-20 13:59 |  | 3 | 2014-08-24 13:59 | 2014-09-10 13:04 |  | 0 | 2014-09-11 13:04 | 2014-09-28 12:09 |  | v008 |  | 0.10608 |  | 80 | 0 | 0 | 7 | 3 | 0 | 90 | 127.2953 |  | 189.5062 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 77.3333 |  |  |  | 0 |  |  |  | 0 |  |  |  | 25 |  |  |  | 0.6 |  |  |  | 25.5333 | [5 empty] | 0.066667 |  | 77.3333 | 0 | 0 | 25 | 0.6 | 25.5333 | 128.4667 | 94.678 | Average | 304.6383 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 1160 |  |  |  | 0 |  |  |  | 0 |  |  |  | 375 |  |  |  | 9 |  |  |  | 383 | [5 empty] | 1 |  | 1160 | 0 | 0 | 375 | 9 | 383 | 1927 | 1420.1706 | Total | 4569.5746 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 4
| Days: | 5.8802
E
N
SIT - Violation | Count: | 2 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 2.1029
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-27 00:22 | 2014-04-07 13:16 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-11 04:00 | 2014-04-23 16:53 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-22 04:48 | 2014-03-01 21:36 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-04 15:09 | 2014-05-21 04:56 | v004 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 1.0392 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-04-23 05:42 | 2014-05-05 16:06 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2015-05-16 00:04 | 2015-06-10 00:54 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-31 09:11 | 2015-10-14 14:30 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-20 01:32 | 2014-01-22 04:26 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2015-02-08 18:48 | 2015-04-21 01:16 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-06-04 05:32 | 2014-06-20 22:36 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-12-10 22:15 | 2015-02-06 18:49 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-30 13:09 | 2014-09-30 20:29 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-08 04:34 | 2014-11-19 14:45 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-22 16:48 | 2014-07-10 17:21 | v006 | [30 empty] | 1.0637 | E | bar: Count P-A15
Project-A15 | 2014-07-09 15:49 | 2014-07-26 14:54 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-12 13:16 | 2014-04-24 02:10 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-26 16:53 | 2014-05-09 05:45 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-02 21:36 | 2014-03-10 14:24 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-22 04:56 | 2014-06-07 18:42 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-06 16:06 | 2014-05-19 02:29 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2016-06-07 00:54 | 2016-07-02 01:43 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-15 14:30 | 2015-11-28 19:48 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-23 04:26 | 2014-01-25 07:20 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-04-22 01:16 | 2015-07-02 07:43 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-21 22:36 | 2014-07-08 15:40 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-02-07 18:49 | 2015-04-06 15:23 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-01 20:29 | 2014-11-02 03:49 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-11-20 14:45 | 2015-01-02 00:55 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-11 17:21 | 2014-07-29 17:54 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-03 14:54 | 2014-08-20 13:59 | v008
NFT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 2.388
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-05-01 02:10 | 2014-05-12 15:04 | v001 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.388 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-10 05:45 | 2014-05-22 18:37 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-11 14:24 | 2014-03-19 07:12 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-08 18:42 | 2014-06-25 08:28 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-20 02:29 | 2014-06-01 12:53 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2016-07-03 01:43 | 2016-07-28 02:33 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-11-29 19:48 | 2016-01-13 01:07 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-26 07:20 | 2014-01-28 10:15 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-07-03 07:43 | 2015-09-12 14:11 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-09 15:40 | 2014-07-26 08:44 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-04-07 15:23 | 2015-06-04 11:57 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-03 03:49 | 2014-12-04 11:08 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-03 00:55 | 2015-02-14 11:06 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-30 17:54 | 2014-08-17 18:27 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-24 13:59 | 2014-09-10 13:04 | v008
Prod - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 1.3892
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-05-13 15:04 | 2014-05-25 03:58 | v001 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.3892 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-23 18:37 | 2014-06-05 07:30 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-22 07:12 | 2014-03-30 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-26 08:28 | 2014-07-12 22:15 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-06-02 12:53 | 2014-06-14 23:17 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2016-07-31 02:33 | 2016-08-25 03:23 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-01-17 01:07 | 2016-03-01 06:26 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-31 10:15 | 2014-02-02 13:09 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-09-14 14:11 | 2015-11-24 20:38 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-08-01 08:44 | 2014-08-18 01:48 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-06-07 11:57 | 2015-08-04 08:30 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-07 11:08 | 2015-01-07 18:28 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-02-15 11:06 | 2015-03-29 21:16 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-08-17 18:27 | 2015-09-04 18:59 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-11 13:04 | 2014-09-28 12:09 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.14592 | 14.5919 | 14
0.73675 | 73.6751 | 73
0.71896 | 71.8964 | 71
0.41201 | 41.2012 | 41
0.63463 | 63.4626 | 63
0.6403 | 64.0299 | 64
0.59945 | 59.9447 | 59
0.0099685 | 0.99685 | 0
0.73695 | 73.6952 | 73
0.65951 | 65.951 | 65
0.78495 | 78.4949 | 78
0.89517 | 89.5172 | 89
0.013539 | 1.3539 | 1
0.8765 | 87.6504 | 87
0.10077 | 10.0775 | 10
0.67665 | 67.6645 | 67
0.1774 | 17.7401 | 17
0.54186 | 54.186 | 54
0.92127 | 92.1266 | 92
0.42741 | 42.7407 | 42
0.58649 | 58.6494 | 58
0.54195 | 54.1946 | 54
0.81004 | 81.0043 | 81
0.081571 | 8.1571 | 8
0.50519 | 50.5189 | 50
0.052309 | 5.2309 | 5
0.67359 | 67.3595 | 67
0.64112 | 64.1119 | 64
0.49533 | 49.5327 | 49
0.34994 | 34.9937 | 34
0.17319 | 17.319 | 17
0.67607 | 67.607 | 67
0.069142 | 6.9142 | 6
0.75621 | 75.6206 | 75
0.14423 | 14.4234 | 14
0.045503 | 4.5503 | 4
0.99101 | 99.1006 | 99
0.78382 | 78.3819 | 78
0.39571 | 39.5712 | 39

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1659.467 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.9 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH