## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.51222 | 0.28602 |  |  |  | 17 | 17.76 | 34.76 | 62.0927 |  | 4.08 | 74 | 78.08 | 258.7198 |  | 4.08 | 17.76 | 21.84 | 62.0927 |  | 4.08 | 17.76 | 21.84 | 62.0927 |  | 4.08 | 17.76 | 21.84 | 62.0927 |  | 4.08 | 17.76 | 21.84 | 62.0927 |  | 200.2 | 569.1835 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 73.0159 | 569.1835 | 569.1835
Project-A02 |  | v002 |  | 0.52786 | 1.6051 |  |  |  | 15 | 19.2 | 34.2 | 28.4165 |  | 3.6 | 80 | 83.6 | 49.8397 |  | 3.6 | 19.2 | 22.8 | 11.9615 |  | 3.6 | 19.2 | 22.8 | 11.9615 |  | 3.6 | 19.2 | 22.8 | 11.9615 |  | 3.6 | 19.2 | 22.8 | 11.9615 |  | 209 | 126.1023 | 104500 |  | 0.058933 |  | 33 | 176 |  | 62.5162 | 109.6474 | 109.6474 | [12 empty] | E
Project-A03 |  | v003 |  | 0.51086 | 2.4685 |  |  |  | 16 | 6.48 | 22.48 | 31.32 |  | 3.84 | 27 | 30.84 | 10.9376 |  | 3.84 | 6.48 | 10.32 | 7.5168 |  | 3.84 | 6.48 | 10.32 | 7.5168 |  | 3.84 | 6.48 | 10.32 | 7.5168 |  | 3.84 | 6.48 | 10.32 | 7.5168 |  | 94.6 | 72.3248 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 68.904 | 24.0628 | 68.904 | [12 empty] | N
Project-A04 |  | v004 |  | 0.53027 | 1.528 |  |  |  | 35 | 4.32 | 39.32 | 66.0042 |  | 8.4 | 18 | 26.4 | 15.841 |  | 8.4 | 4.32 | 12.72 | 15.841 |  | 8.4 | 4.32 | 12.72 | 15.841 |  | 8.4 | 4.32 | 12.72 | 15.841 |  | 8.4 | 4.32 | 12.72 | 15.841 |  | 116.6 | 145.2093 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 145.2093 | 25.9155 | 145.2093 | [12 empty] | D
Project-A05 |  | v002 |  | 0.50706 | 1.4253 |  |  |  | 6 | 19.2 | 25.2 | 13.4712 |  | 1.44 | 80 | 81.44 | 56.1302 |  | 1.44 | 19.2 | 20.64 | 13.4712 |  | 1.44 | 19.2 | 20.64 | 13.4712 |  | 1.44 | 19.2 | 20.64 | 13.4712 |  | 1.44 | 19.2 | 20.64 | 13.4712 |  | 189.2 | 123.4864 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 26.0324 | 123.4864 | 123.4864
Project-A06 |  | v003 |  | 0.54266 | 1.6096 |  |  |  | 52 | 10.56 | 62.56 | 95.8234 |  | 12.48 | 44 | 56.48 | 27.3367 |  | 12.48 | 10.56 | 23.04 | 22.9976 |  | 12.48 | 10.56 | 23.04 | 22.9976 |  | 12.48 | 10.56 | 23.04 | 22.9976 |  | 12.48 | 10.56 | 23.04 | 22.9976 |  | 211.2 | 215.1506 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 210.8116 | 60.1407 | 210.8116 | [12 empty] | O
Project-A07 |  | v005 |  | 0.49594 | 0.36955 |  |  |  | 93 | 19.92 | 112.92 | 187.5224 |  | 22.32 | 83 | 105.32 | 224.5954 |  | 22.32 | 19.92 | 42.24 | 53.9029 |  | 22.32 | 19.92 | 42.24 | 53.9029 |  | 22.32 | 19.92 | 42.24 | 53.9029 |  | 22.32 | 19.92 | 42.24 | 53.9029 |  | 387.2 | 627.7294 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 412.5494 | 494.1098 | 494.1098 | [12 empty] | F
Project-A08 |  | v006 |  | 0.52953 | 2.3793 |  |  |  | 5 | 2.64 | 7.64 | 9.4424 |  | 1.2 | 11 | 12.2 | 4.6231 |  | 1.2 | 2.64 | 3.84 | 2.2662 |  | 1.2 | 2.64 | 3.84 | 2.2662 |  | 1.2 | 2.64 | 3.84 | 2.2662 |  | 1.2 | 2.64 | 3.84 | 2.2662 |  | 35.2 | 23.1302 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 20.7733 | 10.1708 | 20.7733
Project-A09 |  | v003 |  | 0.27991 | 1.4735 |  |  |  | 49 | 20.64 | 69.64 | 175.0592 |  | 11.76 | 86 | 97.76 | 58.3658 |  | 11.76 | 20.64 | 32.4 | 42.0142 |  | 11.76 | 20.64 | 32.4 | 42.0142 |  | 11.76 | 20.64 | 32.4 | 42.0142 |  | 11.76 | 20.64 | 32.4 | 42.0142 |  | 297 | 401.4819 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 385.1303 | 128.4048 | 385.1303 | [12 empty] | T
Project-A10 |  | v001 |  | 0.54563 | 1.5331 |  |  |  | 36 | 20.88 | 56.88 | 65.9793 |  | 8.64 | 87 | 95.64 | 56.7482 |  | 8.64 | 20.88 | 29.52 | 15.835 |  | 8.64 | 20.88 | 29.52 | 15.835 |  | 8.64 | 20.88 | 29.52 | 15.835 |  | 8.64 | 20.88 | 29.52 | 15.835 |  | 270.6 | 186.0676 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 145.1544 | 124.8461 | 145.1544 | [12 empty] | H
Project-A11 |  | v002 |  | 0.50491 | 1.5267 |  |  |  | 63 | 19.2 | 82.2 | 124.7743 |  | 15.12 | 80 | 95.12 | 52.402 |  | 15.12 | 19.2 | 34.32 | 29.9458 |  | 15.12 | 19.2 | 34.32 | 29.9458 |  | 15.12 | 19.2 | 34.32 | 29.9458 |  | 15.12 | 19.2 | 34.32 | 29.9458 |  | 314.6 | 296.9597 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 274.5035 | 115.2845 | 274.5035 | [12 empty] | I
Project-A12 |  | v004 |  | 0.50946 | 0.25001 |  |  |  | 65 | 21.84 | 86.84 | 127.5861 |  | 15.6 | 91 | 106.6 | 363.9833 |  | 15.6 | 21.84 | 37.44 | 87.356 |  | 15.6 | 21.84 | 37.44 | 87.356 |  | 15.6 | 21.84 | 37.44 | 87.356 |  | 15.6 | 21.84 | 37.44 | 87.356 |  | 343.2 | 840.9933 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 280.6894 | 800.7632 | 800.7632 | [12 empty] | S
Project-A13 |  | v007 |  | 0.50836 | 1.9963 |  |  |  | 96 | 9.6 | 105.6 | 188.8409 |  | 23.04 | 40 | 63.04 | 45.3218 |  | 23.04 | 9.6 | 32.64 | 45.3218 |  | 23.04 | 9.6 | 32.64 | 45.3218 |  | 23.04 | 9.6 | 32.64 | 45.3218 |  | 23.04 | 9.6 | 32.64 | 45.3218 |  | 299.2 | 415.45 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 415.45 | 44.0811 | 415.45
Project-A14 |  | v006 |  | 0.49786 | 3.5312 |  |  |  | 39 | 12.72 | 51.72 | 78.3357 |  | 9.36 | 53 | 62.36 | 18.8006 |  | 9.36 | 12.72 | 22.08 | 18.8006 |  | 9.36 | 12.72 | 22.08 | 18.8006 |  | 9.36 | 12.72 | 22.08 | 18.8006 |  | 9.36 | 12.72 | 22.08 | 18.8006 |  | 202.4 | 172.3386 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 172.3386 | 33.0203 | 172.3386 | [12 empty] | W
Project-A15 |  | v008 |  | 0.99748 | 2.0178 |  |  |  | 72 | 23.76 | 95.76 | 72.182 |  | 17.28 | 99 | 116.28 | 49.0627 |  | 17.28 | 23.76 | 41.04 | 17.3237 |  | 17.28 | 23.76 | 41.04 | 17.3237 |  | 17.28 | 23.76 | 41.04 | 17.3237 |  | 17.28 | 23.76 | 41.04 | 17.3237 |  | 376.2 | 190.5395 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 158.8005 | 107.938 | 158.8005 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 88.4567 |  | 10.544 | 63.5333 | 74.0773 | 86.1805 |  | 10.544 | 15.248 | 25.792 | 29.7765 |  | 10.544 | 15.248 | 25.792 | 29.7765 |  | 10.544 | 15.248 | 25.792 | 29.7765 |  | 10.544 | 15.248 | 25.792 | 29.7765 |  | 236.4267 | 293.7431 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 190.1252 | 184.737 | 272.951 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1326.8505 |  | 158.16 | 953 | 1111.16 | 1292.708 |  | 158.16 | 228.72 | 386.88 | 446.6472 |  | 158.16 | 228.72 | 386.88 | 446.6472 |  | 158.16 | 228.72 | 386.88 | 446.6472 |  | 158.16 | 228.72 | 386.88 | 446.6472 |  | 3546.4 | 4406.1471 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2851.8787 | 2771.055 | 4094.2657 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 979.1835 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 302.0098 |  | <- To shorten average individual project span |  |  |  | <----------> | 272.951
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 92.5 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 2106.458 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 3480.1513 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.51222 | 0.28602 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-03-05 02:14 |  | 0 | 2015-03-06 02:14 | 2015-11-19 19:30 |  | 0 | 2015-11-20 19:30 | 2016-01-21 21:44 |  | 0 | 2016-01-22 21:44 | 2016-03-24 23:57 |  | 29 | 2016-04-23 23:57 | 2016-06-25 02:11 |  | 11 | 2016-07-07 02:11 | 2016-09-07 04:24 |  | v001 |  | 0.056452 |  | 365 | 0 | 0 | 0 | 29 | 11 | 405 | 309.0726 |  | 614.1835 | 979.1835 | [14 empty] | E
Project-A02 |  | 0.52786 | 1.6051 |  |  |  | 2014-01-01 |  | 15 | 2014-01-17 | 2014-02-14 10:00 |  | 0 | 2014-02-15 10:00 | 2014-04-06 06:09 |  | 0 | 2014-04-07 06:09 | 2014-04-19 05:14 |  | 0 | 2014-04-20 05:14 | 2014-05-02 04:18 |  | 0 | 2014-05-03 04:18 | 2014-05-15 03:23 |  | 0 | 2014-05-16 03:23 | 2014-05-28 02:27 |  | v002 |  | 0.058933 |  | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 13.2599 |  | 131.1023 | [15 empty] | N
Project-A03 |  | 0.51086 | 2.4685 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-02-25 07:41 |  | 0 | 2014-02-26 07:41 | 2014-03-09 06:11 |  | 0 | 2014-03-10 06:11 | 2014-03-17 18:35 |  | 0 | 2014-03-18 18:35 | 2014-03-26 06:59 |  | 0 | 2014-03-27 06:59 | 2014-04-03 19:24 |  | 0 | 2014-04-04 19:24 | 2014-04-12 07:48 |  | v003 |  | 0.026675 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 9.2029 |  | 77.3248 | [15 empty] | D
Project-A04 |  | 0.53027 | 1.528 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-03-09 00:06 |  | 0 | 2015-03-10 00:06 | 2015-03-25 20:17 |  | 0 | 2015-03-26 20:17 | 2015-04-11 16:28 |  | 0 | 2015-04-12 16:28 | 2015-04-28 12:39 |  | 3 | 2015-05-02 12:39 | 2015-05-18 08:50 |  | 5 | 2015-05-24 08:50 | 2015-06-09 05:01 |  | v004 |  | 0.032878 |  | 365 | 0 | 0 | 0 | 3 | 5 | 373 | 180.0093 |  | 158.2093
Project-A05 |  | 0.50706 | 1.4253 |  |  |  | 2014-01-01 |  | 47 | 2014-02-18 | 2014-03-03 11:19 |  | 0 | 2014-03-04 11:19 | 2014-04-29 14:26 |  | 0 | 2014-04-30 14:26 | 2014-05-14 01:45 |  | 0 | 2014-05-15 01:45 | 2014-05-28 13:03 |  | 0 | 2014-05-29 13:03 | 2014-06-12 00:22 |  | 0 | 2014-06-13 00:22 | 2014-06-26 11:40 |  | v002 |  | 0.05335 |  | 47 | 0 | 0 | 0 | 0 | 0 | 47 | 37.6117 |  | 128.4864 | [15 empty] | O
Project-A06 |  | 0.54266 | 1.6096 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-04-07 19:46 |  | 0 | 2015-04-08 19:46 | 2015-05-06 03:51 |  | 0 | 2015-05-07 03:51 | 2015-05-30 03:47 |  | 0 | 2015-05-31 03:47 | 2015-06-23 03:44 |  | 0 | 2015-06-24 03:44 | 2015-07-17 03:40 |  | 0 | 2015-07-18 03:40 | 2015-08-10 03:37 |  | v003 |  | 0.059553 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 326.0546 |  | 220.1506 | [15 empty] | F
Project-A07 |  | 0.49594 | 0.36955 |  |  |  | 2014-01-01 |  | 71 | 2014-03-14 | 2014-09-17 12:32 |  | 0 | 2014-09-18 12:32 | 2015-05-01 02:50 |  | 0 | 2015-05-02 02:50 | 2015-06-25 00:30 |  | 0 | 2015-06-26 00:30 | 2015-08-18 22:10 |  | 0 | 2015-08-19 22:10 | 2015-10-12 19:50 |  | 0 | 2015-10-13 19:50 | 2015-12-06 17:30 |  | v005 |  | 0.10918 |  | 71 | 0 | 0 | 0 | 0 | 0 | 71 | 116.2779 |  | 632.7294
Project-A08 |  | 0.52953 | 2.3793 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 10:37 |  | 0 | 2014-01-12 10:37 | 2014-01-17 01:34 |  | 0 | 2014-01-18 01:34 | 2014-01-20 07:58 |  | 0 | 2014-01-21 07:58 | 2014-01-23 14:21 |  | 0 | 2014-01-24 14:21 | 2014-01-26 20:44 |  | 0 | 2014-01-27 20:44 | 2014-01-30 03:07 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28.1302 | [15 empty] | T
Project-A09 |  | 0.27991 | 1.4735 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-06-26 01:25 |  | 0 | 2014-06-27 01:25 | 2014-08-24 10:12 |  | 0 | 2014-08-25 10:12 | 2014-10-06 10:33 |  | 0 | 2014-10-07 10:33 | 2014-11-18 10:53 |  | 0 | 2014-11-19 10:53 | 2014-12-31 11:13 |  | 0 | 2015-01-01 11:13 | 2015-02-12 11:34 |  | v003 |  | 0.083747 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 406.4819 | [15 empty] | H
Project-A10 |  | 0.54563 | 1.5331 |  |  |  | 2014-01-01 |  | 24 | 2014-01-26 | 2014-04-01 23:30 |  | 0 | 2014-04-02 23:30 | 2014-05-29 17:28 |  | 0 | 2014-05-30 17:28 | 2014-06-15 13:30 |  | 0 | 2014-06-16 13:30 | 2014-07-02 09:32 |  | 0 | 2014-07-03 09:32 | 2014-07-19 05:35 |  | 0 | 2014-07-20 05:35 | 2014-08-05 01:37 |  | v001 |  | 0.076303 |  | 24 | 0 | 0 | 0 | 0 | 0 | 24 | 27.469 |  | 191.0676 | [15 empty] | I
Project-A11 |  | 0.50491 | 1.5267 |  |  |  | 2014-01-01 |  | 35 | 2014-02-06 | 2014-06-10 18:35 |  | 0 | 2014-06-11 18:35 | 2014-08-03 04:14 |  | 0 | 2014-08-04 04:14 | 2014-09-03 02:56 |  | 0 | 2014-09-04 02:56 | 2014-10-04 01:38 |  | 1 | 2014-10-06 01:38 | 2014-11-05 00:20 |  | 0 | 2014-11-06 00:20 | 2014-12-05 23:02 |  | v002 |  | 0.08871 |  | 35 | 0 | 0 | 0 | 1 | 0 | 36 | 46.5726 |  | 302.9597 | [15 empty] | S
Project-A12 |  | 0.50946 | 0.25001 |  |  |  | 2014-01-01 |  | 46 | 2014-02-17 | 2014-06-24 14:04 |  | 0 | 2014-06-25 14:04 | 2015-06-24 13:40 |  | 0 | 2015-06-25 13:40 | 2015-09-20 22:12 |  | 0 | 2015-09-21 22:12 | 2015-12-18 06:45 |  | 0 | 2015-12-19 06:45 | 2016-03-15 15:18 |  | 0 | 2016-03-16 15:18 | 2016-06-11 23:50 |  | v004 |  | 0.096774 |  | 46 | 0 | 0 | 0 | 0 | 0 | 46 | 66.7742 |  | 845.9933
Project-A13 |  | 0.50836 | 1.9963 |  |  |  | 2014-01-01 |  | 57 | 2014-02-28 | 2014-09-04 20:11 |  | 0 | 2014-09-05 20:11 | 2014-10-21 03:54 |  | 0 | 2014-10-22 03:54 | 2014-12-06 11:38 |  | 0 | 2014-12-07 11:38 | 2015-01-21 19:21 |  | 0 | 2015-01-22 19:21 | 2015-03-09 03:05 |  | 0 | 2015-03-10 03:05 | 2015-04-24 10:48 |  | v007 |  | 0.084367 |  | 57 | 0 | 0 | 0 | 0 | 0 | 57 | 72.134 |  | 420.45 | [15 empty] | W
Project-A14 |  | 0.49786 | 3.5312 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-27 08:03 |  | 0 | 2014-05-28 08:03 | 2014-06-16 03:16 |  | 0 | 2014-06-17 03:16 | 2014-07-05 22:29 |  | 0 | 2014-07-06 22:29 | 2014-07-25 17:42 |  | 0 | 2014-07-26 17:42 | 2014-08-14 12:55 |  | 0 | 2014-08-15 12:55 | 2014-09-03 08:08 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 57.3573 |  | 177.3386 | [15 empty] | O
Project-A15 |  | 0.99748 | 2.0178 |  |  |  | 2014-01-01 |  | 79 | 2014-03-22 | 2014-06-02 04:22 |  | 0 | 2014-06-03 04:22 | 2014-07-22 05:52 |  | 0 | 2014-07-23 05:52 | 2014-08-09 13:39 |  | 0 | 2014-08-10 13:39 | 2014-08-27 21:25 |  | 0 | 2014-08-28 21:25 | 2014-09-15 05:11 |  | 0 | 2014-09-16 05:11 | 2014-10-03 12:57 |  | v008 |  | 0.10608 |  | 79 | 0 | 0 | 0 | 0 | 0 | 79 | 125.7041 |  | 195.5395 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 103.9333 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 2.2 |  |  |  | 1.0667 | [5 empty] | 0.066667 |  | 103.9333 | 0 | 0 | 0 | 2.2 | 1.0667 | 107.2 | 92.5 | Average | 302.0098 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 1559 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 33 |  |  |  | 16 | [5 empty] | 1 |  | 1559 | 0 | 0 | 0 | 33 | 16 | 1608 | 1387.5 | Total | 4530.1471 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 3
| Days: | 42.1292
E
N
SIT - Violation | Count: | 3 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 42.1292
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2015-11-20 19:30 | 2016-01-21 21:44 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-07 06:09 | 2014-04-19 05:14 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-03-10 06:11 | 2014-03-17 18:35 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2015-03-26 20:17 | 2015-04-11 16:28 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-04-30 14:26 | 2014-05-14 01:45 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2015-05-07 03:51 | 2015-05-30 03:47 | v003 | [7 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 28.0399 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-05-02 02:50 | 2015-06-25 00:30 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-18 01:34 | 2014-01-20 07:58 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-08-25 10:12 | 2014-10-06 10:33 | v003 |  | Count P-A10: 0; Count P-A11: 1; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 8.6971 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-05-30 17:28 | 2014-06-15 13:30 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-08-04 04:14 | 2014-09-03 02:56 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 1 | [11 empty] | 0 | 0 | 0 | 5.3921 | S
Project-A12 | 2015-06-25 13:40 | 2015-09-20 22:12 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-22 03:54 | 2014-12-06 11:38 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-17 03:16 | 2014-07-05 22:29 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-23 05:52 | 2014-08-09 13:39 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-01-22 21:44 | 2016-03-24 23:57 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-20 05:14 | 2014-05-02 04:18 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-18 18:35 | 2014-03-26 06:59 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2015-04-12 16:28 | 2015-04-28 12:39 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-15 01:45 | 2014-05-28 13:03 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-05-31 03:47 | 2015-06-23 03:44 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-06-26 00:30 | 2015-08-18 22:10 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-21 07:58 | 2014-01-23 14:21 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-10-07 10:33 | 2014-11-18 10:53 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-16 13:30 | 2014-07-02 09:32 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-04 02:56 | 2014-10-04 01:38 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2015-09-21 22:12 | 2015-12-18 06:45 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-07 11:38 | 2015-01-21 19:21 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-06 22:29 | 2014-07-25 17:42 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-10 13:39 | 2014-08-27 21:25 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-04-23 23:57 | 2016-06-25 02:11 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-03 04:18 | 2014-05-15 03:23 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-27 06:59 | 2014-04-03 19:24 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2015-05-02 12:39 | 2015-05-18 08:50 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-29 13:03 | 2014-06-12 00:22 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-06-24 03:44 | 2015-07-17 03:40 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-19 22:10 | 2015-10-12 19:50 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-24 14:21 | 2014-01-26 20:44 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-11-19 10:53 | 2014-12-31 11:13 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-03 09:32 | 2014-07-19 05:35 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-06 01:38 | 2014-11-05 00:20 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2015-12-19 06:45 | 2016-03-15 15:18 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-22 19:21 | 2015-03-09 03:05 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-26 17:42 | 2014-08-14 12:55 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-28 21:25 | 2014-09-15 05:11 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-07-07 02:11 | 2016-09-07 04:24 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-16 03:23 | 2014-05-28 02:27 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-04-04 19:24 | 2014-04-12 07:48 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2015-05-24 08:50 | 2015-06-09 05:01 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-06-13 00:22 | 2014-06-26 11:40 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-07-18 03:40 | 2015-08-10 03:37 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-13 19:50 | 2015-12-06 17:30 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-27 20:44 | 2014-01-30 03:07 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-01-01 11:13 | 2015-02-12 11:34 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-20 05:35 | 2014-08-05 01:37 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-11-06 00:20 | 2014-12-05 23:02 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2016-03-16 15:18 | 2016-06-11 23:50 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-10 03:05 | 2015-04-24 10:48 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-15 12:55 | 2014-09-03 08:08 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-16 05:11 | 2014-10-03 12:57 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.66993 | 66.9925 | 66
0.4336 | 43.3603 | 43
0.86886 | 86.8862 | 86
0.47726 | 47.7261 | 47
0.74695 | 74.6949 | 74
0.10722 | 10.7219 | 10
0.29823 | 29.8225 | 29
0.88433 | 88.4334 | 88
0.96898 | 96.8976 | 96
0.86735 | 86.7351 | 86
0.2033 | 20.3296 | 20
0.16357 | 16.357 | 16
0.033345 | 3.3345 | 3
0.21797 | 21.7971 | 21
0.29447 | 29.4466 | 29
0.90467 | 90.4666 | 90
0.68601 | 68.601 | 68
0.96302 | 96.3024 | 96
0.76679 | 76.6788 | 76
0.82441 | 82.4409 | 82
0.75434 | 75.4344 | 75
0.44997 | 44.9975 | 44
0.60534 | 60.5341 | 60
0.47486 | 47.4859 | 47
0.3007 | 30.0705 | 30
0.20089 | 20.0888 | 20
0.96465 | 96.4651 | 96
0.44598 | 44.5978 | 44
0.95032 | 95.0317 | 95
0.26164 | 26.1645 | 26
0.17047 | 17.0467 | 17
0.18798 | 18.7984 | 18
0.82596 | 82.596 | 82
0.25751 | 25.7507 | 25
0.32621 | 32.6213 | 32
0.43634 | 43.634 | 43
0.85724 | 85.724 | 85
0.14121 | 14.1208 | 14
0.75005 | 75.0045 | 75

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 3480.1513 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.9 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH