## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.56225 | 0.28167 |  |  |  | 17 | 17.76 | 34.76 | 63.0519 |  | 4.08 | 74 | 78.08 | 262.7164 |  | 4.08 | 17.76 | 21.84 | 63.0519 |  | 4.08 | 17.76 | 21.84 | 63.0519 |  | 4.08 | 17.76 | 21.84 | 63.0519 |  | 4.08 | 17.76 | 21.84 | 63.0519 |  | 200.2 | 577.9762 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 66.5188 | 577.9762 | 577.9762
Project-A02 |  | v002 |  | 0.54869 | 5 |  |  |  | 15 | 19.2 | 34.2 | 27.3379 |  | 3.6 | 80 | 83.6 | 16 |  | 3.6 | 19.2 | 22.8 | 6.5611 |  | 3.6 | 19.2 | 22.8 | 6.5611 |  | 3.6 | 19.2 | 22.8 | 6.5611 |  | 3.6 | 19.2 | 22.8 | 6.5611 |  | 209 | 69.5824 | 104500 |  | 0.058933 |  | 33 | 176 |  | 60.1435 | 35.2 | 60.1435 | [12 empty] | E
Project-A03 |  | v003 |  | 0.55092 | 1.7717 |  |  |  | 16 | 6.48 | 22.48 | 29.0425 |  | 3.84 | 27 | 30.84 | 15.2392 |  | 3.84 | 6.48 | 10.32 | 6.9702 |  | 3.84 | 6.48 | 10.32 | 6.9702 |  | 3.84 | 6.48 | 10.32 | 6.9702 |  | 3.84 | 6.48 | 10.32 | 6.9702 |  | 94.6 | 72.1625 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 63.8935 | 33.5262 | 63.8935 | [12 empty] | N
Project-A04 |  | v004 |  | 0.54791 | 1.5281 |  |  |  | 35 | 4.32 | 39.32 | 63.8786 |  | 8.4 | 18 | 26.4 | 15.3309 |  | 8.4 | 4.32 | 12.72 | 15.3309 |  | 8.4 | 4.32 | 12.72 | 15.3309 |  | 8.4 | 4.32 | 12.72 | 15.3309 |  | 8.4 | 4.32 | 12.72 | 15.3309 |  | 116.6 | 140.5328 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 140.5328 | 25.9139 | 140.5328 | [12 empty] | D
Project-A05 |  | v002 |  | 0.50677 | 0.28367 |  |  |  | 6 | 19.2 | 25.2 | 67.6848 |  | 1.44 | 80 | 81.44 | 282.0201 |  | 1.44 | 19.2 | 20.64 | 67.6848 |  | 1.44 | 19.2 | 20.64 | 67.6848 |  | 1.44 | 19.2 | 20.64 | 67.6848 |  | 1.44 | 19.2 | 20.64 | 67.6848 |  | 189.2 | 620.4442 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 26.0471 | 620.4442 | 620.4442
Project-A06 |  | v003 |  | 0.50719 | 1.6972 |  |  |  | 52 | 10.56 | 62.56 | 102.5259 |  | 12.48 | 44 | 56.48 | 25.9256 |  | 12.48 | 10.56 | 23.04 | 24.6062 |  | 12.48 | 10.56 | 23.04 | 24.6062 |  | 12.48 | 10.56 | 23.04 | 24.6062 |  | 12.48 | 10.56 | 23.04 | 24.6062 |  | 211.2 | 226.8763 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 225.557 | 57.0362 | 225.557 | [12 empty] | O
Project-A07 |  | v005 |  | 0.28593 | 1.5283 |  |  |  | 93 | 19.92 | 112.92 | 325.2568 |  | 22.32 | 83 | 105.32 | 78.0616 |  | 22.32 | 19.92 | 42.24 | 78.0616 |  | 22.32 | 19.92 | 42.24 | 78.0616 |  | 22.32 | 19.92 | 42.24 | 78.0616 |  | 22.32 | 19.92 | 42.24 | 78.0616 |  | 387.2 | 715.565 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 715.565 | 119.4756 | 715.565 | [12 empty] | F
Project-A08 |  | v006 |  | 0.585 | 1.5261 |  |  |  | 5 | 2.64 | 7.64 | 8.547 |  | 1.2 | 11 | 12.2 | 7.2077 |  | 1.2 | 2.64 | 3.84 | 2.0513 |  | 1.2 | 2.64 | 3.84 | 2.0513 |  | 1.2 | 2.64 | 3.84 | 2.0513 |  | 1.2 | 2.64 | 3.84 | 2.0513 |  | 35.2 | 23.9598 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 18.8033 | 15.857 | 18.8033
Project-A09 |  | v003 |  | 0.54112 | 1.5707 |  |  |  | 49 | 20.64 | 69.64 | 90.5531 |  | 11.76 | 86 | 97.76 | 54.7542 |  | 11.76 | 20.64 | 32.4 | 21.7327 |  | 11.76 | 20.64 | 32.4 | 21.7327 |  | 11.76 | 20.64 | 32.4 | 21.7327 |  | 11.76 | 20.64 | 32.4 | 21.7327 |  | 297 | 232.2382 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 199.2167 | 120.4592 | 199.2167 | [12 empty] | T
Project-A10 |  | v001 |  | 0.55711 | 1.492 |  |  |  | 36 | 20.88 | 56.88 | 64.6197 |  | 8.64 | 87 | 95.64 | 58.3108 |  | 8.64 | 20.88 | 29.52 | 15.5087 |  | 8.64 | 20.88 | 29.52 | 15.5087 |  | 8.64 | 20.88 | 29.52 | 15.5087 |  | 8.64 | 20.88 | 29.52 | 15.5087 |  | 270.6 | 184.9653 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 142.1633 | 128.2837 | 142.1633 | [12 empty] | H
Project-A11 |  | v002 |  | 0.51936 | 1.5113 |  |  |  | 63 | 19.2 | 82.2 | 121.3041 |  | 15.12 | 80 | 95.12 | 52.9351 |  | 15.12 | 19.2 | 34.32 | 29.113 |  | 15.12 | 19.2 | 34.32 | 29.113 |  | 15.12 | 19.2 | 34.32 | 29.113 |  | 15.12 | 19.2 | 34.32 | 29.113 |  | 314.6 | 290.6912 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 266.8691 | 116.4572 | 266.8691 | [12 empty] | I
Project-A12 |  | v004 |  | 0.50912 | 1.4965 |  |  |  | 65 | 21.84 | 86.84 | 127.672 |  | 15.6 | 91 | 106.6 | 60.8074 |  | 15.6 | 21.84 | 37.44 | 30.6413 |  | 15.6 | 21.84 | 37.44 | 30.6413 |  | 15.6 | 21.84 | 37.44 | 30.6413 |  | 15.6 | 21.84 | 37.44 | 30.6413 |  | 343.2 | 311.0444 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 280.8783 | 133.7762 | 280.8783 | [12 empty] | S
Project-A13 |  | v007 |  | 0.51136 | 2.0028 |  |  |  | 96 | 9.6 | 105.6 | 187.7345 |  | 23.04 | 40 | 63.04 | 45.0563 |  | 23.04 | 9.6 | 32.64 | 45.0563 |  | 23.04 | 9.6 | 32.64 | 45.0563 |  | 23.04 | 9.6 | 32.64 | 45.0563 |  | 23.04 | 9.6 | 32.64 | 45.0563 |  | 299.2 | 413.016 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 413.016 | 43.9376 | 413.016
Project-A14 |  | v006 |  | 0.25437 | 2.0584 |  |  |  | 39 | 12.72 | 51.72 | 153.3221 |  | 9.36 | 53 | 62.36 | 36.7973 |  | 9.36 | 12.72 | 22.08 | 36.7973 |  | 9.36 | 12.72 | 22.08 | 36.7973 |  | 9.36 | 12.72 | 22.08 | 36.7973 |  | 9.36 | 12.72 | 22.08 | 36.7973 |  | 202.4 | 337.3085 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 337.3085 | 56.6468 | 337.3085 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0129 | 0.25144 |  |  |  | 72 | 23.76 | 95.76 | 94.4956 |  | 17.28 | 99 | 116.28 | 393.7317 |  | 17.28 | 23.76 | 41.04 | 94.4956 |  | 17.28 | 23.76 | 41.04 | 94.4956 |  | 17.28 | 23.76 | 41.04 | 94.4956 |  | 17.28 | 23.76 | 41.04 | 94.4956 |  | 376.2 | 866.2097 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 156.3806 | 866.2097 | 866.2097 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 101.8018 |  | 10.544 | 63.5333 | 74.0773 | 93.6596 |  | 10.544 | 15.248 | 25.792 | 35.8442 |  | 10.544 | 15.248 | 25.792 | 35.8442 |  | 10.544 | 15.248 | 25.792 | 35.8442 |  | 10.544 | 15.248 | 25.792 | 35.8442 |  | 236.4267 | 338.8382 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 207.5262 | 196.7466 | 328.5718 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1527.0265 |  | 158.16 | 953 | 1111.16 | 1404.8942 |  | 158.16 | 228.72 | 386.88 | 537.663 |  | 158.16 | 228.72 | 386.88 | 537.663 |  | 158.16 | 228.72 | 386.88 | 537.663 |  | 158.16 | 228.72 | 386.88 | 537.663 |  | 3546.4 | 5082.5725 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3112.8935 | 2951.1997 | 4928.5771 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 947.2097 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 369.1715 |  | <- To shorten average individual project span |  |  |  | <----------> | 328.5718
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 44.5664 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 1918.581 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 3279.5286 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.56225 | 0.28167 |  |  |  | 2014-01-01 |  | 3 | 2014-01-05 | 2014-03-09 01:15 |  | 0 | 2014-03-10 01:15 | 2014-11-27 18:26 |  | 0 | 2014-11-28 18:26 | 2015-01-30 19:41 |  | 0 | 2015-01-31 19:41 | 2015-04-04 20:56 |  | 0 | 2015-04-05 20:56 | 2015-06-07 22:11 |  | 0 | 2015-06-08 22:11 | 2015-08-10 23:26 |  | v001 |  | 0.056452 |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 2.5403 |  | 582.9762 | 947.2097 | [14 empty] | E
Project-A02 |  | 0.54869 | 5 |  |  |  | 2014-01-01 |  | 14 | 2014-01-16 | 2014-02-12 08:07 |  | 0 | 2014-02-13 08:07 | 2014-03-01 08:07 |  | 0 | 2014-03-02 08:07 | 2014-03-08 21:35 |  | 0 | 2014-03-09 21:35 | 2014-03-16 11:03 |  | 0 | 2014-03-17 11:03 | 2014-03-24 00:31 |  | 0 | 2014-03-25 00:31 | 2014-03-31 13:59 |  | v002 |  | 0.058933 |  | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 12.3759 |  | 74.5824 | [15 empty] | N
Project-A03 |  | 0.55092 | 1.7717 |  |  |  | 2014-01-01 |  | 26 | 2014-01-28 | 2014-02-26 01:01 |  | 0 | 2014-02-27 01:01 | 2014-03-14 06:46 |  | 0 | 2014-03-15 06:46 | 2014-03-22 06:03 |  | 0 | 2014-03-23 06:03 | 2014-03-30 05:20 |  | 0 | 2014-03-31 05:20 | 2014-04-07 04:37 |  | 0 | 2014-04-08 04:37 | 2014-04-15 03:54 |  | v003 |  | 0.026675 |  | 26 | 0 | 0 | 0 | 0 | 0 | 26 | 10.4032 |  | 77.1625 | [15 empty] | D
Project-A04 |  | 0.54791 | 1.5281 |  |  |  | 2014-01-01 |  | 35 | 2014-02-06 | 2014-04-10 21:05 |  | 0 | 2014-04-11 21:05 | 2014-04-27 05:02 |  | 0 | 2014-04-28 05:02 | 2014-05-13 12:58 |  | 0 | 2014-05-14 12:58 | 2014-05-29 20:54 |  | 0 | 2014-05-30 20:54 | 2014-06-15 04:51 |  | 0 | 2014-06-16 04:51 | 2014-07-01 12:47 |  | v004 |  | 0.032878 |  | 35 | 0 | 0 | 0 | 0 | 0 | 35 | 17.2612 |  | 145.5328
Project-A05 |  | 0.50677 | 0.28367 |  |  |  | 2014-01-01 |  | 46 | 2014-02-17 | 2014-04-25 16:26 |  | 0 | 2014-04-26 16:26 | 2015-02-02 16:55 |  | 0 | 2015-02-03 16:55 | 2015-04-12 09:21 |  | 0 | 2015-04-13 09:21 | 2015-06-20 01:47 |  | 0 | 2015-06-21 01:47 | 2015-08-27 18:13 |  | 0 | 2015-08-28 18:13 | 2015-11-04 10:40 |  | v002 |  | 0.05335 |  | 46 | 0 | 0 | 0 | 0 | 0 | 46 | 36.8114 |  | 625.4442 | [15 empty] | O
Project-A06 |  | 0.50719 | 1.6972 |  |  |  | 2014-01-01 |  | 59 | 2014-03-02 | 2014-06-12 12:37 |  | 0 | 2014-06-13 12:37 | 2014-07-09 10:50 |  | 0 | 2014-07-10 10:50 | 2014-08-04 01:23 |  | 0 | 2014-08-05 01:23 | 2014-08-29 15:56 |  | 0 | 2014-08-30 15:56 | 2014-09-24 06:29 |  | 0 | 2014-09-25 06:29 | 2014-10-19 21:02 |  | v003 |  | 0.059553 |  | 59 | 0 | 0 | 0 | 0 | 0 | 59 | 52.7047 |  | 231.8763 | [15 empty] | F
Project-A07 |  | 0.28593 | 1.5283 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2015-01-29 06:10 |  | 0 | 2015-01-30 06:10 | 2015-04-18 07:39 |  | 0 | 2015-04-19 07:39 | 2015-07-06 09:07 |  | 0 | 2015-07-07 09:07 | 2015-09-23 10:36 |  | 0 | 2015-09-24 10:36 | 2015-12-11 12:05 |  | 0 | 2015-12-12 12:05 | 2016-02-28 13:34 |  | v005 |  | 0.10918 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 109.727 |  | 720.565
Project-A08 |  | 0.585 | 1.5261 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-03-29 13:08 |  | 0 | 2014-03-30 13:08 | 2014-04-06 18:07 |  | 0 | 2014-04-07 18:07 | 2014-04-09 19:21 |  | 0 | 2014-04-10 19:21 | 2014-04-12 20:34 |  | 3 | 2014-04-16 20:34 | 2014-04-18 21:48 |  | 0 | 2014-04-19 21:48 | 2014-04-21 23:02 |  | v006 |  | 0.0099256 |  | 78 | 0 | 0 | 0 | 3 | 0 | 81 | 11.6129 |  | 31.9598 | [15 empty] | T
Project-A09 |  | 0.54112 | 1.5707 |  |  |  | 2014-01-01 |  | 14 | 2014-01-16 | 2014-04-16 13:16 |  | 0 | 2014-04-17 13:16 | 2014-06-11 07:22 |  | 0 | 2014-06-12 07:22 | 2014-07-04 00:58 |  | 0 | 2014-07-05 00:58 | 2014-07-26 18:33 |  | 0 | 2014-07-27 18:33 | 2014-08-18 12:08 |  | 0 | 2014-08-19 12:08 | 2014-09-10 05:43 |  | v003 |  | 0.083747 |  | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 17.5868 |  | 237.2382 | [15 empty] | H
Project-A10 |  | 0.55711 | 1.492 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-03-30 14:52 |  | 0 | 2014-03-31 14:52 | 2014-05-28 22:20 |  | 0 | 2014-05-29 22:20 | 2014-06-14 10:32 |  | 0 | 2014-06-15 10:32 | 2014-06-30 22:45 |  | 0 | 2014-07-01 22:45 | 2014-07-17 10:58 |  | 0 | 2014-07-18 10:58 | 2014-08-02 23:10 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 26.3244 |  | 189.9653 | [15 empty] | I
Project-A11 |  | 0.51936 | 1.5113 |  |  |  | 2014-01-01 |  | 39 | 2014-02-10 | 2014-06-11 07:18 |  | 0 | 2014-06-12 07:18 | 2014-08-04 05:45 |  | 0 | 2014-08-05 05:45 | 2014-09-03 08:27 |  | 0 | 2014-09-04 08:27 | 2014-10-03 11:10 |  | 0 | 2014-10-04 11:10 | 2014-11-02 13:53 |  | 365 | 2015-11-03 13:53 | 2015-12-02 16:35 |  | v002 |  | 0.08871 |  | 39 | 0 | 0 | 0 | 0 | 365 | 404 | 51.8952 |  | 660.6912 | [15 empty] | S
Project-A12 |  | 0.50912 | 1.4965 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-06-23 16:08 |  | 0 | 2014-06-24 16:08 | 2014-08-24 11:30 |  | 0 | 2014-08-25 11:30 | 2014-09-25 02:54 |  | 1 | 2014-09-27 02:54 | 2014-10-27 18:17 |  | 1 | 2014-10-29 18:17 | 2014-11-29 09:41 |  | 0 | 2014-11-30 09:41 | 2014-12-31 01:04 |  | v004 |  | 0.096774 |  | 45 | 0 | 0 | 1 | 1 | 0 | 47 | 65.3226 |  | 318.0444
Project-A13 |  | 0.51136 | 2.0028 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-09-02 17:38 |  | 0 | 2014-09-03 17:38 | 2014-10-18 18:59 |  | 0 | 2014-10-19 18:59 | 2014-12-03 20:20 |  | 6 | 2014-12-10 20:20 | 2015-01-24 21:41 |  | 0 | 2015-01-25 21:41 | 2015-03-11 23:02 |  | 0 | 2015-03-12 23:02 | 2015-04-27 00:23 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 6 | 0 | 0 | 62 | 70.8685 |  | 424.016 | [15 empty] | W
Project-A14 |  | 0.25437 | 2.0584 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-08-10 07:44 |  | 0 | 2014-08-11 07:44 | 2014-09-17 02:52 |  | 0 | 2014-09-18 02:52 | 2014-10-24 22:00 |  | 4 | 2014-10-29 22:00 | 2014-12-05 17:08 |  | 0 | 2014-12-06 17:08 | 2015-01-12 12:16 |  | 0 | 2015-01-13 12:16 | 2015-02-19 07:24 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 4 | 0 | 0 | 71 | 57.3573 |  | 346.3085 | [15 empty] | O
Project-A15 |  | 1.0129 | 0.25144 |  |  |  | 2014-01-01 |  | 79 | 2014-03-22 | 2014-06-24 11:54 |  | 0 | 2014-06-25 11:54 | 2015-07-24 05:27 |  | 0 | 2015-07-25 05:27 | 2015-10-27 17:21 |  | 0 | 2015-10-28 17:21 | 2016-01-31 05:15 |  | 0 | 2016-02-01 05:15 | 2016-05-05 17:08 |  | 0 | 2016-05-06 17:08 | 2016-08-09 05:02 |  | v008 |  | 0.10608 |  | 79 | 0 | 0 | 0 | 0 | 0 | 79 | 125.7041 |  | 871.2097 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 43.4 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.73333 |  |  |  | 0.26667 |  |  |  | 24.3333 | [5 empty] | 0.066667 |  | 43.4 | 0 | 0 | 0.73333 | 0.26667 | 24.3333 | 68.7333 | 44.5664 | Average | 369.1715 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 651 |  |  |  | 0 |  |  |  | 0 |  |  |  | 11 |  |  |  | 4 |  |  |  | 365 | [5 empty] | 1 |  | 651 | 0 | 0 | 11 | 4 | 365 | 1031 | 668.4957 | Total | 5537.5725 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 7
| Days: | 38.3716
E
N
SIT - Violation | Count: | 5 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 28.2106
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-11-28 18:26 | 2015-01-30 19:41 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.0787 | 0 | 0
Project-A02 | 2014-03-02 08:07 | 2014-03-08 21:35 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-03-15 06:46 | 2014-03-22 06:03 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-04-28 05:02 | 2014-05-13 12:58 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2015-02-03 16:55 | 2015-04-12 09:21 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-10 10:50 | 2014-08-04 01:23 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-04-19 07:39 | 2015-07-06 09:07 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-04-07 18:07 | 2014-04-09 19:21 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-12 07:22 | 2014-07-04 00:58 | v003 |  | Count P-A10: 1; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 2.1319 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-05-29 22:20 | 2014-06-14 10:32 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-08-05 05:45 | 2014-09-03 08:27 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 8.8729 | 0 | 0 | 0 | S
Project-A12 | 2014-08-25 11:30 | 2014-09-25 02:54 | v004 |  | Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [12 empty] | 0 | 7.0013 | 0 | H
Project-A13 | 2014-10-19 18:59 | 2014-12-03 20:20 | v007 |  | Count P-A14: 1; Count P-A15: 0 | [13 empty] | 5.1258 | 0 | E
Project-A14 | 2014-09-18 02:52 | 2014-10-24 22:00 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2015-07-25 05:27 | 2015-10-27 17:21 | v008 | [31 empty] | T
UAT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 6.3446
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-01-31 19:41 | 2015-04-04 20:56 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-09 21:35 | 2014-03-16 11:03 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-23 06:03 | 2014-03-30 05:20 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-14 12:58 | 2014-05-29 20:54 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-04-13 09:21 | 2015-06-20 01:47 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-05 01:23 | 2014-08-29 15:56 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-07-07 09:07 | 2015-09-23 10:36 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-04-10 19:21 | 2014-04-12 20:34 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-05 00:58 | 2014-07-26 18:33 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-15 10:32 | 2014-06-30 22:45 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-04 08:27 | 2014-10-03 11:10 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 6.3446 | 0 | 0 | 0
Project-A12 | 2014-09-27 02:54 | 2014-10-27 18:17 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-10 20:20 | 2015-01-24 21:41 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-10-29 22:00 | 2014-12-05 17:08 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-10-28 17:21 | 2016-01-31 05:15 | v008
NFT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 3.8163
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-04-05 20:56 | 2015-06-07 22:11 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-17 11:03 | 2014-03-24 00:31 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-31 05:20 | 2014-04-07 04:37 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-30 20:54 | 2014-06-15 04:51 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-06-21 01:47 | 2015-08-27 18:13 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-30 15:56 | 2014-09-24 06:29 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-09-24 10:36 | 2015-12-11 12:05 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-04-16 20:34 | 2014-04-18 21:48 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-27 18:33 | 2014-08-18 12:08 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-01 22:45 | 2014-07-17 10:58 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-04 11:10 | 2014-11-02 13:53 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 3.8163 | 0 | 0 | 0
Project-A12 | 2014-10-29 18:17 | 2014-11-29 09:41 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-25 21:41 | 2015-03-11 23:02 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-12-06 17:08 | 2015-01-12 12:16 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-02-01 05:15 | 2016-05-05 17:08 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-06-08 22:11 | 2015-08-10 23:26 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-25 00:31 | 2014-03-31 13:59 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-04-08 04:37 | 2014-04-15 03:54 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-16 04:51 | 2014-07-01 12:47 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-08-28 18:13 | 2015-11-04 10:40 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-25 06:29 | 2014-10-19 21:02 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-12-12 12:05 | 2016-02-28 13:34 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-04-19 21:48 | 2014-04-21 23:02 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-19 12:08 | 2014-09-10 05:43 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-18 10:58 | 2014-08-02 23:10 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-11-03 13:53 | 2015-12-02 16:35 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-30 09:41 | 2014-12-31 01:04 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-12 23:02 | 2015-04-27 00:23 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-01-13 12:16 | 2015-02-19 07:24 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-05-06 17:08 | 2016-08-09 05:02 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.20848 | 20.8477 | 20
0.062511 | 6.2511 | 6
0.10518 | 10.5177 | 10
0.87568 | 87.5685 | 87
0.18328 | 18.328 | 18
0.070198 | 7.0198 | 7
0.4269 | 42.6901 | 42
0.89615 | 89.6153 | 89
0.061807 | 6.1807 | 6
0.7951 | 79.5103 | 79
0.73541 | 73.5411 | 73
0.59771 | 59.7713 | 59
0.79546 | 79.5456 | 79
0.99737 | 99.7371 | 99
0.86439 | 86.4387 | 86
0.87638 | 87.6378 | 87
0.36232 | 36.2323 | 36
0.15233 | 15.2326 | 15
0.76082 | 76.0821 | 76
0.55056 | 55.0557 | 55
0.6782 | 67.8199 | 67
0.3461 | 34.6104 | 34
0.86671 | 86.6711 | 86
0.0095851 | 0.95851 | 0
0.7285 | 72.85 | 72
0.57111 | 57.1115 | 57
0.52004 | 52.0042 | 52
0.29961 | 29.9609 | 29
0.87427 | 87.4265 | 87
0.24554 | 24.5543 | 24
0.62664 | 62.6643 | 62
0.51805 | 51.8055 | 51
0.54082 | 54.0825 | 54
0.097379 | 9.7379 | 9
0.43299 | 43.2985 | 43
0.37797 | 37.7968 | 37
0.82361 | 82.3611 | 82
0.45021 | 45.0208 | 45
0.35495 | 35.4951 | 35

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 3279.5286 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.9 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH