## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.53274 | 0.27036 |  |  |  | 17 | 17.76 | 34.76 | 65.6913 |  | 4.08 | 74 | 78.08 | 273.7138 |  | 4.08 | 17.76 | 21.84 | 65.6913 |  | 4.08 | 17.76 | 21.84 | 65.6913 |  | 4.08 | 17.76 | 21.84 | 65.6913 |  | 4.08 | 17.76 | 21.84 | 65.6913 |  | 200.2 | 602.1703 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 70.2029 | 602.1703 | 602.1703
Project-A02 |  | v002 |  | 0.50767 | 1.5307 |  |  |  | 15 | 19.2 | 34.2 | 29.5466 |  | 3.6 | 80 | 83.6 | 52.2624 |  | 3.6 | 19.2 | 22.8 | 12.543 |  | 3.6 | 19.2 | 22.8 | 12.543 |  | 3.6 | 19.2 | 22.8 | 12.543 |  | 3.6 | 19.2 | 22.8 | 12.543 |  | 209 | 131.981 | 104500 |  | 0.058933 |  | 33 | 176 |  | 65.0026 | 114.9774 | 114.9774 | [12 empty] | E
Project-A03 |  | v003 |  | 0.51913 | 5 |  |  |  | 16 | 6.48 | 22.48 | 30.8208 |  | 3.84 | 27 | 30.84 | 7.397 |  | 3.84 | 6.48 | 10.32 | 7.397 |  | 3.84 | 6.48 | 10.32 | 7.397 |  | 3.84 | 6.48 | 10.32 | 7.397 |  | 3.84 | 6.48 | 10.32 | 7.397 |  | 94.6 | 67.8057 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 67.8057 | 11.88 | 67.8057 | [12 empty] | N
Project-A04 |  | v004 |  | 0.55286 | 1.5134 |  |  |  | 35 | 4.32 | 39.32 | 63.3071 |  | 8.4 | 18 | 26.4 | 15.1937 |  | 8.4 | 4.32 | 12.72 | 15.1937 |  | 8.4 | 4.32 | 12.72 | 15.1937 |  | 8.4 | 4.32 | 12.72 | 15.1937 |  | 8.4 | 4.32 | 12.72 | 15.1937 |  | 116.6 | 139.2757 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 139.2757 | 26.1669 | 139.2757 | [12 empty] | D
Project-A05 |  | v002 |  | 0.50817 | 0.26104 |  |  |  | 6 | 19.2 | 25.2 | 73.5518 |  | 1.44 | 80 | 81.44 | 306.466 |  | 1.44 | 19.2 | 20.64 | 73.5518 |  | 1.44 | 19.2 | 20.64 | 73.5518 |  | 1.44 | 19.2 | 20.64 | 73.5518 |  | 1.44 | 19.2 | 20.64 | 73.5518 |  | 189.2 | 674.2252 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 25.9756 | 674.2252 | 674.2252
Project-A06 |  | v003 |  | 0.5362 | 1.5042 |  |  |  | 52 | 10.56 | 62.56 | 96.9781 |  | 12.48 | 44 | 56.48 | 29.2508 |  | 12.48 | 10.56 | 23.04 | 23.2747 |  | 12.48 | 10.56 | 23.04 | 23.2747 |  | 12.48 | 10.56 | 23.04 | 23.2747 |  | 12.48 | 10.56 | 23.04 | 23.2747 |  | 211.2 | 219.3279 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 213.3518 | 64.3519 | 213.3518 | [12 empty] | O
Project-A07 |  | v005 |  | 0.26383 | 1.5016 |  |  |  | 93 | 19.92 | 112.92 | 352.5027 |  | 22.32 | 83 | 105.32 | 84.6006 |  | 22.32 | 19.92 | 42.24 | 84.6006 |  | 22.32 | 19.92 | 42.24 | 84.6006 |  | 22.32 | 19.92 | 42.24 | 84.6006 |  | 22.32 | 19.92 | 42.24 | 84.6006 |  | 387.2 | 775.5059 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 775.5059 | 121.6073 | 775.5059 | [12 empty] | F
Project-A08 |  | v006 |  | 0.6705 | 1.9432 |  |  |  | 5 | 2.64 | 7.64 | 7.4571 |  | 1.2 | 11 | 12.2 | 5.6609 |  | 1.2 | 2.64 | 3.84 | 1.7897 |  | 1.2 | 2.64 | 3.84 | 1.7897 |  | 1.2 | 2.64 | 3.84 | 1.7897 |  | 1.2 | 2.64 | 3.84 | 1.7897 |  | 35.2 | 20.2768 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 16.4056 | 12.4539 | 16.4056
Project-A09 |  | v003 |  | 0.53435 | 1.5165 |  |  |  | 49 | 20.64 | 69.64 | 91.7006 |  | 11.76 | 86 | 97.76 | 56.7098 |  | 11.76 | 20.64 | 32.4 | 22.0081 |  | 11.76 | 20.64 | 32.4 | 22.0081 |  | 11.76 | 20.64 | 32.4 | 22.0081 |  | 11.76 | 20.64 | 32.4 | 22.0081 |  | 297 | 236.443 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 201.7413 | 124.7615 | 201.7413 | [12 empty] | T
Project-A10 |  | v001 |  | 0.51029 | 1.7237 |  |  |  | 36 | 20.88 | 56.88 | 70.5477 |  | 8.64 | 87 | 95.64 | 50.4721 |  | 8.64 | 20.88 | 29.52 | 16.9315 |  | 8.64 | 20.88 | 29.52 | 16.9315 |  | 8.64 | 20.88 | 29.52 | 16.9315 |  | 8.64 | 20.88 | 29.52 | 16.9315 |  | 270.6 | 188.7456 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 155.205 | 111.0386 | 155.205 | [12 empty] | H
Project-A11 |  | v002 |  | 0.54277 | 1.5034 |  |  |  | 63 | 19.2 | 82.2 | 116.0721 |  | 15.12 | 80 | 95.12 | 53.211 |  | 15.12 | 19.2 | 34.32 | 27.8573 |  | 15.12 | 19.2 | 34.32 | 27.8573 |  | 15.12 | 19.2 | 34.32 | 27.8573 |  | 15.12 | 19.2 | 34.32 | 27.8573 |  | 314.6 | 280.7123 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 255.3586 | 117.0641 | 255.3586 | [12 empty] | I
Project-A12 |  | v004 |  | 0.53552 | 1.4935 |  |  |  | 65 | 21.84 | 86.84 | 121.3784 |  | 15.6 | 91 | 106.6 | 60.9288 |  | 15.6 | 21.84 | 37.44 | 29.1308 |  | 15.6 | 21.84 | 37.44 | 29.1308 |  | 15.6 | 21.84 | 37.44 | 29.1308 |  | 15.6 | 21.84 | 37.44 | 29.1308 |  | 343.2 | 298.8305 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 267.0325 | 134.0433 | 267.0325 | [12 empty] | S
Project-A13 |  | v007 |  | 0.51121 | 1.9952 |  |  |  | 96 | 9.6 | 105.6 | 187.7915 |  | 23.04 | 40 | 63.04 | 45.07 |  | 23.04 | 9.6 | 32.64 | 45.07 |  | 23.04 | 9.6 | 32.64 | 45.07 |  | 23.04 | 9.6 | 32.64 | 45.07 |  | 23.04 | 9.6 | 32.64 | 45.07 |  | 299.2 | 413.1414 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 413.1414 | 44.1065 | 413.1414
Project-A14 |  | v006 |  | 0.26506 | 1.9911 |  |  |  | 39 | 12.72 | 51.72 | 147.1361 |  | 9.36 | 53 | 62.36 | 35.3127 |  | 9.36 | 12.72 | 22.08 | 35.3127 |  | 9.36 | 12.72 | 22.08 | 35.3127 |  | 9.36 | 12.72 | 22.08 | 35.3127 |  | 9.36 | 12.72 | 22.08 | 35.3127 |  | 202.4 | 323.6995 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 323.6995 | 58.5599 | 323.6995 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0097 | 0.25206 |  |  |  | 72 | 23.76 | 95.76 | 94.2643 |  | 17.28 | 99 | 116.28 | 392.768 |  | 17.28 | 23.76 | 41.04 | 94.2643 |  | 17.28 | 23.76 | 41.04 | 94.2643 |  | 17.28 | 23.76 | 41.04 | 94.2643 |  | 17.28 | 23.76 | 41.04 | 94.2643 |  | 376.2 | 864.0896 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 156.8775 | 864.0896 | 864.0896 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 103.2498 |  | 10.544 | 63.5333 | 74.0773 | 97.9345 |  | 10.544 | 15.248 | 25.792 | 36.9744 |  | 10.544 | 15.248 | 25.792 | 36.9744 |  | 10.544 | 15.248 | 25.792 | 36.9744 |  | 10.544 | 15.248 | 25.792 | 36.9744 |  | 236.4267 | 349.082 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 209.7721 | 205.4331 | 338.9324 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1548.7463 |  | 158.16 | 953 | 1111.16 | 1469.0176 |  | 158.16 | 228.72 | 386.88 | 554.6166 |  | 158.16 | 228.72 | 386.88 | 554.6166 |  | 158.16 | 228.72 | 386.88 | 554.6166 |  | 158.16 | 228.72 | 386.88 | 554.6166 |  | 3546.4 | 5236.2303 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3146.5815 | 3081.4965 | 5083.9854 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 1234.0896 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 354.3487 |  | <- To shorten average individual project span |  |  |  | <----------> | 338.9324
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 72.8226 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 720.5011 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 2381.762 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.53274 | 0.27036 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-08 16:35 |  | 0 | 2014-03-09 16:35 | 2014-12-08 09:43 |  | 0 | 2014-12-09 09:43 | 2015-02-13 02:19 |  | 0 | 2015-02-14 02:19 | 2015-04-20 18:54 |  | 0 | 2015-04-21 18:54 | 2015-06-26 11:30 |  | 0 | 2015-06-27 11:30 | 2015-09-01 04:05 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 607.1703 | 1234.0896 | [14 empty] | E
Project-A02 |  | 0.50767 | 1.5307 |  |  |  | 2014-01-01 |  | 13 | 2014-01-15 | 2014-02-13 13:07 |  | 0 | 2014-02-14 13:07 | 2014-04-07 19:25 |  | 0 | 2014-04-08 19:25 | 2014-04-21 08:27 |  | 0 | 2014-04-22 08:27 | 2014-05-04 21:29 |  | 0 | 2014-05-05 21:29 | 2014-05-18 10:31 |  | 0 | 2014-05-19 10:31 | 2014-05-31 23:33 |  | v002 |  | 0.058933 |  | 13 | 0 | 0 | 0 | 0 | 0 | 13 | 11.4919 |  | 136.981 | [15 empty] | N
Project-A03 |  | 0.51913 | 5 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-01 19:42 |  | 0 | 2014-02-02 19:42 | 2014-02-10 05:14 |  | 0 | 2014-02-11 05:14 | 2014-02-18 14:45 |  | 0 | 2014-02-19 14:45 | 2014-02-27 00:17 |  | 0 | 2014-02-28 00:17 | 2014-03-07 09:49 |  | 0 | 2014-03-08 09:49 | 2014-03-15 19:20 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 72.8057 | [15 empty] | D
Project-A04 |  | 0.55286 | 1.5134 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-04-09 07:22 |  | 0 | 2014-04-10 07:22 | 2014-04-25 12:01 |  | 0 | 2014-04-26 12:01 | 2014-05-11 16:40 |  | 0 | 2014-05-12 16:40 | 2014-05-27 21:19 |  | 0 | 2014-05-28 21:19 | 2014-06-13 01:58 |  | 0 | 2014-06-14 01:58 | 2014-06-29 06:37 |  | v004 |  | 0.032878 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 16.768 |  | 144.2757
Project-A05 |  | 0.50817 | 0.26104 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-04-30 13:15 |  | 0 | 2014-05-01 13:15 | 2015-03-04 00:26 |  | 0 | 2015-03-05 00:26 | 2015-05-17 13:40 |  | 0 | 2015-05-18 13:40 | 2015-07-31 02:55 |  | 0 | 2015-08-01 02:55 | 2015-10-13 16:10 |  | 0 | 2015-10-14 16:10 | 2015-12-27 05:24 |  | v002 |  | 0.05335 |  | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 36.0112 |  | 679.2252 | [15 empty] | O
Project-A06 |  | 0.5362 | 1.5042 |  |  |  | 2014-01-01 |  | 58 | 2014-03-01 | 2014-06-05 23:28 |  | 0 | 2014-06-06 23:28 | 2014-07-06 05:30 |  | 0 | 2014-07-07 05:30 | 2014-07-30 12:05 |  | 0 | 2014-07-31 12:05 | 2014-08-23 18:41 |  | 0 | 2014-08-24 18:41 | 2014-09-17 01:17 |  | 0 | 2014-09-18 01:17 | 2014-10-11 07:52 |  | v003 |  | 0.059553 |  | 58 | 0 | 0 | 0 | 0 | 0 | 58 | 51.8114 |  | 224.3279 | [15 empty] | F
Project-A07 |  | 0.26383 | 1.5016 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2015-02-25 12:04 |  | 0 | 2015-02-26 12:04 | 2015-05-22 02:29 |  | 0 | 2015-05-23 02:29 | 2015-08-15 16:54 |  | 0 | 2015-08-16 16:54 | 2015-11-09 07:19 |  | 0 | 2015-11-10 07:19 | 2016-02-02 21:44 |  | 0 | 2016-02-03 21:44 | 2016-04-28 12:09 |  | v005 |  | 0.10918 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 109.727 |  | 780.5059
Project-A08 |  | 0.6705 | 1.9432 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-09 10:58 |  | 0 | 2014-01-10 10:58 | 2014-01-16 02:50 |  | 0 | 2014-01-17 02:50 | 2014-01-18 21:47 |  | 0 | 2014-01-19 21:47 | 2014-01-21 16:44 |  | 0 | 2014-01-22 16:44 | 2014-01-24 11:41 |  | 0 | 2014-01-25 11:41 | 2014-01-27 06:39 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 25.2768 | [15 empty] | T
Project-A09 |  | 0.53435 | 1.5165 |  |  |  | 2014-01-01 |  | 14 | 2014-01-16 | 2014-04-17 16:49 |  | 0 | 2014-04-18 16:49 | 2014-06-14 09:51 |  | 0 | 2014-06-15 09:51 | 2014-07-07 10:03 |  | 0 | 2014-07-08 10:03 | 2014-07-30 10:14 |  | 0 | 2014-07-31 10:14 | 2014-08-22 10:26 |  | 0 | 2014-08-23 10:26 | 2014-09-14 10:38 |  | v003 |  | 0.083747 |  | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 17.5868 |  | 241.443 | [15 empty] | H
Project-A10 |  | 0.51029 | 1.7237 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-04-05 13:09 |  | 0 | 2014-04-06 13:09 | 2014-05-27 00:29 |  | 0 | 2014-05-28 00:29 | 2014-06-13 22:50 |  | 0 | 2014-06-14 22:50 | 2014-07-01 21:11 |  | 0 | 2014-07-02 21:11 | 2014-07-19 19:32 |  | 0 | 2014-07-20 19:32 | 2014-08-06 17:54 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 26.3244 |  | 193.7456 | [15 empty] | I
Project-A11 |  | 0.54277 | 1.5034 |  |  |  | 2014-01-01 |  | 35 | 2014-02-06 | 2014-06-02 01:44 |  | 0 | 2014-06-03 01:44 | 2014-07-26 06:48 |  | 0 | 2014-07-27 06:48 | 2014-08-24 03:22 |  | 0 | 2014-08-25 03:22 | 2014-09-21 23:57 |  | 0 | 2014-09-22 23:57 | 2014-10-20 20:31 |  | 0 | 2014-10-21 20:31 | 2014-11-18 17:06 |  | v002 |  | 0.08871 |  | 35 | 0 | 0 | 0 | 0 | 0 | 35 | 46.5726 |  | 285.7123 | [15 empty] | S
Project-A12 |  | 0.53552 | 1.4935 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-06-17 09:05 |  | 0 | 2014-06-18 09:05 | 2014-08-18 07:22 |  | 0 | 2014-08-19 07:22 | 2014-09-17 10:31 |  | 3 | 2014-09-21 10:31 | 2014-10-20 13:39 |  | 0 | 2014-10-21 13:39 | 2014-11-19 16:48 |  | 0 | 2014-11-20 16:48 | 2014-12-19 19:56 |  | v004 |  | 0.096774 |  | 45 | 0 | 0 | 3 | 0 | 0 | 48 | 65.3226 |  | 306.8305
Project-A13 |  | 0.51121 | 1.9952 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-09-02 19:00 |  | 0 | 2014-09-03 19:00 | 2014-10-18 20:41 |  | 0 | 2014-10-19 20:41 | 2014-12-03 22:21 |  | 0 | 2014-12-04 22:21 | 2015-01-19 00:02 |  | 0 | 2015-01-20 00:02 | 2015-03-06 01:43 |  | 0 | 2015-03-07 01:43 | 2015-04-21 03:24 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 418.1414 | [15 empty] | W
Project-A14 |  | 0.26506 | 1.9911 |  |  |  | 2014-01-01 |  | 69 | 2014-03-12 | 2014-08-06 03:16 |  | 0 | 2014-08-07 03:16 | 2014-09-11 10:46 |  | 0 | 2014-09-12 10:46 | 2014-10-17 18:17 |  | 1 | 2014-10-19 18:17 | 2014-11-24 01:47 |  | 0 | 2014-11-25 01:47 | 2014-12-30 09:17 |  | 0 | 2014-12-31 09:17 | 2015-02-04 16:47 |  | v006 |  | 0.057072 |  | 69 | 0 | 0 | 1 | 0 | 0 | 70 | 59.0695 |  | 329.6995 | [15 empty] | O
Project-A15 |  | 1.0097 | 0.25206 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-04-06 06:21 |  | 0 | 2015-04-07 06:21 | 2016-05-04 00:47 |  | 0 | 2016-05-05 00:47 | 2016-08-07 07:07 |  | 0 | 2016-08-08 07:07 | 2016-11-10 13:28 |  | 0 | 2016-11-11 13:28 | 2017-02-13 19:48 |  | 0 | 2017-02-14 19:48 | 2017-05-20 02:09 |  | v008 |  | 0.10608 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 580.7847 |  | 869.0896 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 54.9333 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.26667 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 0.066667 |  | 54.9333 | 0 | 0 | 0.26667 | 0 | 0 | 55.2 | 72.8226 | Average | 354.3487 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 824 |  |  |  | 0 |  |  |  | 0 |  |  |  | 4 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 1 |  | 824 | 0 | 0 | 4 | 0 | 0 | 828 | 1092.3387 | Total | 5315.2303 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 5
| Days: | 14.41
E
N
SIT - Violation | Count: | 3 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 13.043
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-12-09 09:43 | 2015-02-13 02:19 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-08 19:25 | 2014-04-21 08:27 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-11 05:14 | 2014-02-18 14:45 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-04-26 12:01 | 2014-05-11 16:40 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2015-03-05 00:26 | 2015-05-17 13:40 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-07 05:30 | 2014-07-30 12:05 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 3.2206 | 0 | 0 | 0 | 0
Project-A07 | 2015-05-23 02:29 | 2015-08-15 16:54 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-17 02:50 | 2014-01-18 21:47 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-15 09:51 | 2014-07-07 10:03 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-05-28 00:29 | 2014-06-13 22:50 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-07-27 06:48 | 2014-08-24 03:22 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 4.8332 | 0 | 0 | 0 | S
Project-A12 | 2014-08-19 07:22 | 2014-09-17 10:31 | v004 |  | Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [12 empty] | 0 | 4.9892 | 0 | H
Project-A13 | 2014-10-19 20:41 | 2014-12-03 22:21 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-09-12 10:46 | 2014-10-17 18:17 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2016-05-05 00:47 | 2016-08-07 07:07 | v008 | [31 empty] | T
UAT - Violation | Count: | 2 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 1.367
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-02-14 02:19 | 2015-04-20 18:54 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-22 08:27 | 2014-05-04 21:29 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-19 14:45 | 2014-02-27 00:17 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-12 16:40 | 2014-05-27 21:19 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-05-18 13:40 | 2015-07-31 02:55 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-07-31 12:05 | 2014-08-23 18:41 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-16 16:54 | 2015-11-09 07:19 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-19 21:47 | 2014-01-21 16:44 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-08 10:03 | 2014-07-30 10:14 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-14 22:50 | 2014-07-01 21:11 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-08-25 03:22 | 2014-09-21 23:57 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0.55966 | 0 | 0 | 0
Project-A12 | 2014-09-21 10:31 | 2014-10-20 13:39 | v004 |  | Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [12 empty] | 0 | 0.80738 | 0
Project-A13 | 2014-12-04 22:21 | 2015-01-19 00:02 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-10-19 18:17 | 2014-11-24 01:47 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-08-08 07:07 | 2016-11-10 13:28 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-04-21 18:54 | 2015-06-26 11:30 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-05 21:29 | 2014-05-18 10:31 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-28 00:17 | 2014-03-07 09:49 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-28 21:19 | 2014-06-13 01:58 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-08-01 02:55 | 2015-10-13 16:10 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-24 18:41 | 2014-09-17 01:17 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-11-10 07:19 | 2016-02-02 21:44 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-22 16:44 | 2014-01-24 11:41 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-31 10:14 | 2014-08-22 10:26 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-02 21:11 | 2014-07-19 19:32 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-22 23:57 | 2014-10-20 20:31 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-21 13:39 | 2014-11-19 16:48 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-20 00:02 | 2015-03-06 01:43 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-11-25 01:47 | 2014-12-30 09:17 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-11-11 13:28 | 2017-02-13 19:48 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-06-27 11:30 | 2015-09-01 04:05 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-19 10:31 | 2014-05-31 23:33 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-08 09:49 | 2014-03-15 19:20 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-14 01:58 | 2014-06-29 06:37 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-10-14 16:10 | 2015-12-27 05:24 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-18 01:17 | 2014-10-11 07:52 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-02-03 21:44 | 2016-04-28 12:09 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-25 11:41 | 2014-01-27 06:39 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-23 10:26 | 2014-09-14 10:38 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-20 19:32 | 2014-08-06 17:54 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-21 20:31 | 2014-11-18 17:06 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-20 16:48 | 2014-12-19 19:56 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-07 01:43 | 2015-04-21 03:24 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-12-31 09:17 | 2015-02-04 16:47 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2017-02-14 19:48 | 2017-05-20 02:09 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.27535 | 27.5346 | 27
0.52144 | 52.1439 | 52
0.74484 | 74.4838 | 74
0.053442 | 5.3442 | 5
0.33167 | 33.167 | 33
0.53683 | 53.6827 | 53
0.34953 | 34.9526 | 34
0.81723 | 81.7228 | 81
0.84206 | 84.2059 | 84
0.61447 | 61.4469 | 61
0.26052 | 26.0518 | 26
0.34235 | 34.235 | 34
0.64573 | 64.5727 | 64
0.53713 | 53.713 | 53
0.02269 | 2.269 | 2
0.19245 | 19.245 | 19
0.21571 | 21.5707 | 21
0.1348 | 13.4798 | 13
0.76813 | 76.8131 | 76
0.1478 | 14.7798 | 14
0.44743 | 44.7428 | 44
0.49745 | 49.7449 | 49
0.52266 | 52.2665 | 52
0.43971 | 43.9708 | 43
0.5247 | 52.4705 | 52
0.17034 | 17.0342 | 17
0.43984 | 43.9838 | 43
0.32449 | 32.4485 | 32
0.034167 | 3.4167 | 3
0.077594 | 7.7594 | 7
0.054073 | 5.4073 | 5
0.16123 | 16.1228 | 16
0.9237 | 92.3698 | 92
0.47658 | 47.6584 | 47
0.035413 | 3.5413 | 3
0.0064843 | 0.64843 | 0
0.78082 | 78.0817 | 78
0.068006 | 6.8006 | 6
0.81343 | 81.3432 | 81

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 2381.762 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.9 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH