## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.52649 | 0.28938 |  |  |  | 17 | 17.76 | 34.76 | 61.3735 |  | 4.08 | 74 | 78.08 | 255.723 |  | 4.08 | 17.76 | 21.84 | 61.3735 |  | 4.08 | 17.76 | 21.84 | 61.3735 |  | 4.08 | 17.76 | 21.84 | 61.3735 |  | 4.08 | 17.76 | 21.84 | 61.3735 |  | 200.2 | 562.5907 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 71.0369 | 562.5907 | 562.5907
Project-A02 |  | v002 |  | 0.52854 | 1.5218 |  |  |  | 15 | 19.2 | 34.2 | 28.3801 |  | 3.6 | 80 | 83.6 | 52.5681 |  | 3.6 | 19.2 | 22.8 | 12.6164 |  | 3.6 | 19.2 | 22.8 | 12.6164 |  | 3.6 | 19.2 | 22.8 | 12.6164 |  | 3.6 | 19.2 | 22.8 | 12.6164 |  | 209 | 131.4137 | 104500 |  | 0.058933 |  | 33 | 176 |  | 62.4363 | 115.6499 | 115.6499 | [12 empty] | E
Project-A03 |  | v003 |  | 0.49917 | 4.9889 |  |  |  | 16 | 6.48 | 22.48 | 32.0535 |  | 3.84 | 27 | 30.84 | 7.6928 |  | 3.84 | 6.48 | 10.32 | 7.6928 |  | 3.84 | 6.48 | 10.32 | 7.6928 |  | 3.84 | 6.48 | 10.32 | 7.6928 |  | 3.84 | 6.48 | 10.32 | 7.6928 |  | 94.6 | 70.5177 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 70.5177 | 11.9066 | 70.5177 | [12 empty] | N
Project-A04 |  | v004 |  | 0.50387 | 1.5032 |  |  |  | 35 | 4.32 | 39.32 | 69.4627 |  | 8.4 | 18 | 26.4 | 16.6711 |  | 8.4 | 4.32 | 12.72 | 16.6711 |  | 8.4 | 4.32 | 12.72 | 16.6711 |  | 8.4 | 4.32 | 12.72 | 16.6711 |  | 8.4 | 4.32 | 12.72 | 16.6711 |  | 116.6 | 152.818 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 152.818 | 26.344 | 152.818 | [12 empty] | D
Project-A05 |  | v002 |  | 0.53952 | 0.27239 |  |  |  | 6 | 19.2 | 25.2 | 70.4861 |  | 1.44 | 80 | 81.44 | 293.6919 |  | 1.44 | 19.2 | 20.64 | 70.4861 |  | 1.44 | 19.2 | 20.64 | 70.4861 |  | 1.44 | 19.2 | 20.64 | 70.4861 |  | 1.44 | 19.2 | 20.64 | 70.4861 |  | 189.2 | 646.1223 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 24.4663 | 646.1223 | 646.1223
Project-A06 |  | v003 |  | 0.5155 | 1.4923 |  |  |  | 52 | 10.56 | 62.56 | 100.8726 |  | 12.48 | 44 | 56.48 | 29.484 |  | 12.48 | 10.56 | 23.04 | 24.2094 |  | 12.48 | 10.56 | 23.04 | 24.2094 |  | 12.48 | 10.56 | 23.04 | 24.2094 |  | 12.48 | 10.56 | 23.04 | 24.2094 |  | 211.2 | 227.1943 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 221.9197 | 64.8648 | 221.9197 | [12 empty] | O
Project-A07 |  | v005 |  | 0.50117 | 1.4839 |  |  |  | 93 | 19.92 | 112.92 | 185.5661 |  | 22.32 | 83 | 105.32 | 55.9354 |  | 22.32 | 19.92 | 42.24 | 44.5359 |  | 22.32 | 19.92 | 42.24 | 44.5359 |  | 22.32 | 19.92 | 42.24 | 44.5359 |  | 22.32 | 19.92 | 42.24 | 44.5359 |  | 387.2 | 419.6449 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 408.2453 | 123.0578 | 408.2453 | [12 empty] | F
Project-A08 |  | v006 |  | 0.49988 | 1.6144 |  |  |  | 5 | 2.64 | 7.64 | 10.0023 |  | 1.2 | 11 | 12.2 | 6.8139 |  | 1.2 | 2.64 | 3.84 | 2.4006 |  | 1.2 | 2.64 | 3.84 | 2.4006 |  | 1.2 | 2.64 | 3.84 | 2.4006 |  | 1.2 | 2.64 | 3.84 | 2.4006 |  | 35.2 | 26.4184 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 22.0051 | 14.9905 | 22.0051
Project-A09 |  | v003 |  | 0.52823 | 1.4902 |  |  |  | 49 | 20.64 | 69.64 | 92.7621 |  | 11.76 | 86 | 97.76 | 57.711 |  | 11.76 | 20.64 | 32.4 | 22.2629 |  | 11.76 | 20.64 | 32.4 | 22.2629 |  | 11.76 | 20.64 | 32.4 | 22.2629 |  | 11.76 | 20.64 | 32.4 | 22.2629 |  | 297 | 239.5246 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 204.0766 | 126.9641 | 204.0766 | [12 empty] | T
Project-A10 |  | v001 |  | 0.55444 | 1.5497 |  |  |  | 36 | 20.88 | 56.88 | 64.9306 |  | 8.64 | 87 | 95.64 | 56.1384 |  | 8.64 | 20.88 | 29.52 | 15.5834 |  | 8.64 | 20.88 | 29.52 | 15.5834 |  | 8.64 | 20.88 | 29.52 | 15.5834 |  | 8.64 | 20.88 | 29.52 | 15.5834 |  | 270.6 | 183.4025 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 142.8474 | 123.5045 | 142.8474 | [12 empty] | H
Project-A11 |  | v002 |  | 0.49717 | 0.2872 |  |  |  | 63 | 19.2 | 82.2 | 126.7172 |  | 15.12 | 80 | 95.12 | 278.5543 |  | 15.12 | 19.2 | 34.32 | 66.853 |  | 15.12 | 19.2 | 34.32 | 66.853 |  | 15.12 | 19.2 | 34.32 | 66.853 |  | 15.12 | 19.2 | 34.32 | 66.853 |  | 314.6 | 672.6837 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 278.7779 | 612.8196 | 612.8196 | [12 empty] | I
Project-A12 |  | v004 |  | 0.51173 | 1.4993 |  |  |  | 65 | 21.84 | 86.84 | 127.0195 |  | 15.6 | 91 | 106.6 | 60.6959 |  | 15.6 | 21.84 | 37.44 | 30.4847 |  | 15.6 | 21.84 | 37.44 | 30.4847 |  | 15.6 | 21.84 | 37.44 | 30.4847 |  | 15.6 | 21.84 | 37.44 | 30.4847 |  | 343.2 | 309.654 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 279.4428 | 133.531 | 279.4428 | [12 empty] | S
Project-A13 |  | v007 |  | 0.52932 | 2.0055 |  |  |  | 96 | 9.6 | 105.6 | 181.3631 |  | 23.04 | 40 | 63.04 | 43.5271 |  | 23.04 | 9.6 | 32.64 | 43.5271 |  | 23.04 | 9.6 | 32.64 | 43.5271 |  | 23.04 | 9.6 | 32.64 | 43.5271 |  | 23.04 | 9.6 | 32.64 | 43.5271 |  | 299.2 | 398.9989 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 398.9989 | 43.8786 | 398.9989
Project-A14 |  | v006 |  | 0.2635 | 1.9865 |  |  |  | 39 | 12.72 | 51.72 | 148.0062 |  | 9.36 | 53 | 62.36 | 35.5215 |  | 9.36 | 12.72 | 22.08 | 35.5215 |  | 9.36 | 12.72 | 22.08 | 35.5215 |  | 9.36 | 12.72 | 22.08 | 35.5215 |  | 9.36 | 12.72 | 22.08 | 35.5215 |  | 202.4 | 325.6136 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 325.6136 | 58.6961 | 325.6136 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0015 | 2.0154 |  |  |  | 72 | 23.76 | 95.76 | 71.8943 |  | 17.28 | 99 | 116.28 | 49.1224 |  | 17.28 | 23.76 | 41.04 | 17.2546 |  | 17.28 | 23.76 | 41.04 | 17.2546 |  | 17.28 | 23.76 | 41.04 | 17.2546 |  | 17.28 | 23.76 | 41.04 | 17.2546 |  | 376.2 | 190.0353 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 158.1675 | 108.0693 | 158.1675 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 91.3927 |  | 10.544 | 63.5333 | 74.0773 | 86.6567 |  | 10.544 | 15.248 | 25.792 | 31.4315 |  | 10.544 | 15.248 | 25.792 | 31.4315 |  | 10.544 | 15.248 | 25.792 | 31.4315 |  | 10.544 | 15.248 | 25.792 | 31.4315 |  | 236.4267 | 303.7755 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 188.0913 | 184.866 | 288.1223 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1370.8899 |  | 158.16 | 953 | 1111.16 | 1299.8509 |  | 158.16 | 228.72 | 386.88 | 471.4729 |  | 158.16 | 228.72 | 386.88 | 471.4729 |  | 158.16 | 228.72 | 386.88 | 471.4729 |  | 158.16 | 228.72 | 386.88 | 471.4729 |  | 3546.4 | 4556.6325 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2821.37 | 2772.9897 | 4321.835 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 932.5907 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 333.7088 |  | <- To shorten average individual project span |  |  |  | <----------> | 288.1223
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 106.9696 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 1545.7898 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 2919.0588 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.52649 | 0.28938 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-03-04 08:58 |  | 0 | 2015-03-05 08:58 | 2015-11-16 02:19 |  | 0 | 2015-11-17 02:19 | 2016-01-17 11:17 |  | 0 | 2016-01-18 11:17 | 2016-03-19 20:15 |  | 0 | 2016-03-20 20:15 | 2016-05-21 05:13 |  | 0 | 2016-05-22 05:13 | 2016-07-22 14:11 |  | v001 |  | 0.056452 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 309.0726 |  | 567.5907 | 932.5907 | [14 empty] | E
Project-A02 |  | 0.52854 | 1.5218 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-01-30 09:07 |  | 0 | 2015-01-31 09:07 | 2015-03-24 22:46 |  | 0 | 2015-03-25 22:46 | 2015-04-07 13:33 |  | 0 | 2015-04-08 13:33 | 2015-04-21 04:21 |  | 0 | 2015-04-22 04:21 | 2015-05-04 19:08 |  | 0 | 2015-05-05 19:08 | 2015-05-18 09:56 |  | v002 |  | 0.058933 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 322.6582 |  | 136.4137 | [15 empty] | N
Project-A03 |  | 0.49917 | 4.9889 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-03 01:17 |  | 0 | 2014-02-04 01:17 | 2014-02-11 17:55 |  | 0 | 2014-02-12 17:55 | 2014-02-20 10:32 |  | 0 | 2014-02-21 10:32 | 2014-03-01 03:10 |  | 0 | 2014-03-02 03:10 | 2014-03-09 19:48 |  | 0 | 2014-03-10 19:48 | 2014-03-18 12:25 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 75.5177 | [15 empty] | D
Project-A04 |  | 0.50387 | 1.5032 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-12 11:06 |  | 0 | 2014-03-13 11:06 | 2014-03-30 03:13 |  | 0 | 2014-03-31 03:13 | 2014-04-16 19:19 |  | 0 | 2014-04-17 19:19 | 2014-05-04 11:25 |  | 0 | 2014-05-05 11:25 | 2014-05-22 03:32 |  | 0 | 2014-05-23 03:32 | 2014-06-08 19:38 |  | v004 |  | 0.032878 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 157.818
Project-A05 |  | 0.53952 | 0.27239 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-04-27 11:40 |  | 0 | 2014-04-28 11:40 | 2015-02-16 04:16 |  | 0 | 2015-02-17 04:16 | 2015-04-28 15:56 |  | 0 | 2015-04-29 15:56 | 2015-07-09 03:36 |  | 0 | 2015-07-10 03:36 | 2015-09-18 15:16 |  | 0 | 2015-09-19 15:16 | 2015-11-29 02:56 |  | v002 |  | 0.05335 |  | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 36.0112 |  | 651.1223 | [15 empty] | O
Project-A06 |  | 0.5155 | 1.4923 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-04-12 20:57 |  | 0 | 2014-04-13 20:57 | 2014-05-13 08:34 |  | 0 | 2014-05-14 08:34 | 2014-06-07 13:35 |  | 0 | 2014-06-08 13:35 | 2014-07-02 18:37 |  | 0 | 2014-07-03 18:37 | 2014-07-27 23:38 |  | 0 | 2014-07-28 23:38 | 2014-08-22 04:40 |  | v003 |  | 0.059553 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 232.1943 | [15 empty] | F
Project-A07 |  | 0.50117 | 1.4839 |  |  |  | 2014-01-01 |  | 364 | 2015-01-01 | 2015-07-05 13:35 |  | 0 | 2015-07-06 13:35 | 2015-08-31 12:02 |  | 0 | 2015-09-01 12:02 | 2015-10-16 00:54 |  | 0 | 2015-10-17 00:54 | 2015-11-30 13:45 |  | 0 | 2015-12-01 13:45 | 2016-01-15 02:37 |  | 0 | 2016-01-16 02:37 | 2016-02-29 15:29 |  | v005 |  | 0.10918 |  | 364 | 0 | 0 | 0 | 0 | 0 | 364 | 596.129 |  | 424.6449
Project-A08 |  | 0.49988 | 1.6144 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-12 00:03 |  | 0 | 2014-01-13 00:03 | 2014-01-19 19:35 |  | 0 | 2014-01-20 19:35 | 2014-01-23 05:12 |  | 0 | 2014-01-24 05:12 | 2014-01-26 14:49 |  | 0 | 2014-01-27 14:49 | 2014-01-30 00:26 |  | 0 | 2014-01-31 00:26 | 2014-02-02 10:03 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 31.4184 | [15 empty] | T
Project-A09 |  | 0.52823 | 1.4902 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-04-16 18:17 |  | 0 | 2014-04-17 18:17 | 2014-06-14 11:21 |  | 0 | 2014-06-15 11:21 | 2014-07-07 17:40 |  | 0 | 2014-07-08 17:40 | 2014-07-30 23:58 |  | 0 | 2014-07-31 23:58 | 2014-08-23 06:17 |  | 0 | 2014-08-24 06:17 | 2014-09-15 12:35 |  | v003 |  | 0.083747 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 15.0744 |  | 244.5246 | [15 empty] | H
Project-A10 |  | 0.55444 | 1.5497 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-07 22:20 |  | 0 | 2014-03-08 22:20 | 2014-05-04 01:39 |  | 0 | 2014-05-05 01:39 | 2014-05-20 15:39 |  | 0 | 2014-05-21 15:39 | 2014-06-06 05:40 |  | 365 | 2015-06-07 05:40 | 2015-06-22 19:40 |  | 0 | 2015-06-23 19:40 | 2015-07-09 09:40 |  | v001 |  | 0.076303 |  | 0 | 0 | 0 | 0 | 365 | 0 | 365 | 0 |  | 553.4025 | [15 empty] | I
Project-A11 |  | 0.49717 | 0.2872 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-05-08 17:13 |  | 0 | 2014-05-09 17:13 | 2015-02-12 06:31 |  | 0 | 2015-02-13 06:31 | 2015-04-21 02:59 |  | 0 | 2015-04-22 02:59 | 2015-06-27 23:28 |  | 0 | 2015-06-28 23:28 | 2015-09-03 19:56 |  | 0 | 2015-09-04 19:56 | 2015-11-10 16:25 |  | v002 |  | 0.08871 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 677.6837 | [15 empty] | S
Project-A12 |  | 0.51173 | 1.4993 |  |  |  | 2014-01-01 |  | 46 | 2014-02-17 | 2014-06-24 00:28 |  | 0 | 2014-06-25 00:28 | 2014-08-24 17:10 |  | 0 | 2014-08-25 17:10 | 2014-09-25 04:48 |  | 0 | 2014-09-26 04:48 | 2014-10-26 16:26 |  | 0 | 2014-10-27 16:26 | 2014-11-27 04:04 |  | 0 | 2014-11-28 04:04 | 2014-12-28 15:42 |  | v004 |  | 0.096774 |  | 46 | 0 | 0 | 0 | 0 | 0 | 46 | 66.7742 |  | 314.654
Project-A13 |  | 0.52932 | 2.0055 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-08-27 08:43 |  | 0 | 2014-08-28 08:43 | 2014-10-10 21:22 |  | 0 | 2014-10-11 21:22 | 2014-11-24 10:01 |  | 0 | 2014-11-25 10:01 | 2015-01-07 22:40 |  | 0 | 2015-01-08 22:40 | 2015-02-21 11:19 |  | 0 | 2015-02-22 11:19 | 2015-04-06 23:58 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 403.9989 | [15 empty] | W
Project-A14 |  | 0.2635 | 1.9865 |  |  |  | 2014-01-01 |  | 69 | 2014-03-12 | 2014-08-07 00:09 |  | 0 | 2014-08-08 00:09 | 2014-09-12 12:40 |  | 0 | 2014-09-13 12:40 | 2014-10-19 01:11 |  | 3 | 2014-10-23 01:11 | 2014-11-27 13:42 |  | 3 | 2014-12-01 13:42 | 2015-01-06 02:13 |  | 0 | 2015-01-07 02:13 | 2015-02-11 14:44 |  | v006 |  | 0.057072 |  | 69 | 0 | 0 | 3 | 3 | 0 | 75 | 59.0695 |  | 336.6136 | [15 empty] | O
Project-A15 |  | 1.0015 | 2.0154 |  |  |  | 2014-01-01 |  | 81 | 2014-03-24 | 2014-06-03 21:28 |  | 0 | 2014-06-04 21:28 | 2014-07-24 00:24 |  | 0 | 2014-07-25 00:24 | 2014-08-11 06:31 |  | 0 | 2014-08-12 06:31 | 2014-08-29 12:37 |  | 0 | 2014-08-30 12:37 | 2014-09-16 18:44 |  | 3 | 2014-09-20 18:44 | 2014-10-08 00:51 |  | v008 |  | 0.10608 |  | 81 | 0 | 0 | 0 | 0 | 3 | 84 | 128.8865 |  | 198.0353 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 93.5333 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.2 |  |  |  | 24.5333 |  |  |  | 0.2 | [5 empty] | 0.066667 |  | 93.5333 | 0 | 0 | 0.2 | 24.5333 | 0.2 | 118.4667 | 106.9696 | Average | 333.7088 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 1403 |  |  |  | 0 |  |  |  | 0 |  |  |  | 3 |  |  |  | 368 |  |  |  | 3 | [5 empty] | 1 |  | 1403 | 0 | 0 | 3 | 368 | 3 | 1777 | 1604.544 | Total | 5005.6325 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 5
| Days: | 30.9158
E
N
SIT - Violation | Count: | 3 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 25.127
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2015-11-17 02:19 | 2016-01-17 11:17 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2015-03-25 22:46 | 2015-04-07 13:33 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-12 17:55 | 2014-02-20 10:32 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-03-31 03:13 | 2014-04-16 19:19 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2015-02-17 04:16 | 2015-04-28 15:56 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-05-14 08:34 | 2014-06-07 13:35 | v003 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 6.2958 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-09-01 12:02 | 2015-10-16 00:54 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-20 19:35 | 2014-01-23 05:12 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-15 11:21 | 2014-07-07 17:40 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-05-05 01:39 | 2014-05-20 15:39 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2015-02-13 06:31 | 2015-04-21 02:59 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-25 17:10 | 2014-09-25 04:48 | v004 |  | Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [12 empty] | 0 | 11.6724 | 0 | H
Project-A13 | 2014-10-11 21:22 | 2014-11-24 10:01 | v007 |  | Count P-A14: 1; Count P-A15: 0 | [13 empty] | 7.1589 | 0 | E
Project-A14 | 2014-09-13 12:40 | 2014-10-19 01:11 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-25 00:24 | 2014-08-11 06:31 | v008 | [31 empty] | T
UAT - Violation | Count: | 2 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 5.7888
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-01-18 11:17 | 2016-03-19 20:15 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2015-04-08 13:33 | 2015-04-21 04:21 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-21 10:32 | 2014-03-01 03:10 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-04-17 19:19 | 2014-05-04 11:25 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-04-29 15:56 | 2015-07-09 03:36 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-06-08 13:35 | 2014-07-02 18:37 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-17 00:54 | 2015-11-30 13:45 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-24 05:12 | 2014-01-26 14:49 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-08 17:40 | 2014-07-30 23:58 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-05-21 15:39 | 2014-06-06 05:40 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-04-22 02:59 | 2015-06-27 23:28 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-26 04:48 | 2014-10-26 16:26 | v004 |  | Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [12 empty] | 0 | 3.6356 | 0
Project-A13 | 2014-11-25 10:01 | 2015-01-07 22:40 | v007 |  | Count P-A14: 1; Count P-A15: 0 | [13 empty] | 2.1532 | 0
Project-A14 | 2014-10-23 01:11 | 2014-11-27 13:42 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-12 06:31 | 2014-08-29 12:37 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-03-20 20:15 | 2016-05-21 05:13 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2015-04-22 04:21 | 2015-05-04 19:08 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-02 03:10 | 2014-03-09 19:48 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-05 11:25 | 2014-05-22 03:32 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-07-10 03:36 | 2015-09-18 15:16 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-07-03 18:37 | 2014-07-27 23:38 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-12-01 13:45 | 2016-01-15 02:37 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-27 14:49 | 2014-01-30 00:26 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-31 23:58 | 2014-08-23 06:17 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-06-07 05:40 | 2015-06-22 19:40 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-06-28 23:28 | 2015-09-03 19:56 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-27 16:26 | 2014-11-27 04:04 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-08 22:40 | 2015-02-21 11:19 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-12-01 13:42 | 2015-01-06 02:13 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-30 12:37 | 2014-09-16 18:44 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-05-22 05:13 | 2016-07-22 14:11 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2015-05-05 19:08 | 2015-05-18 09:56 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-10 19:48 | 2014-03-18 12:25 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-23 03:32 | 2014-06-08 19:38 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-09-19 15:16 | 2015-11-29 02:56 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-07-28 23:38 | 2014-08-22 04:40 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-01-16 02:37 | 2016-02-29 15:29 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-31 00:26 | 2014-02-02 10:03 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-24 06:17 | 2014-09-15 12:35 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-06-23 19:40 | 2015-07-09 09:40 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-09-04 19:56 | 2015-11-10 16:25 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-28 04:04 | 2014-12-28 15:42 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-02-22 11:19 | 2015-04-06 23:58 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-01-07 02:13 | 2015-02-11 14:44 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-20 18:44 | 2014-10-08 00:51 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.95432 | 95.4318 | 95
0.2904 | 29.0399 | 29
0.11367 | 11.3669 | 11
0.093638 | 9.3638 | 9
0.69818 | 69.8183 | 69
0.67075 | 67.075 | 67
0.846 | 84.6001 | 84
0.5784 | 57.8397 | 57
0.44848 | 44.8481 | 44
0.52787 | 52.7871 | 52
0.87208 | 87.2078 | 87
0.95956 | 95.9556 | 95
0.63942 | 63.942 | 63
0.17651 | 17.6514 | 17
0.9936 | 99.3604 | 99
0.78546 | 78.5457 | 78
0.50265 | 50.2653 | 50
0.44349 | 44.3492 | 44
0.93663 | 93.6634 | 93
0.36737 | 36.7374 | 36
0.81638 | 81.638 | 81
0.72341 | 72.3413 | 72
0.62468 | 62.4682 | 62
0.64435 | 64.4354 | 64
0.59339 | 59.3385 | 59
0.81918 | 81.9184 | 81
0.75479 | 75.4789 | 75
0.51701 | 51.7007 | 51
0.0035891 | 0.35891 | 0
0.27247 | 27.2465 | 27
0.2799 | 27.9898 | 27
0.49341 | 49.3413 | 49
0.62267 | 62.2669 | 62
0.72927 | 72.9269 | 72
0.66295 | 66.295 | 66
0.86146 | 86.1462 | 86
0.97779 | 97.779 | 97
0.62863 | 62.863 | 62
0.032401 | 3.2401 | 3

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 2919.0588 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.9 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH