## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.50909 | 1.5446 |  |  |  | 17 | 17.76 | 34.76 | 33.3928 |  | 4.08 | 74 | 78.08 | 47.9079 |  | 4.08 | 17.76 | 21.84 | 11.4979 |  | 4.08 | 17.76 | 21.84 | 11.4979 |  | 4.08 | 17.76 | 21.84 | 11.4979 |  | 4.08 | 17.76 | 21.84 | 11.4979 |  | 200.2 | 127.2924 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 73.4642 | 105.3974 | 105.3974
Project-A02 |  | v002 |  | 0.50806 | 1.5192 |  |  |  | 15 | 19.2 | 34.2 | 29.5241 |  | 3.6 | 80 | 83.6 | 52.6602 |  | 3.6 | 19.2 | 22.8 | 12.6385 |  | 3.6 | 19.2 | 22.8 | 12.6385 |  | 3.6 | 19.2 | 22.8 | 12.6385 |  | 3.6 | 19.2 | 22.8 | 12.6385 |  | 209 | 132.7382 | 104500 |  | 0.058933 |  | 33 | 176 |  | 64.9531 | 115.8525 | 115.8525 | [12 empty] | E
Project-A03 |  | v003 |  | 0.52355 | 1.5472 |  |  |  | 16 | 6.48 | 22.48 | 30.5604 |  | 3.84 | 27 | 30.84 | 17.4514 |  | 3.84 | 6.48 | 10.32 | 7.3345 |  | 3.84 | 6.48 | 10.32 | 7.3345 |  | 3.84 | 6.48 | 10.32 | 7.3345 |  | 3.84 | 6.48 | 10.32 | 7.3345 |  | 94.6 | 77.3498 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 67.2328 | 38.3932 | 67.2328 | [12 empty] | N
Project-A04 |  | v004 |  | 0.50186 | 1.5426 |  |  |  | 35 | 4.32 | 39.32 | 69.7407 |  | 8.4 | 18 | 26.4 | 16.7378 |  | 8.4 | 4.32 | 12.72 | 16.7378 |  | 8.4 | 4.32 | 12.72 | 16.7378 |  | 8.4 | 4.32 | 12.72 | 16.7378 |  | 8.4 | 4.32 | 12.72 | 16.7378 |  | 116.6 | 153.4295 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 153.4295 | 25.6705 | 153.4295 | [12 empty] | D
Project-A05 |  | v002 |  | 0.54288 | 1.5936 |  |  |  | 6 | 19.2 | 25.2 | 12.0483 |  | 1.44 | 80 | 81.44 | 50.2012 |  | 1.44 | 19.2 | 20.64 | 12.0483 |  | 1.44 | 19.2 | 20.64 | 12.0483 |  | 1.44 | 19.2 | 20.64 | 12.0483 |  | 1.44 | 19.2 | 20.64 | 12.0483 |  | 189.2 | 110.4426 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 24.3149 | 110.4426 | 110.4426
Project-A06 |  | v003 |  | 0.51408 | 3.1872 |  |  |  | 52 | 10.56 | 62.56 | 101.1512 |  | 12.48 | 44 | 56.48 | 24.2763 |  | 12.48 | 10.56 | 23.04 | 24.2763 |  | 12.48 | 10.56 | 23.04 | 24.2763 |  | 12.48 | 10.56 | 23.04 | 24.2763 |  | 12.48 | 10.56 | 23.04 | 24.2763 |  | 211.2 | 222.5327 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 222.5327 | 30.3712 | 222.5327 | [12 empty] | O
Project-A07 |  | v005 |  | 0.49428 | 1.5777 |  |  |  | 93 | 19.92 | 112.92 | 188.1527 |  | 22.32 | 83 | 105.32 | 52.6082 |  | 22.32 | 19.92 | 42.24 | 45.1567 |  | 22.32 | 19.92 | 42.24 | 45.1567 |  | 22.32 | 19.92 | 42.24 | 45.1567 |  | 22.32 | 19.92 | 42.24 | 45.1567 |  | 387.2 | 421.3875 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 413.936 | 115.738 | 413.936 | [12 empty] | F
Project-A08 |  | v006 |  | 0.53187 | 1.5359 |  |  |  | 5 | 2.64 | 7.64 | 9.4009 |  | 1.2 | 11 | 12.2 | 7.1619 |  | 1.2 | 2.64 | 3.84 | 2.2562 |  | 1.2 | 2.64 | 3.84 | 2.2562 |  | 1.2 | 2.64 | 3.84 | 2.2562 |  | 1.2 | 2.64 | 3.84 | 2.2562 |  | 35.2 | 25.5876 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 20.6819 | 15.7561 | 20.6819
Project-A09 |  | v003 |  | 0.53993 | 0.35223 |  |  |  | 49 | 20.64 | 69.64 | 90.7533 |  | 11.76 | 86 | 97.76 | 244.1552 |  | 11.76 | 20.64 | 32.4 | 58.5972 |  | 11.76 | 20.64 | 32.4 | 58.5972 |  | 11.76 | 20.64 | 32.4 | 58.5972 |  | 11.76 | 20.64 | 32.4 | 58.5972 |  | 297 | 569.2975 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 199.6573 | 537.1415 | 537.1415 | [12 empty] | T
Project-A10 |  | v001 |  | 0.50027 | 1.5252 |  |  |  | 36 | 20.88 | 56.88 | 71.9611 |  | 8.64 | 87 | 95.64 | 57.0406 |  | 8.64 | 20.88 | 29.52 | 17.2707 |  | 8.64 | 20.88 | 29.52 | 17.2707 |  | 8.64 | 20.88 | 29.52 | 17.2707 |  | 8.64 | 20.88 | 29.52 | 17.2707 |  | 270.6 | 198.0842 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 158.3143 | 125.4893 | 158.3143 | [12 empty] | H
Project-A11 |  | v002 |  | 0.49954 | 1.5596 |  |  |  | 63 | 19.2 | 82.2 | 126.116 |  | 15.12 | 80 | 95.12 | 51.2966 |  | 15.12 | 19.2 | 34.32 | 30.2678 |  | 15.12 | 19.2 | 34.32 | 30.2678 |  | 15.12 | 19.2 | 34.32 | 30.2678 |  | 15.12 | 19.2 | 34.32 | 30.2678 |  | 314.6 | 298.484 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 277.4552 | 112.8526 | 277.4552 | [12 empty] | I
Project-A12 |  | v004 |  | 0.28026 | 0.2744 |  |  |  | 65 | 21.84 | 86.84 | 231.9298 |  | 15.6 | 91 | 106.6 | 331.6284 |  | 15.6 | 21.84 | 37.44 | 79.5908 |  | 15.6 | 21.84 | 37.44 | 79.5908 |  | 15.6 | 21.84 | 37.44 | 79.5908 |  | 15.6 | 21.84 | 37.44 | 79.5908 |  | 343.2 | 881.9215 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 510.2456 | 729.5825 | 729.5825 | [12 empty] | S
Project-A13 |  | v007 |  | 0.52334 | 2.0507 |  |  |  | 96 | 9.6 | 105.6 | 183.4356 |  | 23.04 | 40 | 63.04 | 44.0245 |  | 23.04 | 9.6 | 32.64 | 44.0245 |  | 23.04 | 9.6 | 32.64 | 44.0245 |  | 23.04 | 9.6 | 32.64 | 44.0245 |  | 23.04 | 9.6 | 32.64 | 44.0245 |  | 299.2 | 403.5582 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 403.5582 | 42.9127 | 403.5582
Project-A14 |  | v006 |  | 0.4991 | 1.9896 |  |  |  | 39 | 12.72 | 51.72 | 78.1406 |  | 9.36 | 53 | 62.36 | 26.6388 |  | 9.36 | 12.72 | 22.08 | 18.7537 |  | 9.36 | 12.72 | 22.08 | 18.7537 |  | 9.36 | 12.72 | 22.08 | 18.7537 |  | 9.36 | 12.72 | 22.08 | 18.7537 |  | 202.4 | 179.7944 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 171.9093 | 58.6054 | 171.9093 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0319 | 2.0522 |  |  |  | 72 | 23.76 | 95.76 | 69.7745 |  | 17.28 | 99 | 116.28 | 48.2414 |  | 17.28 | 23.76 | 41.04 | 16.7459 |  | 17.28 | 23.76 | 41.04 | 16.7459 |  | 17.28 | 23.76 | 41.04 | 16.7459 |  | 17.28 | 23.76 | 41.04 | 16.7459 |  | 376.2 | 184.9995 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 153.5039 | 106.1312 | 153.5039 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.5901 |  |  |  | 43.9333 | 15.248 | 59.1813 | 88.4055 |  | 10.544 | 63.5333 | 74.0773 | 71.4687 |  | 10.544 | 15.248 | 25.792 | 26.4798 |  | 10.544 | 15.248 | 25.792 | 26.4798 |  | 10.544 | 15.248 | 25.792 | 26.4798 |  | 10.544 | 15.248 | 25.792 | 26.4798 |  | 236.4267 | 265.7933 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 194.3459 | 151.3558 | 242.7314 | [12 empty] | S
|  | Total |  | 8 | 23.8519 |  |  |  | 659 | 228.72 | 887.72 | 1326.082 |  | 158.16 | 953 | 1111.16 | 1072.0305 |  | 158.16 | 228.72 | 386.88 | 397.1968 |  | 158.16 | 228.72 | 386.88 | 397.1968 |  | 158.16 | 228.72 | 386.88 | 397.1968 |  | 158.16 | 228.72 | 386.88 | 397.1968 |  | 3546.4 | 3986.8995 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2915.189 | 2270.3365 | 3640.9704 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 892.9215 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 298.26 |  | <- To shorten average individual project span |  |  |  | <----------> | 242.7314
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 48.5025 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 113.437 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1353.1209 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.50909 | 1.5446 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-04 09:26 |  | 0 | 2014-02-05 09:26 | 2014-03-25 07:13 |  | 0 | 2014-03-26 07:13 | 2014-04-06 19:10 |  | 0 | 2014-04-07 19:10 | 2014-04-19 07:07 |  | 3 | 2014-04-23 07:07 | 2014-05-04 19:04 |  | 0 | 2014-05-05 19:04 | 2014-05-17 07:01 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 |  | 135.2924 | 892.9215 | [14 empty] | E
Project-A02 |  | 0.50806 | 1.5192 |  |  |  | 2014-01-01 |  | 13 | 2014-01-15 | 2014-02-13 12:35 |  | 0 | 2014-02-14 12:35 | 2014-04-08 04:25 |  | 0 | 2014-04-09 04:25 | 2014-04-21 19:45 |  | 5 | 2014-04-27 19:45 | 2014-05-10 11:04 |  | 0 | 2014-05-11 11:04 | 2014-05-24 02:24 |  | 3 | 2014-05-28 02:24 | 2014-06-09 17:43 |  | v002 |  | 0.058933 |  | 13 | 0 | 0 | 5 | 0 | 3 | 21 | 11.4919 |  | 145.7382 | [15 empty] | N
Project-A03 |  | 0.52355 | 1.5472 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-01 13:27 |  | 0 | 2014-02-02 13:27 | 2014-02-20 00:17 |  | 0 | 2014-02-21 00:17 | 2014-02-28 08:19 |  | 0 | 2014-03-01 08:19 | 2014-03-08 16:20 |  | 0 | 2014-03-09 16:20 | 2014-03-17 00:22 |  | 3 | 2014-03-21 00:22 | 2014-03-28 08:24 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 3 | 3 | 0 |  | 85.3498 | [15 empty] | D
Project-A04 |  | 0.50186 | 1.5426 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-04-15 17:47 |  | 0 | 2014-04-16 17:47 | 2014-05-03 11:29 |  | 0 | 2014-05-04 11:29 | 2014-05-21 05:11 |  | 0 | 2014-05-22 05:11 | 2014-06-07 22:54 |  | 0 | 2014-06-08 22:54 | 2014-06-25 16:36 |  | 0 | 2014-06-26 16:36 | 2014-07-13 10:18 |  | v004 |  | 0.032878 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 16.768 |  | 158.4295
Project-A05 |  | 0.54288 | 1.5936 |  |  |  | 2014-01-01 |  | 46 | 2014-02-17 | 2014-03-01 01:10 |  | 0 | 2014-03-02 01:10 | 2014-04-21 05:59 |  | 0 | 2014-04-22 05:59 | 2014-05-04 07:09 |  | 0 | 2014-05-05 07:09 | 2014-05-17 08:18 |  | 3 | 2014-05-21 08:18 | 2014-06-02 09:28 |  | 0 | 2014-06-03 09:28 | 2014-06-15 10:37 |  | v002 |  | 0.05335 |  | 46 | 0 | 0 | 0 | 3 | 0 | 49 | 36.8114 |  | 118.4426 | [15 empty] | O
Project-A06 |  | 0.51408 | 3.1872 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-04-13 03:38 |  | 0 | 2015-04-14 03:38 | 2015-05-08 10:16 |  | 0 | 2015-05-09 10:16 | 2015-06-02 16:53 |  | 0 | 2015-06-03 16:53 | 2015-06-27 23:31 |  | 0 | 2015-06-28 23:31 | 2015-07-23 06:09 |  | 0 | 2015-07-24 06:09 | 2015-08-17 12:47 |  | v003 |  | 0.059553 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 326.0546 |  | 227.5327 | [15 empty] | F
Project-A07 |  | 0.49428 | 1.5777 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-07-09 03:40 |  | 0 | 2014-07-10 03:40 | 2014-08-31 18:16 |  | 0 | 2014-09-01 18:16 | 2014-10-16 22:01 |  | 0 | 2014-10-17 22:01 | 2014-12-02 01:47 |  | 6 | 2014-12-09 01:47 | 2015-01-23 05:32 |  | 365 | 2016-01-24 05:32 | 2016-03-09 09:18 |  | v005 |  | 0.10918 |  | 0 | 0 | 0 | 0 | 6 | 365 | 371 | 0 |  | 797.3875
Project-A08 |  | 0.53187 | 1.5359 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 09:37 |  | 0 | 2014-01-12 09:37 | 2014-01-19 13:30 |  | 0 | 2014-01-20 13:30 | 2014-01-22 19:39 |  | 0 | 2014-01-23 19:39 | 2014-01-26 01:48 |  | 0 | 2014-01-27 01:48 | 2014-01-29 07:57 |  | 0 | 2014-01-30 07:57 | 2014-02-01 14:06 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30.5876 | [15 empty] | T
Project-A09 |  | 0.53993 | 0.35223 |  |  |  | 2014-01-01 |  | 3 | 2014-01-05 | 2014-04-05 18:05 |  | 0 | 2014-04-06 18:05 | 2014-12-06 21:48 |  | 0 | 2014-12-07 21:48 | 2015-02-04 12:08 |  | 0 | 2015-02-05 12:08 | 2015-04-05 02:28 |  | 3 | 2015-04-09 02:28 | 2015-06-06 16:48 |  | 0 | 2015-06-07 16:48 | 2015-08-05 07:08 |  | v003 |  | 0.083747 |  | 3 | 0 | 0 | 0 | 3 | 0 | 6 | 3.7686 |  | 577.2975 | [15 empty] | H
Project-A10 |  | 0.50027 | 1.5252 |  |  |  | 2014-01-01 |  | 24 | 2014-01-26 | 2014-04-07 23:04 |  | 0 | 2014-04-08 23:04 | 2014-06-05 00:02 |  | 0 | 2014-06-06 00:02 | 2014-06-23 06:32 |  | 0 | 2014-06-24 06:32 | 2014-07-11 13:02 |  | 0 | 2014-07-12 13:02 | 2014-07-29 19:32 |  | 0 | 2014-07-30 19:32 | 2014-08-17 02:01 |  | v001 |  | 0.076303 |  | 24 | 0 | 0 | 0 | 0 | 0 | 24 | 27.469 |  | 203.0842 | [15 empty] | I
Project-A11 |  | 0.49954 | 1.5596 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-06-11 02:47 |  | 0 | 2014-06-12 02:47 | 2014-08-02 09:54 |  | 0 | 2014-08-03 09:54 | 2014-09-02 16:20 |  | 0 | 2014-09-03 16:20 | 2014-10-03 22:46 |  | 0 | 2014-10-04 22:46 | 2014-11-04 05:11 |  | 3 | 2014-11-08 05:11 | 2014-12-08 11:37 |  | v002 |  | 0.08871 |  | 34 | 0 | 0 | 0 | 0 | 3 | 37 | 45.2419 |  | 306.484 | [15 empty] | S
Project-A12 |  | 0.28026 | 0.2744 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-08-21 22:19 |  | 0 | 2014-08-22 22:19 | 2015-07-20 13:24 |  | 0 | 2015-07-21 13:24 | 2015-10-09 03:35 |  | 0 | 2015-10-10 03:35 | 2015-12-28 17:45 |  | 3 | 2016-01-01 17:45 | 2016-03-21 07:56 |  | 3 | 2016-03-25 07:56 | 2016-06-12 22:07 |  | v004 |  | 0.096774 |  | 0 | 0 | 0 | 0 | 3 | 3 | 6 | 0 |  | 892.9215
Project-A13 |  | 0.52334 | 2.0507 |  |  |  | 2014-01-01 |  | 62 | 2014-03-05 | 2014-09-04 10:27 |  | 0 | 2014-09-05 10:27 | 2014-10-19 11:03 |  | 0 | 2014-10-20 11:03 | 2014-12-03 11:38 |  | 0 | 2014-12-04 11:38 | 2015-01-17 12:13 |  | 5 | 2015-01-23 12:13 | 2015-03-08 12:49 |  | 0 | 2015-03-09 12:49 | 2015-04-22 13:24 |  | v007 |  | 0.084367 |  | 62 | 0 | 0 | 0 | 5 | 0 | 67 | 78.4615 |  | 413.5582 | [15 empty] | W
Project-A14 |  | 0.4991 | 1.9896 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-27 03:22 |  | 0 | 2014-05-28 03:22 | 2014-06-23 18:42 |  | 0 | 2014-06-24 18:42 | 2014-07-13 12:48 |  | 0 | 2014-07-14 12:48 | 2014-08-02 06:53 |  | 0 | 2014-08-03 06:53 | 2014-08-22 00:59 |  | 0 | 2014-08-23 00:59 | 2014-09-10 19:04 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 57.3573 |  | 184.7944 | [15 empty] | O
Project-A15 |  | 1.0319 | 2.0522 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-05-29 18:35 |  | 0 | 2014-05-30 18:35 | 2014-07-18 00:23 |  | 0 | 2014-07-19 00:23 | 2014-08-04 18:17 |  | 0 | 2014-08-05 18:17 | 2014-08-22 12:11 |  | 4 | 2014-08-27 12:11 | 2014-09-13 06:05 |  | 3 | 2014-09-17 06:05 | 2014-10-03 23:59 |  | v008 |  | 0.10608 |  | 78 | 0 | 0 | 0 | 4 | 3 | 85 | 124.1129 |  | 196.9995 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.5901 | [5 empty] | 48.4 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.33333 |  |  |  | 1.8 |  |  |  | 25.3333 | [5 empty] | 0.066667 |  | 48.4 | 0 | 0 | 0.33333 | 1.8 | 25.3333 | 75.8667 | 48.5025 | Average | 298.26 | [15 empty] | H
Total |  | 8 | 23.8519 | [5 empty] | 726 |  |  |  | 0 |  |  |  | 0 |  |  |  | 5 |  |  |  | 27 |  |  |  | 380 | [5 empty] | 1 |  | 726 | 0 | 0 | 5 | 27 | 380 | 1138 | 727.5372 | Total | 4473.8995 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 2
| Days: | 2.2687
E
N
SIT - Violation | Count: | 2 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 2.2687
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-26 07:13 | 2014-04-06 19:10 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-09 04:25 | 2014-04-21 19:45 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-21 00:17 | 2014-02-28 08:19 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-04 11:29 | 2014-05-21 05:11 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-04-22 05:59 | 2014-05-04 07:09 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2015-05-09 10:16 | 2015-06-02 16:53 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2014-09-01 18:16 | 2014-10-16 22:01 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 1; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0.91953 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-20 13:30 | 2014-01-22 19:39 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-12-07 21:48 | 2015-02-04 12:08 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-06-06 00:02 | 2014-06-23 06:32 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-08-03 09:54 | 2014-09-02 16:20 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 1 | [11 empty] | 0 | 0 | 0 | 1.3492 | S
Project-A12 | 2015-07-21 13:24 | 2015-10-09 03:35 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-20 11:03 | 2014-12-03 11:38 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-24 18:42 | 2014-07-13 12:48 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-19 00:23 | 2014-08-04 18:17 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-07 19:10 | 2014-04-19 07:07 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-27 19:45 | 2014-05-10 11:04 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-01 08:19 | 2014-03-08 16:20 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-22 05:11 | 2014-06-07 22:54 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-05 07:09 | 2014-05-17 08:18 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-06-03 16:53 | 2015-06-27 23:31 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2014-10-17 22:01 | 2014-12-02 01:47 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-23 19:39 | 2014-01-26 01:48 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-02-05 12:08 | 2015-04-05 02:28 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-24 06:32 | 2014-07-11 13:02 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-03 16:20 | 2014-10-03 22:46 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2015-10-10 03:35 | 2015-12-28 17:45 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-04 11:38 | 2015-01-17 12:13 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-14 12:48 | 2014-08-02 06:53 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-05 18:17 | 2014-08-22 12:11 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-23 07:07 | 2014-05-04 19:04 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-11 11:04 | 2014-05-24 02:24 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-09 16:20 | 2014-03-17 00:22 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-08 22:54 | 2014-06-25 16:36 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-21 08:18 | 2014-06-02 09:28 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-06-28 23:31 | 2015-07-23 06:09 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2014-12-09 01:47 | 2015-01-23 05:32 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-27 01:48 | 2014-01-29 07:57 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-04-09 02:28 | 2015-06-06 16:48 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-12 13:02 | 2014-07-29 19:32 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-04 22:46 | 2014-11-04 05:11 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2016-01-01 17:45 | 2016-03-21 07:56 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-23 12:13 | 2015-03-08 12:49 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-03 06:53 | 2014-08-22 00:59 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-27 12:11 | 2014-09-13 06:05 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-05-05 19:04 | 2014-05-17 07:01 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-28 02:24 | 2014-06-09 17:43 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-21 00:22 | 2014-03-28 08:24 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-26 16:36 | 2014-07-13 10:18 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-06-03 09:28 | 2014-06-15 10:37 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-07-24 06:09 | 2015-08-17 12:47 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-01-24 05:32 | 2016-03-09 09:18 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-30 07:57 | 2014-02-01 14:06 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-06-07 16:48 | 2015-08-05 07:08 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-30 19:32 | 2014-08-17 02:01 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-11-08 05:11 | 2014-12-08 11:37 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2016-03-25 07:56 | 2016-06-12 22:07 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-09 12:49 | 2015-04-22 13:24 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-23 00:59 | 2014-09-10 19:04 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-17 06:05 | 2014-10-03 23:59 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.75347 | 75.3468 | 75
0.20376 | 20.3762 | 20
0.83061 | 83.0607 | 83
0.88795 | 88.7952 | 88
0.63967 | 63.9669 | 63
0.90132 | 90.132 | 90
0.44283 | 44.2833 | 44
0.10896 | 10.8961 | 10
0.7379 | 73.7901 | 73
0.04547 | 4.547 | 4
0.036759 | 3.6759 | 3
0.49532 | 49.5316 | 49
0.67827 | 67.8272 | 67
0.40274 | 40.2741 | 40
0.55724 | 55.7238 | 55
0.32183 | 32.1829 | 32
0.63159 | 63.1588 | 63
0.46132 | 46.1321 | 46
0.96959 | 96.9585 | 96
0.99101 | 99.1005 | 99
0.66104 | 66.1042 | 66
0.77948 | 77.9479 | 77
0.95695 | 95.6946 | 95
0.79011 | 79.0115 | 79
0.17337 | 17.337 | 17
0.014215 | 1.4215 | 1
0.81543 | 81.5427 | 81
0.24574 | 24.5744 | 24
0.28981 | 28.9809 | 28
0.30989 | 30.9894 | 30
0.32064 | 32.0636 | 32
0.3592 | 35.9196 | 35
0.03693 | 3.693 | 3
0.63245 | 63.2451 | 63
0.76124 | 76.1241 | 76
0.50914 | 50.9136 | 50
0.81172 | 81.1719 | 81
0.35643 | 35.6428 | 35
0.44619 | 44.6187 | 44

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1353.1209 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.9 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 23.8519 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH