## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.53938 | 0.28229 |  |  |  | 17 | 17.76 | 34.76 | 62.9149 |  | 4.08 | 74 | 78.08 | 262.1456 |  | 4.08 | 17.76 | 21.84 | 62.9149 |  | 4.08 | 17.76 | 21.84 | 62.9149 |  | 4.08 | 17.76 | 21.84 | 62.9149 |  | 4.08 | 17.76 | 21.84 | 62.9149 |  | 200.2 | 576.7203 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 69.3384 | 576.7203 | 576.7203
Project-A02 |  | v002 |  | 0.32036 | 1.5504 |  |  |  | 15 | 19.2 | 34.2 | 46.8217 |  | 3.6 | 80 | 83.6 | 51.5992 |  | 3.6 | 19.2 | 22.8 | 12.3838 |  | 3.6 | 19.2 | 22.8 | 12.3838 |  | 3.6 | 19.2 | 22.8 | 12.3838 |  | 3.6 | 19.2 | 22.8 | 12.3838 |  | 209 | 147.9561 | 104500 |  | 0.058933 |  | 33 | 176 |  | 103.0077 | 113.5182 | 113.5182 | [12 empty] | E
Project-A03 |  | v003 |  | 0.59381 | 2.3585 |  |  |  | 16 | 6.48 | 22.48 | 26.9445 |  | 3.84 | 27 | 30.84 | 11.4481 |  | 3.84 | 6.48 | 10.32 | 6.4667 |  | 3.84 | 6.48 | 10.32 | 6.4667 |  | 3.84 | 6.48 | 10.32 | 6.4667 |  | 3.84 | 6.48 | 10.32 | 6.4667 |  | 94.6 | 64.2593 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 59.2779 | 25.1858 | 59.2779 | [12 empty] | N
Project-A04 |  | v004 |  | 0.50778 | 1.567 |  |  |  | 35 | 4.32 | 39.32 | 68.928 |  | 8.4 | 18 | 26.4 | 16.5427 |  | 8.4 | 4.32 | 12.72 | 16.5427 |  | 8.4 | 4.32 | 12.72 | 16.5427 |  | 8.4 | 4.32 | 12.72 | 16.5427 |  | 8.4 | 4.32 | 12.72 | 16.5427 |  | 116.6 | 151.6416 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 151.6416 | 25.2718 | 151.6416 | [12 empty] | D
Project-A05 |  | v002 |  | 0.52473 | 1.5099 |  |  |  | 6 | 19.2 | 25.2 | 12.7162 |  | 1.44 | 80 | 81.44 | 52.9843 |  | 1.44 | 19.2 | 20.64 | 12.7162 |  | 1.44 | 19.2 | 20.64 | 12.7162 |  | 1.44 | 19.2 | 20.64 | 12.7162 |  | 1.44 | 19.2 | 20.64 | 12.7162 |  | 189.2 | 116.5654 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 25.1559 | 116.5654 | 116.5654
Project-A06 |  | v003 |  | 0.56527 | 1.4717 |  |  |  | 52 | 10.56 | 62.56 | 91.991 |  | 12.48 | 44 | 56.48 | 29.8978 |  | 12.48 | 10.56 | 23.04 | 22.0778 |  | 12.48 | 10.56 | 23.04 | 22.0778 |  | 12.48 | 10.56 | 23.04 | 22.0778 |  | 12.48 | 10.56 | 23.04 | 22.0778 |  | 211.2 | 210.2001 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 202.3802 | 65.7751 | 202.3802 | [12 empty] | O
Project-A07 |  | v005 |  | 0.50601 | 1.4944 |  |  |  | 93 | 19.92 | 112.92 | 183.7896 |  | 22.32 | 83 | 105.32 | 55.5424 |  | 22.32 | 19.92 | 42.24 | 44.1095 |  | 22.32 | 19.92 | 42.24 | 44.1095 |  | 22.32 | 19.92 | 42.24 | 44.1095 |  | 22.32 | 19.92 | 42.24 | 44.1095 |  | 387.2 | 415.77 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 404.337 | 122.1934 | 404.337 | [12 empty] | F
Project-A08 |  | v006 |  | 0.51353 | 2.6086 |  |  |  | 5 | 2.64 | 7.64 | 9.7366 |  | 1.2 | 11 | 12.2 | 4.2169 |  | 1.2 | 2.64 | 3.84 | 2.3368 |  | 1.2 | 2.64 | 3.84 | 2.3368 |  | 1.2 | 2.64 | 3.84 | 2.3368 |  | 1.2 | 2.64 | 3.84 | 2.3368 |  | 35.2 | 23.3005 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 21.4204 | 9.2771 | 21.4204
Project-A09 |  | v003 |  | 0.51339 | 1.7007 |  |  |  | 49 | 20.64 | 69.64 | 95.4448 |  | 11.76 | 86 | 97.76 | 50.5678 |  | 11.76 | 20.64 | 32.4 | 22.9067 |  | 11.76 | 20.64 | 32.4 | 22.9067 |  | 11.76 | 20.64 | 32.4 | 22.9067 |  | 11.76 | 20.64 | 32.4 | 22.9067 |  | 297 | 237.6396 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 209.9785 | 111.2491 | 209.9785 | [12 empty] | T
Project-A10 |  | v001 |  | 0.51628 | 1.5142 |  |  |  | 36 | 20.88 | 56.88 | 69.7303 |  | 8.64 | 87 | 95.64 | 57.4565 |  | 8.64 | 20.88 | 29.52 | 16.7353 |  | 8.64 | 20.88 | 29.52 | 16.7353 |  | 8.64 | 20.88 | 29.52 | 16.7353 |  | 8.64 | 20.88 | 29.52 | 16.7353 |  | 270.6 | 194.1279 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 153.4066 | 126.4043 | 153.4066 | [12 empty] | H
Project-A11 |  | v002 |  | 0.28136 | 0.28145 |  |  |  | 63 | 19.2 | 82.2 | 223.915 |  | 15.12 | 80 | 95.12 | 284.245 |  | 15.12 | 19.2 | 34.32 | 68.2188 |  | 15.12 | 19.2 | 34.32 | 68.2188 |  | 15.12 | 19.2 | 34.32 | 68.2188 |  | 15.12 | 19.2 | 34.32 | 68.2188 |  | 314.6 | 781.0353 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 492.6131 | 625.3391 | 625.3391 | [12 empty] | I
Project-A12 |  | v004 |  | 0.54002 | 1.4999 |  |  |  | 65 | 21.84 | 86.84 | 120.3665 |  | 15.6 | 91 | 106.6 | 60.67 |  | 15.6 | 21.84 | 37.44 | 28.888 |  | 15.6 | 21.84 | 37.44 | 28.888 |  | 15.6 | 21.84 | 37.44 | 28.888 |  | 15.6 | 21.84 | 37.44 | 28.888 |  | 343.2 | 296.5883 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 264.8062 | 133.4741 | 264.8062 | [12 empty] | S
Project-A13 |  | v007 |  | 0.56803 | 1.9849 |  |  |  | 96 | 9.6 | 105.6 | 169.0041 |  | 23.04 | 40 | 63.04 | 40.561 |  | 23.04 | 9.6 | 32.64 | 40.561 |  | 23.04 | 9.6 | 32.64 | 40.561 |  | 23.04 | 9.6 | 32.64 | 40.561 |  | 23.04 | 9.6 | 32.64 | 40.561 |  | 299.2 | 371.8091 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 371.8091 | 44.3341 | 371.8091
Project-A14 |  | v006 |  | 0.54648 | 2.0102 |  |  |  | 39 | 12.72 | 51.72 | 71.3661 |  | 9.36 | 53 | 62.36 | 26.3652 |  | 9.36 | 12.72 | 22.08 | 17.1279 |  | 9.36 | 12.72 | 22.08 | 17.1279 |  | 9.36 | 12.72 | 22.08 | 17.1279 |  | 9.36 | 12.72 | 22.08 | 17.1279 |  | 202.4 | 166.2427 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 157.0053 | 58.0034 | 157.0053 | [12 empty] | W
Project-A15 |  | v008 |  | 0.96357 | 2.166 |  |  |  | 72 | 23.76 | 95.76 | 74.7219 |  | 17.28 | 99 | 116.28 | 45.707 |  | 17.28 | 23.76 | 41.04 | 17.9333 |  | 17.28 | 23.76 | 41.04 | 17.9333 |  | 17.28 | 23.76 | 41.04 | 17.9333 |  | 17.28 | 23.76 | 41.04 | 17.9333 |  | 376.2 | 192.1619 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 164.3882 | 100.5554 | 164.3882 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 88.5594 |  | 10.544 | 63.5333 | 74.0773 | 69.9966 |  | 10.544 | 15.248 | 25.792 | 26.128 |  | 10.544 | 15.248 | 25.792 | 26.128 |  | 10.544 | 15.248 | 25.792 | 26.128 |  | 10.544 | 15.248 | 25.792 | 26.128 |  | 236.4267 | 263.0679 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 190.0377 | 150.2578 | 239.5063 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1328.3911 |  | 158.16 | 953 | 1111.16 | 1049.9494 |  | 158.16 | 228.72 | 386.88 | 391.9194 |  | 158.16 | 228.72 | 386.88 | 391.9194 |  | 158.16 | 228.72 | 386.88 | 391.9194 |  | 158.16 | 228.72 | 386.88 | 391.9194 |  | 3546.4 | 3946.018 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2850.5662 | 2253.8665 | 3592.5941 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 786.0353 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 271.0012 |  | <- To shorten average individual project span |  |  |  | <----------> | 239.5063
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 57.987 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 1345.3325 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 2460.3559 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.53938 | 0.28229 |  |  |  | 2014-01-01 |  | 30 | 2014-02-01 | 2014-04-04 21:58 |  | 0 | 2014-04-05 21:58 | 2014-12-24 01:27 |  | 0 | 2014-12-25 01:27 | 2015-02-25 23:25 |  | 0 | 2015-02-26 23:25 | 2015-04-30 21:22 |  | 0 | 2015-05-01 21:22 | 2015-07-03 19:20 |  | 0 | 2015-07-04 19:20 | 2015-09-05 17:17 |  | v001 |  | 0.056452 |  | 30 | 0 | 0 | 0 | 0 | 0 | 30 | 25.4032 |  | 581.7203 | 786.0353 | [14 empty] | E
Project-A02 |  | 0.32036 | 1.5504 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-17 19:43 |  | 0 | 2014-02-18 19:43 | 2014-04-11 10:06 |  | 0 | 2014-04-12 10:06 | 2014-04-24 19:19 |  | 0 | 2014-04-25 19:19 | 2014-05-08 04:31 |  | 0 | 2014-05-09 04:31 | 2014-05-21 13:44 |  | 0 | 2014-05-22 13:44 | 2014-06-03 22:57 |  | v002 |  | 0.058933 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 152.9561 | [15 empty] | N
Project-A03 |  | 0.59381 | 2.3585 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-02-20 22:40 |  | 0 | 2014-02-21 22:40 | 2014-03-05 09:25 |  | 0 | 2014-03-06 09:25 | 2014-03-12 20:37 |  | 0 | 2014-03-13 20:37 | 2014-03-20 07:49 |  | 0 | 2014-03-21 07:49 | 2014-03-27 19:01 |  | 0 | 2014-03-28 19:01 | 2014-04-04 06:13 |  | v003 |  | 0.026675 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 9.2029 |  | 69.2593 | [15 empty] | D
Project-A04 |  | 0.50778 | 1.567 |  |  |  | 2014-01-01 |  | 44 | 2014-02-15 | 2014-04-24 22:16 |  | 0 | 2014-04-25 22:16 | 2014-05-12 11:18 |  | 0 | 2014-05-13 11:18 | 2014-05-30 00:19 |  | 13 | 2014-06-13 00:19 | 2014-06-29 13:21 |  | 0 | 2014-06-30 13:21 | 2014-07-17 02:22 |  | 1 | 2014-07-19 02:22 | 2014-08-04 15:24 |  | v004 |  | 0.032878 |  | 44 | 0 | 0 | 13 | 0 | 1 | 58 | 21.6998 |  | 170.6416
Project-A05 |  | 0.52473 | 1.5099 |  |  |  | 2014-01-01 |  | 48 | 2014-02-19 | 2014-03-03 17:11 |  | 0 | 2014-03-04 17:11 | 2014-04-26 16:49 |  | 0 | 2014-04-27 16:49 | 2014-05-10 10:00 |  | 0 | 2014-05-11 10:00 | 2014-05-24 03:11 |  | 0 | 2014-05-25 03:11 | 2014-06-06 20:23 |  | 0 | 2014-06-07 20:23 | 2014-06-20 13:34 |  | v002 |  | 0.05335 |  | 48 | 0 | 0 | 0 | 0 | 0 | 48 | 38.4119 |  | 121.5654 | [15 empty] | O
Project-A06 |  | 0.56527 | 1.4717 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-05-29 23:47 |  | 0 | 2014-05-30 23:47 | 2014-06-29 21:20 |  | 0 | 2014-06-30 21:20 | 2014-07-22 23:12 |  | 0 | 2014-07-23 23:12 | 2014-08-15 01:04 |  | 0 | 2014-08-16 01:04 | 2014-09-07 02:56 |  | 0 | 2014-09-08 02:56 | 2014-09-30 04:48 |  | v003 |  | 0.059553 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 50.0248 |  | 215.2001 | [15 empty] | F
Project-A07 |  | 0.50601 | 1.4944 |  |  |  | 2014-01-01 |  | 71 | 2014-03-14 | 2014-09-13 18:57 |  | 0 | 2014-09-14 18:57 | 2014-11-09 07:58 |  | 0 | 2014-11-10 07:58 | 2014-12-24 10:36 |  | 3 | 2014-12-28 10:36 | 2015-02-10 13:13 |  | 0 | 2015-02-11 13:13 | 2015-03-27 15:51 |  | 0 | 2015-03-28 15:51 | 2015-05-11 18:29 |  | v005 |  | 0.10918 |  | 71 | 0 | 0 | 3 | 0 | 0 | 74 | 116.2779 |  | 423.77
Project-A08 |  | 0.51353 | 2.6086 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 17:41 |  | 0 | 2014-01-12 17:41 | 2014-01-16 22:53 |  | 0 | 2014-01-17 22:53 | 2014-01-20 06:58 |  | 0 | 2014-01-21 06:58 | 2014-01-23 15:03 |  | 0 | 2014-01-24 15:03 | 2014-01-26 23:08 |  | 0 | 2014-01-27 23:08 | 2014-01-30 07:13 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28.3005 | [15 empty] | T
Project-A09 |  | 0.51339 | 1.7007 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-04-07 10:40 |  | 0 | 2014-04-08 10:40 | 2014-05-29 00:18 |  | 0 | 2014-05-30 00:18 | 2014-06-21 22:04 |  | 23 | 2014-07-15 22:04 | 2014-08-07 19:50 |  | 4 | 2014-08-12 19:50 | 2014-09-04 17:35 |  | 0 | 2014-09-05 17:35 | 2014-09-28 15:21 |  | v003 |  | 0.083747 |  | 0 | 0 | 0 | 23 | 4 | 0 | 27 | 0 |  | 269.6396 | [15 empty] | H
Project-A10 |  | 0.51628 | 1.5142 |  |  |  | 2014-01-01 |  | 364 | 2015-01-01 | 2015-03-11 17:32 |  | 0 | 2015-03-12 17:32 | 2015-05-09 04:29 |  | 0 | 2015-05-10 04:29 | 2015-05-26 22:08 |  | 0 | 2015-05-27 22:08 | 2015-06-13 15:47 |  | 0 | 2015-06-14 15:47 | 2015-07-01 09:25 |  | 0 | 2015-07-02 09:25 | 2015-07-19 03:04 |  | v001 |  | 0.076303 |  | 364 | 0 | 0 | 0 | 0 | 0 | 364 | 416.6129 |  | 199.1279 | [15 empty] | I
Project-A11 |  | 0.28136 | 0.28145 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-08-13 21:58 |  | 0 | 2014-08-14 21:58 | 2015-05-26 03:50 |  | 0 | 2015-05-27 03:50 | 2015-08-03 09:06 |  | 0 | 2015-08-04 09:06 | 2015-10-11 14:21 |  | 0 | 2015-10-12 14:21 | 2015-12-19 19:36 |  | 0 | 2015-12-20 19:36 | 2016-02-27 00:51 |  | v002 |  | 0.08871 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 786.0353 | [15 empty] | S
Project-A12 |  | 0.54002 | 1.4999 |  |  |  | 2014-01-01 |  | 47 | 2014-02-18 | 2014-06-18 08:48 |  | 0 | 2014-06-19 08:48 | 2014-08-19 00:53 |  | 0 | 2014-08-20 00:53 | 2014-09-17 22:11 |  | 0 | 2014-09-18 22:11 | 2014-10-17 19:30 |  | 0 | 2014-10-18 19:30 | 2014-11-16 16:48 |  | 0 | 2014-11-17 16:48 | 2014-12-16 14:07 |  | v004 |  | 0.096774 |  | 47 | 0 | 0 | 0 | 0 | 0 | 47 | 68.2258 |  | 301.5883
Project-A13 |  | 0.56803 | 1.9849 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-08-15 00:06 |  | 0 | 2014-08-16 00:06 | 2014-09-25 13:34 |  | 0 | 2014-09-26 13:34 | 2014-11-06 03:02 |  | 0 | 2014-11-07 03:02 | 2014-12-17 16:29 |  | 0 | 2014-12-18 16:29 | 2015-01-28 05:57 |  | 0 | 2015-01-29 05:57 | 2015-03-10 19:25 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 376.8091 | [15 empty] | W
Project-A14 |  | 0.54648 | 2.0102 |  |  |  | 2014-01-01 |  | 62 | 2014-03-05 | 2014-05-15 08:47 |  | 0 | 2014-05-16 08:47 | 2014-06-11 17:33 |  | 0 | 2014-06-12 17:33 | 2014-06-29 20:37 |  | 0 | 2014-06-30 20:37 | 2014-07-17 23:41 |  | 0 | 2014-07-18 23:41 | 2014-08-05 02:45 |  | 0 | 2014-08-06 02:45 | 2014-08-23 05:49 |  | v006 |  | 0.057072 |  | 62 | 0 | 0 | 0 | 0 | 0 | 62 | 53.0769 |  | 171.2427 | [15 empty] | O
Project-A15 |  | 0.96357 | 2.166 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-17 17:20 |  | 0 | 2014-03-18 17:20 | 2014-05-03 10:18 |  | 0 | 2014-05-04 10:18 | 2014-05-22 08:41 |  | 0 | 2014-05-23 08:41 | 2014-06-10 07:05 |  | 0 | 2014-06-11 07:05 | 2014-06-29 05:29 |  | 0 | 2014-06-30 05:29 | 2014-07-18 03:53 |  | v008 |  | 0.10608 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 197.1619 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 53.4 |  |  |  | 0 |  |  |  | 0 |  |  |  | 2.6 |  |  |  | 0.26667 |  |  |  | 0.066667 | [5 empty] | 0.066667 |  | 53.4 | 0 | 0 | 2.6 | 0.26667 | 0.066667 | 56.3333 | 57.987 | Average | 271.0012 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 801 |  |  |  | 0 |  |  |  | 0 |  |  |  | 39 |  |  |  | 4 |  |  |  | 1 | [5 empty] | 1 |  | 801 | 0 | 0 | 39 | 4 | 1 | 845 | 869.8046 | Total | 4065.018 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 6
| Days: | 26.9067
E
N
SIT - Violation | Count: | 4 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 24.0682
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-12-25 01:27 | 2015-02-25 23:25 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-12 10:06 | 2014-04-24 19:19 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-03-06 09:25 | 2014-03-12 20:37 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-13 11:18 | 2014-05-30 00:19 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | 0 | 0 | 0 | 0 | 0.00085704 | 0 | 0 | 0 | 0 | 0 | 8.8914 | I
Project-A05 | 2014-04-27 16:49 | 2014-05-10 10:00 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.9878 | S
Project-A06 | 2014-06-30 21:20 | 2014-07-22 23:12 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2014-11-10 07:58 | 2014-12-24 10:36 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-17 22:53 | 2014-01-20 06:58 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-05-30 00:18 | 2014-06-21 22:04 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 9.1881 | 0 | R
Project-A10 | 2015-05-10 04:29 | 2015-05-26 22:08 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2015-05-27 03:50 | 2015-08-03 09:06 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-20 00:53 | 2014-09-17 22:11 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-09-26 13:34 | 2014-11-06 03:02 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-12 17:33 | 2014-06-29 20:37 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-05-04 10:18 | 2014-05-22 08:41 | v008 | [31 empty] | T
UAT - Violation | Count: | 2 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 2.8385
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-02-26 23:25 | 2015-04-30 21:22 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-25 19:19 | 2014-05-08 04:31 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-13 20:37 | 2014-03-20 07:49 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-13 00:19 | 2014-06-29 13:21 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-11 10:00 | 2014-05-24 03:11 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.77081
Project-A06 | 2014-07-23 23:12 | 2014-08-15 01:04 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2014-12-28 10:36 | 2015-02-10 13:13 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-21 06:58 | 2014-01-23 15:03 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-15 22:04 | 2014-08-07 19:50 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 2.0677 | 0
Project-A10 | 2015-05-27 22:08 | 2015-06-13 15:47 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-08-04 09:06 | 2015-10-11 14:21 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-18 22:11 | 2014-10-17 19:30 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-11-07 03:02 | 2014-12-17 16:29 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-06-30 20:37 | 2014-07-17 23:41 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-05-23 08:41 | 2014-06-10 07:05 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-05-01 21:22 | 2015-07-03 19:20 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-09 04:31 | 2014-05-21 13:44 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-21 07:49 | 2014-03-27 19:01 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-30 13:21 | 2014-07-17 02:22 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-25 03:11 | 2014-06-06 20:23 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-16 01:04 | 2014-09-07 02:56 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-02-11 13:13 | 2015-03-27 15:51 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-24 15:03 | 2014-01-26 23:08 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-12 19:50 | 2014-09-04 17:35 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-06-14 15:47 | 2015-07-01 09:25 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-10-12 14:21 | 2015-12-19 19:36 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-18 19:30 | 2014-11-16 16:48 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-18 16:29 | 2015-01-28 05:57 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-18 23:41 | 2014-08-05 02:45 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-06-11 07:05 | 2014-06-29 05:29 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-07-04 19:20 | 2015-09-05 17:17 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-22 13:44 | 2014-06-03 22:57 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-28 19:01 | 2014-04-04 06:13 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-07-19 02:22 | 2014-08-04 15:24 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-06-07 20:23 | 2014-06-20 13:34 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-08 02:56 | 2014-09-30 04:48 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-03-28 15:51 | 2015-05-11 18:29 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-27 23:08 | 2014-01-30 07:13 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-09-05 17:35 | 2014-09-28 15:21 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-07-02 09:25 | 2015-07-19 03:04 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-12-20 19:36 | 2016-02-27 00:51 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-17 16:48 | 2014-12-16 14:07 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-29 05:57 | 2015-03-10 19:25 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-06 02:45 | 2014-08-23 05:49 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-06-30 05:29 | 2014-07-18 03:53 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.72051 | 72.051 | 72
0.97986 | 97.9855 | 97
0.57624 | 57.6239 | 57
0.72972 | 72.9723 | 72
0.12819 | 12.8192 | 12
0.32411 | 32.4107 | 32
0.62507 | 62.5072 | 62
0.3084 | 30.8403 | 30
0.89393 | 89.3934 | 89
0.45523 | 45.5228 | 45
0.39095 | 39.0949 | 39
0.037118 | 3.7118 | 3
0.43125 | 43.1247 | 43
0.85148 | 85.1478 | 85
0.40026 | 40.0255 | 40
0.0021839 | 0.21839 | 0
0.52459 | 52.4594 | 52
0.85297 | 85.2973 | 85
0.45695 | 45.6945 | 45
0.9061 | 90.6102 | 90
0.011 | 1.1 | 1
0.12612 | 12.6117 | 12
0.48779 | 48.779 | 48
0.50864 | 50.8636 | 50
0.27473 | 27.4729 | 27
0.031156 | 3.1156 | 3
0.033143 | 3.3143 | 3
0.52148 | 52.1477 | 52
0.26903 | 26.9032 | 26
0.28354 | 28.354 | 28
0.67181 | 67.1813 | 67
0.93453 | 93.4533 | 93
0.79305 | 79.305 | 79
0.45441 | 45.4412 | 45
0.46864 | 46.8642 | 46
0.1807 | 18.0696 | 18
0.89469 | 89.4686 | 89
0.087903 | 8.7903 | 8
0.7801 | 78.0099 | 78

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 2460.3559 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.9 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH