## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.5 | 0.25003 |  |  |  | 17 | 17.76 | 34.76 | 71.0322 |  | 4.08 | 74 | 78.08 | 295.9675 |  | 4.08 | 17.76 | 21.84 | 71.0322 |  | 4.08 | 17.76 | 21.84 | 71.0322 |  | 4.08 | 17.76 | 21.84 | 71.0322 |  | 4.08 | 17.76 | 21.84 | 71.0322 |  | 200.2 | 651.1284 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 74.8 | 651.1284 | 651.1284
Project-A02 |  | v002 |  | 0.5 | 1.5 |  |  |  | 15 | 19.2 | 34.2 | 30 |  | 3.6 | 80 | 83.6 | 53.3329 |  | 3.6 | 19.2 | 22.8 | 12.7999 |  | 3.6 | 19.2 | 22.8 | 12.7999 |  | 3.6 | 19.2 | 22.8 | 12.7999 |  | 3.6 | 19.2 | 22.8 | 12.7999 |  | 209 | 134.5325 | 104500 |  | 0.058933 |  | 33 | 176 |  | 65.9999 | 117.3324 | 117.3324 | [12 empty] | E
Project-A03 |  | v003 |  | 0.50002 | 5 |  |  |  | 16 | 6.48 | 22.48 | 31.9987 |  | 3.84 | 27 | 30.84 | 7.6797 |  | 3.84 | 6.48 | 10.32 | 7.6797 |  | 3.84 | 6.48 | 10.32 | 7.6797 |  | 3.84 | 6.48 | 10.32 | 7.6797 |  | 3.84 | 6.48 | 10.32 | 7.6797 |  | 94.6 | 70.3972 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 70.3972 | 11.88 | 70.3972 | [12 empty] | N
Project-A04 |  | v004 |  | 0.5 | 1.5 |  |  |  | 35 | 4.32 | 39.32 | 69.9998 |  | 8.4 | 18 | 26.4 | 16.8 |  | 8.4 | 4.32 | 12.72 | 16.8 |  | 8.4 | 4.32 | 12.72 | 16.8 |  | 8.4 | 4.32 | 12.72 | 16.8 |  | 8.4 | 4.32 | 12.72 | 16.8 |  | 116.6 | 153.9996 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 153.9996 | 26.3995 | 153.9996 | [12 empty] | D
Project-A05 |  | v002 |  | 0.5 | 1.7444 |  |  |  | 6 | 19.2 | 25.2 | 12.0001 |  | 1.44 | 80 | 81.44 | 45.8619 |  | 1.44 | 19.2 | 20.64 | 11.0068 |  | 1.44 | 19.2 | 20.64 | 11.0068 |  | 1.44 | 19.2 | 20.64 | 11.0068 |  | 1.44 | 19.2 | 20.64 | 11.0068 |  | 189.2 | 101.8893 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 26.4002 | 100.8961 | 100.8961
Project-A06 |  | v003 |  | 0.5 | 1.5 |  |  |  | 52 | 10.56 | 62.56 | 104.0006 |  | 12.48 | 44 | 56.48 | 29.3333 |  | 12.48 | 10.56 | 23.04 | 24.9601 |  | 12.48 | 10.56 | 23.04 | 24.9601 |  | 12.48 | 10.56 | 23.04 | 24.9601 |  | 12.48 | 10.56 | 23.04 | 24.9601 |  | 211.2 | 233.1744 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 228.8013 | 64.5333 | 228.8013 | [12 empty] | O
Project-A07 |  | v005 |  | 0.5 | 0.25 |  |  |  | 93 | 19.92 | 112.92 | 186.0001 |  | 22.32 | 83 | 105.32 | 331.9996 |  | 22.32 | 19.92 | 42.24 | 79.6799 |  | 22.32 | 19.92 | 42.24 | 79.6799 |  | 22.32 | 19.92 | 42.24 | 79.6799 |  | 22.32 | 19.92 | 42.24 | 79.6799 |  | 387.2 | 836.7194 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 409.2002 | 730.3992 | 730.3992 | [12 empty] | F
Project-A08 |  | v006 |  | 0.50001 | 1.5034 |  |  |  | 5 | 2.64 | 7.64 | 9.9999 |  | 1.2 | 11 | 12.2 | 7.3167 |  | 1.2 | 2.64 | 3.84 | 2.4 |  | 1.2 | 2.64 | 3.84 | 2.4 |  | 1.2 | 2.64 | 3.84 | 2.4 |  | 1.2 | 2.64 | 3.84 | 2.4 |  | 35.2 | 26.9164 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 21.9998 | 16.0966 | 21.9998
Project-A09 |  | v003 |  | 0.5 | 0.25 |  |  |  | 49 | 20.64 | 69.64 | 98.0004 |  | 11.76 | 86 | 97.76 | 343.9974 |  | 11.76 | 20.64 | 32.4 | 82.5594 |  | 11.76 | 20.64 | 32.4 | 82.5594 |  | 11.76 | 20.64 | 32.4 | 82.5594 |  | 11.76 | 20.64 | 32.4 | 82.5594 |  | 297 | 772.2353 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 215.6009 | 756.7943 | 756.7943 | [12 empty] | T
Project-A10 |  | v001 |  | 0.5 | 1.5017 |  |  |  | 36 | 20.88 | 56.88 | 71.9997 |  | 8.64 | 87 | 95.64 | 57.9346 |  | 8.64 | 20.88 | 29.52 | 17.2799 |  | 8.64 | 20.88 | 29.52 | 17.2799 |  | 8.64 | 20.88 | 29.52 | 17.2799 |  | 8.64 | 20.88 | 29.52 | 17.2799 |  | 270.6 | 199.054 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 158.3993 | 127.4561 | 158.3993 | [12 empty] | H
Project-A11 |  | v002 |  | 0.50001 | 1.5 |  |  |  | 63 | 19.2 | 82.2 | 125.9985 |  | 15.12 | 80 | 95.12 | 53.3332 |  | 15.12 | 19.2 | 34.32 | 30.2396 |  | 15.12 | 19.2 | 34.32 | 30.2396 |  | 15.12 | 19.2 | 34.32 | 30.2396 |  | 15.12 | 19.2 | 34.32 | 30.2396 |  | 314.6 | 300.2903 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 277.1968 | 117.333 | 277.1968 | [12 empty] | I
Project-A12 |  | v004 |  | 0.5 | 1.5 |  |  |  | 65 | 21.84 | 86.84 | 130.0011 |  | 15.6 | 91 | 106.6 | 60.6683 |  | 15.6 | 21.84 | 37.44 | 31.2003 |  | 15.6 | 21.84 | 37.44 | 31.2003 |  | 15.6 | 21.84 | 37.44 | 31.2003 |  | 15.6 | 21.84 | 37.44 | 31.2003 |  | 343.2 | 315.4705 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 286.0025 | 133.4703 | 286.0025 | [12 empty] | S
Project-A13 |  | v007 |  | 0.5 | 2 |  |  |  | 96 | 9.6 | 105.6 | 191.9999 |  | 23.04 | 40 | 63.04 | 46.08 |  | 23.04 | 9.6 | 32.64 | 46.08 |  | 23.04 | 9.6 | 32.64 | 46.08 |  | 23.04 | 9.6 | 32.64 | 46.08 |  | 23.04 | 9.6 | 32.64 | 46.08 |  | 299.2 | 422.3998 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 422.3998 | 43.9999 | 422.3998
Project-A14 |  | v006 |  | 0.5 | 2.0005 |  |  |  | 39 | 12.72 | 51.72 | 78.0002 |  | 9.36 | 53 | 62.36 | 26.4934 |  | 9.36 | 12.72 | 22.08 | 18.72 |  | 9.36 | 12.72 | 22.08 | 18.72 |  | 9.36 | 12.72 | 22.08 | 18.72 |  | 9.36 | 12.72 | 22.08 | 18.72 |  | 202.4 | 179.3737 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 171.6004 | 58.2854 | 171.6004 | [12 empty] | W
Project-A15 |  | v008 |  | 0.99998 | 2 |  |  |  | 72 | 23.76 | 95.76 | 72.0016 |  | 17.28 | 99 | 116.28 | 49.5004 |  | 17.28 | 23.76 | 41.04 | 17.2804 |  | 17.28 | 23.76 | 41.04 | 17.2804 |  | 17.28 | 23.76 | 41.04 | 17.2804 |  | 17.28 | 23.76 | 41.04 | 17.2804 |  | 376.2 | 190.6235 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 158.4036 | 108.9008 | 158.4036 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 85.5355 |  | 10.544 | 63.5333 | 74.0773 | 95.0866 |  | 10.544 | 15.248 | 25.792 | 31.3145 |  | 10.544 | 15.248 | 25.792 | 31.3145 |  | 10.544 | 15.248 | 25.792 | 31.3145 |  | 10.544 | 15.248 | 25.792 | 31.3145 |  | 236.4267 | 305.8803 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 182.7467 | 204.327 | 287.05 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1283.0327 |  | 158.16 | 953 | 1111.16 | 1426.2987 |  | 158.16 | 228.72 | 386.88 | 469.7182 |  | 158.16 | 228.72 | 386.88 | 469.7182 |  | 158.16 | 228.72 | 386.88 | 469.7182 |  | 158.16 | 228.72 | 386.88 | 469.7182 |  | 3546.4 | 4588.2045 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2741.2012 | 3064.9055 | 4305.7505 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 908.7194 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 359.6803 |  | <- To shorten average individual project span |  |  |  | <----------> | 287.05
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 38.7215 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 2991.1385 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 4298.2596 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.5 | 0.25003 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-14 00:46 |  | 0 | 2014-03-15 00:46 | 2015-01-05 |  | 0 | 2015-01-06 | 2015-03-18 00:46 |  | 0 | 2015-03-19 00:46 | 2015-05-29 01:32 |  | 0 | 2015-05-30 01:32 | 2015-08-09 02:19 |  | 0 | 2015-08-10 02:19 | 2015-10-20 03:05 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 656.1284 | 908.7194 | [14 empty] | E
Project-A02 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-01 |  | 0 | 2014-02-02 | 2014-03-27 07:59 |  | 0 | 2014-03-28 07:59 | 2014-04-10 03:11 |  | 0 | 2014-04-11 03:11 | 2014-04-23 22:23 |  | 0 | 2014-04-24 22:23 | 2014-05-07 17:35 |  | 0 | 2014-05-08 17:35 | 2014-05-21 12:47 |  | v002 |  | 0.058933 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 139.5325 | [15 empty] | N
Project-A03 |  | 0.50002 | 5 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-02 23:58 |  | 0 | 2014-02-03 23:58 | 2014-02-11 16:17 |  | 0 | 2014-02-12 16:17 | 2014-02-20 08:36 |  | 0 | 2014-02-21 08:36 | 2014-03-01 00:54 |  | 0 | 2014-03-02 00:54 | 2014-03-09 17:13 |  | 0 | 2014-03-10 17:13 | 2014-03-18 09:32 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 75.3972 | [15 empty] | D
Project-A04 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-04-16 |  | 0 | 2014-04-17 | 2014-05-03 19:12 |  | 0 | 2014-05-04 19:12 | 2014-05-21 14:24 |  | 0 | 2014-05-22 14:24 | 2014-06-08 09:36 |  | 0 | 2014-06-09 09:36 | 2014-06-26 04:48 |  | 0 | 2014-06-27 04:48 | 2014-07-13 23:59 |  | v004 |  | 0.032878 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 16.768 |  | 158.9996
Project-A05 |  | 0.5 | 1.7444 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-14 |  | 0 | 2014-01-15 | 2014-03-01 20:41 |  | 0 | 2014-03-02 20:41 | 2014-03-13 20:51 |  | 0 | 2014-03-14 20:51 | 2014-03-25 21:01 |  | 0 | 2014-03-26 21:01 | 2014-04-06 21:11 |  | 0 | 2014-04-07 21:11 | 2014-04-18 21:21 |  | v002 |  | 0.05335 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 106.8893 | [15 empty] | O
Project-A06 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-06-11 00:01 |  | 0 | 2014-06-12 00:01 | 2014-07-11 08:01 |  | 0 | 2014-07-12 08:01 | 2014-08-06 07:03 |  | 365 | 2015-08-07 07:03 | 2015-09-01 06:06 |  | 0 | 2015-09-02 06:06 | 2015-09-27 05:09 |  | 1 | 2015-09-29 05:09 | 2015-10-24 04:11 |  | v003 |  | 0.059553 |  | 56 | 0 | 0 | 365 | 0 | 1 | 422 | 50.0248 |  | 604.1744 | [15 empty] | F
Project-A07 |  | 0.5 | 0.25 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-09-12 |  | 0 | 2014-09-13 | 2015-08-11 |  | 0 | 2015-08-12 | 2015-10-30 16:19 |  | 0 | 2015-10-31 16:19 | 2016-01-19 08:38 |  | 0 | 2016-01-20 08:38 | 2016-04-09 00:57 |  | 0 | 2016-04-10 00:57 | 2016-06-28 17:16 |  | v005 |  | 0.10918 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 109.727 |  | 841.7194
Project-A08 |  | 0.50001 | 1.5034 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-12 |  | 0 | 2014-01-13 | 2014-01-20 07:36 |  | 0 | 2014-01-21 07:36 | 2014-01-23 17:12 |  | 0 | 2014-01-24 17:12 | 2014-01-27 02:48 |  | 0 | 2014-01-28 02:48 | 2014-01-30 12:24 |  | 0 | 2014-01-31 12:24 | 2014-02-02 22:00 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 31.9164 | [15 empty] | T
Project-A09 |  | 0.5 | 0.25 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-04-22 00:01 |  | 0 | 2014-04-23 00:01 | 2015-04-01 23:57 |  | 0 | 2015-04-02 23:57 | 2015-06-24 13:22 |  | 0 | 2015-06-25 13:22 | 2015-09-16 02:48 |  | 0 | 2015-09-17 02:48 | 2015-12-08 16:13 |  | 0 | 2015-12-09 16:13 | 2016-03-01 05:39 |  | v003 |  | 0.083747 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 15.0744 |  | 777.2353 | [15 empty] | H
Project-A10 |  | 0.5 | 1.5017 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-04-07 |  | 0 | 2014-04-08 | 2014-06-04 22:25 |  | 0 | 2014-06-05 22:25 | 2014-06-23 05:08 |  | 0 | 2014-06-24 05:08 | 2014-07-11 11:52 |  | 0 | 2014-07-12 11:52 | 2014-07-29 18:35 |  | 0 | 2014-07-30 18:35 | 2014-08-17 01:18 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 26.3244 |  | 204.054 | [15 empty] | I
Project-A11 |  | 0.50001 | 1.5 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-06-10 23:58 |  | 0 | 2014-06-11 23:58 | 2014-08-04 07:58 |  | 0 | 2014-08-05 07:58 | 2014-09-04 13:43 |  | 0 | 2014-09-05 13:43 | 2014-10-05 19:28 |  | 0 | 2014-10-06 19:28 | 2014-11-06 01:13 |  | 365 | 2015-11-07 01:13 | 2015-12-07 06:58 |  | v002 |  | 0.08871 |  | 34 | 0 | 0 | 0 | 0 | 365 | 399 | 45.2419 |  | 670.2903 | [15 empty] | S
Project-A12 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-06-26 00:02 |  | 0 | 2014-06-27 00:02 | 2014-08-26 16:04 |  | 0 | 2014-08-27 16:04 | 2014-09-27 20:52 |  | 1 | 2014-09-29 20:52 | 2014-10-31 01:41 |  | 0 | 2014-11-01 01:41 | 2014-12-02 06:29 |  | 0 | 2014-12-03 06:29 | 2015-01-03 11:18 |  | v004 |  | 0.096774 |  | 45 | 0 | 0 | 1 | 0 | 0 | 46 | 65.3226 |  | 321.4705
Project-A13 |  | 0.5 | 2 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-09-07 |  | 0 | 2014-09-08 | 2014-10-24 01:55 |  | 0 | 2014-10-25 01:55 | 2014-12-10 03:50 |  | 0 | 2014-12-11 03:50 | 2015-01-26 05:45 |  | 0 | 2015-01-27 05:45 | 2015-03-14 07:41 |  | 0 | 2015-03-15 07:41 | 2015-04-30 09:36 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 427.3998 | [15 empty] | W
Project-A14 |  | 0.5 | 2.0005 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-27 |  | 0 | 2014-05-28 | 2014-06-23 11:51 |  | 0 | 2014-06-24 11:51 | 2014-07-13 05:08 |  | 0 | 2014-07-14 05:08 | 2014-08-01 22:24 |  | 0 | 2014-08-02 22:24 | 2014-08-21 15:41 |  | 0 | 2014-08-22 15:41 | 2014-09-10 08:58 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 57.3573 |  | 184.3737 | [15 empty] | O
Project-A15 |  | 0.99998 | 2 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-06-01 00:02 |  | 0 | 2014-06-02 00:02 | 2014-07-21 12:03 |  | 0 | 2014-07-22 12:03 | 2014-08-08 18:47 |  | 0 | 2014-08-09 18:47 | 2014-08-27 01:30 |  | 0 | 2014-08-28 01:30 | 2014-09-14 08:14 |  | 0 | 2014-09-15 08:14 | 2014-10-02 14:58 |  | v008 |  | 0.10608 |  | 78 | 0 | 0 | 0 | 0 | 0 | 78 | 124.1129 |  | 195.6235 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 31.4667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 24.4 |  |  |  | 0 |  |  |  | 24.4 | [5 empty] | 0.066667 |  | 31.4667 | 0 | 0 | 24.4 | 0 | 24.4 | 80.2667 | 38.7215 | Average | 359.6803 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 472 |  |  |  | 0 |  |  |  | 0 |  |  |  | 366 |  |  |  | 0 |  |  |  | 366 | [5 empty] | 1 |  | 472 | 0 | 0 | 366 | 0 | 366 | 1204 | 580.822 | Total | 5395.2045 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 8
| Days: | 59.8228
E
N
SIT - Violation | Count: | 5 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 27.9866
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2015-01-06 | 2015-03-18 00:46 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-28 07:59 | 2014-04-10 03:11 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-12 16:17 | 2014-02-20 08:36 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-04 19:12 | 2014-05-21 14:24 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-03-02 20:41 | 2014-03-13 20:51 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-12 08:01 | 2014-08-06 07:03 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0.96229 | 0 | 0 | 0.87967 | 14.792
Project-A07 | 2015-08-12 | 2015-10-30 16:19 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-21 07:36 | 2014-01-23 17:12 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2015-04-02 23:57 | 2015-06-24 13:22 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-06-05 22:25 | 2014-06-23 05:08 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-08-05 07:58 | 2014-09-04 13:43 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 1 | [11 empty] | 7.9019 | 0 | 0 | 3.4507 | S
Project-A12 | 2014-08-27 16:04 | 2014-09-27 20:52 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-25 01:55 | 2014-12-10 03:50 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-24 11:51 | 2014-07-13 05:08 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-22 12:03 | 2014-08-08 18:47 | v008 | [31 empty] | T
UAT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 5.9413
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-03-19 00:46 | 2015-05-29 01:32 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-11 03:11 | 2014-04-23 22:23 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-21 08:36 | 2014-03-01 00:54 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-22 14:24 | 2014-06-08 09:36 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-14 20:51 | 2014-03-25 21:01 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-08-07 07:03 | 2015-09-01 06:06 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-31 16:19 | 2016-01-19 08:38 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-24 17:12 | 2014-01-27 02:48 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-06-25 13:22 | 2015-09-16 02:48 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-24 05:08 | 2014-07-11 11:52 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-05 13:43 | 2014-10-05 19:28 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 5.9413 | 0 | 0 | 0
Project-A12 | 2014-09-29 20:52 | 2014-10-31 01:41 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-11 03:50 | 2015-01-26 05:45 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-14 05:08 | 2014-08-01 22:24 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-09 18:47 | 2014-08-27 01:30 | v008
NFT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 4.9807
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-05-30 01:32 | 2015-08-09 02:19 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-24 22:23 | 2014-05-07 17:35 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-02 00:54 | 2014-03-09 17:13 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-09 09:36 | 2014-06-26 04:48 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-26 21:01 | 2014-04-06 21:11 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-09-02 06:06 | 2015-09-27 05:09 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-01-20 08:38 | 2016-04-09 00:57 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-28 02:48 | 2014-01-30 12:24 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-09-17 02:48 | 2015-12-08 16:13 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-12 11:52 | 2014-07-29 18:35 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-06 19:28 | 2014-11-06 01:13 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 4.9807 | 0 | 0 | 0
Project-A12 | 2014-11-01 01:41 | 2014-12-02 06:29 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-27 05:45 | 2015-03-14 07:41 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-02 22:24 | 2014-08-21 15:41 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-28 01:30 | 2014-09-14 08:14 | v008
Prod - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 20.9142
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-08-10 02:19 | 2015-10-20 03:05 | v001 |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 20.9142 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-08 17:35 | 2014-05-21 12:47 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-10 17:13 | 2014-03-18 09:32 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-27 04:48 | 2014-07-13 23:59 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-07 21:11 | 2014-04-18 21:21 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-09-29 05:09 | 2015-10-24 04:11 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-04-10 00:57 | 2016-06-28 17:16 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-31 12:24 | 2014-02-02 22:00 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-12-09 16:13 | 2016-03-01 05:39 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-30 18:35 | 2014-08-17 01:18 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-11-07 01:13 | 2015-12-07 06:58 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-03 06:29 | 2015-01-03 11:18 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-15 07:41 | 2015-04-30 09:36 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-22 15:41 | 2014-09-10 08:58 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-15 08:14 | 2014-10-02 14:58 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.1441 | 14.4096 | 14
0.59114 | 59.1144 | 59
0.0079929 | 0.79929 | 0
0.28984 | 28.9845 | 28
0.99992 | 99.992 | 99
0.38507 | 38.507 | 38
0.36096 | 36.0961 | 36
0.72422 | 72.4224 | 72
0.89168 | 89.1682 | 89
0.78434 | 78.4342 | 78
0.80925 | 80.9247 | 80
0.64735 | 64.7351 | 64
0.30421 | 30.4206 | 30
0.10857 | 10.8569 | 10
0.22456 | 22.4563 | 22
0.26163 | 26.1628 | 26
0.64773 | 64.7725 | 64
0.55403 | 55.4032 | 55
0.601 | 60.0997 | 60
0.84602 | 84.6016 | 84
0.45791 | 45.7905 | 45
0.40666 | 40.6658 | 40
0.89285 | 89.2852 | 89
0.92112 | 92.1124 | 92
0.86571 | 86.5706 | 86
0.10927 | 10.9272 | 10
0.93548 | 93.5477 | 93
0.19573 | 19.5732 | 19
0.028051 | 2.8051 | 2
0.27465 | 27.4651 | 27
0.4022 | 40.2198 | 40
0.17846 | 17.8464 | 17
0.81815 | 81.8151 | 81
0.43312 | 43.3124 | 43
0.854 | 85.3997 | 85
0.50419 | 50.4188 | 50
0.78544 | 78.5445 | 78
0.7978 | 79.7804 | 79
0.55946 | 55.9463 | 55

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 4298.2596 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.9 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH