## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.55284 | 1.4989 |  |  |  | 17 | 17.76 | 34.76 | 30.7504 |  | 4.08 | 74 | 78.08 | 49.3693 |  | 4.08 | 17.76 | 21.84 | 11.8486 |  | 4.08 | 17.76 | 21.84 | 11.8486 |  | 4.08 | 17.76 | 21.84 | 11.8486 |  | 4.08 | 17.76 | 21.84 | 11.8486 |  | 200.2 | 127.5141 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 67.6508 | 108.6124 | 108.6124
Project-A02 |  | v002 |  | 0.50127 | 1.4887 |  |  |  | 15 | 19.2 | 34.2 | 29.9241 |  | 3.6 | 80 | 83.6 | 53.7389 |  | 3.6 | 19.2 | 22.8 | 12.8973 |  | 3.6 | 19.2 | 22.8 | 12.8973 |  | 3.6 | 19.2 | 22.8 | 12.8973 |  | 3.6 | 19.2 | 22.8 | 12.8973 |  | 209 | 135.2525 | 104500 |  | 0.058933 |  | 33 | 176 |  | 65.8331 | 118.2257 | 118.2257 | [12 empty] | E
Project-A03 |  | v003 |  | 0.50584 | 1.4995 |  |  |  | 16 | 6.48 | 22.48 | 31.6305 |  | 3.84 | 27 | 30.84 | 18.0056 |  | 3.84 | 6.48 | 10.32 | 7.5913 |  | 3.84 | 6.48 | 10.32 | 7.5913 |  | 3.84 | 6.48 | 10.32 | 7.5913 |  | 3.84 | 6.48 | 10.32 | 7.5913 |  | 94.6 | 80.0014 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 69.587 | 39.6124 | 69.587 | [12 empty] | N
Project-A04 |  | v004 |  | 0.50907 | 1.5367 |  |  |  | 35 | 4.32 | 39.32 | 68.7523 |  | 8.4 | 18 | 26.4 | 16.5006 |  | 8.4 | 4.32 | 12.72 | 16.5006 |  | 8.4 | 4.32 | 12.72 | 16.5006 |  | 8.4 | 4.32 | 12.72 | 16.5006 |  | 8.4 | 4.32 | 12.72 | 16.5006 |  | 116.6 | 151.2551 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 151.2551 | 25.7691 | 151.2551 | [12 empty] | D
Project-A05 |  | v002 |  | 0.5039 | 1.5068 |  |  |  | 6 | 19.2 | 25.2 | 12.7422 |  | 1.44 | 80 | 81.44 | 53.0924 |  | 1.44 | 19.2 | 20.64 | 12.7422 |  | 1.44 | 19.2 | 20.64 | 12.7422 |  | 1.44 | 19.2 | 20.64 | 12.7422 |  | 1.44 | 19.2 | 20.64 | 12.7422 |  | 189.2 | 116.8033 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 26.1957 | 116.8033 | 116.8033
Project-A06 |  | v003 |  | 0.50299 | 1.4983 |  |  |  | 52 | 10.56 | 62.56 | 103.3821 |  | 12.48 | 44 | 56.48 | 29.3663 |  | 12.48 | 10.56 | 23.04 | 24.8117 |  | 12.48 | 10.56 | 23.04 | 24.8117 |  | 12.48 | 10.56 | 23.04 | 24.8117 |  | 12.48 | 10.56 | 23.04 | 24.8117 |  | 211.2 | 231.9952 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 227.4405 | 64.606 | 227.4405 | [12 empty] | O
Project-A07 |  | v005 |  | 0.30069 | 0.25 |  |  |  | 93 | 19.92 | 112.92 | 309.2846 |  | 22.32 | 83 | 105.32 | 332 |  | 22.32 | 19.92 | 42.24 | 79.68 |  | 22.32 | 19.92 | 42.24 | 79.68 |  | 22.32 | 19.92 | 42.24 | 79.68 |  | 22.32 | 19.92 | 42.24 | 79.68 |  | 387.2 | 960.0046 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 680.4262 | 730.4 | 730.4 | [12 empty] | F
Project-A08 |  | v006 |  | 0.64311 | 1.5044 |  |  |  | 5 | 2.64 | 7.64 | 7.7748 |  | 1.2 | 11 | 12.2 | 7.3118 |  | 1.2 | 2.64 | 3.84 | 1.8659 |  | 1.2 | 2.64 | 3.84 | 1.8659 |  | 1.2 | 2.64 | 3.84 | 1.8659 |  | 1.2 | 2.64 | 3.84 | 1.8659 |  | 35.2 | 22.5503 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 17.1045 | 16.0859 | 17.1045
Project-A09 |  | v003 |  | 0.55745 | 1.5037 |  |  |  | 49 | 20.64 | 69.64 | 87.8995 |  | 11.76 | 86 | 97.76 | 57.1914 |  | 11.76 | 20.64 | 32.4 | 21.0959 |  | 11.76 | 20.64 | 32.4 | 21.0959 |  | 11.76 | 20.64 | 32.4 | 21.0959 |  | 11.76 | 20.64 | 32.4 | 21.0959 |  | 297 | 229.4745 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 193.379 | 125.8212 | 193.379 | [12 empty] | T
Project-A10 |  | v001 |  | 0.54354 | 2.3698 |  |  |  | 36 | 20.88 | 56.88 | 66.2323 |  | 8.64 | 87 | 95.64 | 36.7113 |  | 8.64 | 20.88 | 29.52 | 15.8958 |  | 8.64 | 20.88 | 29.52 | 15.8958 |  | 8.64 | 20.88 | 29.52 | 15.8958 |  | 8.64 | 20.88 | 29.52 | 15.8958 |  | 270.6 | 166.5267 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 145.7111 | 80.7649 | 145.7111 | [12 empty] | H
Project-A11 |  | v002 |  | 0.25323 | 1.5299 |  |  |  | 63 | 19.2 | 82.2 | 248.788 |  | 15.12 | 80 | 95.12 | 59.7091 |  | 15.12 | 19.2 | 34.32 | 59.7091 |  | 15.12 | 19.2 | 34.32 | 59.7091 |  | 15.12 | 19.2 | 34.32 | 59.7091 |  | 15.12 | 19.2 | 34.32 | 59.7091 |  | 314.6 | 547.3335 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 547.3335 | 115.0399 | 547.3335 | [12 empty] | I
Project-A12 |  | v004 |  | 0.54908 | 1.5 |  |  |  | 65 | 21.84 | 86.84 | 118.3797 |  | 15.6 | 91 | 106.6 | 60.6654 |  | 15.6 | 21.84 | 37.44 | 28.4111 |  | 15.6 | 21.84 | 37.44 | 28.4111 |  | 15.6 | 21.84 | 37.44 | 28.4111 |  | 15.6 | 21.84 | 37.44 | 28.4111 |  | 343.2 | 292.6897 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 260.4354 | 133.4639 | 260.4354 | [12 empty] | S
Project-A13 |  | v007 |  | 0.57037 | 2.0041 |  |  |  | 96 | 9.6 | 105.6 | 168.3105 |  | 23.04 | 40 | 63.04 | 40.3945 |  | 23.04 | 9.6 | 32.64 | 40.3945 |  | 23.04 | 9.6 | 32.64 | 40.3945 |  | 23.04 | 9.6 | 32.64 | 40.3945 |  | 23.04 | 9.6 | 32.64 | 40.3945 |  | 299.2 | 370.283 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 370.283 | 43.9103 | 370.283
Project-A14 |  | v006 |  | 0.49831 | 1.9676 |  |  |  | 39 | 12.72 | 51.72 | 78.2643 |  | 9.36 | 53 | 62.36 | 26.9358 |  | 9.36 | 12.72 | 22.08 | 18.7834 |  | 9.36 | 12.72 | 22.08 | 18.7834 |  | 9.36 | 12.72 | 22.08 | 18.7834 |  | 9.36 | 12.72 | 22.08 | 18.7834 |  | 202.4 | 180.3338 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 172.1814 | 59.2588 | 172.1814 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0083 | 1.9805 |  |  |  | 72 | 23.76 | 95.76 | 71.4074 |  | 17.28 | 99 | 116.28 | 49.9871 |  | 17.28 | 23.76 | 41.04 | 17.1378 |  | 17.28 | 23.76 | 41.04 | 17.1378 |  | 17.28 | 23.76 | 41.04 | 17.1378 |  | 17.28 | 23.76 | 41.04 | 17.1378 |  | 376.2 | 189.9456 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 157.0962 | 109.9717 | 157.0962 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.5759 |  |  |  | 43.9333 | 15.248 | 59.1813 | 95.5682 |  | 10.544 | 63.5333 | 74.0773 | 59.3986 |  | 10.544 | 15.248 | 25.792 | 24.6244 |  | 10.544 | 15.248 | 25.792 | 24.6244 |  | 10.544 | 15.248 | 25.792 | 24.6244 |  | 10.544 | 15.248 | 25.792 | 24.6244 |  | 236.4267 | 253.4642 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 210.1275 | 125.8897 | 225.7232 | [12 empty] | S
|  | Total |  | 8 | 23.6391 |  |  |  | 659 | 228.72 | 887.72 | 1433.5226 |  | 158.16 | 953 | 1111.16 | 890.9797 |  | 158.16 | 228.72 | 386.88 | 369.3653 |  | 158.16 | 228.72 | 386.88 | 369.3653 |  | 158.16 | 228.72 | 386.88 | 369.3653 |  | 158.16 | 228.72 | 386.88 | 369.3653 |  | 3546.4 | 3801.9633 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3151.9126 | 1888.3454 | 3385.8482 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 1036.0046 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 307.4642 |  | <- To shorten average individual project span |  |  |  | <----------> | 225.7232
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 110.7674 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 1393.8624 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 2848.0987 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.55284 | 1.4989 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-01 18:01 |  | 0 | 2014-02-02 18:01 | 2014-03-24 02:52 |  | 0 | 2014-03-25 02:52 | 2014-04-05 23:14 |  | 365 | 2015-04-06 23:14 | 2015-04-18 19:36 |  | 4 | 2015-04-23 19:36 | 2015-05-05 15:58 |  | 0 | 2015-05-06 15:58 | 2015-05-18 12:20 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 365 | 4 | 0 | 369 | 0 |  | 501.5141 | 1036.0046 | [14 empty] | E
Project-A02 |  | 0.50127 | 1.4887 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-02-12 22:11 |  | 0 | 2014-02-13 22:11 | 2014-04-08 15:55 |  | 0 | 2014-04-09 15:55 | 2014-04-22 13:27 |  | 0 | 2014-04-23 13:27 | 2014-05-06 10:59 |  | 0 | 2014-05-07 10:59 | 2014-05-20 08:31 |  | 0 | 2014-05-21 08:31 | 2014-06-03 06:04 |  | v002 |  | 0.058933 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 10.6079 |  | 140.2525 | [15 empty] | N
Project-A03 |  | 0.50584 | 1.4995 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-02 15:08 |  | 0 | 2014-02-03 15:08 | 2014-02-21 15:16 |  | 0 | 2014-02-22 15:16 | 2014-03-02 05:27 |  | 0 | 2014-03-03 05:27 | 2014-03-10 19:39 |  | 0 | 2014-03-11 19:39 | 2014-03-19 09:50 |  | 0 | 2014-03-20 09:50 | 2014-03-28 00:02 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 85.0014 | [15 empty] | D
Project-A04 |  | 0.50907 | 1.5367 |  |  |  | 2014-01-01 |  | 37 | 2014-02-08 | 2014-04-17 18:03 |  | 0 | 2014-04-18 18:03 | 2014-05-05 06:04 |  | 0 | 2014-05-06 06:04 | 2014-05-22 18:05 |  | 0 | 2014-05-23 18:05 | 2014-06-09 06:06 |  | 0 | 2014-06-10 06:06 | 2014-06-26 18:07 |  | 0 | 2014-06-27 18:07 | 2014-07-14 06:07 |  | v004 |  | 0.032878 |  | 37 | 0 | 0 | 0 | 0 | 0 | 37 | 18.2475 |  | 156.2551
Project-A05 |  | 0.5039 | 1.5068 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-01-14 17:49 |  | 0 | 2015-01-15 17:49 | 2015-03-09 20:02 |  | 0 | 2015-03-10 20:02 | 2015-03-23 13:51 |  | 0 | 2015-03-24 13:51 | 2015-04-06 07:39 |  | 0 | 2015-04-07 07:39 | 2015-04-20 01:28 |  | 0 | 2015-04-21 01:28 | 2015-05-03 19:17 |  | v002 |  | 0.05335 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 292.0906 |  | 121.8033 | [15 empty] | O
Project-A06 |  | 0.50299 | 1.4983 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-04-15 09:10 |  | 0 | 2014-04-16 09:10 | 2014-05-15 17:58 |  | 0 | 2014-05-16 17:58 | 2014-06-10 13:27 |  | 0 | 2014-06-11 13:27 | 2014-07-06 08:55 |  | 365 | 2015-07-07 08:55 | 2015-08-01 04:24 |  | 0 | 2015-08-02 04:24 | 2015-08-26 23:53 |  | v003 |  | 0.059553 |  | 0 | 0 | 0 | 0 | 365 | 0 | 365 | 0 |  | 601.9952 | [15 empty] | F
Project-A07 |  | 0.30069 | 0.25 |  |  |  | 2014-01-01 |  | 71 | 2014-03-14 | 2015-01-17 06:50 |  | 0 | 2015-01-18 06:50 | 2015-12-16 06:50 |  | 0 | 2015-12-17 06:50 | 2016-03-05 23:09 |  | 0 | 2016-03-06 23:09 | 2016-05-25 15:28 |  | 0 | 2016-05-26 15:28 | 2016-08-14 07:47 |  | 0 | 2016-08-15 07:47 | 2016-11-03 00:07 |  | v005 |  | 0.10918 |  | 71 | 0 | 0 | 0 | 0 | 0 | 71 | 116.2779 |  | 965.0046
Project-A08 |  | 0.64311 | 1.5044 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-09 18:36 |  | 0 | 2014-01-10 18:36 | 2014-01-18 02:05 |  | 0 | 2014-01-19 02:05 | 2014-01-20 22:52 |  | 0 | 2014-01-21 22:52 | 2014-01-23 19:38 |  | 0 | 2014-01-24 19:38 | 2014-01-26 16:25 |  | 0 | 2014-01-27 16:25 | 2014-01-29 13:12 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27.5503 | [15 empty] | T
Project-A09 |  | 0.55745 | 1.5037 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-30 21:35 |  | 0 | 2014-03-31 21:35 | 2014-05-28 02:11 |  | 0 | 2014-05-29 02:11 | 2014-06-19 04:29 |  | 0 | 2014-06-20 04:29 | 2014-07-11 06:47 |  | 0 | 2014-07-12 06:47 | 2014-08-02 09:05 |  | 0 | 2014-08-03 09:05 | 2014-08-24 11:23 |  | v003 |  | 0.083747 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 234.4745 | [15 empty] | H
Project-A10 |  | 0.54354 | 2.3698 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-03-09 05:35 |  | 0 | 2015-03-10 05:35 | 2015-04-15 22:39 |  | 0 | 2015-04-16 22:39 | 2015-05-02 20:09 |  | 0 | 2015-05-03 20:09 | 2015-05-19 17:39 |  | 0 | 2015-05-20 17:39 | 2015-06-05 15:09 |  | 0 | 2015-06-06 15:09 | 2015-06-22 12:38 |  | v001 |  | 0.076303 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 417.7574 |  | 171.5267 | [15 empty] | I
Project-A11 |  | 0.25323 | 1.5299 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-09-07 18:55 |  | 0 | 2015-09-08 18:55 | 2015-11-07 11:56 |  | 0 | 2015-11-08 11:56 | 2016-01-07 04:57 |  | 0 | 2016-01-08 04:57 | 2016-03-07 21:58 |  | 0 | 2016-03-08 21:58 | 2016-05-07 14:59 |  | 0 | 2016-05-08 14:59 | 2016-07-07 08:00 |  | v002 |  | 0.08871 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 485.6855 |  | 552.3335 | [15 empty] | S
Project-A12 |  | 0.54908 | 1.5 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-06-14 09:07 |  | 0 | 2014-06-15 09:07 | 2014-08-15 01:05 |  | 0 | 2014-08-16 01:05 | 2014-09-13 10:57 |  | 0 | 2014-09-14 10:57 | 2014-10-12 20:49 |  | 0 | 2014-10-13 20:49 | 2014-11-11 06:41 |  | 0 | 2014-11-12 06:41 | 2014-12-10 16:33 |  | v004 |  | 0.096774 |  | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 65.3226 |  | 297.6897
Project-A13 |  | 0.57037 | 2.0041 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-08-14 07:27 |  | 0 | 2014-08-15 07:27 | 2014-09-24 16:55 |  | 0 | 2014-09-25 16:55 | 2014-11-05 02:23 |  | 0 | 2014-11-06 02:23 | 2014-12-16 11:51 |  | 0 | 2014-12-17 11:51 | 2015-01-26 21:19 |  | 0 | 2015-01-27 21:19 | 2015-03-09 06:48 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 375.283 | [15 empty] | W
Project-A14 |  | 0.49831 | 1.9676 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-27 06:21 |  | 0 | 2014-05-28 06:21 | 2014-06-24 04:48 |  | 0 | 2014-06-25 04:48 | 2014-07-13 23:36 |  | 1 | 2014-07-15 23:36 | 2014-08-03 18:24 |  | 0 | 2014-08-04 18:24 | 2014-08-23 13:13 |  | 0 | 2014-08-24 13:13 | 2014-09-12 08:01 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 1 | 0 | 0 | 68 | 57.3573 |  | 186.3338 | [15 empty] | O
Project-A15 |  | 1.0083 | 1.9805 |  |  |  | 2014-01-01 |  | 80 | 2014-03-23 | 2014-06-02 09:47 |  | 0 | 2014-06-03 09:47 | 2014-07-23 09:28 |  | 0 | 2014-07-24 09:28 | 2014-08-10 12:46 |  | 0 | 2014-08-11 12:46 | 2014-08-28 16:05 |  | 0 | 2014-08-29 16:05 | 2014-09-15 19:23 |  | 0 | 2014-09-16 19:23 | 2014-10-03 22:42 |  | v008 |  | 0.10608 |  | 80 | 0 | 0 | 0 | 0 | 0 | 80 | 127.2953 |  | 194.9456 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.5759 | [5 empty] | 97.5333 |  |  |  | 0 |  |  |  | 0 |  |  |  | 24.4 |  |  |  | 24.6 |  |  |  | 0 | [5 empty] | 0.066667 |  | 97.5333 | 0 | 0 | 24.4 | 24.6 | 0 | 146.5333 | 110.7674 | Average | 307.4642 | [15 empty] | H
Total |  | 8 | 23.6391 | [5 empty] | 1463 |  |  |  | 0 |  |  |  | 0 |  |  |  | 366 |  |  |  | 369 |  |  |  | 0 | [5 empty] | 1 |  | 1463 | 0 | 0 | 366 | 369 | 0 | 2198 | 1661.5105 | Total | 4611.9633 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 3
| Days: | 27.8772
E
N
SIT - Violation | Count: | 2 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 26.9266
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-25 02:52 | 2014-04-05 23:14 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-09 15:55 | 2014-04-22 13:27 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-22 15:16 | 2014-03-02 05:27 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-06 06:04 | 2014-05-22 18:05 | v004 | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 6.005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2015-03-10 20:02 | 2015-03-23 13:51 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-05-16 17:58 | 2014-06-10 13:27 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-12-17 06:50 | 2016-03-05 23:09 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 1; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 20.9216 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-19 02:05 | 2014-01-20 22:52 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-05-29 02:11 | 2014-06-19 04:29 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2015-04-16 22:39 | 2015-05-02 20:09 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2015-11-08 11:56 | 2016-01-07 04:57 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-16 01:05 | 2014-09-13 10:57 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-09-25 16:55 | 2014-11-05 02:23 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-25 04:48 | 2014-07-13 23:36 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-24 09:28 | 2014-08-10 12:46 | v008 | [31 empty] | T
UAT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0.95068
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-04-06 23:14 | 2015-04-18 19:36 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-23 13:27 | 2014-05-06 10:59 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-03 05:27 | 2014-03-10 19:39 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-23 18:05 | 2014-06-09 06:06 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-03-24 13:51 | 2015-04-06 07:39 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-06-11 13:27 | 2014-07-06 08:55 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-03-06 23:09 | 2016-05-25 15:28 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 1; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0.95068 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-21 22:52 | 2014-01-23 19:38 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-06-20 04:29 | 2014-07-11 06:47 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-05-03 20:09 | 2015-05-19 17:39 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2016-01-08 04:57 | 2016-03-07 21:58 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-14 10:57 | 2014-10-12 20:49 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-11-06 02:23 | 2014-12-16 11:51 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-15 23:36 | 2014-08-03 18:24 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-11 12:46 | 2014-08-28 16:05 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-04-23 19:36 | 2015-05-05 15:58 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-07 10:59 | 2014-05-20 08:31 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-11 19:39 | 2014-03-19 09:50 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-10 06:06 | 2014-06-26 18:07 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-04-07 07:39 | 2015-04-20 01:28 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-07-07 08:55 | 2015-08-01 04:24 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-05-26 15:28 | 2016-08-14 07:47 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-24 19:38 | 2014-01-26 16:25 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-12 06:47 | 2014-08-02 09:05 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-05-20 17:39 | 2015-06-05 15:09 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2016-03-08 21:58 | 2016-05-07 14:59 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-13 20:49 | 2014-11-11 06:41 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-17 11:51 | 2015-01-26 21:19 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-04 18:24 | 2014-08-23 13:13 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-29 16:05 | 2014-09-15 19:23 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-05-06 15:58 | 2015-05-18 12:20 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-21 08:31 | 2014-06-03 06:04 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-20 09:50 | 2014-03-28 00:02 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-27 18:07 | 2014-07-14 06:07 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-04-21 01:28 | 2015-05-03 19:17 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-08-02 04:24 | 2015-08-26 23:53 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-08-15 07:47 | 2016-11-03 00:07 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-27 16:25 | 2014-01-29 13:12 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-03 09:05 | 2014-08-24 11:23 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-06-06 15:09 | 2015-06-22 12:38 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2016-05-08 14:59 | 2016-07-07 08:00 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-12 06:41 | 2014-12-10 16:33 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-27 21:19 | 2015-03-09 06:48 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-24 13:13 | 2014-09-12 08:01 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-16 19:23 | 2014-10-03 22:42 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.30872 | 30.8718 | 30
0.69082 | 69.0819 | 69
0.47018 | 47.0181 | 47
0.75057 | 75.0572 | 75
0.62312 | 62.3119 | 62
0.054045 | 5.4045 | 5
0.46719 | 46.7191 | 46
0.83251 | 83.2514 | 83
0.2237 | 22.3703 | 22
0.60972 | 60.972 | 60
0.58017 | 58.0168 | 58
0.36606 | 36.6063 | 36
0.90088 | 90.0883 | 90
0.32933 | 32.9332 | 32
0.46649 | 46.6489 | 46
0.59634 | 59.6335 | 59
0.042952 | 4.2952 | 4
0.71794 | 71.7938 | 71
0.68243 | 68.2434 | 68
0.83755 | 83.7555 | 83
0.72435 | 72.4351 | 72
0.24293 | 24.2928 | 24
0.17218 | 17.2176 | 17
0.0012319 | 0.12319 | 0
0.48211 | 48.2108 | 48
0.73286 | 73.2863 | 73
0.74013 | 74.0132 | 74
0.11557 | 11.5566 | 11
0.93709 | 93.7088 | 93
0.93468 | 93.468 | 93
0.8698 | 86.98 | 86
0.16478 | 16.4782 | 16
0.19353 | 19.3533 | 19
0.31299 | 31.2986 | 31
0.10695 | 10.6948 | 10
0.45543 | 45.5428 | 45
0.64243 | 64.2429 | 64
0.25069 | 25.0694 | 25
0.54556 | 54.5559 | 54

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 2848.0987 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.9 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 23.6391 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH