## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.60311 | 1.7951 |  |  |  | 17 | 17.76 | 34.76 | 28.1873 |  | 4.08 | 74 | 78.08 | 41.224 |  | 4.08 | 17.76 | 21.84 | 9.8938 |  | 4.08 | 17.76 | 21.84 | 9.8938 |  | 4.08 | 17.76 | 21.84 | 9.8938 |  | 4.08 | 17.76 | 21.84 | 9.8938 |  | 200.2 | 108.9864 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 62.012 | 90.6929 | 90.6929
Project-A02 |  | v002 |  | 0.50235 | 2.4325 |  |  |  | 15 | 19.2 | 34.2 | 29.8594 |  | 3.6 | 80 | 83.6 | 32.8883 |  | 3.6 | 19.2 | 22.8 | 7.8932 |  | 3.6 | 19.2 | 22.8 | 7.8932 |  | 3.6 | 19.2 | 22.8 | 7.8932 |  | 3.6 | 19.2 | 22.8 | 7.8932 |  | 209 | 94.3206 | 104500 |  | 0.058933 |  | 33 | 176 |  | 65.6908 | 72.3543 | 72.3543 | [12 empty] | E
Project-A03 |  | v003 |  | 0.52572 | 4.2153 |  |  |  | 16 | 6.48 | 22.48 | 30.4347 |  | 3.84 | 27 | 30.84 | 7.3043 |  | 3.84 | 6.48 | 10.32 | 7.3043 |  | 3.84 | 6.48 | 10.32 | 7.3043 |  | 3.84 | 6.48 | 10.32 | 7.3043 |  | 3.84 | 6.48 | 10.32 | 7.3043 |  | 94.6 | 66.9562 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 66.9562 | 14.0916 | 66.9562 | [12 empty] | N
Project-A04 |  | v004 |  | 0.32548 | 1.5452 |  |  |  | 35 | 4.32 | 39.32 | 107.5324 |  | 8.4 | 18 | 26.4 | 25.8078 |  | 8.4 | 4.32 | 12.72 | 25.8078 |  | 8.4 | 4.32 | 12.72 | 25.8078 |  | 8.4 | 4.32 | 12.72 | 25.8078 |  | 8.4 | 4.32 | 12.72 | 25.8078 |  | 116.6 | 236.5713 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 236.5713 | 25.6274 | 236.5713 | [12 empty] | D
Project-A05 |  | v002 |  | 0.30445 | 0.41202 |  |  |  | 6 | 19.2 | 25.2 | 46.5999 |  | 1.44 | 80 | 81.44 | 194.1662 |  | 1.44 | 19.2 | 20.64 | 46.5999 |  | 1.44 | 19.2 | 20.64 | 46.5999 |  | 1.44 | 19.2 | 20.64 | 46.5999 |  | 1.44 | 19.2 | 20.64 | 46.5999 |  | 189.2 | 427.1657 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 43.3567 | 427.1657 | 427.1657
Project-A06 |  | v003 |  | 0.87165 | 0.25281 |  |  |  | 52 | 10.56 | 62.56 | 59.6567 |  | 12.48 | 44 | 56.48 | 174.0432 |  | 12.48 | 10.56 | 23.04 | 41.7704 |  | 12.48 | 10.56 | 23.04 | 41.7704 |  | 12.48 | 10.56 | 23.04 | 41.7704 |  | 12.48 | 10.56 | 23.04 | 41.7704 |  | 211.2 | 400.7813 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 131.2447 | 382.895 | 382.895 | [12 empty] | O
Project-A07 |  | v005 |  | 0.57058 | 1.4925 |  |  |  | 93 | 19.92 | 112.92 | 162.9911 |  | 22.32 | 83 | 105.32 | 55.6115 |  | 22.32 | 19.92 | 42.24 | 39.1179 |  | 22.32 | 19.92 | 42.24 | 39.1179 |  | 22.32 | 19.92 | 42.24 | 39.1179 |  | 22.32 | 19.92 | 42.24 | 39.1179 |  | 387.2 | 375.0741 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 358.5805 | 122.3452 | 358.5805 | [12 empty] | F
Project-A08 |  | v006 |  | 0.2985 | 0.25746 |  |  |  | 5 | 2.64 | 7.64 | 16.7507 |  | 1.2 | 11 | 12.2 | 42.7249 |  | 1.2 | 2.64 | 3.84 | 10.254 |  | 1.2 | 2.64 | 3.84 | 10.254 |  | 1.2 | 2.64 | 3.84 | 10.254 |  | 1.2 | 2.64 | 3.84 | 10.254 |  | 35.2 | 100.4914 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 36.8515 | 93.9947 | 93.9947
Project-A09 |  | v003 |  | 0.50435 | 1.5028 |  |  |  | 49 | 20.64 | 69.64 | 97.1553 |  | 11.76 | 86 | 97.76 | 57.2279 |  | 11.76 | 20.64 | 32.4 | 23.3173 |  | 11.76 | 20.64 | 32.4 | 23.3173 |  | 11.76 | 20.64 | 32.4 | 23.3173 |  | 11.76 | 20.64 | 32.4 | 23.3173 |  | 297 | 247.6522 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 213.7416 | 125.9013 | 213.7416 | [12 empty] | T
Project-A10 |  | v001 |  | 0.52747 | 3.4532 |  |  |  | 36 | 20.88 | 56.88 | 68.2499 |  | 8.64 | 87 | 95.64 | 25.194 |  | 8.64 | 20.88 | 29.52 | 16.38 |  | 8.64 | 20.88 | 29.52 | 16.38 |  | 8.64 | 20.88 | 29.52 | 16.38 |  | 8.64 | 20.88 | 29.52 | 16.38 |  | 270.6 | 158.9638 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 150.1498 | 55.4268 | 150.1498 | [12 empty] | H
Project-A11 |  | v002 |  | 0.50191 | 1.5578 |  |  |  | 63 | 19.2 | 82.2 | 125.5214 |  | 15.12 | 80 | 95.12 | 51.3535 |  | 15.12 | 19.2 | 34.32 | 30.1251 |  | 15.12 | 19.2 | 34.32 | 30.1251 |  | 15.12 | 19.2 | 34.32 | 30.1251 |  | 15.12 | 19.2 | 34.32 | 30.1251 |  | 314.6 | 297.3755 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 276.1471 | 112.9777 | 276.1471 | [12 empty] | I
Project-A12 |  | v004 |  | 0.77592 | 1.4619 |  |  |  | 65 | 21.84 | 86.84 | 83.7711 |  | 15.6 | 91 | 106.6 | 62.249 |  | 15.6 | 21.84 | 37.44 | 20.1051 |  | 15.6 | 21.84 | 37.44 | 20.1051 |  | 15.6 | 21.84 | 37.44 | 20.1051 |  | 15.6 | 21.84 | 37.44 | 20.1051 |  | 343.2 | 226.4404 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 184.2965 | 136.9477 | 184.2965 | [12 empty] | S
Project-A13 |  | v007 |  | 0.3013 | 0.62976 |  |  |  | 96 | 9.6 | 105.6 | 318.6234 |  | 23.04 | 40 | 63.04 | 76.4696 |  | 23.04 | 9.6 | 32.64 | 76.4696 |  | 23.04 | 9.6 | 32.64 | 76.4696 |  | 23.04 | 9.6 | 32.64 | 76.4696 |  | 23.04 | 9.6 | 32.64 | 76.4696 |  | 299.2 | 700.9715 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 700.9715 | 139.7355 | 700.9715
Project-A14 |  | v006 |  | 0.73696 | 2.0532 |  |  |  | 39 | 12.72 | 51.72 | 52.92 |  | 9.36 | 53 | 62.36 | 25.8135 |  | 9.36 | 12.72 | 22.08 | 12.7008 |  | 9.36 | 12.72 | 22.08 | 12.7008 |  | 9.36 | 12.72 | 22.08 | 12.7008 |  | 9.36 | 12.72 | 22.08 | 12.7008 |  | 202.4 | 129.5368 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 116.4241 | 56.7897 | 116.4241 | [12 empty] | W
Project-A15 |  | v008 |  | 0.65025 | 0.93813 |  |  |  | 72 | 23.76 | 95.76 | 110.7274 |  | 17.28 | 99 | 116.28 | 105.5295 |  | 17.28 | 23.76 | 41.04 | 26.5746 |  | 17.28 | 23.76 | 41.04 | 26.5746 |  | 17.28 | 23.76 | 41.04 | 26.5746 |  | 17.28 | 23.76 | 41.04 | 26.5746 |  | 376.2 | 322.5551 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 243.6002 | 232.1648 | 243.6002 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 89.2654 |  | 10.544 | 63.5333 | 74.0773 | 65.1738 |  | 10.544 | 15.248 | 25.792 | 26.2876 |  | 10.544 | 15.248 | 25.792 | 26.2876 |  | 10.544 | 15.248 | 25.792 | 26.2876 |  | 10.544 | 15.248 | 25.792 | 26.2876 |  | 236.4267 | 259.5895 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 192.4396 | 139.274 | 240.9694 | [12 empty] | S
|  | Total |  | 8 | 23.9996 |  |  |  | 659 | 228.72 | 887.72 | 1338.9807 |  | 158.16 | 953 | 1111.16 | 977.6071 |  | 158.16 | 228.72 | 386.88 | 394.3136 |  | 158.16 | 228.72 | 386.88 | 394.3136 |  | 158.16 | 228.72 | 386.88 | 394.3136 |  | 158.16 | 228.72 | 386.88 | 394.3136 |  | 3546.4 | 3893.8422 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2886.5944 | 2089.1104 | 3614.5413 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 1012.9715 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 333.5895 |  | <- To shorten average individual project span |  |  |  | <----------> | 240.9694
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 196.6104 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 585.1811 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 2128.3525 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.60311 | 1.7951 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-01-30 04:30 |  | 0 | 2015-01-31 04:30 | 2015-03-13 09:52 |  | 0 | 2015-03-14 09:52 | 2015-03-24 07:19 |  | 0 | 2015-03-25 07:19 | 2015-04-04 04:46 |  | 365 | 2016-04-04 04:46 | 2016-04-14 02:13 |  | 0 | 2016-04-15 02:13 | 2016-04-24 23:40 |  | v001 |  | 0.056452 |  | 365 | 0 | 0 | 0 | 365 | 0 | 730 | 309.0726 |  | 478.9864 | 1012.9715 | [14 empty] | E
Project-A02 |  | 0.50235 | 2.4325 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-31 20:38 |  | 0 | 2014-02-01 20:38 | 2014-03-06 17:57 |  | 0 | 2014-03-07 17:57 | 2014-03-15 15:23 |  | 0 | 2014-03-16 15:23 | 2014-03-24 12:49 |  | 0 | 2014-03-25 12:49 | 2014-04-02 10:15 |  | 0 | 2014-04-03 10:15 | 2014-04-11 07:42 |  | v002 |  | 0.058933 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 99.3206 | [15 empty] | N
Project-A03 |  | 0.52572 | 4.2153 |  |  |  | 2014-01-01 |  | 362 | 2014-12-30 | 2015-01-29 10:26 |  | 0 | 2015-01-30 10:26 | 2015-02-06 17:44 |  | 0 | 2015-02-07 17:44 | 2015-02-15 01:02 |  | 0 | 2015-02-16 01:02 | 2015-02-23 08:21 |  | 0 | 2015-02-24 08:21 | 2015-03-03 15:39 |  | 0 | 2015-03-04 15:39 | 2015-03-11 22:57 |  | v003 |  | 0.026675 |  | 362 | 0 | 0 | 0 | 0 | 0 | 362 | 144.8449 |  | 71.9562 | [15 empty] | D
Project-A04 |  | 0.32548 | 1.5452 |  |  |  | 2014-01-01 |  | 316 | 2014-11-14 | 2015-03-01 12:47 |  | 0 | 2015-03-02 12:47 | 2015-03-28 08:10 |  | 0 | 2015-03-29 08:10 | 2015-04-24 03:33 |  | 15 | 2015-05-10 03:33 | 2015-06-04 22:56 |  | 0 | 2015-06-05 22:56 | 2015-07-01 18:19 |  | 0 | 2015-07-02 18:19 | 2015-07-28 13:43 |  | v004 |  | 0.032878 |  | 316 | 0 | 0 | 15 | 0 | 0 | 331 | 155.8437 |  | 256.5713
Project-A05 |  | 0.30445 | 0.41202 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-02-17 14:24 |  | 0 | 2015-02-18 14:24 | 2015-08-31 18:23 |  | 0 | 2015-09-01 18:23 | 2015-10-18 08:47 |  | 0 | 2015-10-19 08:47 | 2015-12-04 23:11 |  | 0 | 2015-12-05 23:11 | 2016-01-21 13:35 |  | 0 | 2016-01-22 13:35 | 2016-03-09 03:59 |  | v002 |  | 0.05335 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 292.0906 |  | 432.1657 | [15 empty] | O
Project-A06 |  | 0.87165 | 0.25281 |  |  |  | 2014-01-01 |  | 75 | 2014-03-18 | 2014-05-16 15:46 |  | 0 | 2014-05-17 15:46 | 2014-11-07 16:48 |  | 0 | 2014-11-08 16:48 | 2014-12-20 11:17 |  | 0 | 2014-12-21 11:17 | 2015-02-01 05:46 |  | 0 | 2015-02-02 05:46 | 2015-03-16 00:16 |  | 0 | 2015-03-17 00:16 | 2015-04-27 18:45 |  | v003 |  | 0.059553 |  | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 66.9975 |  | 405.7813 | [15 empty] | F
Project-A07 |  | 0.57058 | 1.4925 |  |  |  | 2014-01-01 |  | 11 | 2014-01-13 | 2014-06-24 23:47 |  | 0 | 2014-06-25 23:47 | 2014-08-20 14:28 |  | 0 | 2014-08-21 14:28 | 2014-09-29 17:17 |  | 0 | 2014-09-30 17:17 | 2014-11-08 20:07 |  | 0 | 2014-11-09 20:07 | 2014-12-18 22:57 |  | 0 | 2014-12-19 22:57 | 2015-01-28 01:47 |  | v005 |  | 0.10918 |  | 11 | 0 | 0 | 0 | 0 | 0 | 11 | 18.0149 |  | 380.0741
Project-A08 |  | 0.2985 | 0.25746 |  |  |  | 2014-01-01 |  | 79 | 2014-03-22 | 2014-04-07 18:01 |  | 0 | 2014-04-08 18:01 | 2014-05-21 11:25 |  | 0 | 2014-05-22 11:25 | 2014-06-01 17:31 |  | 0 | 2014-06-02 17:31 | 2014-06-12 23:36 |  | 0 | 2014-06-13 23:36 | 2014-06-24 05:42 |  | 32 | 2014-07-27 05:42 | 2014-08-06 11:48 |  | v006 |  | 0.0099256 |  | 79 | 0 | 0 | 0 | 0 | 32 | 111 | 11.7618 |  | 137.4914 | [15 empty] | T
Project-A09 |  | 0.50435 | 1.5028 |  |  |  | 2014-01-01 |  | 362 | 2014-12-30 | 2015-04-06 03:44 |  | 0 | 2015-04-07 03:44 | 2015-06-03 09:12 |  | 0 | 2015-06-04 09:12 | 2015-06-27 16:49 |  | 0 | 2015-06-28 16:49 | 2015-07-22 00:25 |  | 0 | 2015-07-23 00:25 | 2015-08-15 08:02 |  | 0 | 2015-08-16 08:02 | 2015-09-08 15:39 |  | v003 |  | 0.083747 |  | 362 | 0 | 0 | 0 | 0 | 0 | 362 | 454.7457 |  | 252.6522 | [15 empty] | H
Project-A10 |  | 0.52747 | 3.4532 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-11 06:00 |  | 0 | 2014-03-12 06:00 | 2014-04-06 10:39 |  | 0 | 2014-04-07 10:39 | 2014-04-23 19:46 |  | 0 | 2014-04-24 19:46 | 2014-05-11 04:54 |  | 0 | 2014-05-12 04:54 | 2014-05-28 14:01 |  | 0 | 2014-05-29 14:01 | 2014-06-14 23:08 |  | v001 |  | 0.076303 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 163.9638 | [15 empty] | I
Project-A11 |  | 0.50191 | 1.5578 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-05-07 12:31 |  | 0 | 2014-05-08 12:31 | 2014-06-28 21:00 |  | 0 | 2014-06-29 21:00 | 2014-07-30 |  | 0 | 2014-07-31 | 2014-08-30 03:00 |  | 295 | 2015-06-22 03:00 | 2015-07-22 06:00 |  | 297 | 2016-05-15 06:00 | 2016-06-14 09:01 |  | v002 |  | 0.08871 |  | 0 | 0 | 0 | 0 | 295 | 297 | 592 | 0 |  | 894.3755 | [15 empty] | S
Project-A12 |  | 0.77592 | 1.4619 |  |  |  | 2014-01-01 |  | 322 | 2014-11-20 | 2015-02-11 18:30 |  | 0 | 2015-02-12 18:30 | 2015-04-16 00:29 |  | 0 | 2015-04-17 00:29 | 2015-05-07 03:00 |  | 0 | 2015-05-08 03:00 | 2015-05-28 05:32 |  | 0 | 2015-05-29 05:32 | 2015-06-18 08:03 |  | 0 | 2015-06-19 08:03 | 2015-07-09 10:34 |  | v004 |  | 0.096774 |  | 322 | 0 | 0 | 0 | 0 | 0 | 322 | 467.4194 |  | 231.4404
Project-A13 |  | 0.3013 | 0.62976 |  |  |  | 2014-01-01 |  | 307 | 2014-11-05 | 2015-09-19 14:58 |  | 0 | 2015-09-20 14:58 | 2015-12-06 02:14 |  | 0 | 2015-12-07 02:14 | 2016-02-21 13:30 |  | 0 | 2016-02-22 13:30 | 2016-05-09 00:46 |  | 0 | 2016-05-10 00:46 | 2016-07-25 12:03 |  | 0 | 2016-07-26 12:03 | 2016-10-10 23:19 |  | v007 |  | 0.084367 |  | 307 | 0 | 0 | 0 | 0 | 0 | 307 | 388.5112 |  | 705.9715 | [15 empty] | W
Project-A14 |  | 0.73696 | 2.0532 |  |  |  | 2014-01-01 |  | 69 | 2014-03-12 | 2014-05-03 22:05 |  | 0 | 2014-05-04 22:05 | 2014-05-30 17:36 |  | 0 | 2014-05-31 17:36 | 2014-06-13 10:25 |  | 0 | 2014-06-14 10:25 | 2014-06-27 03:15 |  | 0 | 2014-06-28 03:15 | 2014-07-10 20:04 |  | 31 | 2014-08-11 20:04 | 2014-08-24 12:53 |  | v006 |  | 0.057072 |  | 69 | 0 | 0 | 0 | 0 | 31 | 100 | 59.0695 |  | 165.5368 | [15 empty] | O
Project-A15 |  | 0.65025 | 0.93813 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-04-22 17:27 |  | 0 | 2015-04-23 17:27 | 2015-08-07 06:10 |  | 0 | 2015-08-08 06:10 | 2015-09-03 19:57 |  | 0 | 2015-09-04 19:57 | 2015-10-01 09:45 |  | 0 | 2015-10-02 09:45 | 2015-10-28 23:32 |  | 0 | 2015-10-29 23:32 | 2015-11-25 13:19 |  | v008 |  | 0.10608 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 580.7847 |  | 327.5551 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 199.8667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 1 |  |  |  | 44 |  |  |  | 24 | [5 empty] | 0.066667 |  | 199.8667 | 0 | 0 | 1 | 44 | 24 | 268.8667 | 196.6104 | Average | 333.5895 | [15 empty] | H
Total |  | 8 | 23.9996 | [5 empty] | 2998 |  |  |  | 0 |  |  |  | 0 |  |  |  | 15 |  |  |  | 660 |  |  |  | 360 | [5 empty] | 1 |  | 2998 | 0 | 0 | 15 | 660 | 360 | 4033 | 2949.1563 | Total | 5003.8422 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 2
| Days: | 11.7036
E
N
SIT - Violation | Count: | 1 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 2.0653
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2015-03-14 09:52 | 2015-03-24 07:19 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-07 17:57 | 2014-03-15 15:23 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2015-02-07 17:44 | 2015-02-15 01:02 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2015-03-29 08:10 | 2015-04-24 03:33 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2015-09-01 18:23 | 2015-10-18 08:47 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.0653 | S
Project-A06 | 2014-11-08 16:48 | 2014-12-20 11:17 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2014-08-21 14:28 | 2014-09-29 17:17 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-05-22 11:25 | 2014-06-01 17:31 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2015-06-04 09:12 | 2015-06-27 16:49 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-04-07 10:39 | 2014-04-23 19:46 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-06-29 21:00 | 2014-07-30 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2015-04-17 00:29 | 2015-05-07 03:00 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2015-12-07 02:14 | 2016-02-21 13:30 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-05-31 17:36 | 2014-06-13 10:25 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2015-08-08 06:10 | 2015-09-03 19:57 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-03-25 07:19 | 2015-04-04 04:46 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-16 15:23 | 2014-03-24 12:49 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2015-02-16 01:02 | 2015-02-23 08:21 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2015-05-10 03:33 | 2015-06-04 22:56 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-10-19 08:47 | 2015-12-04 23:11 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-12-21 11:17 | 2015-02-01 05:46 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2014-09-30 17:17 | 2014-11-08 20:07 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-06-02 17:31 | 2014-06-12 23:36 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-06-28 16:49 | 2015-07-22 00:25 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-04-24 19:46 | 2014-05-11 04:54 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-07-31 | 2014-08-30 03:00 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2015-05-08 03:00 | 2015-05-28 05:32 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2016-02-22 13:30 | 2016-05-09 00:46 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-06-14 10:25 | 2014-06-27 03:15 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-09-04 19:57 | 2015-10-01 09:45 | v008
NFT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 9.6383
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-04-04 04:46 | 2016-04-14 02:13 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-25 12:49 | 2014-04-02 10:15 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2015-02-24 08:21 | 2015-03-03 15:39 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2015-06-05 22:56 | 2015-07-01 18:19 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 9.6383 | 0 | 0 | 0 | 0
Project-A05 | 2015-12-05 23:11 | 2016-01-21 13:35 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-02-02 05:46 | 2015-03-16 00:16 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2014-11-09 20:07 | 2014-12-18 22:57 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-06-13 23:36 | 2014-06-24 05:42 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-07-23 00:25 | 2015-08-15 08:02 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-05-12 04:54 | 2014-05-28 14:01 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-06-22 03:00 | 2015-07-22 06:00 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2015-05-29 05:32 | 2015-06-18 08:03 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2016-05-10 00:46 | 2016-07-25 12:03 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-06-28 03:15 | 2014-07-10 20:04 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-10-02 09:45 | 2015-10-28 23:32 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-04-15 02:13 | 2016-04-24 23:40 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-03 10:15 | 2014-04-11 07:42 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2015-03-04 15:39 | 2015-03-11 22:57 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2015-07-02 18:19 | 2015-07-28 13:43 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2016-01-22 13:35 | 2016-03-09 03:59 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-03-17 00:16 | 2015-04-27 18:45 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2014-12-19 22:57 | 2015-01-28 01:47 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-07-27 05:42 | 2014-08-06 11:48 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-08-16 08:02 | 2015-09-08 15:39 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-05-29 14:01 | 2014-06-14 23:08 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2016-05-15 06:00 | 2016-06-14 09:01 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2015-06-19 08:03 | 2015-07-09 10:34 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2016-07-26 12:03 | 2016-10-10 23:19 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-11 20:04 | 2014-08-24 12:53 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-10-29 23:32 | 2015-11-25 13:19 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.68528 | 68.5276 | 68
0.85127 | 85.1269 | 85
0.29909 | 29.9087 | 29
0.1834 | 18.3402 | 18
0.55467 | 55.4672 | 55
0.60728 | 60.7276 | 60
0.14015 | 14.0153 | 14
0.25507 | 25.5069 | 25
0.43303 | 43.3027 | 43
0.58743 | 58.7428 | 58
0.056315 | 5.6315 | 5
0.64674 | 64.6738 | 64
0.55315 | 55.3148 | 55
0.12008 | 12.0084 | 12
0.74724 | 74.7235 | 74
0.46843 | 46.8434 | 46
0.76756 | 76.7564 | 76
0.88399 | 88.3986 | 88
0.0068827 | 0.68827 | 0
0.034414 | 3.4414 | 3
0.9001 | 90.0098 | 90
0.44068 | 44.0675 | 44
0.87804 | 87.8041 | 87
0.014324 | 1.4324 | 1
0.68657 | 68.6569 | 68
0.93176 | 93.1757 | 93
0.52709 | 52.7086 | 52
0.54942 | 54.9422 | 54
0.17147 | 17.1473 | 17
0.32565 | 32.5647 | 32
0.38601 | 38.601 | 38
0.028035 | 2.8035 | 2
0.79268 | 79.2676 | 79
0.22404 | 22.4042 | 22
0.79702 | 79.7023 | 79
0.5484 | 54.8401 | 54
0.15494 | 15.4938 | 15
0.028316 | 2.8316 | 2
0.19897 | 19.897 | 19

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 2128.3525 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.9 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 23.9996 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH