## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.49975 | 0.25068 |  |  |  | 17 | 17.76 | 34.76 | 70.8479 |  | 4.08 | 74 | 78.08 | 295.1995 |  | 4.08 | 17.76 | 21.84 | 70.8479 |  | 4.08 | 17.76 | 21.84 | 70.8479 |  | 4.08 | 17.76 | 21.84 | 70.8479 |  | 4.08 | 17.76 | 21.84 | 70.8479 |  | 200.2 | 649.439 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 74.8381 | 649.439 | 649.439
Project-A02 |  | v002 |  | 0.4997 | 3.251 |  |  |  | 15 | 19.2 | 34.2 | 30.0178 |  | 3.6 | 80 | 83.6 | 24.6077 |  | 3.6 | 19.2 | 22.8 | 7.2043 |  | 3.6 | 19.2 | 22.8 | 7.2043 |  | 3.6 | 19.2 | 22.8 | 7.2043 |  | 3.6 | 19.2 | 22.8 | 7.2043 |  | 209 | 83.4427 | 104500 |  | 0.058933 |  | 33 | 176 |  | 66.0393 | 54.137 | 66.0393 | [12 empty] | E
Project-A03 |  | v003 |  | 0.49985 | 3.0304 |  |  |  | 16 | 6.48 | 22.48 | 32.0095 |  | 3.84 | 27 | 30.84 | 8.9097 |  | 3.84 | 6.48 | 10.32 | 7.6823 |  | 3.84 | 6.48 | 10.32 | 7.6823 |  | 3.84 | 6.48 | 10.32 | 7.6823 |  | 3.84 | 6.48 | 10.32 | 7.6823 |  | 94.6 | 71.6484 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 70.421 | 19.6013 | 70.421 | [12 empty] | N
Project-A04 |  | v004 |  | 0.50093 | 1.499 |  |  |  | 35 | 4.32 | 39.32 | 69.8698 |  | 8.4 | 18 | 26.4 | 16.7688 |  | 8.4 | 4.32 | 12.72 | 16.7688 |  | 8.4 | 4.32 | 12.72 | 16.7688 |  | 8.4 | 4.32 | 12.72 | 16.7688 |  | 8.4 | 4.32 | 12.72 | 16.7688 |  | 116.6 | 153.7136 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 153.7136 | 26.4169 | 153.7136 | [12 empty] | D
Project-A05 |  | v002 |  | 0.49971 | 1.924 |  |  |  | 6 | 19.2 | 25.2 | 12.007 |  | 1.44 | 80 | 81.44 | 41.5798 |  | 1.44 | 19.2 | 20.64 | 9.9792 |  | 1.44 | 19.2 | 20.64 | 9.9792 |  | 1.44 | 19.2 | 20.64 | 9.9792 |  | 1.44 | 19.2 | 20.64 | 9.9792 |  | 189.2 | 93.5034 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 26.4153 | 91.4756 | 91.4756
Project-A06 |  | v003 |  | 0.49973 | 1.5006 |  |  |  | 52 | 10.56 | 62.56 | 104.0553 |  | 12.48 | 44 | 56.48 | 29.3212 |  | 12.48 | 10.56 | 23.04 | 24.9733 |  | 12.48 | 10.56 | 23.04 | 24.9733 |  | 12.48 | 10.56 | 23.04 | 24.9733 |  | 12.48 | 10.56 | 23.04 | 24.9733 |  | 211.2 | 233.2695 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 228.9216 | 64.5065 | 228.9216 | [12 empty] | O
Project-A07 |  | v005 |  | 0.50007 | 0.25137 |  |  |  | 93 | 19.92 | 112.92 | 185.9752 |  | 22.32 | 83 | 105.32 | 330.1962 |  | 22.32 | 19.92 | 42.24 | 79.2471 |  | 22.32 | 19.92 | 42.24 | 79.2471 |  | 22.32 | 19.92 | 42.24 | 79.2471 |  | 22.32 | 19.92 | 42.24 | 79.2471 |  | 387.2 | 833.1597 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 409.1455 | 726.4315 | 726.4315 | [12 empty] | F
Project-A08 |  | v006 |  | 0.50036 | 1.5284 |  |  |  | 5 | 2.64 | 7.64 | 9.9927 |  | 1.2 | 11 | 12.2 | 7.1973 |  | 1.2 | 2.64 | 3.84 | 2.3983 |  | 1.2 | 2.64 | 3.84 | 2.3983 |  | 1.2 | 2.64 | 3.84 | 2.3983 |  | 1.2 | 2.64 | 3.84 | 2.3983 |  | 35.2 | 26.783 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 21.984 | 15.834 | 21.984
Project-A09 |  | v003 |  | 0.49973 | 0.25076 |  |  |  | 49 | 20.64 | 69.64 | 98.053 |  | 11.76 | 86 | 97.76 | 342.9553 |  | 11.76 | 20.64 | 32.4 | 82.3093 |  | 11.76 | 20.64 | 32.4 | 82.3093 |  | 11.76 | 20.64 | 32.4 | 82.3093 |  | 11.76 | 20.64 | 32.4 | 82.3093 |  | 297 | 770.2454 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 215.7166 | 754.5017 | 754.5017 | [12 empty] | T
Project-A10 |  | v001 |  | 0.49982 | 1.5001 |  |  |  | 36 | 20.88 | 56.88 | 72.0263 |  | 8.64 | 87 | 95.64 | 57.9954 |  | 8.64 | 20.88 | 29.52 | 17.2863 |  | 8.64 | 20.88 | 29.52 | 17.2863 |  | 8.64 | 20.88 | 29.52 | 17.2863 |  | 8.64 | 20.88 | 29.52 | 17.2863 |  | 270.6 | 199.1669 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 158.4578 | 127.5898 | 158.4578 | [12 empty] | H
Project-A11 |  | v002 |  | 0.50099 | 1.5143 |  |  |  | 63 | 19.2 | 82.2 | 125.7499 |  | 15.12 | 80 | 95.12 | 52.8285 |  | 15.12 | 19.2 | 34.32 | 30.18 |  | 15.12 | 19.2 | 34.32 | 30.18 |  | 15.12 | 19.2 | 34.32 | 30.18 |  | 15.12 | 19.2 | 34.32 | 30.18 |  | 314.6 | 299.2984 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 276.6499 | 116.2227 | 276.6499 | [12 empty] | I
Project-A12 |  | v004 |  | 0.4998 | 1.4995 |  |  |  | 65 | 21.84 | 86.84 | 130.0514 |  | 15.6 | 91 | 106.6 | 60.6862 |  | 15.6 | 21.84 | 37.44 | 31.2123 |  | 15.6 | 21.84 | 37.44 | 31.2123 |  | 15.6 | 21.84 | 37.44 | 31.2123 |  | 15.6 | 21.84 | 37.44 | 31.2123 |  | 343.2 | 315.587 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 286.1131 | 133.5097 | 286.1131 | [12 empty] | S
Project-A13 |  | v007 |  | 0.49975 | 2.0004 |  |  |  | 96 | 9.6 | 105.6 | 192.0943 |  | 23.04 | 40 | 63.04 | 46.1026 |  | 23.04 | 9.6 | 32.64 | 46.1026 |  | 23.04 | 9.6 | 32.64 | 46.1026 |  | 23.04 | 9.6 | 32.64 | 46.1026 |  | 23.04 | 9.6 | 32.64 | 46.1026 |  | 299.2 | 422.6075 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 422.6075 | 43.9909 | 422.6075
Project-A14 |  | v006 |  | 0.49973 | 1.9996 |  |  |  | 39 | 12.72 | 51.72 | 78.0428 |  | 9.36 | 53 | 62.36 | 26.5052 |  | 9.36 | 12.72 | 22.08 | 18.7303 |  | 9.36 | 12.72 | 22.08 | 18.7303 |  | 9.36 | 12.72 | 22.08 | 18.7303 |  | 9.36 | 12.72 | 22.08 | 18.7303 |  | 202.4 | 179.4691 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 171.6942 | 58.3114 | 171.6942 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0001 | 1.9998 |  |  |  | 72 | 23.76 | 95.76 | 71.9949 |  | 17.28 | 99 | 116.28 | 49.5061 |  | 17.28 | 23.76 | 41.04 | 17.2788 |  | 17.28 | 23.76 | 41.04 | 17.2788 |  | 17.28 | 23.76 | 41.04 | 17.2788 |  | 17.28 | 23.76 | 41.04 | 17.2788 |  | 376.2 | 190.6161 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 158.3887 | 108.9135 | 158.3887 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 85.5192 |  | 10.544 | 63.5333 | 74.0773 | 92.6906 |  | 10.544 | 15.248 | 25.792 | 30.8134 |  | 10.544 | 15.248 | 25.792 | 30.8134 |  | 10.544 | 15.248 | 25.792 | 30.8134 |  | 10.544 | 15.248 | 25.792 | 30.8134 |  | 236.4267 | 301.4633 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 182.7404 | 199.3921 | 282.4559 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1282.788 |  | 158.16 | 953 | 1111.16 | 1390.3595 |  | 158.16 | 228.72 | 386.88 | 462.2006 |  | 158.16 | 228.72 | 386.88 | 462.2006 |  | 158.16 | 228.72 | 386.88 | 462.2006 |  | 158.16 | 228.72 | 386.88 | 462.2006 |  | 3546.4 | 4521.9497 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2741.1063 | 2990.8816 | 4236.8385 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 968.2695 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 379.5966 |  | <- To shorten average individual project span |  |  |  | <----------> | 282.4559
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 36.0937 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 1476.2777 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 2860.2375 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.49975 | 0.25068 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-13 20:21 |  | 0 | 2014-03-14 20:21 | 2015-01-04 01:08 |  | 0 | 2015-01-05 01:08 | 2015-03-16 21:29 |  | 0 | 2015-03-17 21:29 | 2015-05-27 17:50 |  | 0 | 2015-05-28 17:50 | 2015-08-07 14:11 |  | 0 | 2015-08-08 14:11 | 2015-10-18 10:32 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 654.439 | 968.2695 | [14 empty] | E
Project-A02 |  | 0.4997 | 3.251 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-02-13 00:26 |  | 0 | 2014-02-14 00:26 | 2014-03-10 15:01 |  | 0 | 2014-03-11 15:01 | 2014-03-18 19:55 |  | 0 | 2014-03-19 19:55 | 2014-03-27 00:49 |  | 0 | 2014-03-28 00:49 | 2014-04-04 05:43 |  | 0 | 2014-04-05 05:43 | 2014-04-12 10:38 |  | v002 |  | 0.058933 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 10.6079 |  | 88.4427 | [15 empty] | N
Project-A03 |  | 0.49985 | 3.0304 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-03 00:14 |  | 0 | 2014-02-04 00:14 | 2014-02-12 22:04 |  | 0 | 2014-02-13 22:04 | 2014-02-21 14:26 |  | 0 | 2014-02-22 14:26 | 2014-03-02 06:49 |  | 0 | 2014-03-03 06:49 | 2014-03-10 23:11 |  | 0 | 2014-03-11 23:11 | 2014-03-19 15:34 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 76.6484 | [15 empty] | D
Project-A04 |  | 0.50093 | 1.499 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-04-15 20:53 |  | 0 | 2014-04-16 20:53 | 2014-05-03 15:20 |  | 0 | 2014-05-04 15:20 | 2014-05-21 09:47 |  | 0 | 2014-05-22 09:47 | 2014-06-08 04:14 |  | 0 | 2014-06-09 04:14 | 2014-06-25 22:41 |  | 0 | 2014-06-26 22:41 | 2014-07-13 17:08 |  | v004 |  | 0.032878 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 16.768 |  | 158.7136
Project-A05 |  | 0.49971 | 1.924 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-14 00:10 |  | 0 | 2014-01-15 00:10 | 2014-02-25 14:05 |  | 0 | 2014-02-26 14:05 | 2014-03-08 13:35 |  | 0 | 2014-03-09 13:35 | 2014-03-19 13:05 |  | 0 | 2014-03-20 13:05 | 2014-03-30 12:35 |  | 0 | 2014-03-31 12:35 | 2014-04-10 12:05 |  | v002 |  | 0.05335 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 98.5034 | [15 empty] | O
Project-A06 |  | 0.49973 | 1.5006 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-04-16 01:20 |  | 0 | 2014-04-17 01:20 | 2014-05-16 09:02 |  | 0 | 2014-05-17 09:02 | 2014-06-11 08:24 |  | 365 | 2015-06-12 08:24 | 2015-07-07 07:45 |  | 365 | 2016-07-07 07:45 | 2016-08-01 07:07 |  | 0 | 2016-08-02 07:07 | 2016-08-27 06:28 |  | v003 |  | 0.059553 |  | 0 | 0 | 0 | 365 | 365 | 0 | 730 | 0 |  | 968.2695 | [15 empty] | F
Project-A07 |  | 0.50007 | 0.25137 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-09-11 23:24 |  | 0 | 2014-09-12 23:24 | 2015-08-09 04:07 |  | 0 | 2015-08-10 04:07 | 2015-10-28 10:03 |  | 0 | 2015-10-29 10:03 | 2016-01-16 15:58 |  | 0 | 2016-01-17 15:58 | 2016-04-05 21:54 |  | 0 | 2016-04-06 21:54 | 2016-06-25 03:50 |  | v005 |  | 0.10918 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 109.727 |  | 838.1597
Project-A08 |  | 0.50036 | 1.5284 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 23:50 |  | 0 | 2014-01-12 23:50 | 2014-01-20 04:34 |  | 0 | 2014-01-21 04:34 | 2014-01-23 14:07 |  | 0 | 2014-01-24 14:07 | 2014-01-26 23:41 |  | 0 | 2014-01-27 23:41 | 2014-01-30 09:14 |  | 1 | 2014-02-01 09:14 | 2014-02-03 18:48 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 |  | 32.783 | [15 empty] | T
Project-A09 |  | 0.49973 | 0.25076 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-04-22 01:16 |  | 0 | 2014-04-23 01:16 | 2015-04-01 00:12 |  | 0 | 2015-04-02 00:12 | 2015-06-23 07:37 |  | 0 | 2015-06-24 07:37 | 2015-09-14 15:03 |  | 0 | 2015-09-15 15:03 | 2015-12-06 22:28 |  | 0 | 2015-12-07 22:28 | 2016-02-28 05:53 |  | v003 |  | 0.083747 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 15.0744 |  | 775.2454 | [15 empty] | H
Project-A10 |  | 0.49982 | 1.5001 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-04-07 00:38 |  | 0 | 2014-04-08 00:38 | 2014-06-05 00:31 |  | 0 | 2014-06-06 00:31 | 2014-06-23 07:23 |  | 0 | 2014-06-24 07:23 | 2014-07-11 14:16 |  | 0 | 2014-07-12 14:16 | 2014-07-29 21:08 |  | 0 | 2014-07-30 21:08 | 2014-08-17 04:00 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 26.3244 |  | 204.1669 | [15 empty] | I
Project-A11 |  | 0.50099 | 1.5143 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-06-10 18:00 |  | 0 | 2014-06-11 18:00 | 2014-08-03 13:53 |  | 0 | 2014-08-04 13:53 | 2014-09-03 18:12 |  | 0 | 2014-09-04 18:12 | 2014-10-04 22:31 |  | 0 | 2014-10-05 22:31 | 2014-11-05 02:50 |  | 365 | 2015-11-06 02:50 | 2015-12-06 07:10 |  | v002 |  | 0.08871 |  | 34 | 0 | 0 | 0 | 0 | 365 | 399 | 45.2419 |  | 669.2984 | [15 empty] | S
Project-A12 |  | 0.4998 | 1.4995 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-06-26 01:14 |  | 0 | 2014-06-27 01:14 | 2014-08-26 17:42 |  | 0 | 2014-08-27 17:42 | 2014-09-27 22:48 |  | 1 | 2014-09-29 22:48 | 2014-10-31 03:54 |  | 0 | 2014-11-01 03:54 | 2014-12-02 09:00 |  | 0 | 2014-12-03 09:00 | 2015-01-03 14:05 |  | v004 |  | 0.096774 |  | 45 | 0 | 0 | 1 | 0 | 0 | 46 | 65.3226 |  | 321.587
Project-A13 |  | 0.49975 | 2.0004 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-09-07 02:16 |  | 0 | 2014-09-08 02:16 | 2014-10-24 04:44 |  | 0 | 2014-10-25 04:44 | 2014-12-10 07:11 |  | 0 | 2014-12-11 07:11 | 2015-01-26 09:39 |  | 0 | 2015-01-27 09:39 | 2015-03-14 12:07 |  | 0 | 2015-03-15 12:07 | 2015-04-30 14:35 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 427.6075 | [15 empty] | W
Project-A14 |  | 0.49973 | 1.9996 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-27 01:02 |  | 0 | 2014-05-28 01:02 | 2014-06-23 13:09 |  | 0 | 2014-06-24 13:09 | 2014-07-13 06:41 |  | 0 | 2014-07-14 06:41 | 2014-08-02 00:12 |  | 0 | 2014-08-03 00:12 | 2014-08-21 17:44 |  | 0 | 2014-08-22 17:44 | 2014-09-10 11:15 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 57.3573 |  | 184.4691 | [15 empty] | O
Project-A15 |  | 1.0001 | 1.9998 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-05-31 23:53 |  | 0 | 2014-06-01 23:53 | 2014-07-21 12:01 |  | 0 | 2014-07-22 12:01 | 2014-08-08 18:43 |  | 0 | 2014-08-09 18:43 | 2014-08-27 01:24 |  | 0 | 2014-08-28 01:24 | 2014-09-14 08:06 |  | 0 | 2014-09-15 08:06 | 2014-10-02 14:47 |  | v008 |  | 0.10608 |  | 78 | 0 | 0 | 0 | 0 | 0 | 78 | 124.1129 |  | 195.6161 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 28.5333 |  |  |  | 0 |  |  |  | 0 |  |  |  | 24.4 |  |  |  | 24.3333 |  |  |  | 24.4 | [5 empty] | 0.066667 |  | 28.5333 | 0 | 0 | 24.4 | 24.3333 | 24.4 | 101.6667 | 36.0937 | Average | 379.5966 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 428 |  |  |  | 0 |  |  |  | 0 |  |  |  | 366 |  |  |  | 365 |  |  |  | 366 | [5 empty] | 1 |  | 428 | 0 | 0 | 366 | 365 | 366 | 1525 | 541.4051 | Total | 5693.9497 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 6
| Days: | 29.5256
E
N
SIT - Violation | Count: | 4 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 20.5811
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2015-01-05 01:08 | 2015-03-16 21:29 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-11 15:01 | 2014-03-18 19:55 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-13 22:04 | 2014-02-21 14:26 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-04 15:20 | 2014-05-21 09:47 | v004 | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4.0309 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-02-26 14:05 | 2014-03-08 13:35 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-05-17 09:02 | 2014-06-11 08:24 | v003 | [7 empty] | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 5.3281 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-10 04:07 | 2015-10-28 10:03 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-21 04:34 | 2014-01-23 14:07 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2015-04-02 00:12 | 2015-06-23 07:37 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-06-06 00:31 | 2014-06-23 07:23 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-08-04 13:53 | 2014-09-03 18:12 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 1 | [11 empty] | 7.0208 | 0 | 0 | 4.2014 | S
Project-A12 | 2014-08-27 17:42 | 2014-09-27 22:48 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-25 04:44 | 2014-12-10 07:11 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-24 13:09 | 2014-07-13 06:41 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-22 12:01 | 2014-08-08 18:43 | v008 | [31 empty] | T
UAT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 4.9884
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-03-17 21:29 | 2015-05-27 17:50 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-19 19:55 | 2014-03-27 00:49 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-22 14:26 | 2014-03-02 06:49 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-22 09:47 | 2014-06-08 04:14 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-09 13:35 | 2014-03-19 13:05 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-06-12 08:24 | 2015-07-07 07:45 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-29 10:03 | 2016-01-16 15:58 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-24 14:07 | 2014-01-26 23:41 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-06-24 07:37 | 2015-09-14 15:03 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-24 07:23 | 2014-07-11 14:16 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-04 18:12 | 2014-10-04 22:31 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 4.9884 | 0 | 0 | 0
Project-A12 | 2014-09-29 22:48 | 2014-10-31 03:54 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-11 07:11 | 2015-01-26 09:39 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-14 06:41 | 2014-08-02 00:12 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-09 18:43 | 2014-08-27 01:24 | v008
NFT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 3.9561
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-05-28 17:50 | 2015-08-07 14:11 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-28 00:49 | 2014-04-04 05:43 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-03 06:49 | 2014-03-10 23:11 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-09 04:14 | 2014-06-25 22:41 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-20 13:05 | 2014-03-30 12:35 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2016-07-07 07:45 | 2016-08-01 07:07 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-01-17 15:58 | 2016-04-05 21:54 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-27 23:41 | 2014-01-30 09:14 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-09-15 15:03 | 2015-12-06 22:28 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-12 14:16 | 2014-07-29 21:08 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-05 22:31 | 2014-11-05 02:50 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 3.9561 | 0 | 0 | 0
Project-A12 | 2014-11-01 03:54 | 2014-12-02 09:00 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-27 09:39 | 2015-03-14 12:07 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-03 00:12 | 2014-08-21 17:44 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-28 01:24 | 2014-09-14 08:06 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-08-08 14:11 | 2015-10-18 10:32 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-05 05:43 | 2014-04-12 10:38 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-11 23:11 | 2014-03-19 15:34 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-26 22:41 | 2014-07-13 17:08 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-31 12:35 | 2014-04-10 12:05 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2016-08-02 07:07 | 2016-08-27 06:28 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-04-06 21:54 | 2016-06-25 03:50 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-02-01 09:14 | 2014-02-03 18:48 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-12-07 22:28 | 2016-02-28 05:53 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-30 21:08 | 2014-08-17 04:00 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-11-06 02:50 | 2015-12-06 07:10 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-03 09:00 | 2015-01-03 14:05 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-15 12:07 | 2015-04-30 14:35 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-22 17:44 | 2014-09-10 11:15 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-15 08:06 | 2014-10-02 14:47 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.77211 | 77.2112 | 77
0.48351 | 48.3509 | 48
0.78312 | 78.3122 | 78
0.1259 | 12.5904 | 12
0.55328 | 55.3277 | 55
0.15809 | 15.8089 | 15
0.42806 | 42.8055 | 42
0.031321 | 3.1321 | 3
0.59877 | 59.8773 | 59
0.99367 | 99.3666 | 99
0.84757 | 84.7568 | 84
0.23448 | 23.4475 | 23
0.93398 | 93.3975 | 93
0.94337 | 94.3373 | 94
0.65594 | 65.5936 | 65
0.58966 | 58.9656 | 58
0.80058 | 80.0582 | 80
0.33774 | 33.7743 | 33
0.35959 | 35.9592 | 35
0.10169 | 10.169 | 10
0.91574 | 91.5742 | 91
0.13203 | 13.2029 | 13
0.57465 | 57.4649 | 57
0.24962 | 24.9623 | 24
0.32889 | 32.8887 | 32
0.86862 | 86.8618 | 86
0.22041 | 22.0407 | 22
0.78298 | 78.2983 | 78
0.012836 | 1.2836 | 1
0.30355 | 30.3548 | 30
0.095888 | 9.5888 | 9
0.33197 | 33.1972 | 33
0.87914 | 87.9144 | 87
0.80625 | 80.6254 | 80
0.79853 | 79.8526 | 79
0.10488 | 10.4882 | 10
0.40114 | 40.1141 | 40
0.73801 | 73.8012 | 73
0.30424 | 30.4237 | 30

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 2860.2375 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.9 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH