## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.5262 | 0.27435 |  |  |  | 17 | 17.76 | 34.76 | 64.736 |  | 4.08 | 74 | 78.08 | 269.7333 |  | 4.08 | 17.76 | 21.84 | 64.736 |  | 4.08 | 17.76 | 21.84 | 64.736 |  | 4.08 | 17.76 | 21.84 | 64.736 |  | 4.08 | 17.76 | 21.84 | 64.736 |  | 200.2 | 593.4133 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 71.0752 | 593.4133 | 593.4133
Project-A02 |  | v002 |  | 0.51745 | 3.2595 |  |  |  | 15 | 19.2 | 34.2 | 28.9882 |  | 3.6 | 80 | 83.6 | 24.544 |  | 3.6 | 19.2 | 22.8 | 6.9572 |  | 3.6 | 19.2 | 22.8 | 6.9572 |  | 3.6 | 19.2 | 22.8 | 6.9572 |  | 3.6 | 19.2 | 22.8 | 6.9572 |  | 209 | 81.3609 | 104500 |  | 0.058933 |  | 33 | 176 |  | 63.7741 | 53.9968 | 63.7741 | [12 empty] | E
Project-A03 |  | v003 |  | 0.50977 | 2.5257 |  |  |  | 16 | 6.48 | 22.48 | 31.387 |  | 3.84 | 27 | 30.84 | 10.69 |  | 3.84 | 6.48 | 10.32 | 7.5329 |  | 3.84 | 6.48 | 10.32 | 7.5329 |  | 3.84 | 6.48 | 10.32 | 7.5329 |  | 3.84 | 6.48 | 10.32 | 7.5329 |  | 94.6 | 72.2085 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 69.0514 | 23.518 | 69.0514 | [12 empty] | N
Project-A04 |  | v004 |  | 0.51396 | 1.5113 |  |  |  | 35 | 4.32 | 39.32 | 68.0985 |  | 8.4 | 18 | 26.4 | 16.3436 |  | 8.4 | 4.32 | 12.72 | 16.3436 |  | 8.4 | 4.32 | 12.72 | 16.3436 |  | 8.4 | 4.32 | 12.72 | 16.3436 |  | 8.4 | 4.32 | 12.72 | 16.3436 |  | 116.6 | 149.8167 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 149.8167 | 26.2032 | 149.8167 | [12 empty] | D
Project-A05 |  | v002 |  | 0.5371 | 0.26155 |  |  |  | 6 | 19.2 | 25.2 | 73.408 |  | 1.44 | 80 | 81.44 | 305.8667 |  | 1.44 | 19.2 | 20.64 | 73.408 |  | 1.44 | 19.2 | 20.64 | 73.408 |  | 1.44 | 19.2 | 20.64 | 73.408 |  | 1.44 | 19.2 | 20.64 | 73.408 |  | 189.2 | 672.9068 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 24.5766 | 672.9068 | 672.9068
Project-A06 |  | v003 |  | 0.50631 | 1.5019 |  |  |  | 52 | 10.56 | 62.56 | 102.7038 |  | 12.48 | 44 | 56.48 | 29.2959 |  | 12.48 | 10.56 | 23.04 | 24.6489 |  | 12.48 | 10.56 | 23.04 | 24.6489 |  | 12.48 | 10.56 | 23.04 | 24.6489 |  | 12.48 | 10.56 | 23.04 | 24.6489 |  | 211.2 | 230.5953 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 225.9483 | 64.451 | 225.9483 | [12 empty] | O
Project-A07 |  | v005 |  | 0.5174 | 1.5075 |  |  |  | 93 | 19.92 | 112.92 | 179.7462 |  | 22.32 | 83 | 105.32 | 55.0595 |  | 22.32 | 19.92 | 42.24 | 43.1391 |  | 22.32 | 19.92 | 42.24 | 43.1391 |  | 22.32 | 19.92 | 42.24 | 43.1391 |  | 22.32 | 19.92 | 42.24 | 43.1391 |  | 387.2 | 407.3621 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 395.4417 | 121.1309 | 395.4417 | [12 empty] | F
Project-A08 |  | v006 |  | 0.52953 | 2.412 |  |  |  | 5 | 2.64 | 7.64 | 9.4423 |  | 1.2 | 11 | 12.2 | 4.5606 |  | 1.2 | 2.64 | 3.84 | 2.2662 |  | 1.2 | 2.64 | 3.84 | 2.2662 |  | 1.2 | 2.64 | 3.84 | 2.2662 |  | 1.2 | 2.64 | 3.84 | 2.2662 |  | 35.2 | 23.0675 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 20.7731 | 10.0333 | 20.7731
Project-A09 |  | v003 |  | 0.52619 | 1.5015 |  |  |  | 49 | 20.64 | 69.64 | 93.1231 |  | 11.76 | 86 | 97.76 | 57.2771 |  | 11.76 | 20.64 | 32.4 | 22.3495 |  | 11.76 | 20.64 | 32.4 | 22.3495 |  | 11.76 | 20.64 | 32.4 | 22.3495 |  | 11.76 | 20.64 | 32.4 | 22.3495 |  | 297 | 239.7984 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 204.8708 | 126.0097 | 204.8708 | [12 empty] | T
Project-A10 |  | v001 |  | 0.51843 | 1.5217 |  |  |  | 36 | 20.88 | 56.88 | 69.4407 |  | 8.64 | 87 | 95.64 | 57.1737 |  | 8.64 | 20.88 | 29.52 | 16.6658 |  | 8.64 | 20.88 | 29.52 | 16.6658 |  | 8.64 | 20.88 | 29.52 | 16.6658 |  | 8.64 | 20.88 | 29.52 | 16.6658 |  | 270.6 | 193.2775 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 152.7695 | 125.7822 | 152.7695 | [12 empty] | H
Project-A11 |  | v002 |  | 0.50876 | 0.25111 |  |  |  | 63 | 19.2 | 82.2 | 123.8305 |  | 15.12 | 80 | 95.12 | 318.5812 |  | 15.12 | 19.2 | 34.32 | 76.4595 |  | 15.12 | 19.2 | 34.32 | 76.4595 |  | 15.12 | 19.2 | 34.32 | 76.4595 |  | 15.12 | 19.2 | 34.32 | 76.4595 |  | 314.6 | 748.2497 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 272.4272 | 700.8787 | 700.8787 | [12 empty] | I
Project-A12 |  | v004 |  | 0.51366 | 1.4954 |  |  |  | 65 | 21.84 | 86.84 | 126.5416 |  | 15.6 | 91 | 106.6 | 60.852 |  | 15.6 | 21.84 | 37.44 | 30.37 |  | 15.6 | 21.84 | 37.44 | 30.37 |  | 15.6 | 21.84 | 37.44 | 30.37 |  | 15.6 | 21.84 | 37.44 | 30.37 |  | 343.2 | 308.8736 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 278.3916 | 133.8745 | 278.3916 | [12 empty] | S
Project-A13 |  | v007 |  | 0.51057 | 1.9847 |  |  |  | 96 | 9.6 | 105.6 | 188.024 |  | 23.04 | 40 | 63.04 | 45.1258 |  | 23.04 | 9.6 | 32.64 | 45.1258 |  | 23.04 | 9.6 | 32.64 | 45.1258 |  | 23.04 | 9.6 | 32.64 | 45.1258 |  | 23.04 | 9.6 | 32.64 | 45.1258 |  | 299.2 | 413.6528 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 413.6528 | 44.3392 | 413.6528
Project-A14 |  | v006 |  | 0.25032 | 2.0059 |  |  |  | 39 | 12.72 | 51.72 | 155.7987 |  | 9.36 | 53 | 62.36 | 37.3917 |  | 9.36 | 12.72 | 22.08 | 37.3917 |  | 9.36 | 12.72 | 22.08 | 37.3917 |  | 9.36 | 12.72 | 22.08 | 37.3917 |  | 9.36 | 12.72 | 22.08 | 37.3917 |  | 202.4 | 342.7572 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 342.7572 | 58.1287 | 342.7572 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0144 | 1.986 |  |  |  | 72 | 23.76 | 95.76 | 70.9814 |  | 17.28 | 99 | 116.28 | 49.8481 |  | 17.28 | 23.76 | 41.04 | 17.0355 |  | 17.28 | 23.76 | 41.04 | 17.0355 |  | 17.28 | 23.76 | 41.04 | 17.0355 |  | 17.28 | 23.76 | 41.04 | 17.0355 |  | 376.2 | 188.9715 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 156.159 | 109.6658 | 156.159 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 92.4167 |  | 10.544 | 63.5333 | 74.0773 | 89.4896 |  | 10.544 | 15.248 | 25.792 | 32.2953 |  | 10.544 | 15.248 | 25.792 | 32.2953 |  | 10.544 | 15.248 | 25.792 | 32.2953 |  | 10.544 | 15.248 | 25.792 | 32.2953 |  | 236.4267 | 311.0875 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 189.4323 | 190.9555 | 296.0403 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1386.2501 |  | 158.16 | 953 | 1111.16 | 1342.3433 |  | 158.16 | 228.72 | 386.88 | 484.4296 |  | 158.16 | 228.72 | 386.88 | 484.4296 |  | 158.16 | 228.72 | 386.88 | 484.4296 |  | 158.16 | 228.72 | 386.88 | 484.4296 |  | 3546.4 | 4666.3119 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2841.4852 | 2864.332 | 4440.6049 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 1450.9068 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 389.3541 |  | <- To shorten average individual project span |  |  |  | <----------> | 296.0403
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 71.5428 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 3107.793 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 5019.5967 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.5262 | 0.27435 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-07 17:40 |  | 0 | 2014-03-08 17:40 | 2014-12-03 11:16 |  | 0 | 2014-12-04 11:16 | 2015-02-07 04:56 |  | 0 | 2015-02-08 04:56 | 2015-04-13 22:35 |  | 0 | 2015-04-14 22:35 | 2015-06-18 16:15 |  | 0 | 2015-06-19 16:15 | 2015-08-23 09:55 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 598.4133 | 1450.9068 | [14 empty] | E
Project-A02 |  | 0.51745 | 3.2595 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-02-11 23:43 |  | 0 | 2014-02-12 23:43 | 2014-03-09 12:46 |  | 0 | 2014-03-10 12:46 | 2014-03-17 11:45 |  | 0 | 2014-03-18 11:45 | 2014-03-25 10:43 |  | 0 | 2014-03-26 10:43 | 2014-04-02 09:41 |  | 0 | 2014-04-03 09:41 | 2014-04-10 08:40 |  | v002 |  | 0.058933 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 10.6079 |  | 86.3609 | [15 empty] | N
Project-A03 |  | 0.50977 | 2.5257 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-02 09:17 |  | 0 | 2014-02-03 09:17 | 2014-02-14 01:51 |  | 0 | 2014-02-15 01:51 | 2014-02-22 14:38 |  | 0 | 2014-02-23 14:38 | 2014-03-03 03:26 |  | 0 | 2014-03-04 03:26 | 2014-03-11 16:13 |  | 0 | 2014-03-12 16:13 | 2014-03-20 05:00 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 77.2085 | [15 empty] | D
Project-A04 |  | 0.51396 | 1.5113 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-04-14 02:22 |  | 0 | 2014-04-15 02:22 | 2014-05-01 10:37 |  | 0 | 2014-05-02 10:37 | 2014-05-18 18:52 |  | 0 | 2014-05-19 18:52 | 2014-06-05 03:06 |  | 0 | 2014-06-06 03:06 | 2014-06-22 11:21 |  | 0 | 2014-06-23 11:21 | 2014-07-09 19:36 |  | v004 |  | 0.032878 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 16.768 |  | 154.8167
Project-A05 |  | 0.5371 | 0.26155 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-04-30 09:48 |  | 0 | 2014-05-01 09:48 | 2015-03-03 06:36 |  | 0 | 2015-03-04 06:36 | 2015-05-16 16:23 |  | 365 | 2016-05-16 16:23 | 2016-07-29 02:11 |  | 363 | 2017-07-28 02:11 | 2017-10-09 11:58 |  | 0 | 2017-10-10 11:58 | 2017-12-22 21:46 |  | v002 |  | 0.05335 |  | 45 | 0 | 0 | 365 | 363 | 0 | 773 | 36.0112 |  | 1405.9068 | [15 empty] | O
Project-A06 |  | 0.50631 | 1.5019 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-06-09 16:53 |  | 0 | 2014-06-10 16:53 | 2014-07-09 23:59 |  | 0 | 2014-07-10 23:59 | 2014-08-04 15:34 |  | 2 | 2014-08-07 15:34 | 2014-09-01 07:08 |  | 0 | 2014-09-02 07:08 | 2014-09-26 22:43 |  | 4 | 2014-10-01 22:43 | 2014-10-26 14:17 |  | v003 |  | 0.059553 |  | 56 | 0 | 0 | 2 | 0 | 4 | 62 | 50.0248 |  | 241.5953 | [15 empty] | F
Project-A07 |  | 0.5174 | 1.5075 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-06-30 17:55 |  | 0 | 2015-07-01 17:55 | 2015-08-25 19:20 |  | 0 | 2015-08-26 19:20 | 2015-10-08 22:41 |  | 365 | 2016-10-08 22:41 | 2016-11-21 02:01 |  | 0 | 2016-11-22 02:01 | 2017-01-04 05:21 |  | 0 | 2017-01-05 05:21 | 2017-02-17 08:41 |  | v005 |  | 0.10918 |  | 365 | 0 | 0 | 365 | 0 | 0 | 730 | 597.7667 |  | 777.3621
Project-A08 |  | 0.52953 | 2.412 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 10:37 |  | 0 | 2014-01-12 10:37 | 2014-01-17 00:04 |  | 0 | 2014-01-18 00:04 | 2014-01-20 06:27 |  | 0 | 2014-01-21 06:27 | 2014-01-23 12:51 |  | 0 | 2014-01-24 12:51 | 2014-01-26 19:14 |  | 0 | 2014-01-27 19:14 | 2014-01-30 01:37 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28.0675 | [15 empty] | T
Project-A09 |  | 0.52619 | 1.5015 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-04-17 02:57 |  | 0 | 2014-04-18 02:57 | 2014-06-14 09:36 |  | 0 | 2014-06-15 09:36 | 2014-07-07 18:00 |  | 0 | 2014-07-08 18:00 | 2014-07-31 02:23 |  | 0 | 2014-08-01 02:23 | 2014-08-23 10:46 |  | 0 | 2014-08-24 10:46 | 2014-09-15 19:10 |  | v003 |  | 0.083747 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 15.0744 |  | 244.7984 | [15 empty] | H
Project-A10 |  | 0.51843 | 1.5217 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-04-04 10:35 |  | 0 | 2014-04-05 10:35 | 2014-06-01 14:45 |  | 0 | 2014-06-02 14:45 | 2014-06-19 06:43 |  | 0 | 2014-06-20 06:43 | 2014-07-06 22:42 |  | 0 | 2014-07-07 22:42 | 2014-07-24 14:41 |  | 0 | 2014-07-25 14:41 | 2014-08-11 06:40 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 26.3244 |  | 198.2775 | [15 empty] | I
Project-A11 |  | 0.50876 | 0.25111 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-05-05 19:56 |  | 0 | 2014-05-06 19:56 | 2015-03-21 09:53 |  | 0 | 2015-03-22 09:53 | 2015-06-06 20:55 |  | 0 | 2015-06-07 20:55 | 2015-08-23 07:56 |  | 0 | 2015-08-24 07:56 | 2015-11-08 18:58 |  | 0 | 2015-11-09 18:58 | 2016-01-25 06:00 |  | v002 |  | 0.08871 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 753.2497 | [15 empty] | S
Project-A12 |  | 0.51366 | 1.4954 |  |  |  | 2014-01-01 |  | 47 | 2014-02-18 | 2014-06-24 13:00 |  | 0 | 2014-06-25 13:00 | 2014-08-25 09:27 |  | 0 | 2014-08-26 09:27 | 2014-09-25 18:20 |  | 0 | 2014-09-26 18:20 | 2014-10-27 03:12 |  | 0 | 2014-10-28 03:12 | 2014-11-27 12:05 |  | 0 | 2014-11-28 12:05 | 2014-12-28 20:58 |  | v004 |  | 0.096774 |  | 47 | 0 | 0 | 0 | 0 | 0 | 47 | 68.2258 |  | 313.8736
Project-A13 |  | 0.51057 | 1.9847 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-09-03 00:35 |  | 0 | 2014-09-04 00:35 | 2014-10-19 03:36 |  | 0 | 2014-10-20 03:36 | 2014-12-04 06:37 |  | 0 | 2014-12-05 06:37 | 2015-01-19 09:38 |  | 0 | 2015-01-20 09:38 | 2015-03-06 12:39 |  | 0 | 2015-03-07 12:39 | 2015-04-21 15:40 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 418.6528 | [15 empty] | W
Project-A14 |  | 0.25032 | 2.0059 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-08-12 19:10 |  | 0 | 2014-08-13 19:10 | 2014-09-20 04:34 |  | 0 | 2014-09-21 04:34 | 2014-10-28 13:58 |  | 0 | 2014-10-29 13:58 | 2014-12-05 23:22 |  | 0 | 2014-12-06 23:22 | 2015-01-13 08:46 |  | 0 | 2015-01-14 08:46 | 2015-02-20 18:10 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 57.3573 |  | 347.7572 | [15 empty] | O
Project-A15 |  | 1.0144 | 1.986 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-05-30 23:33 |  | 0 | 2014-05-31 23:33 | 2014-07-20 19:54 |  | 0 | 2014-07-21 19:54 | 2014-08-07 20:46 |  | 0 | 2014-08-08 20:46 | 2014-08-25 21:37 |  | 0 | 2014-08-26 21:37 | 2014-09-12 22:28 |  | 0 | 2014-09-13 22:28 | 2014-09-30 23:19 |  | v008 |  | 0.10608 |  | 78 | 0 | 0 | 0 | 0 | 0 | 78 | 124.1129 |  | 193.9715 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 53 |  |  |  | 0 |  |  |  | 0 |  |  |  | 48.8 |  |  |  | 24.2 |  |  |  | 0.26667 | [5 empty] | 0.066667 |  | 53 | 0 | 0 | 48.8 | 24.2 | 0.26667 | 126.2667 | 71.5428 | Average | 389.3541 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 795 |  |  |  | 0 |  |  |  | 0 |  |  |  | 732 |  |  |  | 363 |  |  |  | 4 | [5 empty] | 1 |  | 795 | 0 | 0 | 732 | 363 | 4 | 1894 | 1073.1421 | Total | 5840.3119 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 8
| Days: | 62.1559
E
N
SIT - Violation | Count: | 4 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 30.7047
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-12-04 11:16 | 2015-02-07 04:56 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-10 12:46 | 2014-03-17 11:45 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-15 01:51 | 2014-02-22 14:38 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-02 10:37 | 2014-05-18 18:52 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2015-03-04 06:36 | 2015-05-16 16:23 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-10 23:59 | 2014-08-04 15:34 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 13.8191
Project-A07 | 2015-08-26 19:20 | 2015-10-08 22:41 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-18 00:04 | 2014-01-20 06:27 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-15 09:36 | 2014-07-07 18:00 | v003 |  | Count P-A10: 1; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 3.88 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-06-02 14:45 | 2014-06-19 06:43 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2015-03-22 09:53 | 2015-06-06 20:55 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-26 09:27 | 2014-09-25 18:20 | v004 |  | Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [12 empty] | 0 | 4.5732 | 0 | H
Project-A13 | 2014-10-20 03:36 | 2014-12-04 06:37 | v007 |  | Count P-A14: 1; Count P-A15: 0 | [13 empty] | 8.4324 | 0 | E
Project-A14 | 2014-09-21 04:34 | 2014-10-28 13:58 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-21 19:54 | 2014-08-07 20:46 | v008 | [31 empty] | T
UAT - Violation | Count: | 2 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 18.9502
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-02-08 04:56 | 2015-04-13 22:35 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-18 11:45 | 2014-03-25 10:43 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-23 14:38 | 2014-03-03 03:26 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-19 18:52 | 2014-06-05 03:06 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2016-05-16 16:23 | 2016-07-29 02:11 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-07 15:34 | 2014-09-01 07:08 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.2519
Project-A07 | 2016-10-08 22:41 | 2016-11-21 02:01 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-21 06:27 | 2014-01-23 12:51 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-08 18:00 | 2014-07-31 02:23 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-20 06:43 | 2014-07-06 22:42 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-06-07 20:55 | 2015-08-23 07:56 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-26 18:20 | 2014-10-27 03:12 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-05 06:37 | 2015-01-19 09:38 | v007 |  | Count P-A14: 1; Count P-A15: 0 | [13 empty] | 0.6983 | 0
Project-A14 | 2014-10-29 13:58 | 2014-12-05 23:22 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-08 20:46 | 2014-08-25 21:37 | v008
NFT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 10.6386
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-04-14 22:35 | 2015-06-18 16:15 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-26 10:43 | 2014-04-02 09:41 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-04 03:26 | 2014-03-11 16:13 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-06 03:06 | 2014-06-22 11:21 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2017-07-28 02:11 | 2017-10-09 11:58 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-02 07:08 | 2014-09-26 22:43 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10.6386
Project-A07 | 2016-11-22 02:01 | 2017-01-04 05:21 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-24 12:51 | 2014-01-26 19:14 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-01 02:23 | 2014-08-23 10:46 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-07 22:42 | 2014-07-24 14:41 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-08-24 07:56 | 2015-11-08 18:58 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-28 03:12 | 2014-11-27 12:05 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-20 09:38 | 2015-03-06 12:39 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-12-06 23:22 | 2015-01-13 08:46 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-26 21:37 | 2014-09-12 22:28 | v008
Prod - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 1.8624
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-06-19 16:15 | 2015-08-23 09:55 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-03 09:41 | 2014-04-10 08:40 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-12 16:13 | 2014-03-20 05:00 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-23 11:21 | 2014-07-09 19:36 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2017-10-10 11:58 | 2017-12-22 21:46 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-10-01 22:43 | 2014-10-26 14:17 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2017-01-05 05:21 | 2017-02-17 08:41 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-27 19:14 | 2014-01-30 01:37 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-24 10:46 | 2014-09-15 19:10 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 1 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 1.8624
Project-A10 | 2014-07-25 14:41 | 2014-08-11 06:40 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-11-09 18:58 | 2016-01-25 06:00 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-28 12:05 | 2014-12-28 20:58 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-07 12:39 | 2015-04-21 15:40 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-01-14 08:46 | 2015-02-20 18:10 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-13 22:28 | 2014-09-30 23:19 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.075206 | 7.5206 | 7
0.98839 | 98.8391 | 98
0.19482 | 19.4825 | 19
0.27874 | 27.8744 | 27
0.18558 | 18.558 | 18
0.38568 | 38.5676 | 38
0.85501 | 85.5009 | 85
0.31221 | 31.2207 | 31
0.55183 | 55.1828 | 55
0.16015 | 16.0152 | 16
0.012587 | 1.2587 | 1
0.59467 | 59.467 | 59
0.38726 | 38.7257 | 38
0.96927 | 96.9269 | 96
0.90279 | 90.2788 | 90
0.99564 | 99.5637 | 99
0.27829 | 27.8287 | 27
0.45044 | 45.0441 | 45
0.44486 | 44.4862 | 44
0.12474 | 12.4741 | 12
0.12876 | 12.8764 | 12
0.36404 | 36.4043 | 36
0.73608 | 73.6083 | 73
0.10562 | 10.5617 | 10
0.89994 | 89.9937 | 89
0.57811 | 57.8109 | 57
0.38747 | 38.7474 | 38
0.34909 | 34.9087 | 34
0.53879 | 53.8785 | 53
0.39266 | 39.2661 | 39
0.12739 | 12.7386 | 12
0.033963 | 3.3963 | 3
0.77914 | 77.9139 | 77
0.70468 | 70.4681 | 70
0.67232 | 67.2321 | 67
0.56373 | 56.3725 | 56
0.95442 | 95.4415 | 95
0.63761 | 63.7612 | 63
0.29023 | 29.023 | 29

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 5019.5967 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.9 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH