## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.58226 | 1.4895 |  |  |  | 17 | 17.76 | 34.76 | 29.1967 |  | 4.08 | 74 | 78.08 | 49.6821 |  | 4.08 | 17.76 | 21.84 | 11.9237 |  | 4.08 | 17.76 | 21.84 | 11.9237 |  | 4.08 | 17.76 | 21.84 | 11.9237 |  | 4.08 | 17.76 | 21.84 | 11.9237 |  | 200.2 | 126.5736 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 64.2327 | 109.3006 | 109.3006
Project-A02 |  | v002 |  | 0.60324 | 1.5041 |  |  |  | 15 | 19.2 | 34.2 | 24.8659 |  | 3.6 | 80 | 83.6 | 53.1876 |  | 3.6 | 19.2 | 22.8 | 12.765 |  | 3.6 | 19.2 | 22.8 | 12.765 |  | 3.6 | 19.2 | 22.8 | 12.765 |  | 3.6 | 19.2 | 22.8 | 12.765 |  | 209 | 129.1136 | 104500 |  | 0.058933 |  | 33 | 176 |  | 54.705 | 117.0127 | 117.0127 | [12 empty] | E
Project-A03 |  | v003 |  | 0.54291 | 1.4813 |  |  |  | 16 | 6.48 | 22.48 | 29.4709 |  | 3.84 | 27 | 30.84 | 18.2273 |  | 3.84 | 6.48 | 10.32 | 7.073 |  | 3.84 | 6.48 | 10.32 | 7.073 |  | 3.84 | 6.48 | 10.32 | 7.073 |  | 3.84 | 6.48 | 10.32 | 7.073 |  | 94.6 | 75.9903 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 64.836 | 40.1 | 64.836 | [12 empty] | N
Project-A04 |  | v004 |  | 0.53467 | 1.4937 |  |  |  | 35 | 4.32 | 39.32 | 65.4614 |  | 8.4 | 18 | 26.4 | 15.7107 |  | 8.4 | 4.32 | 12.72 | 15.7107 |  | 8.4 | 4.32 | 12.72 | 15.7107 |  | 8.4 | 4.32 | 12.72 | 15.7107 |  | 8.4 | 4.32 | 12.72 | 15.7107 |  | 116.6 | 144.015 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 144.015 | 26.5119 | 144.015 | [12 empty] | D
Project-A05 |  | v002 |  | 0.63353 | 1.5006 |  |  |  | 6 | 19.2 | 25.2 | 12.7945 |  | 1.44 | 80 | 81.44 | 53.3106 |  | 1.44 | 19.2 | 20.64 | 12.7945 |  | 1.44 | 19.2 | 20.64 | 12.7945 |  | 1.44 | 19.2 | 20.64 | 12.7945 |  | 1.44 | 19.2 | 20.64 | 12.7945 |  | 189.2 | 117.2833 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 20.8356 | 117.2833 | 117.2833
Project-A06 |  | v003 |  | 0.51637 | 1.5166 |  |  |  | 52 | 10.56 | 62.56 | 100.7026 |  | 12.48 | 44 | 56.48 | 29.0116 |  | 12.48 | 10.56 | 23.04 | 24.1686 |  | 12.48 | 10.56 | 23.04 | 24.1686 |  | 12.48 | 10.56 | 23.04 | 24.1686 |  | 12.48 | 10.56 | 23.04 | 24.1686 |  | 211.2 | 226.3886 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 221.5456 | 63.8254 | 221.5456 | [12 empty] | O
Project-A07 |  | v005 |  | 0.58423 | 1.4775 |  |  |  | 93 | 19.92 | 112.92 | 159.1831 |  | 22.32 | 83 | 105.32 | 56.1741 |  | 22.32 | 19.92 | 42.24 | 38.204 |  | 22.32 | 19.92 | 42.24 | 38.204 |  | 22.32 | 19.92 | 42.24 | 38.204 |  | 22.32 | 19.92 | 42.24 | 38.204 |  | 387.2 | 368.1731 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 350.2029 | 123.5831 | 350.2029 | [12 empty] | F
Project-A08 |  | v006 |  | 0.57507 | 1.5048 |  |  |  | 5 | 2.64 | 7.64 | 8.6946 |  | 1.2 | 11 | 12.2 | 7.31 |  | 1.2 | 2.64 | 3.84 | 2.0867 |  | 1.2 | 2.64 | 3.84 | 2.0867 |  | 1.2 | 2.64 | 3.84 | 2.0867 |  | 1.2 | 2.64 | 3.84 | 2.0867 |  | 35.2 | 24.3515 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 19.1281 | 16.082 | 19.1281
Project-A09 |  | v003 |  | 0.50384 | 1.4854 |  |  |  | 49 | 20.64 | 69.64 | 97.2522 |  | 11.76 | 86 | 97.76 | 57.898 |  | 11.76 | 20.64 | 32.4 | 23.3405 |  | 11.76 | 20.64 | 32.4 | 23.3405 |  | 11.76 | 20.64 | 32.4 | 23.3405 |  | 11.76 | 20.64 | 32.4 | 23.3405 |  | 297 | 248.5124 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 213.9549 | 127.3757 | 213.9549 | [12 empty] | T
Project-A10 |  | v001 |  | 0.64467 | 1.4895 |  |  |  | 36 | 20.88 | 56.88 | 55.8425 |  | 8.64 | 87 | 95.64 | 58.4087 |  | 8.64 | 20.88 | 29.52 | 14.0181 |  | 8.64 | 20.88 | 29.52 | 14.0181 |  | 8.64 | 20.88 | 29.52 | 14.0181 |  | 8.64 | 20.88 | 29.52 | 14.0181 |  | 270.6 | 170.3235 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 122.8535 | 128.4991 | 128.4991 | [12 empty] | H
Project-A11 |  | v002 |  | 0.28954 | 1.5082 |  |  |  | 63 | 19.2 | 82.2 | 217.5896 |  | 15.12 | 80 | 95.12 | 53.0446 |  | 15.12 | 19.2 | 34.32 | 52.2215 |  | 15.12 | 19.2 | 34.32 | 52.2215 |  | 15.12 | 19.2 | 34.32 | 52.2215 |  | 15.12 | 19.2 | 34.32 | 52.2215 |  | 314.6 | 479.5202 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 478.6971 | 116.6982 | 478.6971 | [12 empty] | I
Project-A12 |  | v004 |  | 0.5429 | 1.5379 |  |  |  | 65 | 21.84 | 86.84 | 119.7283 |  | 15.6 | 91 | 106.6 | 59.1714 |  | 15.6 | 21.84 | 37.44 | 28.7348 |  | 15.6 | 21.84 | 37.44 | 28.7348 |  | 15.6 | 21.84 | 37.44 | 28.7348 |  | 15.6 | 21.84 | 37.44 | 28.7348 |  | 343.2 | 293.8389 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 263.4023 | 130.1771 | 263.4023 | [12 empty] | S
Project-A13 |  | v007 |  | 0.56747 | 1.9909 |  |  |  | 96 | 9.6 | 105.6 | 169.1712 |  | 23.04 | 40 | 63.04 | 40.6011 |  | 23.04 | 9.6 | 32.64 | 40.6011 |  | 23.04 | 9.6 | 32.64 | 40.6011 |  | 23.04 | 9.6 | 32.64 | 40.6011 |  | 23.04 | 9.6 | 32.64 | 40.6011 |  | 299.2 | 372.1767 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 372.1767 | 44.2013 | 372.1767
Project-A14 |  | v006 |  | 0.58595 | 2.036 |  |  |  | 39 | 12.72 | 51.72 | 66.559 |  | 9.36 | 53 | 62.36 | 26.0317 |  | 9.36 | 12.72 | 22.08 | 15.9742 |  | 9.36 | 12.72 | 22.08 | 15.9742 |  | 9.36 | 12.72 | 22.08 | 15.9742 |  | 9.36 | 12.72 | 22.08 | 15.9742 |  | 202.4 | 156.4873 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 146.4297 | 57.2698 | 146.4297 | [12 empty] | W
Project-A15 |  | v008 |  | 0.29336 | 1.984 |  |  |  | 72 | 23.76 | 95.76 | 245.4306 |  | 17.28 | 99 | 116.28 | 58.9033 |  | 17.28 | 23.76 | 41.04 | 58.9033 |  | 17.28 | 23.76 | 41.04 | 58.9033 |  | 17.28 | 23.76 | 41.04 | 58.9033 |  | 17.28 | 23.76 | 41.04 | 58.9033 |  | 376.2 | 539.9473 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 539.9473 | 109.7764 | 539.9473 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 93.4629 |  | 10.544 | 63.5333 | 74.0773 | 42.4449 |  | 10.544 | 15.248 | 25.792 | 23.9013 |  | 10.544 | 15.248 | 25.792 | 23.9013 |  | 10.544 | 15.248 | 25.792 | 23.9013 |  | 10.544 | 15.248 | 25.792 | 23.9013 |  | 236.4267 | 231.513 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 205.1308 | 88.5131 | 219.0954 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1401.9432 |  | 158.16 | 953 | 1111.16 | 636.6729 |  | 158.16 | 228.72 | 386.88 | 358.5198 |  | 158.16 | 228.72 | 386.88 | 358.5198 |  | 158.16 | 228.72 | 386.88 | 358.5198 |  | 158.16 | 228.72 | 386.88 | 358.5198 |  | 3546.4 | 3472.6953 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3076.9626 | 1327.6966 | 3286.4315 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 731.1731 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 261.5797 |  | <- To shorten average individual project span |  |  |  | <----------> | 219.0954
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 73.0199 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 257.6889 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1323.4615 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.58226 | 1.4895 |  |  |  | 2014-01-01 |  | 2 | 2014-01-04 | 2014-02-02 04:43 |  | 0 | 2014-02-03 04:43 | 2014-03-24 21:05 |  | 0 | 2014-03-25 21:05 | 2014-04-06 19:16 |  | 0 | 2014-04-07 19:16 | 2014-04-19 17:26 |  | 4 | 2014-04-24 17:26 | 2014-05-06 15:36 |  | 0 | 2014-05-07 15:36 | 2014-05-19 13:46 |  | v001 |  | 0.056452 |  | 2 | 0 | 0 | 0 | 4 | 0 | 6 | 1.6935 |  | 135.5736 | 731.1731 | [14 empty] | E
Project-A02 |  | 0.60324 | 1.5041 |  |  |  | 2014-01-01 |  | 20 | 2014-01-22 | 2014-02-15 20:47 |  | 0 | 2014-02-16 20:47 | 2014-04-11 01:17 |  | 0 | 2014-04-12 01:17 | 2014-04-24 19:39 |  | 0 | 2014-04-25 19:39 | 2014-05-08 14:00 |  | 0 | 2014-05-09 14:00 | 2014-05-22 08:22 |  | 0 | 2014-05-23 08:22 | 2014-06-05 02:44 |  | v002 |  | 0.058933 |  | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 17.6799 |  | 134.1136 | [15 empty] | N
Project-A03 |  | 0.54291 | 1.4813 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-31 11:18 |  | 0 | 2014-02-01 11:18 | 2014-02-19 16:45 |  | 0 | 2014-02-20 16:45 | 2014-02-27 18:31 |  | 0 | 2014-02-28 18:31 | 2014-03-07 20:16 |  | 0 | 2014-03-08 20:16 | 2014-03-15 22:01 |  | 0 | 2014-03-16 22:01 | 2014-03-23 23:46 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80.9903 | [15 empty] | D
Project-A04 |  | 0.53467 | 1.4937 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-04-11 11:04 |  | 0 | 2014-04-12 11:04 | 2014-04-28 04:08 |  | 0 | 2014-04-29 04:08 | 2014-05-14 21:11 |  | 0 | 2014-05-15 21:11 | 2014-05-31 14:15 |  | 0 | 2014-06-01 14:15 | 2014-06-17 07:18 |  | 0 | 2014-06-18 07:18 | 2014-07-04 00:22 |  | v004 |  | 0.032878 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 16.768 |  | 149.015
Project-A05 |  | 0.63353 | 1.5006 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-14 19:04 |  | 0 | 2014-01-15 19:04 | 2014-03-10 02:31 |  | 0 | 2014-03-11 02:31 | 2014-03-23 21:36 |  | 0 | 2014-03-24 21:36 | 2014-04-06 16:40 |  | 0 | 2014-04-07 16:40 | 2014-04-20 11:44 |  | 365 | 2015-04-21 11:44 | 2015-05-04 06:48 |  | v002 |  | 0.05335 |  | 0 | 0 | 0 | 0 | 0 | 365 | 365 | 0 |  | 487.2833 | [15 empty] | O
Project-A06 |  | 0.51637 | 1.5166 |  |  |  | 2014-01-01 |  | 57 | 2014-02-28 | 2014-06-08 16:52 |  | 0 | 2014-06-09 16:52 | 2014-07-08 17:08 |  | 0 | 2014-07-09 17:08 | 2014-08-02 21:11 |  | 0 | 2014-08-03 21:11 | 2014-08-28 01:14 |  | 0 | 2014-08-29 01:14 | 2014-09-22 05:17 |  | 0 | 2014-09-23 05:17 | 2014-10-17 09:20 |  | v003 |  | 0.059553 |  | 57 | 0 | 0 | 0 | 0 | 0 | 57 | 50.9181 |  | 231.3886 | [15 empty] | F
Project-A07 |  | 0.58423 | 1.4775 |  |  |  | 2014-01-01 |  | 358 | 2014-12-26 | 2015-06-03 04:24 |  | 0 | 2015-06-04 04:24 | 2015-07-30 08:34 |  | 0 | 2015-07-31 08:34 | 2015-09-07 13:28 |  | 0 | 2015-09-08 13:28 | 2015-10-16 18:22 |  | 0 | 2015-10-17 18:22 | 2015-11-24 23:16 |  | 0 | 2015-11-25 23:16 | 2016-01-03 04:09 |  | v005 |  | 0.10918 |  | 358 | 0 | 0 | 0 | 0 | 0 | 358 | 586.3027 |  | 373.1731
Project-A08 |  | 0.57507 | 1.5048 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-10 16:40 |  | 0 | 2014-01-11 16:40 | 2014-01-19 00:07 |  | 0 | 2014-01-20 00:07 | 2014-01-22 02:12 |  | 0 | 2014-01-23 02:12 | 2014-01-25 04:16 |  | 0 | 2014-01-26 04:16 | 2014-01-28 06:21 |  | 0 | 2014-01-29 06:21 | 2014-01-31 08:26 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 29.3515 | [15 empty] | T
Project-A09 |  | 0.50384 | 1.4854 |  |  |  | 2014-01-01 |  | 16 | 2014-01-18 | 2014-04-25 06:03 |  | 0 | 2014-04-26 06:03 | 2014-06-23 03:36 |  | 0 | 2014-06-24 03:36 | 2014-07-17 11:47 |  | 0 | 2014-07-18 11:47 | 2014-08-10 19:57 |  | 0 | 2014-08-11 19:57 | 2014-09-04 04:07 |  | 0 | 2014-09-05 04:07 | 2014-09-28 12:18 |  | v003 |  | 0.083747 |  | 16 | 0 | 0 | 0 | 0 | 0 | 16 | 20.0993 |  | 253.5124 | [15 empty] | H
Project-A10 |  | 0.64467 | 1.4895 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-03-21 20:13 |  | 0 | 2014-03-22 20:13 | 2014-05-20 06:02 |  | 0 | 2014-05-21 06:02 | 2014-06-04 06:28 |  | 7 | 2014-06-12 06:28 | 2014-06-26 06:54 |  | 0 | 2014-06-27 06:54 | 2014-07-11 07:20 |  | 0 | 2014-07-12 07:20 | 2014-07-26 07:46 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 7 | 0 | 0 | 30 | 26.3244 |  | 182.3235 | [15 empty] | I
Project-A11 |  | 0.28954 | 1.5082 |  |  |  | 2014-01-01 |  | 37 | 2014-02-08 | 2014-09-13 14:09 |  | 0 | 2014-09-14 14:09 | 2014-11-06 15:13 |  | 0 | 2014-11-07 15:13 | 2014-12-29 20:32 |  | 0 | 2014-12-30 20:32 | 2015-02-21 01:51 |  | 0 | 2015-02-22 01:51 | 2015-04-15 07:10 |  | 0 | 2015-04-16 07:10 | 2015-06-07 12:29 |  | v002 |  | 0.08871 |  | 37 | 0 | 0 | 0 | 0 | 0 | 37 | 49.2339 |  | 484.5202 | [15 empty] | S
Project-A12 |  | 0.5429 | 1.5379 |  |  |  | 2014-01-01 |  | 47 | 2014-02-18 | 2014-06-17 17:29 |  | 0 | 2014-06-18 17:29 | 2014-08-16 21:36 |  | 0 | 2014-08-17 21:36 | 2014-09-15 15:14 |  | 0 | 2014-09-16 15:14 | 2014-10-15 08:52 |  | 0 | 2014-10-16 08:52 | 2014-11-14 02:30 |  | 0 | 2014-11-15 02:30 | 2014-12-13 20:08 |  | v004 |  | 0.096774 |  | 47 | 0 | 0 | 0 | 0 | 0 | 47 | 68.2258 |  | 298.8389
Project-A13 |  | 0.56747 | 1.9909 |  |  |  | 2014-01-01 |  | 58 | 2014-03-01 | 2014-08-17 04:07 |  | 0 | 2014-08-18 04:07 | 2014-09-27 18:32 |  | 0 | 2014-09-28 18:32 | 2014-11-08 08:58 |  | 0 | 2014-11-09 08:58 | 2014-12-19 23:23 |  | 0 | 2014-12-20 23:23 | 2015-01-30 13:49 |  | 0 | 2015-01-31 13:49 | 2015-03-13 04:14 |  | v007 |  | 0.084367 |  | 58 | 0 | 0 | 0 | 0 | 0 | 58 | 73.3995 |  | 377.1767 | [15 empty] | W
Project-A14 |  | 0.58595 | 2.036 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-15 13:25 |  | 0 | 2014-05-16 13:25 | 2014-06-11 14:11 |  | 0 | 2014-06-12 14:11 | 2014-06-28 13:33 |  | 0 | 2014-06-29 13:33 | 2014-07-15 12:56 |  | 0 | 2014-07-16 12:56 | 2014-08-01 12:19 |  | 0 | 2014-08-02 12:19 | 2014-08-18 11:42 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 57.3573 |  | 161.4873 | [15 empty] | O
Project-A15 |  | 0.29336 | 1.984 |  |  |  | 2014-01-01 |  | 80 | 2014-03-23 | 2014-11-23 10:20 |  | 0 | 2014-11-24 10:20 | 2015-01-22 08:01 |  | 0 | 2015-01-23 08:01 | 2015-03-23 05:42 |  | 0 | 2015-03-24 05:42 | 2015-05-22 03:22 |  | 0 | 2015-05-23 03:22 | 2015-07-21 01:03 |  | 0 | 2015-07-22 01:03 | 2015-09-18 22:44 |  | v008 |  | 0.10608 |  | 80 | 0 | 0 | 0 | 0 | 0 | 80 | 127.2953 |  | 544.9473 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 53.2667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.46667 |  |  |  | 0.26667 |  |  |  | 24.3333 | [5 empty] | 0.066667 |  | 53.2667 | 0 | 0 | 0.46667 | 0.26667 | 24.3333 | 78.3333 | 73.0199 | Average | 261.5797 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 799 |  |  |  | 0 |  |  |  | 0 |  |  |  | 7 |  |  |  | 4 |  |  |  | 365 | [5 empty] | 1 |  | 799 | 0 | 0 | 7 | 4 | 365 | 1175 | 1095.2978 | Total | 3923.6953 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 2
| Days: | 5.1538
E
N
SIT - Violation | Count: | 2 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 5.1538
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-25 21:05 | 2014-04-06 19:16 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-12 01:17 | 2014-04-24 19:39 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-20 16:45 | 2014-02-27 18:31 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-04-29 04:08 | 2014-05-14 21:11 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-03-11 02:31 | 2014-03-23 21:36 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-09 17:08 | 2014-08-02 21:11 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-07-31 08:34 | 2015-09-07 13:28 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-20 00:07 | 2014-01-22 02:12 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-24 03:36 | 2014-07-17 11:47 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 4.4146 | 0 | R
Project-A10 | 2014-05-21 06:02 | 2014-06-04 06:28 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-11-07 15:13 | 2014-12-29 20:32 | v002 |  | Count P-A12: 0; Count P-A13: 1; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0.73919 | 0 | 0 | S
Project-A12 | 2014-08-17 21:36 | 2014-09-15 15:14 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-09-28 18:32 | 2014-11-08 08:58 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-12 14:11 | 2014-06-28 13:33 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2015-01-23 08:01 | 2015-03-23 05:42 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-07 19:16 | 2014-04-19 17:26 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-25 19:39 | 2014-05-08 14:00 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-28 18:31 | 2014-03-07 20:16 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-15 21:11 | 2014-05-31 14:15 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-24 21:36 | 2014-04-06 16:40 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-03 21:11 | 2014-08-28 01:14 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-09-08 13:28 | 2015-10-16 18:22 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-23 02:12 | 2014-01-25 04:16 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-18 11:47 | 2014-08-10 19:57 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-12 06:28 | 2014-06-26 06:54 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-12-30 20:32 | 2015-02-21 01:51 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-16 15:14 | 2014-10-15 08:52 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-11-09 08:58 | 2014-12-19 23:23 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-06-29 13:33 | 2014-07-15 12:56 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-03-24 05:42 | 2015-05-22 03:22 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-24 17:26 | 2014-05-06 15:36 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-09 14:00 | 2014-05-22 08:22 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-08 20:16 | 2014-03-15 22:01 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-01 14:15 | 2014-06-17 07:18 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-07 16:40 | 2014-04-20 11:44 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-29 01:14 | 2014-09-22 05:17 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-17 18:22 | 2015-11-24 23:16 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-26 04:16 | 2014-01-28 06:21 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-11 19:57 | 2014-09-04 04:07 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-27 06:54 | 2014-07-11 07:20 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-02-22 01:51 | 2015-04-15 07:10 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-16 08:52 | 2014-11-14 02:30 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-20 23:23 | 2015-01-30 13:49 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-16 12:56 | 2014-08-01 12:19 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-05-23 03:22 | 2015-07-21 01:03 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-05-07 15:36 | 2014-05-19 13:46 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-23 08:22 | 2014-06-05 02:44 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-16 22:01 | 2014-03-23 23:46 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-18 07:18 | 2014-07-04 00:22 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-04-21 11:44 | 2015-05-04 06:48 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-23 05:17 | 2014-10-17 09:20 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-11-25 23:16 | 2016-01-03 04:09 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-29 06:21 | 2014-01-31 08:26 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-09-05 04:07 | 2014-09-28 12:18 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-12 07:20 | 2014-07-26 07:46 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-04-16 07:10 | 2015-06-07 12:29 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-15 02:30 | 2014-12-13 20:08 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-31 13:49 | 2015-03-13 04:14 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-02 12:19 | 2014-08-18 11:42 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-07-22 01:03 | 2015-09-18 22:44 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.11948 | 11.9482 | 11
0.092123 | 9.2123 | 9
0.57827 | 57.8269 | 57
0.42492 | 42.4919 | 42
0.26925 | 26.9251 | 26
0.87439 | 87.4391 | 87
0.36556 | 36.5556 | 36
0.76761 | 76.7612 | 76
0.60852 | 60.8517 | 60
0.4179 | 41.79 | 41
0.88947 | 88.9469 | 88
0.25527 | 25.5272 | 25
0.80753 | 80.7526 | 80
0.043718 | 4.3718 | 4
0.70402 | 70.4025 | 70
0.17297 | 17.2967 | 17
0.17577 | 17.5774 | 17
0.45592 | 45.592 | 45
0.51994 | 51.994 | 51
0.71735 | 71.7348 | 71
0.40782 | 40.7823 | 40
0.84187 | 84.1874 | 84
0.013146 | 1.3146 | 1
0.32614 | 32.614 | 32
0.81844 | 81.844 | 81
0.16536 | 16.5364 | 16
0.81362 | 81.362 | 81
0.23043 | 23.0433 | 23
0.3535 | 35.3501 | 35
0.14957 | 14.9571 | 14
0.33731 | 33.7306 | 33
0.49405 | 49.4046 | 49
0.93193 | 93.1928 | 93
0.40656 | 40.6561 | 40
0.11413 | 11.4125 | 11
0.5556 | 55.5604 | 55
0.75708 | 75.7083 | 75
0.055789 | 5.5789 | 5
0.82229 | 82.2287 | 82

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1323.4615 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.9 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH