## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.50963 | 1.4361 |  |  |  | 17 | 17.76 | 34.76 | 33.3573 |  | 4.08 | 74 | 78.08 | 51.5291 |  | 4.08 | 17.76 | 21.84 | 12.367 |  | 4.08 | 17.76 | 21.84 | 12.367 |  | 4.08 | 17.76 | 21.84 | 12.367 |  | 4.08 | 17.76 | 21.84 | 12.367 |  | 200.2 | 134.3543 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 73.3861 | 113.3639 | 113.3639
Project-A02 |  | v002 |  | 0.54999 | 3.4292 |  |  |  | 15 | 19.2 | 34.2 | 27.273 |  | 3.6 | 80 | 83.6 | 23.3289 |  | 3.6 | 19.2 | 22.8 | 6.5455 |  | 3.6 | 19.2 | 22.8 | 6.5455 |  | 3.6 | 19.2 | 22.8 | 6.5455 |  | 3.6 | 19.2 | 22.8 | 6.5455 |  | 209 | 76.7841 | 104500 |  | 0.058933 |  | 33 | 176 |  | 60.0007 | 51.3236 | 60.0007 | [12 empty] | E
Project-A03 |  | v003 |  | 0.52961 | 1.5258 |  |  |  | 16 | 6.48 | 22.48 | 30.2111 |  | 3.84 | 27 | 30.84 | 17.6961 |  | 3.84 | 6.48 | 10.32 | 7.2507 |  | 3.84 | 6.48 | 10.32 | 7.2507 |  | 3.84 | 6.48 | 10.32 | 7.2507 |  | 3.84 | 6.48 | 10.32 | 7.2507 |  | 94.6 | 76.9099 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 66.4644 | 38.9314 | 66.4644 | [12 empty] | N
Project-A04 |  | v004 |  | 0.46887 | 1.3517 |  |  |  | 35 | 4.32 | 39.32 | 74.6474 |  | 8.4 | 18 | 26.4 | 17.9154 |  | 8.4 | 4.32 | 12.72 | 17.9154 |  | 8.4 | 4.32 | 12.72 | 17.9154 |  | 8.4 | 4.32 | 12.72 | 17.9154 |  | 8.4 | 4.32 | 12.72 | 17.9154 |  | 116.6 | 164.2242 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 164.2242 | 29.2955 | 164.2242 | [12 empty] | D
Project-A05 |  | v002 |  | 0.42307 | 0.26275 |  |  |  | 6 | 19.2 | 25.2 | 73.072 |  | 1.44 | 80 | 81.44 | 304.4665 |  | 1.44 | 19.2 | 20.64 | 73.072 |  | 1.44 | 19.2 | 20.64 | 73.072 |  | 1.44 | 19.2 | 20.64 | 73.072 |  | 1.44 | 19.2 | 20.64 | 73.072 |  | 189.2 | 669.8263 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 31.2005 | 669.8263 | 669.8263
Project-A06 |  | v003 |  | 0.50046 | 3.2412 |  |  |  | 52 | 10.56 | 62.56 | 103.9049 |  | 12.48 | 44 | 56.48 | 24.9372 |  | 12.48 | 10.56 | 23.04 | 24.9372 |  | 12.48 | 10.56 | 23.04 | 24.9372 |  | 12.48 | 10.56 | 23.04 | 24.9372 |  | 12.48 | 10.56 | 23.04 | 24.9372 |  | 211.2 | 228.5908 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 228.5908 | 29.8655 | 228.5908 | [12 empty] | O
Project-A07 |  | v005 |  | 0.25511 | 1.5001 |  |  |  | 93 | 19.92 | 112.92 | 364.553 |  | 22.32 | 83 | 105.32 | 87.4927 |  | 22.32 | 19.92 | 42.24 | 87.4927 |  | 22.32 | 19.92 | 42.24 | 87.4927 |  | 22.32 | 19.92 | 42.24 | 87.4927 |  | 22.32 | 19.92 | 42.24 | 87.4927 |  | 387.2 | 802.0167 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 802.0167 | 121.7274 | 802.0167 | [12 empty] | F
Project-A08 |  | v006 |  | 0.44654 | 1.7291 |  |  |  | 5 | 2.64 | 7.64 | 11.1973 |  | 1.2 | 11 | 12.2 | 6.3617 |  | 1.2 | 2.64 | 3.84 | 2.6873 |  | 1.2 | 2.64 | 3.84 | 2.6873 |  | 1.2 | 2.64 | 3.84 | 2.6873 |  | 1.2 | 2.64 | 3.84 | 2.6873 |  | 35.2 | 28.3083 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 24.634 | 13.9957 | 24.634
Project-A09 |  | v003 |  | 0.49809 | 1.5075 |  |  |  | 49 | 20.64 | 69.64 | 98.376 |  | 11.76 | 86 | 97.76 | 57.0487 |  | 11.76 | 20.64 | 32.4 | 23.6102 |  | 11.76 | 20.64 | 32.4 | 23.6102 |  | 11.76 | 20.64 | 32.4 | 23.6102 |  | 11.76 | 20.64 | 32.4 | 23.6102 |  | 297 | 249.8656 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 216.4271 | 125.5072 | 216.4271 | [12 empty] | T
Project-A10 |  | v001 |  | 0.54793 | 1.5134 |  |  |  | 36 | 20.88 | 56.88 | 65.7017 |  | 8.64 | 87 | 95.64 | 57.4854 |  | 8.64 | 20.88 | 29.52 | 15.7684 |  | 8.64 | 20.88 | 29.52 | 15.7684 |  | 8.64 | 20.88 | 29.52 | 15.7684 |  | 8.64 | 20.88 | 29.52 | 15.7684 |  | 270.6 | 186.2608 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 144.5437 | 126.468 | 144.5437 | [12 empty] | H
Project-A11 |  | v002 |  | 0.57517 | 0.82113 |  |  |  | 63 | 19.2 | 82.2 | 109.5331 |  | 15.12 | 80 | 95.12 | 97.4265 |  | 15.12 | 19.2 | 34.32 | 26.2879 |  | 15.12 | 19.2 | 34.32 | 26.2879 |  | 15.12 | 19.2 | 34.32 | 26.2879 |  | 15.12 | 19.2 | 34.32 | 26.2879 |  | 314.6 | 312.1114 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 240.9728 | 214.3383 | 240.9728 | [12 empty] | I
Project-A12 |  | v004 |  | 0.63527 | 1.2099 |  |  |  | 65 | 21.84 | 86.84 | 102.3185 |  | 15.6 | 91 | 106.6 | 75.2128 |  | 15.6 | 21.84 | 37.44 | 24.5564 |  | 15.6 | 21.84 | 37.44 | 24.5564 |  | 15.6 | 21.84 | 37.44 | 24.5564 |  | 15.6 | 21.84 | 37.44 | 24.5564 |  | 343.2 | 275.7571 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 225.1007 | 165.4681 | 225.1007 | [12 empty] | S
Project-A13 |  | v007 |  | 0.54895 | 2.0281 |  |  |  | 96 | 9.6 | 105.6 | 174.8778 |  | 23.04 | 40 | 63.04 | 41.9707 |  | 23.04 | 9.6 | 32.64 | 41.9707 |  | 23.04 | 9.6 | 32.64 | 41.9707 |  | 23.04 | 9.6 | 32.64 | 41.9707 |  | 23.04 | 9.6 | 32.64 | 41.9707 |  | 299.2 | 384.7311 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 384.7311 | 43.3902 | 384.7311
Project-A14 |  | v006 |  | 0.50481 | 2.1934 |  |  |  | 39 | 12.72 | 51.72 | 77.2571 |  | 9.36 | 53 | 62.36 | 24.1635 |  | 9.36 | 12.72 | 22.08 | 18.5417 |  | 9.36 | 12.72 | 22.08 | 18.5417 |  | 9.36 | 12.72 | 22.08 | 18.5417 |  | 9.36 | 12.72 | 22.08 | 18.5417 |  | 202.4 | 175.5875 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 169.9657 | 53.1596 | 169.9657 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0065 | 0.25061 |  |  |  | 72 | 23.76 | 95.76 | 94.809 |  | 17.28 | 99 | 116.28 | 395.0376 |  | 17.28 | 23.76 | 41.04 | 94.809 |  | 17.28 | 23.76 | 41.04 | 94.809 |  | 17.28 | 23.76 | 41.04 | 94.809 |  | 17.28 | 23.76 | 41.04 | 94.809 |  | 376.2 | 869.0828 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 157.377 | 869.0828 | 869.0828 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 96.0726 |  | 10.544 | 63.5333 | 74.0773 | 85.4715 |  | 10.544 | 15.248 | 25.792 | 31.8541 |  | 10.544 | 15.248 | 25.792 | 31.8541 |  | 10.544 | 15.248 | 25.792 | 31.8541 |  | 10.544 | 15.248 | 25.792 | 31.8541 |  | 236.4267 | 308.9607 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 199.309 | 177.7162 | 291.9963 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1441.0892 |  | 158.16 | 953 | 1111.16 | 1282.0727 |  | 158.16 | 228.72 | 386.88 | 477.8122 |  | 158.16 | 228.72 | 386.88 | 477.8122 |  | 158.16 | 228.72 | 386.88 | 477.8122 |  | 158.16 | 228.72 | 386.88 | 477.8122 |  | 3546.4 | 4634.4107 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2989.6356 | 2665.7435 | 4379.945 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 1172.0167 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 377.694 |  | <- To shorten average individual project span |  |  |  | <----------> | 291.9963
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 80.8139 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 1293.1349 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 2923.6596 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.50963 | 1.4361 |  |  |  | 2014-01-01 |  | 26 | 2014-01-28 | 2014-03-02 08:35 |  | 0 | 2014-03-03 08:35 | 2014-04-23 21:16 |  | 0 | 2014-04-24 21:16 | 2014-05-07 06:05 |  | 365 | 2015-05-08 06:05 | 2015-05-20 14:53 |  | 0 | 2015-05-21 14:53 | 2015-06-02 23:42 |  | 0 | 2015-06-03 23:42 | 2015-06-16 08:30 |  | v001 |  | 0.056452 |  | 26 | 0 | 0 | 365 | 0 | 0 | 391 | 22.0161 |  | 504.3543 | 1172.0167 | [14 empty] | E
Project-A02 |  | 0.54999 | 3.4292 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-03-04 06:33 |  | 0 | 2014-03-05 06:33 | 2014-03-28 14:27 |  | 0 | 2014-03-29 14:27 | 2014-04-05 03:32 |  | 0 | 2014-04-06 03:32 | 2014-04-12 16:38 |  | 0 | 2014-04-13 16:38 | 2014-04-20 05:44 |  | 0 | 2014-04-21 05:44 | 2014-04-27 18:49 |  | v002 |  | 0.058933 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 30.0558 |  | 81.7841 | [15 empty] | N
Project-A03 |  | 0.52961 | 1.5258 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-01 05:04 |  | 0 | 2014-02-02 05:04 | 2014-02-19 21:46 |  | 0 | 2014-02-20 21:46 | 2014-02-28 03:47 |  | 0 | 2014-03-01 03:47 | 2014-03-08 09:48 |  | 0 | 2014-03-09 09:48 | 2014-03-16 15:49 |  | 0 | 2014-03-17 15:49 | 2014-03-24 21:50 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 81.9099 | [15 empty] | D
Project-A04 |  | 0.46887 | 1.3517 |  |  |  | 2014-01-01 |  | 33 | 2014-02-04 | 2014-04-19 15:32 |  | 0 | 2014-04-20 15:32 | 2014-05-08 13:30 |  | 0 | 2014-05-09 13:30 | 2014-05-27 11:28 |  | 0 | 2014-05-28 11:28 | 2014-06-15 09:27 |  | 0 | 2014-06-16 09:27 | 2014-07-04 07:25 |  | 0 | 2014-07-05 07:25 | 2014-07-23 05:23 |  | v004 |  | 0.032878 |  | 33 | 0 | 0 | 0 | 0 | 0 | 33 | 16.2748 |  | 169.2242
Project-A05 |  | 0.42307 | 0.26275 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-04-30 01:44 |  | 0 | 2014-05-01 01:44 | 2015-03-01 12:55 |  | 0 | 2015-03-02 12:55 | 2015-05-14 14:39 |  | 11 | 2015-05-26 14:39 | 2015-08-07 16:23 |  | 0 | 2015-08-08 16:23 | 2015-10-20 18:06 |  | 0 | 2015-10-21 18:06 | 2016-01-02 19:50 |  | v002 |  | 0.05335 |  | 45 | 0 | 0 | 11 | 0 | 0 | 56 | 36.0112 |  | 685.8263 | [15 empty] | O
Project-A06 |  | 0.50046 | 3.2412 |  |  |  | 2014-01-01 |  | 64 | 2014-03-07 | 2014-06-18 21:43 |  | 0 | 2014-06-19 21:43 | 2014-07-14 20:13 |  | 0 | 2014-07-15 20:13 | 2014-08-09 18:42 |  | 0 | 2014-08-10 18:42 | 2014-09-04 17:12 |  | 0 | 2014-09-05 17:12 | 2014-09-30 15:41 |  | 0 | 2014-10-01 15:41 | 2014-10-26 14:11 |  | v003 |  | 0.059553 |  | 64 | 0 | 0 | 0 | 0 | 0 | 64 | 57.1712 |  | 233.5908 | [15 empty] | F
Project-A07 |  | 0.25511 | 1.5001 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2016-01-01 13:16 |  | 0 | 2016-01-02 13:16 | 2016-03-30 01:06 |  | 0 | 2016-03-31 01:06 | 2016-06-26 12:55 |  | 0 | 2016-06-27 12:55 | 2016-09-23 00:45 |  | 0 | 2016-09-24 00:45 | 2016-12-20 12:35 |  | 0 | 2016-12-21 12:35 | 2017-03-19 00:24 |  | v005 |  | 0.10918 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 597.7667 |  | 807.0167
Project-A08 |  | 0.44654 | 1.7291 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-13 04:44 |  | 0 | 2014-01-14 04:44 | 2014-01-20 13:25 |  | 0 | 2014-01-21 13:25 | 2014-01-24 05:55 |  | 0 | 2014-01-25 05:55 | 2014-01-27 22:24 |  | 0 | 2014-01-28 22:24 | 2014-01-31 14:54 |  | 0 | 2014-02-01 14:54 | 2014-02-04 07:24 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 33.3083 | [15 empty] | T
Project-A09 |  | 0.49809 | 1.5075 |  |  |  | 2014-01-01 |  | 15 | 2014-01-17 | 2014-04-25 09:01 |  | 0 | 2014-04-26 09:01 | 2014-06-22 10:12 |  | 0 | 2014-06-23 10:12 | 2014-07-17 00:50 |  | 23 | 2014-08-10 00:50 | 2014-09-02 15:29 |  | 0 | 2014-09-03 15:29 | 2014-09-27 06:08 |  | 0 | 2014-09-28 06:08 | 2014-10-21 20:47 |  | v003 |  | 0.083747 |  | 15 | 0 | 0 | 23 | 0 | 0 | 38 | 18.8431 |  | 277.8656 | [15 empty] | H
Project-A10 |  | 0.54793 | 1.5134 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-03-31 16:50 |  | 0 | 2014-04-01 16:50 | 2014-05-29 04:29 |  | 0 | 2014-05-30 04:29 | 2014-06-14 22:56 |  | 1 | 2014-06-16 22:56 | 2014-07-02 17:22 |  | 162 | 2014-12-12 17:22 | 2014-12-28 11:49 |  | 0 | 2014-12-29 11:49 | 2015-01-14 06:15 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 1 | 162 | 0 | 186 | 26.3244 |  | 354.2608 | [15 empty] | I
Project-A11 |  | 0.57517 | 0.82113 |  |  |  | 2014-01-01 |  | 35 | 2014-02-06 | 2014-05-26 12:48 |  | 0 | 2014-05-27 12:48 | 2014-09-01 23:02 |  | 0 | 2014-09-02 23:02 | 2014-09-29 05:56 |  | 365 | 2015-09-30 05:56 | 2015-10-26 12:51 |  | 0 | 2015-10-27 12:51 | 2015-11-22 19:46 |  | 0 | 2015-11-23 19:46 | 2015-12-20 02:40 |  | v002 |  | 0.08871 |  | 35 | 0 | 0 | 365 | 0 | 0 | 400 | 46.5726 |  | 682.1114 | [15 empty] | S
Project-A12 |  | 0.63527 | 1.2099 |  |  |  | 2014-01-01 |  | 46 | 2014-02-17 | 2014-05-30 07:39 |  | 0 | 2014-05-31 07:39 | 2014-08-14 12:45 |  | 0 | 2014-08-15 12:45 | 2014-09-09 02:06 |  | 0 | 2014-09-10 02:06 | 2014-10-04 15:28 |  | 25 | 2014-10-30 15:28 | 2014-11-24 04:49 |  | 0 | 2014-11-25 04:49 | 2014-12-19 18:10 |  | v004 |  | 0.096774 |  | 46 | 0 | 0 | 0 | 25 | 0 | 71 | 66.7742 |  | 305.7571
Project-A13 |  | 0.54895 | 2.0281 |  |  |  | 2014-01-01 |  | 58 | 2014-03-01 | 2014-08-22 21:04 |  | 0 | 2014-08-23 21:04 | 2014-10-04 20:22 |  | 0 | 2014-10-05 20:22 | 2014-11-16 19:39 |  | 4 | 2014-11-21 19:39 | 2015-01-02 18:57 |  | 0 | 2015-01-03 18:57 | 2015-02-14 18:15 |  | 0 | 2015-02-15 18:15 | 2015-03-29 17:33 |  | v007 |  | 0.084367 |  | 58 | 0 | 0 | 4 | 0 | 0 | 62 | 73.3995 |  | 393.7311 | [15 empty] | W
Project-A14 |  | 0.50481 | 2.1934 |  |  |  | 2014-01-01 |  | 76 | 2014-03-19 | 2014-06-04 06:10 |  | 0 | 2014-06-05 06:10 | 2014-06-29 10:06 |  | 0 | 2014-06-30 10:06 | 2014-07-18 23:06 |  | 0 | 2014-07-19 23:06 | 2014-08-07 12:06 |  | 0 | 2014-08-08 12:06 | 2014-08-27 01:06 |  | 0 | 2014-08-28 01:06 | 2014-09-15 14:06 |  | v006 |  | 0.057072 |  | 76 | 0 | 0 | 0 | 0 | 0 | 76 | 65.062 |  | 180.5875 | [15 empty] | O
Project-A15 |  | 1.0065 | 0.25061 |  |  |  | 2014-01-01 |  | 98 | 2014-04-10 | 2014-07-13 19:25 |  | 0 | 2014-07-14 19:25 | 2015-08-13 20:19 |  | 0 | 2015-08-14 20:19 | 2015-11-17 15:44 |  | 0 | 2015-11-18 15:44 | 2016-02-21 11:09 |  | 0 | 2016-02-22 11:09 | 2016-05-27 06:34 |  | 0 | 2016-05-28 06:34 | 2016-08-31 01:59 |  | v008 |  | 0.10608 |  | 98 | 0 | 0 | 0 | 0 | 0 | 98 | 155.9367 |  | 874.0828 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 61.2 |  |  |  | 0 |  |  |  | 0 |  |  |  | 51.2667 |  |  |  | 12.4667 |  |  |  | 0 | [5 empty] | 0.066667 |  | 61.2 | 0 | 0 | 51.2667 | 12.4667 | 0 | 124.9333 | 80.8139 | Average | 377.694 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 918 |  |  |  | 0 |  |  |  | 0 |  |  |  | 769 |  |  |  | 187 |  |  |  | 0 | [5 empty] | 1 |  | 918 | 0 | 0 | 769 | 187 | 0 | 1874 | 1212.2084 | Total | 5665.4107 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 3
| Days: | 25.8627
E
N
SIT - Violation | Count: | 3 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 25.8627
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-04-24 21:16 | 2014-05-07 06:05 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-29 14:27 | 2014-04-05 03:32 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-20 21:46 | 2014-02-28 03:47 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-09 13:30 | 2014-05-27 11:28 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2015-03-02 12:55 | 2015-05-14 14:39 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-15 20:13 | 2014-08-09 18:42 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.1202 | 0
Project-A07 | 2016-03-31 01:06 | 2016-06-26 12:55 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-21 13:25 | 2014-01-24 05:55 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-23 10:12 | 2014-07-17 00:50 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 16.6143 | 0 | R
Project-A10 | 2014-05-30 04:29 | 2014-06-14 22:56 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-09-02 23:02 | 2014-09-29 05:56 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 6.1281 | 0 | 0 | 0 | S
Project-A12 | 2014-08-15 12:45 | 2014-09-09 02:06 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-05 20:22 | 2014-11-16 19:39 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-30 10:06 | 2014-07-18 23:06 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2015-08-14 20:19 | 2015-11-17 15:44 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-05-08 06:05 | 2015-05-20 14:53 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-06 03:32 | 2014-04-12 16:38 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-01 03:47 | 2014-03-08 09:48 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-28 11:28 | 2014-06-15 09:27 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-05-26 14:39 | 2015-08-07 16:23 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-10 18:42 | 2014-09-04 17:12 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-06-27 12:55 | 2016-09-23 00:45 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-25 05:55 | 2014-01-27 22:24 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-10 00:50 | 2014-09-02 15:29 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-16 22:56 | 2014-07-02 17:22 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-09-30 05:56 | 2015-10-26 12:51 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-10 02:06 | 2014-10-04 15:28 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-11-21 19:39 | 2015-01-02 18:57 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-19 23:06 | 2014-08-07 12:06 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-11-18 15:44 | 2016-02-21 11:09 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-05-21 14:53 | 2015-06-02 23:42 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-13 16:38 | 2014-04-20 05:44 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-09 09:48 | 2014-03-16 15:49 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-16 09:27 | 2014-07-04 07:25 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-08-08 16:23 | 2015-10-20 18:06 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-05 17:12 | 2014-09-30 15:41 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-09-24 00:45 | 2016-12-20 12:35 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-28 22:24 | 2014-01-31 14:54 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-09-03 15:29 | 2014-09-27 06:08 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-12-12 17:22 | 2014-12-28 11:49 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-10-27 12:51 | 2015-11-22 19:46 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-30 15:28 | 2014-11-24 04:49 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-03 18:57 | 2015-02-14 18:15 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-08 12:06 | 2014-08-27 01:06 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-02-22 11:09 | 2016-05-27 06:34 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-06-03 23:42 | 2015-06-16 08:30 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-21 05:44 | 2014-04-27 18:49 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-17 15:49 | 2014-03-24 21:50 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-07-05 07:25 | 2014-07-23 05:23 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-10-21 18:06 | 2016-01-02 19:50 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-10-01 15:41 | 2014-10-26 14:11 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-12-21 12:35 | 2017-03-19 00:24 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-02-01 14:54 | 2014-02-04 07:24 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-09-28 06:08 | 2014-10-21 20:47 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-12-29 11:49 | 2015-01-14 06:15 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-11-23 19:46 | 2015-12-20 02:40 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-25 04:49 | 2014-12-19 18:10 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-02-15 18:15 | 2015-03-29 17:33 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-28 01:06 | 2014-09-15 14:06 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-05-28 06:34 | 2016-08-31 01:59 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.46134 | 46.1341 | 46
0.032047 | 3.2047 | 3
0.42083 | 42.0829 | 42
0.127 | 12.6998 | 12
0.84456 | 84.4557 | 84
0.26962 | 26.9616 | 26
0.22428 | 22.4283 | 22
0.076194 | 7.6194 | 7
0.96062 | 96.0617 | 96
0.80568 | 80.5684 | 80
0.72371 | 72.3705 | 72
0.72153 | 72.1526 | 72
0.37463 | 37.4629 | 37
0.32485 | 32.4845 | 32
0.54477 | 54.4771 | 54
0.40374 | 40.3744 | 40
0.34224 | 34.2241 | 34
0.41183 | 41.1825 | 41
0.78021 | 78.0209 | 78
0.58752 | 58.7524 | 58
0.71403 | 71.4033 | 71
0.39191 | 39.1908 | 39
0.22312 | 22.3124 | 22
0.56749 | 56.7488 | 56
0.0088933 | 0.88933 | 0
0.69751 | 69.7513 | 69
0.9587 | 95.8699 | 95
0.40558 | 40.5576 | 40
0.087913 | 8.7913 | 8
0.65181 | 65.1815 | 65
0.76546 | 76.5457 | 76
0.53709 | 53.7093 | 53
0.3174 | 31.74 | 31
0.65528 | 65.5279 | 65
0.20381 | 20.3807 | 20
0.29453 | 29.4529 | 29
0.56001 | 56.0005 | 56
0.20164 | 20.1643 | 20
0.63293 | 63.2934 | 63

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 2923.6596 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.9 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH