## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.49369 | 0.26086 |  |  |  | 17 | 17.76 | 34.76 | 68.0831 |  | 4.08 | 74 | 78.08 | 283.6796 |  | 4.08 | 17.76 | 21.84 | 68.0831 |  | 4.08 | 17.76 | 21.84 | 68.0831 |  | 4.08 | 17.76 | 21.84 | 68.0831 |  | 4.08 | 17.76 | 21.84 | 68.0831 |  | 200.2 | 624.095 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 75.7558 | 624.095 | 624.095
Project-A02 |  | v002 |  | 0.48067 | 2.0705 |  |  |  | 15 | 19.2 | 34.2 | 31.2065 |  | 3.6 | 80 | 83.6 | 38.6385 |  | 3.6 | 19.2 | 22.8 | 9.2732 |  | 3.6 | 19.2 | 22.8 | 9.2732 |  | 3.6 | 19.2 | 22.8 | 9.2732 |  | 3.6 | 19.2 | 22.8 | 9.2732 |  | 209 | 106.938 | 104500 |  | 0.058933 |  | 33 | 176 |  | 68.6544 | 85.0047 | 85.0047 | [12 empty] | E
Project-A03 |  | v003 |  | 0.48311 | 2.6609 |  |  |  | 16 | 6.48 | 22.48 | 33.1184 |  | 3.84 | 27 | 30.84 | 10.147 |  | 3.84 | 6.48 | 10.32 | 7.9484 |  | 3.84 | 6.48 | 10.32 | 7.9484 |  | 3.84 | 6.48 | 10.32 | 7.9484 |  | 3.84 | 6.48 | 10.32 | 7.9484 |  | 94.6 | 75.0591 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 72.8605 | 22.3233 | 72.8605 | [12 empty] | N
Project-A04 |  | v004 |  | 0.61201 | 1.629 |  |  |  | 35 | 4.32 | 39.32 | 57.1891 |  | 8.4 | 18 | 26.4 | 13.7254 |  | 8.4 | 4.32 | 12.72 | 13.7254 |  | 8.4 | 4.32 | 12.72 | 13.7254 |  | 8.4 | 4.32 | 12.72 | 13.7254 |  | 8.4 | 4.32 | 12.72 | 13.7254 |  | 116.6 | 125.816 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 125.816 | 24.3094 | 125.816 | [12 empty] | D
Project-A05 |  | v002 |  | 0.48431 | 0.25487 |  |  |  | 6 | 19.2 | 25.2 | 75.3324 |  | 1.44 | 80 | 81.44 | 313.8849 |  | 1.44 | 19.2 | 20.64 | 75.3324 |  | 1.44 | 19.2 | 20.64 | 75.3324 |  | 1.44 | 19.2 | 20.64 | 75.3324 |  | 1.44 | 19.2 | 20.64 | 75.3324 |  | 189.2 | 690.5469 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 27.2553 | 690.5469 | 690.5469
Project-A06 |  | v003 |  | 0.48295 | 1.7372 |  |  |  | 52 | 10.56 | 62.56 | 107.6727 |  | 12.48 | 44 | 56.48 | 25.8414 |  | 12.48 | 10.56 | 23.04 | 25.8414 |  | 12.48 | 10.56 | 23.04 | 25.8414 |  | 12.48 | 10.56 | 23.04 | 25.8414 |  | 12.48 | 10.56 | 23.04 | 25.8414 |  | 211.2 | 236.8799 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 236.8799 | 55.7208 | 236.8799 | [12 empty] | O
Project-A07 |  | v005 |  | 0.47748 | 0.25918 |  |  |  | 93 | 19.92 | 112.92 | 194.7715 |  | 22.32 | 83 | 105.32 | 320.2391 |  | 22.32 | 19.92 | 42.24 | 76.8574 |  | 22.32 | 19.92 | 42.24 | 76.8574 |  | 22.32 | 19.92 | 42.24 | 76.8574 |  | 22.32 | 19.92 | 42.24 | 76.8574 |  | 387.2 | 822.4402 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 428.4972 | 704.5261 | 704.5261 | [12 empty] | F
Project-A08 |  | v006 |  | 0.47665 | 1.39 |  |  |  | 5 | 2.64 | 7.64 | 10.4899 |  | 1.2 | 11 | 12.2 | 7.9139 |  | 1.2 | 2.64 | 3.84 | 2.5176 |  | 1.2 | 2.64 | 3.84 | 2.5176 |  | 1.2 | 2.64 | 3.84 | 2.5176 |  | 1.2 | 2.64 | 3.84 | 2.5176 |  | 35.2 | 28.4741 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 23.0778 | 17.4106 | 23.0778
Project-A09 |  | v003 |  | 0.49768 | 3.1622 |  |  |  | 49 | 20.64 | 69.64 | 98.4563 |  | 11.76 | 86 | 97.76 | 27.196 |  | 11.76 | 20.64 | 32.4 | 23.6295 |  | 11.76 | 20.64 | 32.4 | 23.6295 |  | 11.76 | 20.64 | 32.4 | 23.6295 |  | 11.76 | 20.64 | 32.4 | 23.6295 |  | 297 | 220.1703 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 216.6038 | 59.8312 | 216.6038 | [12 empty] | T
Project-A10 |  | v001 |  | 0.47573 | 1.462 |  |  |  | 36 | 20.88 | 56.88 | 75.6732 |  | 8.64 | 87 | 95.64 | 59.5086 |  | 8.64 | 20.88 | 29.52 | 18.1616 |  | 8.64 | 20.88 | 29.52 | 18.1616 |  | 8.64 | 20.88 | 29.52 | 18.1616 |  | 8.64 | 20.88 | 29.52 | 18.1616 |  | 270.6 | 207.828 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 166.481 | 130.9189 | 166.481 | [12 empty] | H
Project-A11 |  | v002 |  | 0.4841 | 1.4672 |  |  |  | 63 | 19.2 | 82.2 | 130.1387 |  | 15.12 | 80 | 95.12 | 54.5261 |  | 15.12 | 19.2 | 34.32 | 31.2333 |  | 15.12 | 19.2 | 34.32 | 31.2333 |  | 15.12 | 19.2 | 34.32 | 31.2333 |  | 15.12 | 19.2 | 34.32 | 31.2333 |  | 314.6 | 309.598 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 286.3052 | 119.9574 | 286.3052 | [12 empty] | I
Project-A12 |  | v004 |  | 0.50162 | 1.5533 |  |  |  | 65 | 21.84 | 86.84 | 129.5814 |  | 15.6 | 91 | 106.6 | 58.5835 |  | 15.6 | 21.84 | 37.44 | 31.0995 |  | 15.6 | 21.84 | 37.44 | 31.0995 |  | 15.6 | 21.84 | 37.44 | 31.0995 |  | 15.6 | 21.84 | 37.44 | 31.0995 |  | 343.2 | 312.563 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 285.079 | 128.8838 | 285.079 | [12 empty] | S
Project-A13 |  | v007 |  | 0.48035 | 2.0795 |  |  |  | 96 | 9.6 | 105.6 | 199.855 |  | 23.04 | 40 | 63.04 | 47.9652 |  | 23.04 | 9.6 | 32.64 | 47.9652 |  | 23.04 | 9.6 | 32.64 | 47.9652 |  | 23.04 | 9.6 | 32.64 | 47.9652 |  | 23.04 | 9.6 | 32.64 | 47.9652 |  | 299.2 | 439.681 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 439.681 | 42.3174 | 439.681
Project-A14 |  | v006 |  | 0.49359 | 2.0521 |  |  |  | 39 | 12.72 | 51.72 | 79.0126 |  | 9.36 | 53 | 62.36 | 25.8271 |  | 9.36 | 12.72 | 22.08 | 18.963 |  | 9.36 | 12.72 | 22.08 | 18.963 |  | 9.36 | 12.72 | 22.08 | 18.963 |  | 9.36 | 12.72 | 22.08 | 18.963 |  | 202.4 | 180.6918 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 173.8278 | 56.8196 | 173.8278 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0761 | 1.9612 |  |  |  | 72 | 23.76 | 95.76 | 66.9104 |  | 17.28 | 99 | 116.28 | 50.48 |  | 17.28 | 23.76 | 41.04 | 16.0585 |  | 17.28 | 23.76 | 41.04 | 16.0585 |  | 17.28 | 23.76 | 41.04 | 16.0585 |  | 17.28 | 23.76 | 41.04 | 16.0585 |  | 376.2 | 181.6244 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 147.2029 | 111.056 | 147.2029 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 90.4994 |  | 10.544 | 63.5333 | 74.0773 | 89.2104 |  | 10.544 | 15.248 | 25.792 | 31.1126 |  | 10.544 | 15.248 | 25.792 | 31.1126 |  | 10.544 | 15.248 | 25.792 | 31.1126 |  | 10.544 | 15.248 | 25.792 | 31.1126 |  | 236.4267 | 304.1604 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 184.9318 | 191.5814 | 285.1992 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1357.4911 |  | 158.16 | 953 | 1111.16 | 1338.1564 |  | 158.16 | 228.72 | 386.88 | 466.6896 |  | 158.16 | 228.72 | 386.88 | 466.6896 |  | 158.16 | 228.72 | 386.88 | 466.6896 |  | 158.16 | 228.72 | 386.88 | 466.6896 |  | 3546.4 | 4562.4057 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2773.9775 | 2873.7211 | 4277.9876 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 827.4402 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 358.1604 |  | <- To shorten average individual project span |  |  |  | <----------> | 285.1992
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 35.2605 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 2337.0375 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 3557.8986 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.49369 | 0.26086 |  |  |  | 2014-01-01 |  | 8 | 2014-01-10 | 2014-03-19 02:00 |  | 0 | 2014-03-20 02:00 | 2014-12-28 18:18 |  | 0 | 2014-12-29 18:18 | 2015-03-07 20:18 |  | 0 | 2015-03-08 20:18 | 2015-05-15 22:18 |  | 0 | 2015-05-16 22:18 | 2015-07-24 00:17 |  | 0 | 2015-07-25 00:17 | 2015-10-01 02:17 |  | v001 |  | 0.056452 |  | 8 | 0 | 0 | 0 | 0 | 0 | 8 | 6.7742 |  | 629.095 | 827.4402 | [14 empty] | E
Project-A02 |  | 0.48067 | 2.0705 |  |  |  | 2014-01-01 |  | 14 | 2014-01-16 | 2014-02-16 04:57 |  | 0 | 2014-02-17 04:57 | 2014-03-27 20:17 |  | 0 | 2014-03-28 20:17 | 2014-04-07 02:50 |  | 0 | 2014-04-08 02:50 | 2014-04-17 09:24 |  | 0 | 2014-04-18 09:24 | 2014-04-27 15:57 |  | 0 | 2014-04-28 15:57 | 2014-05-07 22:31 |  | v002 |  | 0.058933 |  | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 12.3759 |  | 111.938 | [15 empty] | N
Project-A03 |  | 0.48311 | 2.6609 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-04 02:51 |  | 0 | 2014-02-05 02:51 | 2014-02-15 06:22 |  | 0 | 2014-02-16 06:22 | 2014-02-24 05:08 |  | 0 | 2014-02-25 05:08 | 2014-03-05 03:54 |  | 0 | 2014-03-06 03:54 | 2014-03-14 02:39 |  | 0 | 2014-03-15 02:39 | 2014-03-23 01:25 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80.0591 | [15 empty] | D
Project-A04 |  | 0.61201 | 1.629 |  |  |  | 2014-01-01 |  | 44 | 2014-02-15 | 2014-04-13 04:32 |  | 0 | 2014-04-14 04:32 | 2014-04-27 21:57 |  | 0 | 2014-04-28 21:57 | 2014-05-12 15:21 |  | 0 | 2014-05-13 15:21 | 2014-05-27 08:46 |  | 0 | 2014-05-28 08:46 | 2014-06-11 02:10 |  | 0 | 2014-06-12 02:10 | 2014-06-25 19:35 |  | v004 |  | 0.032878 |  | 44 | 0 | 0 | 0 | 0 | 0 | 44 | 21.6998 |  | 130.816
Project-A05 |  | 0.48431 | 0.25487 |  |  |  | 2014-01-01 |  | 41 | 2014-02-12 | 2014-04-28 07:59 |  | 0 | 2014-04-29 07:59 | 2015-03-09 05:13 |  | 0 | 2015-03-10 05:13 | 2015-05-24 13:12 |  | 0 | 2015-05-25 13:12 | 2015-08-08 21:10 |  | 0 | 2015-08-09 21:10 | 2015-10-24 05:09 |  | 0 | 2015-10-25 05:09 | 2016-01-08 13:07 |  | v002 |  | 0.05335 |  | 41 | 0 | 0 | 0 | 0 | 0 | 41 | 32.8102 |  | 695.5469 | [15 empty] | O
Project-A06 |  | 0.48295 | 1.7372 |  |  |  | 2014-01-01 |  | 65 | 2014-03-08 | 2014-06-23 16:09 |  | 0 | 2014-06-24 16:09 | 2014-07-20 12:20 |  | 0 | 2014-07-21 12:20 | 2014-08-16 08:32 |  | 3 | 2014-08-20 08:32 | 2014-09-15 04:44 |  | 0 | 2014-09-16 04:44 | 2014-10-12 00:55 |  | 0 | 2014-10-13 00:55 | 2014-11-07 21:07 |  | v003 |  | 0.059553 |  | 65 | 0 | 0 | 3 | 0 | 0 | 68 | 58.0645 |  | 244.8799 | [15 empty] | F
Project-A07 |  | 0.47748 | 0.25918 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-07-15 18:31 |  | 0 | 2014-07-16 18:31 | 2015-06-02 00:15 |  | 0 | 2015-06-03 00:15 | 2015-08-18 20:50 |  | 0 | 2015-08-19 20:50 | 2015-11-04 17:25 |  | 0 | 2015-11-05 17:25 | 2016-01-21 13:59 |  | 0 | 2016-01-22 13:59 | 2016-04-08 10:34 |  | v005 |  | 0.10918 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 827.4402
Project-A08 |  | 0.47665 | 1.39 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-12 11:45 |  | 0 | 2014-01-13 11:45 | 2014-01-21 09:41 |  | 0 | 2014-01-22 09:41 | 2014-01-24 22:07 |  | 0 | 2014-01-25 22:07 | 2014-01-28 10:32 |  | 0 | 2014-01-29 10:32 | 2014-01-31 22:57 |  | 0 | 2014-02-01 22:57 | 2014-02-04 11:23 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 33.4741 | [15 empty] | T
Project-A09 |  | 0.49768 | 3.1622 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-04-10 10:57 |  | 0 | 2014-04-11 10:57 | 2014-05-08 15:39 |  | 0 | 2014-05-09 15:39 | 2014-06-02 06:46 |  | 0 | 2014-06-03 06:46 | 2014-06-26 21:52 |  | 0 | 2014-06-27 21:52 | 2014-07-21 12:59 |  | 0 | 2014-07-22 12:59 | 2014-08-15 04:05 |  | v003 |  | 0.083747 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 225.1703 | [15 empty] | H
Project-A10 |  | 0.47573 | 1.462 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-04-10 16:09 |  | 0 | 2014-04-11 16:09 | 2014-06-10 04:22 |  | 0 | 2014-06-11 04:22 | 2014-06-29 08:14 |  | 1 | 2014-07-01 08:14 | 2014-07-19 12:07 |  | 357 | 2015-07-12 12:07 | 2015-07-30 16:00 |  | 0 | 2015-07-31 16:00 | 2015-08-18 19:52 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 1 | 357 | 0 | 381 | 26.3244 |  | 570.828 | [15 empty] | I
Project-A11 |  | 0.4841 | 1.4672 |  |  |  | 2014-01-01 |  | 31 | 2014-02-02 | 2014-06-12 03:20 |  | 0 | 2014-06-13 03:20 | 2014-08-06 15:57 |  | 0 | 2014-08-07 15:57 | 2014-09-07 21:33 |  | 6 | 2014-09-14 21:33 | 2014-10-16 03:09 |  | 353 | 2015-10-05 03:09 | 2015-11-05 08:45 |  | 0 | 2015-11-06 08:45 | 2015-12-07 14:21 |  | v002 |  | 0.08871 |  | 31 | 0 | 0 | 6 | 353 | 0 | 390 | 41.25 |  | 673.598 | [15 empty] | S
Project-A12 |  | 0.50162 | 1.5533 |  |  |  | 2014-01-01 |  | 53 | 2014-02-24 | 2014-07-03 13:57 |  | 0 | 2014-07-04 13:57 | 2014-09-01 03:57 |  | 0 | 2014-09-02 03:57 | 2014-10-03 06:21 |  | 9 | 2014-10-13 06:21 | 2014-11-13 08:44 |  | 0 | 2014-11-14 08:44 | 2014-12-15 11:07 |  | 0 | 2014-12-16 11:07 | 2015-01-16 13:31 |  | v004 |  | 0.096774 |  | 53 | 0 | 0 | 9 | 0 | 0 | 62 | 76.9355 |  | 326.563
Project-A13 |  | 0.48035 | 2.0795 |  |  |  | 2014-01-01 |  | 64 | 2014-03-07 | 2014-09-22 20:31 |  | 0 | 2014-09-23 20:31 | 2014-11-10 19:41 |  | 0 | 2014-11-11 19:41 | 2014-12-29 18:51 |  | 0 | 2014-12-30 18:51 | 2015-02-16 18:01 |  | 0 | 2015-02-17 18:01 | 2015-04-06 17:11 |  | 0 | 2015-04-07 17:11 | 2015-05-25 16:21 |  | v007 |  | 0.084367 |  | 64 | 0 | 0 | 0 | 0 | 0 | 64 | 80.9926 |  | 444.681 | [15 empty] | W
Project-A14 |  | 0.49359 | 2.0521 |  |  |  | 2014-01-01 |  | 63 | 2014-03-06 | 2014-05-24 00:18 |  | 0 | 2014-05-25 00:18 | 2014-06-19 20:09 |  | 0 | 2014-06-20 20:09 | 2014-07-09 19:16 |  | 0 | 2014-07-10 19:16 | 2014-07-29 18:23 |  | 0 | 2014-07-30 18:23 | 2014-08-18 17:29 |  | 0 | 2014-08-19 17:29 | 2014-09-07 16:36 |  | v006 |  | 0.057072 |  | 63 | 0 | 0 | 0 | 0 | 0 | 63 | 53.933 |  | 185.6918 | [15 empty] | O
Project-A15 |  | 1.0761 | 1.9612 |  |  |  | 2014-01-01 |  | 74 | 2014-03-17 | 2014-05-22 21:51 |  | 0 | 2014-05-23 21:51 | 2014-07-13 09:22 |  | 0 | 2014-07-14 09:22 | 2014-07-30 10:46 |  | 0 | 2014-07-31 10:46 | 2014-08-16 12:11 |  | 6 | 2014-08-23 12:11 | 2014-09-08 13:35 |  | 0 | 2014-09-09 13:35 | 2014-09-25 14:59 |  | v008 |  | 0.10608 |  | 74 | 0 | 0 | 0 | 6 | 0 | 80 | 117.7481 |  | 192.6244 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 32 |  |  |  | 0 |  |  |  | 0 |  |  |  | 1.2667 |  |  |  | 47.7333 |  |  |  | 0 | [5 empty] | 0.066667 |  | 32 | 0 | 0 | 1.2667 | 47.7333 | 0 | 81 | 35.2605 | Average | 358.1604 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 480 |  |  |  | 0 |  |  |  | 0 |  |  |  | 19 |  |  |  | 716 |  |  |  | 0 | [5 empty] | 1 |  | 480 | 0 | 0 | 19 | 716 | 0 | 1215 | 528.9082 | Total | 5372.4057 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 9
| Days: | 46.7408
E
N
SIT - Violation | Count: | 6 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 34.8727
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-12-29 18:18 | 2015-03-07 20:18 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.022747 | 0 | 0
Project-A02 | 2014-03-28 20:17 | 2014-04-07 02:50 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-16 06:22 | 2014-02-24 05:08 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-04-28 21:57 | 2014-05-12 15:21 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 2.9876 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2015-03-10 05:13 | 2015-05-24 13:12 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-21 12:20 | 2014-08-16 08:32 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 8.6908 | 0 | 0 | 0 | 8.9348
Project-A07 | 2015-06-03 00:15 | 2015-08-18 20:50 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-22 09:41 | 2014-01-24 22:07 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-05-09 15:39 | 2014-06-02 06:46 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-06-11 04:22 | 2014-06-29 08:14 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 8.5036 | 0 | K
Project-A11 | 2014-08-07 15:57 | 2014-09-07 21:33 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 5.7332 | 0 | 0 | 0 | S
Project-A12 | 2014-09-02 03:57 | 2014-10-03 06:21 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-11-11 19:41 | 2014-12-29 18:51 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-20 20:09 | 2014-07-09 19:16 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-14 09:22 | 2014-07-30 10:46 | v008 | [31 empty] | T
UAT - Violation | Count: | 3 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 11.8681
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-03-08 20:18 | 2015-05-15 22:18 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-08 02:50 | 2014-04-17 09:24 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-25 05:08 | 2014-03-05 03:54 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-13 15:21 | 2014-05-27 08:46 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-05-25 13:12 | 2015-08-08 21:10 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-20 08:32 | 2014-09-15 04:44 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0.29895 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-19 20:50 | 2015-11-04 17:25 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-25 22:07 | 2014-01-28 10:32 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-06-03 06:46 | 2014-06-26 21:52 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-01 08:14 | 2014-07-19 12:07 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 8.7022 | 0
Project-A11 | 2014-09-14 21:33 | 2014-10-16 03:09 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 2.867 | 0 | 0 | 0
Project-A12 | 2014-10-13 06:21 | 2014-11-13 08:44 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-30 18:51 | 2015-02-16 18:01 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-10 19:16 | 2014-07-29 18:23 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-07-31 10:46 | 2014-08-16 12:11 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-05-16 22:18 | 2015-07-24 00:17 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-18 09:24 | 2014-04-27 15:57 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-06 03:54 | 2014-03-14 02:39 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-28 08:46 | 2014-06-11 02:10 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-08-09 21:10 | 2015-10-24 05:09 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-16 04:44 | 2014-10-12 00:55 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-11-05 17:25 | 2016-01-21 13:59 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-29 10:32 | 2014-01-31 22:57 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-06-27 21:52 | 2014-07-21 12:59 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-07-12 12:07 | 2015-07-30 16:00 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-10-05 03:09 | 2015-11-05 08:45 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-14 08:44 | 2014-12-15 11:07 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-02-17 18:01 | 2015-04-06 17:11 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-30 18:23 | 2014-08-18 17:29 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-23 12:11 | 2014-09-08 13:35 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-07-25 00:17 | 2015-10-01 02:17 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-28 15:57 | 2014-05-07 22:31 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-15 02:39 | 2014-03-23 01:25 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-12 02:10 | 2014-06-25 19:35 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-10-25 05:09 | 2016-01-08 13:07 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-10-13 00:55 | 2014-11-07 21:07 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-01-22 13:59 | 2016-04-08 10:34 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-02-01 22:57 | 2014-02-04 11:23 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-22 12:59 | 2014-08-15 04:05 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-07-31 16:00 | 2015-08-18 19:52 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-11-06 08:45 | 2015-12-07 14:21 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-16 11:07 | 2015-01-16 13:31 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-04-07 17:11 | 2015-05-25 16:21 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-19 17:29 | 2014-09-07 16:36 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-09 13:35 | 2014-09-25 14:59 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.53955 | 53.9551 | 53
0.13109 | 13.1087 | 13
0.56687 | 56.6872 | 56
0.18079 | 18.0787 | 18
0.027509 | 2.7509 | 2
0.69481 | 69.4814 | 69
0.77702 | 77.7016 | 77
0.78214 | 78.2138 | 78
0.8584 | 85.8399 | 85
0.25733 | 25.733 | 25
0.78406 | 78.4059 | 78
0.026653 | 2.6653 | 2
0.49055 | 49.055 | 49
0.63555 | 63.5554 | 63
0.11604 | 11.6037 | 11
0.18385 | 18.3847 | 18
0.12166 | 12.1664 | 12
0.25951 | 25.9506 | 25
0.21552 | 21.552 | 21
0.50791 | 50.7905 | 50
0.4314 | 43.1404 | 43
0.10029 | 10.0291 | 10
0.9387 | 93.8696 | 93
0.72948 | 72.948 | 72
0.37416 | 37.4156 | 37
0.081645 | 8.1645 | 8
0.75279 | 75.2789 | 75
0.42276 | 42.2756 | 42
0.34372 | 34.3717 | 34
0.77157 | 77.1568 | 77
0.43881 | 43.881 | 43
0.53141 | 53.1409 | 53
0.61274 | 61.2738 | 61
0.17514 | 17.5141 | 17
0.96105 | 96.1053 | 96
0.93452 | 93.4521 | 93
0.22666 | 22.6658 | 22
0.66455 | 66.4546 | 66
0.59393 | 59.3927 | 59

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 3557.8986 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.9 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH