## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.5005 | 1.5336 |  |  |  | 17 | 17.76 | 34.76 | 33.9664 |  | 4.08 | 74 | 78.08 | 48.2533 |  | 4.08 | 17.76 | 21.84 | 11.5808 |  | 4.08 | 17.76 | 21.84 | 11.5808 |  | 4.08 | 17.76 | 21.84 | 11.5808 |  | 4.08 | 17.76 | 21.84 | 11.5808 |  | 200.2 | 128.5429 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 74.726 | 106.1573 | 106.1573
Project-A02 |  | v002 |  | 0.49997 | 3.2566 |  |  |  | 15 | 19.2 | 34.2 | 30.0015 |  | 3.6 | 80 | 83.6 | 24.5655 |  | 3.6 | 19.2 | 22.8 | 7.2004 |  | 3.6 | 19.2 | 22.8 | 7.2004 |  | 3.6 | 19.2 | 22.8 | 7.2004 |  | 3.6 | 19.2 | 22.8 | 7.2004 |  | 209 | 83.3684 | 104500 |  | 0.058933 |  | 33 | 176 |  | 66.0033 | 54.044 | 66.0033 | [12 empty] | E
Project-A03 |  | v003 |  | 0.50005 | 4.9999 |  |  |  | 16 | 6.48 | 22.48 | 31.997 |  | 3.84 | 27 | 30.84 | 7.6793 |  | 3.84 | 6.48 | 10.32 | 7.6793 |  | 3.84 | 6.48 | 10.32 | 7.6793 |  | 3.84 | 6.48 | 10.32 | 7.6793 |  | 3.84 | 6.48 | 10.32 | 7.6793 |  | 94.6 | 70.3934 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 70.3934 | 11.8802 | 70.3934 | [12 empty] | N
Project-A04 |  | v004 |  | 0.50001 | 0.25002 |  |  |  | 35 | 4.32 | 39.32 | 69.9991 |  | 8.4 | 18 | 26.4 | 71.9955 |  | 8.4 | 4.32 | 12.72 | 17.2789 |  | 8.4 | 4.32 | 12.72 | 17.2789 |  | 8.4 | 4.32 | 12.72 | 17.2789 |  | 8.4 | 4.32 | 12.72 | 17.2789 |  | 116.6 | 211.1103 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 153.9981 | 158.3901 | 158.3901 | [12 empty] | D
Project-A05 |  | v002 |  | 0.5 | 1.491 |  |  |  | 6 | 19.2 | 25.2 | 12.8776 |  | 1.44 | 80 | 81.44 | 53.6566 |  | 1.44 | 19.2 | 20.64 | 12.8776 |  | 1.44 | 19.2 | 20.64 | 12.8776 |  | 1.44 | 19.2 | 20.64 | 12.8776 |  | 1.44 | 19.2 | 20.64 | 12.8776 |  | 189.2 | 118.0445 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 26.3997 | 118.0445 | 118.0445
Project-A06 |  | v003 |  | 0.50001 | 1.4997 |  |  |  | 52 | 10.56 | 62.56 | 103.9979 |  | 12.48 | 44 | 56.48 | 29.3396 |  | 12.48 | 10.56 | 23.04 | 24.9595 |  | 12.48 | 10.56 | 23.04 | 24.9595 |  | 12.48 | 10.56 | 23.04 | 24.9595 |  | 12.48 | 10.56 | 23.04 | 24.9595 |  | 211.2 | 233.1755 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 228.7954 | 64.5472 | 228.7954 | [12 empty] | O
Project-A07 |  | v005 |  | 0.49984 | 0.25197 |  |  |  | 93 | 19.92 | 112.92 | 186.0579 |  | 22.32 | 83 | 105.32 | 329.4089 |  | 22.32 | 19.92 | 42.24 | 79.0581 |  | 22.32 | 19.92 | 42.24 | 79.0581 |  | 22.32 | 19.92 | 42.24 | 79.0581 |  | 22.32 | 19.92 | 42.24 | 79.0581 |  | 387.2 | 831.6994 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 409.3273 | 724.6997 | 724.6997 | [12 empty] | F
Project-A08 |  | v006 |  | 0.5 | 1.4996 |  |  |  | 5 | 2.64 | 7.64 | 10 |  | 1.2 | 11 | 12.2 | 7.3352 |  | 1.2 | 2.64 | 3.84 | 2.4 |  | 1.2 | 2.64 | 3.84 | 2.4 |  | 1.2 | 2.64 | 3.84 | 2.4 |  | 1.2 | 2.64 | 3.84 | 2.4 |  | 35.2 | 26.9353 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 22.0001 | 16.1375 | 22.0001
Project-A09 |  | v003 |  | 0.49978 | 0.25001 |  |  |  | 49 | 20.64 | 69.64 | 98.0441 |  | 11.76 | 86 | 97.76 | 343.9851 |  | 11.76 | 20.64 | 32.4 | 82.5564 |  | 11.76 | 20.64 | 32.4 | 82.5564 |  | 11.76 | 20.64 | 32.4 | 82.5564 |  | 11.76 | 20.64 | 32.4 | 82.5564 |  | 297 | 772.2549 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 215.697 | 756.7672 | 756.7672 | [12 empty] | T
Project-A10 |  | v001 |  | 0.50005 | 1.6073 |  |  |  | 36 | 20.88 | 56.88 | 71.9921 |  | 8.64 | 87 | 95.64 | 54.1278 |  | 8.64 | 20.88 | 29.52 | 17.2781 |  | 8.64 | 20.88 | 29.52 | 17.2781 |  | 8.64 | 20.88 | 29.52 | 17.2781 |  | 8.64 | 20.88 | 29.52 | 17.2781 |  | 270.6 | 195.2324 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 158.3827 | 119.0812 | 158.3827 | [12 empty] | H
Project-A11 |  | v002 |  | 0.50046 | 1.5546 |  |  |  | 63 | 19.2 | 82.2 | 125.8845 |  | 15.12 | 80 | 95.12 | 51.4611 |  | 15.12 | 19.2 | 34.32 | 30.2123 |  | 15.12 | 19.2 | 34.32 | 30.2123 |  | 15.12 | 19.2 | 34.32 | 30.2123 |  | 15.12 | 19.2 | 34.32 | 30.2123 |  | 314.6 | 298.1948 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 276.946 | 113.2144 | 276.946 | [12 empty] | I
Project-A12 |  | v004 |  | 0.49921 | 1.4958 |  |  |  | 65 | 21.84 | 86.84 | 130.2066 |  | 15.6 | 91 | 106.6 | 60.8389 |  | 15.6 | 21.84 | 37.44 | 31.2496 |  | 15.6 | 21.84 | 37.44 | 31.2496 |  | 15.6 | 21.84 | 37.44 | 31.2496 |  | 15.6 | 21.84 | 37.44 | 31.2496 |  | 343.2 | 316.0438 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 286.4545 | 133.8456 | 286.4545 | [12 empty] | S
Project-A13 |  | v007 |  | 0.50005 | 1.9998 |  |  |  | 96 | 9.6 | 105.6 | 191.98 |  | 23.04 | 40 | 63.04 | 46.0752 |  | 23.04 | 9.6 | 32.64 | 46.0752 |  | 23.04 | 9.6 | 32.64 | 46.0752 |  | 23.04 | 9.6 | 32.64 | 46.0752 |  | 23.04 | 9.6 | 32.64 | 46.0752 |  | 299.2 | 422.3561 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 422.3561 | 44.0037 | 422.3561
Project-A14 |  | v006 |  | 0.49999 | 0.26275 |  |  |  | 39 | 12.72 | 51.72 | 78.0016 |  | 9.36 | 53 | 62.36 | 201.7142 |  | 9.36 | 12.72 | 22.08 | 48.4114 |  | 9.36 | 12.72 | 22.08 | 48.4114 |  | 9.36 | 12.72 | 22.08 | 48.4114 |  | 9.36 | 12.72 | 22.08 | 48.4114 |  | 202.4 | 473.3615 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 171.6036 | 443.7713 | 443.7713 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0001 | 2.0472 |  |  |  | 72 | 23.76 | 95.76 | 71.9941 |  | 17.28 | 99 | 116.28 | 48.3598 |  | 17.28 | 23.76 | 41.04 | 17.2786 |  | 17.28 | 23.76 | 41.04 | 17.2786 |  | 17.28 | 23.76 | 41.04 | 17.2786 |  | 17.28 | 23.76 | 41.04 | 17.2786 |  | 376.2 | 189.4682 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 158.387 | 106.3915 | 158.387 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 83.1334 |  | 10.544 | 63.5333 | 74.0773 | 91.9197 |  | 10.544 | 15.248 | 25.792 | 29.0731 |  | 10.544 | 15.248 | 25.792 | 29.0731 |  | 10.544 | 15.248 | 25.792 | 29.0731 |  | 10.544 | 15.248 | 25.792 | 29.0731 |  | 236.4267 | 291.3454 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 182.7647 | 198.065 | 266.5032 | [12 empty] | S
|  | Total |  | 8 | 23.9997 |  |  |  | 659 | 228.72 | 887.72 | 1247.0005 |  | 158.16 | 953 | 1111.16 | 1378.7961 |  | 158.16 | 228.72 | 386.88 | 436.0962 |  | 158.16 | 228.72 | 386.88 | 436.0962 |  | 158.16 | 228.72 | 386.88 | 436.0962 |  | 158.16 | 228.72 | 386.88 | 436.0962 |  | 3546.4 | 4370.1815 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2741.4702 | 2970.9754 | 3997.5486 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 903.6994 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 296.7454 |  | <- To shorten average individual project span |  |  |  | <----------> | 266.5032
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 59.4392 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 855.6327 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 2115.5168 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.5005 | 1.5336 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-04 23:12 |  | 0 | 2014-02-05 23:12 | 2014-03-26 05:16 |  | 0 | 2014-03-27 05:16 | 2014-04-07 19:13 |  | 0 | 2014-04-08 19:13 | 2014-04-20 09:09 |  | 0 | 2014-04-21 09:09 | 2014-05-02 23:05 |  | 0 | 2014-05-03 23:05 | 2014-05-15 13:02 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 133.5429 | 903.6994 | [14 empty] | E
Project-A02 |  | 0.49997 | 3.2566 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-02-13 00:02 |  | 0 | 2014-02-14 00:02 | 2014-03-10 13:36 |  | 0 | 2014-03-11 13:36 | 2014-03-18 18:25 |  | 0 | 2014-03-19 18:25 | 2014-03-26 23:13 |  | 0 | 2014-03-27 23:13 | 2014-04-04 04:02 |  | 0 | 2014-04-05 04:02 | 2014-04-12 08:51 |  | v002 |  | 0.058933 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 10.6079 |  | 88.3684 | [15 empty] | N
Project-A03 |  | 0.50005 | 4.9999 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-02 23:56 |  | 0 | 2014-02-03 23:56 | 2014-02-11 16:14 |  | 0 | 2014-02-12 16:14 | 2014-02-20 08:32 |  | 0 | 2014-02-21 08:32 | 2014-03-01 00:50 |  | 0 | 2014-03-02 00:50 | 2014-03-09 17:08 |  | 0 | 2014-03-10 17:08 | 2014-03-18 09:26 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 75.3934 | [15 empty] | D
Project-A04 |  | 0.50001 | 0.25002 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-04-15 23:59 |  | 0 | 2014-04-16 23:59 | 2014-06-27 23:52 |  | 0 | 2014-06-28 23:52 | 2014-07-16 06:34 |  | 1 | 2014-07-18 06:34 | 2014-08-04 13:16 |  | 0 | 2014-08-05 13:16 | 2014-08-22 19:57 |  | 0 | 2014-08-23 19:57 | 2014-09-10 02:39 |  | v004 |  | 0.032878 |  | 34 | 0 | 0 | 1 | 0 | 0 | 35 | 16.768 |  | 217.1103
Project-A05 |  | 0.5 | 1.491 |  |  |  | 2014-01-01 |  | 47 | 2014-02-18 | 2014-03-02 21:04 |  | 0 | 2014-03-03 21:04 | 2014-04-26 12:49 |  | 0 | 2014-04-27 12:49 | 2014-05-10 09:53 |  | 0 | 2014-05-11 09:53 | 2014-05-24 06:57 |  | 0 | 2014-05-25 06:57 | 2014-06-07 04:00 |  | 0 | 2014-06-08 04:00 | 2014-06-21 01:04 |  | v002 |  | 0.05335 |  | 47 | 0 | 0 | 0 | 0 | 0 | 47 | 37.6117 |  | 123.0445 | [15 empty] | O
Project-A06 |  | 0.50001 | 1.4997 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-04-15 23:57 |  | 0 | 2015-04-16 23:57 | 2015-05-16 08:06 |  | 0 | 2015-05-17 08:06 | 2015-06-11 07:08 |  | 0 | 2015-06-12 07:08 | 2015-07-07 06:09 |  | 1 | 2015-07-09 06:09 | 2015-08-03 05:11 |  | 0 | 2015-08-04 05:11 | 2015-08-29 04:13 |  | v003 |  | 0.059553 |  | 365 | 0 | 0 | 0 | 1 | 0 | 366 | 326.0546 |  | 239.1755 | [15 empty] | F
Project-A07 |  | 0.49984 | 0.25197 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-09-12 01:23 |  | 0 | 2014-09-13 01:23 | 2015-08-08 11:12 |  | 0 | 2015-08-09 11:12 | 2015-10-27 12:36 |  | 0 | 2015-10-28 12:36 | 2016-01-15 14:00 |  | 0 | 2016-01-16 14:00 | 2016-04-04 15:23 |  | 0 | 2016-04-05 15:23 | 2016-06-23 16:47 |  | v005 |  | 0.10918 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 109.727 |  | 836.6994
Project-A08 |  | 0.5 | 1.4996 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-12 |  | 0 | 2014-01-13 | 2014-01-20 08:03 |  | 0 | 2014-01-21 08:03 | 2014-01-23 17:39 |  | 1 | 2014-01-25 17:39 | 2014-01-28 03:15 |  | 0 | 2014-01-29 03:15 | 2014-01-31 12:51 |  | 0 | 2014-02-01 12:51 | 2014-02-03 22:27 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 0 |  | 32.9353 | [15 empty] | T
Project-A09 |  | 0.49978 | 0.25001 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-04-10 01:04 |  | 0 | 2014-04-11 01:04 | 2015-03-21 00:42 |  | 0 | 2015-03-22 00:42 | 2015-06-12 14:03 |  | 0 | 2015-06-13 14:03 | 2015-09-04 03:25 |  | 0 | 2015-09-05 03:25 | 2015-11-26 16:46 |  | 0 | 2015-11-27 16:46 | 2016-02-18 06:07 |  | v003 |  | 0.083747 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 777.2549 | [15 empty] | H
Project-A10 |  | 0.50005 | 1.6073 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-04-06 23:49 |  | 0 | 2014-04-07 23:49 | 2014-06-01 02:53 |  | 0 | 2014-06-02 02:53 | 2014-06-19 09:33 |  | 0 | 2014-06-20 09:33 | 2014-07-07 16:14 |  | 0 | 2014-07-08 16:14 | 2014-07-25 22:54 |  | 0 | 2014-07-26 22:54 | 2014-08-13 05:35 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 26.3244 |  | 200.2324 | [15 empty] | I
Project-A11 |  | 0.50046 | 1.5546 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-06-10 21:14 |  | 0 | 2014-06-11 21:14 | 2014-08-02 08:18 |  | 0 | 2014-08-03 08:18 | 2014-09-02 13:23 |  | 0 | 2014-09-03 13:23 | 2014-10-03 18:29 |  | 0 | 2014-10-04 18:29 | 2014-11-03 23:35 |  | 0 | 2014-11-04 23:35 | 2014-12-05 04:40 |  | v002 |  | 0.08871 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 45.2419 |  | 303.1948 | [15 empty] | S
Project-A12 |  | 0.49921 | 1.4958 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-06-26 04:58 |  | 0 | 2014-06-27 04:58 | 2014-08-27 01:06 |  | 0 | 2014-08-28 01:06 | 2014-09-28 07:05 |  | 1 | 2014-09-30 07:05 | 2014-10-31 13:04 |  | 0 | 2014-11-01 13:04 | 2014-12-02 19:04 |  | 1 | 2014-12-04 19:04 | 2015-01-05 01:03 |  | v004 |  | 0.096774 |  | 45 | 0 | 0 | 1 | 0 | 1 | 47 | 65.3226 |  | 323.0438
Project-A13 |  | 0.50005 | 1.9998 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-09-06 23:31 |  | 0 | 2014-09-07 23:31 | 2014-10-24 01:20 |  | 0 | 2014-10-25 01:20 | 2014-12-10 03:08 |  | 0 | 2014-12-11 03:08 | 2015-01-26 04:56 |  | 0 | 2015-01-27 04:56 | 2015-03-14 06:44 |  | 0 | 2015-03-15 06:44 | 2015-04-30 08:33 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 427.3561 | [15 empty] | W
Project-A14 |  | 0.49999 | 0.26275 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-27 00:02 |  | 0 | 2014-05-28 00:02 | 2014-12-15 17:11 |  | 0 | 2014-12-16 17:11 | 2015-02-03 03:03 |  | 0 | 2015-02-04 03:03 | 2015-03-24 12:56 |  | 0 | 2015-03-25 12:56 | 2015-05-12 22:48 |  | 0 | 2015-05-13 22:48 | 2015-07-01 08:41 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 57.3573 |  | 478.3615 | [15 empty] | O
Project-A15 |  | 1.0001 | 2.0472 |  |  |  | 2014-01-01 |  | 79 | 2014-03-22 | 2014-06-01 23:52 |  | 0 | 2014-06-02 23:52 | 2014-07-21 08:30 |  | 0 | 2014-07-22 08:30 | 2014-08-08 15:11 |  | 1 | 2014-08-10 15:11 | 2014-08-27 21:52 |  | 0 | 2014-08-28 21:52 | 2014-09-15 04:33 |  | 0 | 2014-09-16 04:33 | 2014-10-03 11:14 |  | v008 |  | 0.10608 |  | 79 | 0 | 0 | 1 | 0 | 0 | 80 | 125.7041 |  | 195.4682 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 55.2667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.26667 |  |  |  | 0.066667 |  |  |  | 0.066667 | [5 empty] | 0.066667 |  | 55.2667 | 0 | 0 | 0.26667 | 0.066667 | 0.066667 | 55.6667 | 59.4392 | Average | 296.7454 | [15 empty] | H
Total |  | 8 | 23.9997 | [5 empty] | 829 |  |  |  | 0 |  |  |  | 0 |  |  |  | 4 |  |  |  | 1 |  |  |  | 1 | [5 empty] | 1 |  | 829 | 0 | 0 | 4 | 1 | 1 | 835 | 891.5881 | Total | 4451.1815 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 5
| Days: | 17.1127
E
N
SIT - Violation | Count: | 2 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 10.7993
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-27 05:16 | 2014-04-07 19:13 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-11 13:36 | 2014-03-18 18:25 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-12 16:14 | 2014-02-20 08:32 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-06-28 23:52 | 2014-07-16 06:34 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-04-27 12:49 | 2014-05-10 09:53 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2015-05-17 08:06 | 2015-06-11 07:08 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-09 11:12 | 2015-10-27 12:36 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-21 08:03 | 2014-01-23 17:39 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2015-03-22 00:42 | 2015-06-12 14:03 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-06-02 02:53 | 2014-06-19 09:33 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-08-03 08:18 | 2014-09-02 13:23 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 1 | [11 empty] | 5.5124 | 0 | 0 | 5.2869 | S
Project-A12 | 2014-08-28 01:06 | 2014-09-28 07:05 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-25 01:20 | 2014-12-10 03:08 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-12-16 17:11 | 2015-02-03 03:03 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-22 08:30 | 2014-08-08 15:11 | v008 | [31 empty] | T
UAT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 3.4751
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-08 19:13 | 2014-04-20 09:09 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-19 18:25 | 2014-03-26 23:13 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-21 08:32 | 2014-03-01 00:50 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-07-18 06:34 | 2014-08-04 13:16 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-11 09:53 | 2014-05-24 06:57 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-06-12 07:08 | 2015-07-07 06:09 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-28 12:36 | 2016-01-15 14:00 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-25 17:39 | 2014-01-28 03:15 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-06-13 14:03 | 2015-09-04 03:25 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-20 09:33 | 2014-07-07 16:14 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-03 13:23 | 2014-10-03 18:29 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 3.4751 | 0 | 0 | 0
Project-A12 | 2014-09-30 07:05 | 2014-10-31 13:04 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-11 03:08 | 2015-01-26 04:56 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-02-04 03:03 | 2015-03-24 12:56 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-10 15:11 | 2014-08-27 21:52 | v008
NFT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 2.4378
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-21 09:09 | 2014-05-02 23:05 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-27 23:13 | 2014-04-04 04:02 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-02 00:50 | 2014-03-09 17:08 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-08-05 13:16 | 2014-08-22 19:57 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-25 06:57 | 2014-06-07 04:00 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-07-09 06:09 | 2015-08-03 05:11 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-01-16 14:00 | 2016-04-04 15:23 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-29 03:15 | 2014-01-31 12:51 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-09-05 03:25 | 2015-11-26 16:46 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-08 16:14 | 2014-07-25 22:54 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-04 18:29 | 2014-11-03 23:35 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 2.4378 | 0 | 0 | 0
Project-A12 | 2014-11-01 13:04 | 2014-12-02 19:04 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-27 04:56 | 2015-03-14 06:44 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-03-25 12:56 | 2015-05-12 22:48 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-28 21:52 | 2014-09-15 04:33 | v008
Prod - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0.4005
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-05-03 23:05 | 2014-05-15 13:02 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-05 04:02 | 2014-04-12 08:51 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-10 17:08 | 2014-03-18 09:26 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-08-23 19:57 | 2014-09-10 02:39 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-06-08 04:00 | 2014-06-21 01:04 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-08-04 05:11 | 2015-08-29 04:13 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-04-05 15:23 | 2016-06-23 16:47 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-02-01 12:51 | 2014-02-03 22:27 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-11-27 16:46 | 2016-02-18 06:07 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-26 22:54 | 2014-08-13 05:35 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-11-04 23:35 | 2014-12-05 04:40 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0.4005 | 0 | 0 | 0
Project-A12 | 2014-12-04 19:04 | 2015-01-05 01:03 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-15 06:44 | 2015-04-30 08:33 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-05-13 22:48 | 2015-07-01 08:41 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-16 04:33 | 2014-10-03 11:14 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.054298 | 5.4298 | 5
0.20103 | 20.1031 | 20
0.81589 | 81.5891 | 81
0.98856 | 98.8558 | 98
0.3691 | 36.9098 | 36
0.76376 | 76.3759 | 76
0.5502 | 55.02 | 55
0.62073 | 62.0733 | 62
0.52825 | 52.8248 | 52
0.26433 | 26.4331 | 26
0.26179 | 26.1789 | 26
0.56637 | 56.6369 | 56
0.05926 | 5.926 | 5
0.11295 | 11.2949 | 11
0.87631 | 87.631 | 87
0.98185 | 98.1846 | 98
0.048289 | 4.8289 | 4
0.22743 | 22.7428 | 22
0.33421 | 33.421 | 33
0.0198 | 1.98 | 1
0.35088 | 35.0876 | 35
0.31751 | 31.7513 | 31
0.23819 | 23.819 | 23
0.49881 | 49.8813 | 49
0.82594 | 82.5936 | 82
0.49992 | 49.9923 | 49
0.95096 | 95.096 | 95
0.45628 | 45.6282 | 45
0.88852 | 88.8524 | 88
0.23448 | 23.4485 | 23
0.92048 | 92.0482 | 92
0.93255 | 93.2554 | 93
0.98127 | 98.1266 | 98
0.17465 | 17.4647 | 17
0.48776 | 48.7761 | 48
0.63751 | 63.751 | 63
0.76402 | 76.4017 | 76
0.93137 | 93.1374 | 93
0.51004 | 51.004 | 51

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 2115.5168 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.9 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 23.9997 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH