## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.5681 | 1.5778 |  |  |  | 17 | 17.76 | 34.76 | 29.9244 |  | 4.08 | 74 | 78.08 | 46.8993 |  | 4.08 | 17.76 | 21.84 | 11.2558 |  | 4.08 | 17.76 | 21.84 | 11.2558 |  | 4.08 | 17.76 | 21.84 | 11.2558 |  | 4.08 | 17.76 | 21.84 | 11.2558 |  | 200.2 | 121.847 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 65.8337 | 103.1784 | 103.1784
Project-A02 |  | v002 |  | 0.59676 | 1.542 |  |  |  | 15 | 19.2 | 34.2 | 25.1358 |  | 3.6 | 80 | 83.6 | 51.8818 |  | 3.6 | 19.2 | 22.8 | 12.4516 |  | 3.6 | 19.2 | 22.8 | 12.4516 |  | 3.6 | 19.2 | 22.8 | 12.4516 |  | 3.6 | 19.2 | 22.8 | 12.4516 |  | 209 | 126.824 | 104500 |  | 0.058933 |  | 33 | 176 |  | 55.2987 | 114.1399 | 114.1399 | [12 empty] | E
Project-A03 |  | v003 |  | 0.5857 | 3.2629 |  |  |  | 16 | 6.48 | 22.48 | 27.3178 |  | 3.84 | 27 | 30.84 | 8.2749 |  | 3.84 | 6.48 | 10.32 | 6.5563 |  | 3.84 | 6.48 | 10.32 | 6.5563 |  | 3.84 | 6.48 | 10.32 | 6.5563 |  | 3.84 | 6.48 | 10.32 | 6.5563 |  | 94.6 | 61.8177 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 60.0991 | 18.2047 | 60.0991 | [12 empty] | N
Project-A04 |  | v004 |  | 0.53297 | 1.5552 |  |  |  | 35 | 4.32 | 39.32 | 65.67 |  | 8.4 | 18 | 26.4 | 15.7608 |  | 8.4 | 4.32 | 12.72 | 15.7608 |  | 8.4 | 4.32 | 12.72 | 15.7608 |  | 8.4 | 4.32 | 12.72 | 15.7608 |  | 8.4 | 4.32 | 12.72 | 15.7608 |  | 116.6 | 144.474 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 144.474 | 25.4631 | 144.474 | [12 empty] | D
Project-A05 |  | v002 |  | 0.5587 | 1.5611 |  |  |  | 6 | 19.2 | 25.2 | 12.2991 |  | 1.44 | 80 | 81.44 | 51.2463 |  | 1.44 | 19.2 | 20.64 | 12.2991 |  | 1.44 | 19.2 | 20.64 | 12.2991 |  | 1.44 | 19.2 | 20.64 | 12.2991 |  | 1.44 | 19.2 | 20.64 | 12.2991 |  | 189.2 | 112.7418 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 23.6262 | 112.7418 | 112.7418
Project-A06 |  | v003 |  | 0.52599 | 1.4792 |  |  |  | 52 | 10.56 | 62.56 | 98.8616 |  | 12.48 | 44 | 56.48 | 29.7459 |  | 12.48 | 10.56 | 23.04 | 23.7268 |  | 12.48 | 10.56 | 23.04 | 23.7268 |  | 12.48 | 10.56 | 23.04 | 23.7268 |  | 12.48 | 10.56 | 23.04 | 23.7268 |  | 211.2 | 223.5147 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 217.4955 | 65.441 | 217.4955 | [12 empty] | O
Project-A07 |  | v005 |  | 0.5635 | 0.3236 |  |  |  | 93 | 19.92 | 112.92 | 165.0387 |  | 22.32 | 83 | 105.32 | 256.4871 |  | 22.32 | 19.92 | 42.24 | 61.5569 |  | 22.32 | 19.92 | 42.24 | 61.5569 |  | 22.32 | 19.92 | 42.24 | 61.5569 |  | 22.32 | 19.92 | 42.24 | 61.5569 |  | 387.2 | 667.7535 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 363.0851 | 564.2717 | 564.2717 | [12 empty] | F
Project-A08 |  | v006 |  | 0.54572 | 3.2365 |  |  |  | 5 | 2.64 | 7.64 | 9.1622 |  | 1.2 | 11 | 12.2 | 3.3988 |  | 1.2 | 2.64 | 3.84 | 2.1989 |  | 1.2 | 2.64 | 3.84 | 2.1989 |  | 1.2 | 2.64 | 3.84 | 2.1989 |  | 1.2 | 2.64 | 3.84 | 2.1989 |  | 35.2 | 21.3567 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 20.1569 | 7.4773 | 20.1569
Project-A09 |  | v003 |  | 0.52951 | 1.5319 |  |  |  | 49 | 20.64 | 69.64 | 92.5379 |  | 11.76 | 86 | 97.76 | 56.141 |  | 11.76 | 20.64 | 32.4 | 22.2091 |  | 11.76 | 20.64 | 32.4 | 22.2091 |  | 11.76 | 20.64 | 32.4 | 22.2091 |  | 11.76 | 20.64 | 32.4 | 22.2091 |  | 297 | 237.5152 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 203.5833 | 123.5102 | 203.5833 | [12 empty] | T
Project-A10 |  | v001 |  | 0.5661 | 1.5641 |  |  |  | 36 | 20.88 | 56.88 | 63.593 |  | 8.64 | 87 | 95.64 | 55.6221 |  | 8.64 | 20.88 | 29.52 | 15.2623 |  | 8.64 | 20.88 | 29.52 | 15.2623 |  | 8.64 | 20.88 | 29.52 | 15.2623 |  | 8.64 | 20.88 | 29.52 | 15.2623 |  | 270.6 | 180.2645 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 139.9047 | 122.3686 | 139.9047 | [12 empty] | H
Project-A11 |  | v002 |  | 0.28211 | 0.28997 |  |  |  | 63 | 19.2 | 82.2 | 223.3139 |  | 15.12 | 80 | 95.12 | 275.8894 |  | 15.12 | 19.2 | 34.32 | 66.2135 |  | 15.12 | 19.2 | 34.32 | 66.2135 |  | 15.12 | 19.2 | 34.32 | 66.2135 |  | 15.12 | 19.2 | 34.32 | 66.2135 |  | 314.6 | 764.0571 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 491.2906 | 606.9566 | 606.9566 | [12 empty] | I
Project-A12 |  | v004 |  | 0.60114 | 1.6436 |  |  |  | 65 | 21.84 | 86.84 | 108.1271 |  | 15.6 | 91 | 106.6 | 55.3666 |  | 15.6 | 21.84 | 37.44 | 25.9505 |  | 15.6 | 21.84 | 37.44 | 25.9505 |  | 15.6 | 21.84 | 37.44 | 25.9505 |  | 15.6 | 21.84 | 37.44 | 25.9505 |  | 343.2 | 267.2957 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 237.8796 | 121.8065 | 237.8796 | [12 empty] | S
Project-A13 |  | v007 |  | 0.62777 | 2.0554 |  |  |  | 96 | 9.6 | 105.6 | 152.922 |  | 23.04 | 40 | 63.04 | 36.7013 |  | 23.04 | 9.6 | 32.64 | 36.7013 |  | 23.04 | 9.6 | 32.64 | 36.7013 |  | 23.04 | 9.6 | 32.64 | 36.7013 |  | 23.04 | 9.6 | 32.64 | 36.7013 |  | 299.2 | 336.4284 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 336.4284 | 42.8136 | 336.4284
Project-A14 |  | v006 |  | 0.58977 | 0.34435 |  |  |  | 39 | 12.72 | 51.72 | 66.1279 |  | 9.36 | 53 | 62.36 | 153.9131 |  | 9.36 | 12.72 | 22.08 | 36.9391 |  | 9.36 | 12.72 | 22.08 | 36.9391 |  | 9.36 | 12.72 | 22.08 | 36.9391 |  | 9.36 | 12.72 | 22.08 | 36.9391 |  | 202.4 | 367.7974 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 145.4813 | 338.6087 | 338.6087 | [12 empty] | W
Project-A15 |  | v008 |  | 0.32613 | 2.0321 |  |  |  | 72 | 23.76 | 95.76 | 220.7698 |  | 17.28 | 99 | 116.28 | 52.9848 |  | 17.28 | 23.76 | 41.04 | 52.9848 |  | 17.28 | 23.76 | 41.04 | 52.9848 |  | 17.28 | 23.76 | 41.04 | 52.9848 |  | 17.28 | 23.76 | 41.04 | 52.9848 |  | 376.2 | 485.6937 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 485.6937 | 107.178 | 485.6937 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 90.7201 |  | 10.544 | 63.5333 | 74.0773 | 76.6875 |  | 10.544 | 15.248 | 25.792 | 26.8045 |  | 10.544 | 15.248 | 25.792 | 26.8045 |  | 10.544 | 15.248 | 25.792 | 26.8045 |  | 10.544 | 15.248 | 25.792 | 26.8045 |  | 236.4267 | 274.6254 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 199.3554 | 164.944 | 245.7075 | [12 empty] | S
|  | Total |  | 8 | 23.9997 |  |  |  | 659 | 228.72 | 887.72 | 1360.8012 |  | 158.16 | 953 | 1111.16 | 1150.313 |  | 158.16 | 228.72 | 386.88 | 402.0668 |  | 158.16 | 228.72 | 386.88 | 402.0668 |  | 158.16 | 228.72 | 386.88 | 402.0668 |  | 158.16 | 228.72 | 386.88 | 402.0668 |  | 3546.4 | 4119.3814 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2990.3308 | 2474.1601 | 3685.6123 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 1400.7535 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 328.4921 |  | <- To shorten average individual project span |  |  |  | <----------> | 245.7075
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 36.8145 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 0 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1766.0601 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | TRUE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.5681 | 1.5778 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-31 22:11 |  | 0 | 2014-02-01 22:11 | 2014-03-20 19:46 |  | 0 | 2014-03-21 19:46 | 2014-04-02 01:54 |  | 0 | 2014-04-03 01:54 | 2014-04-14 08:03 |  | 0 | 2014-04-15 08:03 | 2014-04-26 14:11 |  | 0 | 2014-04-27 14:11 | 2014-05-08 20:20 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 126.847 | 1400.7535 | [14 empty] | E
Project-A02 |  | 0.59676 | 1.542 |  |  |  | 2014-01-01 |  | 14 | 2014-01-16 | 2014-02-10 03:16 |  | 0 | 2014-02-11 03:16 | 2014-04-04 00:25 |  | 0 | 2014-04-05 00:25 | 2014-04-17 11:16 |  | 0 | 2014-04-18 11:16 | 2014-04-30 22:06 |  | 0 | 2014-05-01 22:06 | 2014-05-14 08:56 |  | 1 | 2014-05-16 08:56 | 2014-05-28 19:47 |  | v002 |  | 0.058933 |  | 14 | 0 | 0 | 0 | 0 | 1 | 15 | 12.3759 |  | 132.824 | [15 empty] | N
Project-A03 |  | 0.5857 | 3.2629 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-29 07:38 |  | 0 | 2014-01-30 07:38 | 2014-02-07 14:13 |  | 0 | 2014-02-08 14:13 | 2014-02-15 03:34 |  | 0 | 2014-02-16 03:34 | 2014-02-22 16:55 |  | 0 | 2014-02-23 16:55 | 2014-03-02 06:17 |  | 0 | 2014-03-03 06:17 | 2014-03-09 19:38 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 66.8177 | [15 empty] | D
Project-A04 |  | 0.53297 | 1.5552 |  |  |  | 2014-01-01 |  | 40 | 2014-02-11 | 2014-04-17 16:05 |  | 0 | 2014-04-18 16:05 | 2014-05-04 10:20 |  | 0 | 2014-05-05 10:20 | 2014-05-21 04:36 |  | 4 | 2014-05-26 04:36 | 2014-06-10 22:51 |  | 0 | 2014-06-11 22:51 | 2014-06-27 17:07 |  | 0 | 2014-06-28 17:07 | 2014-07-14 11:23 |  | v004 |  | 0.032878 |  | 40 | 0 | 0 | 4 | 0 | 0 | 44 | 19.727 |  | 153.474
Project-A05 |  | 0.5587 | 1.5611 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-02-28 07:11 |  | 0 | 2014-03-01 07:11 | 2014-04-21 13:05 |  | 0 | 2014-04-22 13:05 | 2014-05-04 20:16 |  | 0 | 2014-05-05 20:16 | 2014-05-18 03:27 |  | 0 | 2014-05-19 03:27 | 2014-05-31 10:38 |  | 0 | 2014-06-01 10:38 | 2014-06-13 17:48 |  | v002 |  | 0.05335 |  | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 36.0112 |  | 117.7418 | [15 empty] | O
Project-A06 |  | 0.52599 | 1.4792 |  |  |  | 2014-01-01 |  | 58 | 2014-03-01 | 2014-06-07 20:41 |  | 0 | 2014-06-08 20:41 | 2014-07-08 14:35 |  | 0 | 2014-07-09 14:35 | 2014-08-02 08:01 |  | 0 | 2014-08-03 08:01 | 2014-08-27 01:28 |  | 0 | 2014-08-28 01:28 | 2014-09-20 18:55 |  | 0 | 2014-09-21 18:55 | 2014-10-15 12:21 |  | v003 |  | 0.059553 |  | 58 | 0 | 0 | 0 | 0 | 0 | 58 | 51.8114 |  | 228.5147 | [15 empty] | F
Project-A07 |  | 0.5635 | 0.3236 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-06-16 00:56 |  | 0 | 2014-06-17 00:56 | 2015-02-28 12:37 |  | 0 | 2015-03-01 12:37 | 2015-05-02 01:59 |  | 363 | 2016-04-30 01:59 | 2016-06-30 15:21 |  | 365 | 2017-07-01 15:21 | 2017-09-01 04:43 |  | 0 | 2017-09-02 04:43 | 2017-11-02 18:05 |  | v005 |  | 0.10918 |  | 0 | 0 | 0 | 363 | 365 | 0 | 728 | 0 |  | 1400.7535
Project-A08 |  | 0.54572 | 3.2365 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 03:54 |  | 0 | 2014-01-12 03:54 | 2014-01-15 13:28 |  | 0 | 2014-01-16 13:28 | 2014-01-18 18:14 |  | 0 | 2014-01-19 18:14 | 2014-01-21 23:01 |  | 0 | 2014-01-22 23:01 | 2014-01-25 03:47 |  | 0 | 2014-01-26 03:47 | 2014-01-28 08:34 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 26.3567 | [15 empty] | T
Project-A09 |  | 0.52951 | 1.5319 |  |  |  | 2014-01-01 |  | 13 | 2014-01-15 | 2014-04-17 12:55 |  | 0 | 2014-04-18 12:55 | 2014-06-13 16:18 |  | 0 | 2014-06-14 16:18 | 2014-07-06 21:19 |  | 0 | 2014-07-07 21:19 | 2014-07-30 02:20 |  | 0 | 2014-07-31 02:20 | 2014-08-22 07:21 |  | 0 | 2014-08-23 07:21 | 2014-09-14 12:22 |  | v003 |  | 0.083747 |  | 13 | 0 | 0 | 0 | 0 | 0 | 13 | 16.3306 |  | 242.5152 | [15 empty] | H
Project-A10 |  | 0.5661 | 1.5641 |  |  |  | 2014-01-01 |  | 27 | 2014-01-29 | 2014-04-02 14:14 |  | 0 | 2014-04-03 14:14 | 2014-05-29 05:10 |  | 0 | 2014-05-30 05:10 | 2014-06-14 11:28 |  | 0 | 2014-06-15 11:28 | 2014-06-30 17:45 |  | 0 | 2014-07-01 17:45 | 2014-07-17 00:03 |  | 0 | 2014-07-18 00:03 | 2014-08-02 06:21 |  | v001 |  | 0.076303 |  | 27 | 0 | 0 | 0 | 0 | 0 | 27 | 30.9026 |  | 185.2645 | [15 empty] | I
Project-A11 |  | 0.28211 | 0.28997 |  |  |  | 2014-01-01 |  | 44 | 2014-02-15 | 2014-09-26 07:32 |  | 0 | 2014-09-27 07:32 | 2015-06-30 04:53 |  | 0 | 2015-07-01 04:53 | 2015-09-05 10:00 |  | 0 | 2015-09-06 10:00 | 2015-11-11 15:07 |  | 0 | 2015-11-12 15:07 | 2016-01-17 20:15 |  | 0 | 2016-01-18 20:15 | 2016-03-25 01:22 |  | v002 |  | 0.08871 |  | 44 | 0 | 0 | 0 | 0 | 0 | 44 | 58.5484 |  | 769.0571 | [15 empty] | S
Project-A12 |  | 0.60114 | 1.6436 |  |  |  | 2014-01-01 |  | 50 | 2014-02-21 | 2014-06-09 03:03 |  | 0 | 2014-06-10 03:03 | 2014-08-04 11:51 |  | 0 | 2014-08-05 11:51 | 2014-08-31 10:40 |  | 0 | 2014-09-01 10:40 | 2014-09-27 09:28 |  | 0 | 2014-09-28 09:28 | 2014-10-24 08:17 |  | 0 | 2014-10-25 08:17 | 2014-11-20 07:06 |  | v004 |  | 0.096774 |  | 50 | 0 | 0 | 0 | 0 | 0 | 50 | 72.5806 |  | 272.2957
Project-A13 |  | 0.62777 | 2.0554 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-07-29 22:08 |  | 0 | 2014-07-30 22:08 | 2014-09-05 14:58 |  | 0 | 2014-09-06 14:58 | 2014-10-13 07:47 |  | 0 | 2014-10-14 07:47 | 2014-11-20 00:37 |  | 0 | 2014-11-21 00:37 | 2014-12-27 17:27 |  | 0 | 2014-12-28 17:27 | 2015-02-03 10:17 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 341.4284 | [15 empty] | W
Project-A14 |  | 0.58977 | 0.34435 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-15 03:04 |  | 0 | 2014-05-16 03:04 | 2014-10-17 00:59 |  | 0 | 2014-10-18 00:59 | 2014-11-23 23:31 |  | 0 | 2014-11-24 23:31 | 2014-12-31 22:04 |  | 0 | 2015-01-01 22:04 | 2015-02-07 20:36 |  | 0 | 2015-02-08 20:36 | 2015-03-17 19:08 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 57.3573 |  | 372.7974 | [15 empty] | O
Project-A15 |  | 0.32613 | 2.0321 |  |  |  | 2014-01-01 |  | 79 | 2014-03-22 | 2014-10-28 18:29 |  | 0 | 2014-10-29 18:29 | 2014-12-21 18:07 |  | 0 | 2014-12-22 18:07 | 2015-02-13 17:45 |  | 0 | 2015-02-14 17:45 | 2015-04-08 17:23 |  | 0 | 2015-04-09 17:23 | 2015-06-01 17:01 |  | 0 | 2015-06-02 17:01 | 2015-07-25 16:39 |  | v008 |  | 0.10608 |  | 79 | 0 | 0 | 0 | 0 | 0 | 79 | 125.7041 |  | 490.6937 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 32.8667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 24.4667 |  |  |  | 24.3333 |  |  |  | 0.066667 | [5 empty] | 0.066667 |  | 32.8667 | 0 | 0 | 24.4667 | 24.3333 | 0.066667 | 81.7333 | 36.8145 | Average | 328.4921 | [15 empty] | H
Total |  | 8 | 23.9997 | [5 empty] | 493 |  |  |  | 0 |  |  |  | 0 |  |  |  | 367 |  |  |  | 365 |  |  |  | 1 | [5 empty] | 1 |  | 493 | 0 | 0 | 367 | 365 | 1 | 1226 | 552.2177 | Total | 4927.3814 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 0
| Days: | 0
E
N
SIT - Violation | Count: | 0 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 0
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-21 19:46 | 2014-04-02 01:54 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-05 00:25 | 2014-04-17 11:16 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-08 14:13 | 2014-02-15 03:34 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-05 10:20 | 2014-05-21 04:36 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-04-22 13:05 | 2014-05-04 20:16 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-09 14:35 | 2014-08-02 08:01 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-03-01 12:37 | 2015-05-02 01:59 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-16 13:28 | 2014-01-18 18:14 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-14 16:18 | 2014-07-06 21:19 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-05-30 05:10 | 2014-06-14 11:28 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2015-07-01 04:53 | 2015-09-05 10:00 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-05 11:51 | 2014-08-31 10:40 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-09-06 14:58 | 2014-10-13 07:47 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-10-18 00:59 | 2014-11-23 23:31 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-12-22 18:07 | 2015-02-13 17:45 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-03 01:54 | 2014-04-14 08:03 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-18 11:16 | 2014-04-30 22:06 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-16 03:34 | 2014-02-22 16:55 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-26 04:36 | 2014-06-10 22:51 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-05 20:16 | 2014-05-18 03:27 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-03 08:01 | 2014-08-27 01:28 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-04-30 01:59 | 2016-06-30 15:21 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-19 18:14 | 2014-01-21 23:01 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-07 21:19 | 2014-07-30 02:20 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-15 11:28 | 2014-06-30 17:45 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-09-06 10:00 | 2015-11-11 15:07 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-01 10:40 | 2014-09-27 09:28 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-10-14 07:47 | 2014-11-20 00:37 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-11-24 23:31 | 2014-12-31 22:04 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-02-14 17:45 | 2015-04-08 17:23 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-15 08:03 | 2014-04-26 14:11 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-01 22:06 | 2014-05-14 08:56 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-23 16:55 | 2014-03-02 06:17 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-11 22:51 | 2014-06-27 17:07 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-19 03:27 | 2014-05-31 10:38 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-28 01:28 | 2014-09-20 18:55 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2017-07-01 15:21 | 2017-09-01 04:43 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-22 23:01 | 2014-01-25 03:47 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-31 02:20 | 2014-08-22 07:21 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-01 17:45 | 2014-07-17 00:03 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-11-12 15:07 | 2016-01-17 20:15 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-28 09:28 | 2014-10-24 08:17 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-11-21 00:37 | 2014-12-27 17:27 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-01-01 22:04 | 2015-02-07 20:36 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-04-09 17:23 | 2015-06-01 17:01 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-27 14:11 | 2014-05-08 20:20 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-16 08:56 | 2014-05-28 19:47 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-03 06:17 | 2014-03-09 19:38 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-28 17:07 | 2014-07-14 11:23 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-06-01 10:38 | 2014-06-13 17:48 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-21 18:55 | 2014-10-15 12:21 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2017-09-02 04:43 | 2017-11-02 18:05 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-26 03:47 | 2014-01-28 08:34 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-23 07:21 | 2014-09-14 12:22 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-18 00:03 | 2014-08-02 06:21 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2016-01-18 20:15 | 2016-03-25 01:22 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-25 08:17 | 2014-11-20 07:06 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-28 17:27 | 2015-02-03 10:17 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-02-08 20:36 | 2015-03-17 19:08 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-06-02 17:01 | 2015-07-25 16:39 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.36166 | 36.1664 | 36
0.72866 | 72.8659 | 72
0.96656 | 96.656 | 96
0.25871 | 25.8714 | 25
0.1292 | 12.9202 | 12
0.46984 | 46.9836 | 46
0.036896 | 3.6896 | 3
0.82148 | 82.1481 | 82
0.96192 | 96.1921 | 96
0.86313 | 86.3128 | 86
0.70477 | 70.4765 | 70
0.94877 | 94.8769 | 94
0.16449 | 16.449 | 16
0.95943 | 95.9434 | 95
0.10616 | 10.6165 | 10
0.42933 | 42.9332 | 42
0.66067 | 66.0675 | 66
0.55494 | 55.4939 | 55
0.74641 | 74.6406 | 74
0.27292 | 27.2917 | 27
0.43882 | 43.8822 | 43
0.27699 | 27.6985 | 27
0.8674 | 86.7396 | 86
0.17937 | 17.9369 | 17
0.50651 | 50.6507 | 50
0.44194 | 44.1942 | 44
0.96514 | 96.5137 | 96
0.75428 | 75.4278 | 75
0.85241 | 85.2409 | 85
0.43915 | 43.9149 | 43
0.92452 | 92.4522 | 92
0.093658 | 9.3658 | 9
0.29985 | 29.9851 | 29
0.87137 | 87.1366 | 87
0.8717 | 87.1703 | 87
0.0029271 | 0.29271 | 0
0.0056014 | 0.56014 | 0
0.26401 | 26.4007 | 26
0.81143 | 81.1431 | 81

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1766.0601 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.9 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 23.9997 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH