## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.50025 | 1.5229 |  |  |  | 17 | 17.76 | 34.76 | 33.9829 |  | 4.08 | 74 | 78.08 | 48.5901 |  | 4.08 | 17.76 | 21.84 | 11.6616 |  | 4.08 | 17.76 | 21.84 | 11.6616 |  | 4.08 | 17.76 | 21.84 | 11.6616 |  | 4.08 | 17.76 | 21.84 | 11.6616 |  | 200.2 | 129.2195 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 74.7624 | 106.8983 | 106.8983
Project-A02 |  | v002 |  | 0.51931 | 1.5287 |  |  |  | 15 | 19.2 | 34.2 | 28.8844 |  | 3.6 | 80 | 83.6 | 52.3314 |  | 3.6 | 19.2 | 22.8 | 12.5595 |  | 3.6 | 19.2 | 22.8 | 12.5595 |  | 3.6 | 19.2 | 22.8 | 12.5595 |  | 3.6 | 19.2 | 22.8 | 12.5595 |  | 209 | 131.4539 | 104500 |  | 0.058933 |  | 33 | 176 |  | 63.5457 | 115.129 | 115.129 | [12 empty] | E
Project-A03 |  | v003 |  | 0.55012 | 1.5106 |  |  |  | 16 | 6.48 | 22.48 | 29.0846 |  | 3.84 | 27 | 30.84 | 17.874 |  | 3.84 | 6.48 | 10.32 | 6.9803 |  | 3.84 | 6.48 | 10.32 | 6.9803 |  | 3.84 | 6.48 | 10.32 | 6.9803 |  | 3.84 | 6.48 | 10.32 | 6.9803 |  | 94.6 | 74.8798 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 63.9861 | 39.3228 | 63.9861 | [12 empty] | N
Project-A04 |  | v004 |  | 0.50887 | 1.5147 |  |  |  | 35 | 4.32 | 39.32 | 68.7799 |  | 8.4 | 18 | 26.4 | 16.5072 |  | 8.4 | 4.32 | 12.72 | 16.5072 |  | 8.4 | 4.32 | 12.72 | 16.5072 |  | 8.4 | 4.32 | 12.72 | 16.5072 |  | 8.4 | 4.32 | 12.72 | 16.5072 |  | 116.6 | 151.3157 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 151.3157 | 26.1443 | 151.3157 | [12 empty] | D
Project-A05 |  | v002 |  | 0.50354 | 1.4886 |  |  |  | 6 | 19.2 | 25.2 | 12.898 |  | 1.44 | 80 | 81.44 | 53.7416 |  | 1.44 | 19.2 | 20.64 | 12.898 |  | 1.44 | 19.2 | 20.64 | 12.898 |  | 1.44 | 19.2 | 20.64 | 12.898 |  | 1.44 | 19.2 | 20.64 | 12.898 |  | 189.2 | 118.2315 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 26.2145 | 118.2315 | 118.2315
Project-A06 |  | v003 |  | 0.50111 | 1.5151 |  |  |  | 52 | 10.56 | 62.56 | 103.77 |  | 12.48 | 44 | 56.48 | 29.0407 |  | 12.48 | 10.56 | 23.04 | 24.9048 |  | 12.48 | 10.56 | 23.04 | 24.9048 |  | 12.48 | 10.56 | 23.04 | 24.9048 |  | 12.48 | 10.56 | 23.04 | 24.9048 |  | 211.2 | 232.43 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 228.2941 | 63.8895 | 228.2941 | [12 empty] | O
Project-A07 |  | v005 |  | 0.53372 | 1.5142 |  |  |  | 93 | 19.92 | 112.92 | 174.2474 |  | 22.32 | 83 | 105.32 | 54.8129 |  | 22.32 | 19.92 | 42.24 | 41.8194 |  | 22.32 | 19.92 | 42.24 | 41.8194 |  | 22.32 | 19.92 | 42.24 | 41.8194 |  | 22.32 | 19.92 | 42.24 | 41.8194 |  | 387.2 | 396.3378 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 383.3444 | 120.5883 | 383.3444 | [12 empty] | F
Project-A08 |  | v006 |  | 0.50667 | 1.5124 |  |  |  | 5 | 2.64 | 7.64 | 9.8684 |  | 1.2 | 11 | 12.2 | 7.2734 |  | 1.2 | 2.64 | 3.84 | 2.3684 |  | 1.2 | 2.64 | 3.84 | 2.3684 |  | 1.2 | 2.64 | 3.84 | 2.3684 |  | 1.2 | 2.64 | 3.84 | 2.3684 |  | 35.2 | 26.6155 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 21.7105 | 16.0015 | 21.7105
Project-A09 |  | v003 |  | 0.54281 | 0.26831 |  |  |  | 49 | 20.64 | 69.64 | 90.271 |  | 11.76 | 86 | 97.76 | 320.5289 |  | 11.76 | 20.64 | 32.4 | 76.9269 |  | 11.76 | 20.64 | 32.4 | 76.9269 |  | 11.76 | 20.64 | 32.4 | 76.9269 |  | 11.76 | 20.64 | 32.4 | 76.9269 |  | 297 | 718.5077 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 198.5961 | 705.1637 | 705.1637 | [12 empty] | T
Project-A10 |  | v001 |  | 0.50128 | 1.4994 |  |  |  | 36 | 20.88 | 56.88 | 71.8157 |  | 8.64 | 87 | 95.64 | 58.0231 |  | 8.64 | 20.88 | 29.52 | 17.2358 |  | 8.64 | 20.88 | 29.52 | 17.2358 |  | 8.64 | 20.88 | 29.52 | 17.2358 |  | 8.64 | 20.88 | 29.52 | 17.2358 |  | 270.6 | 198.7818 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 157.9946 | 127.6507 | 157.9946 | [12 empty] | H
Project-A11 |  | v002 |  | 0.26061 | 1.5146 |  |  |  | 63 | 19.2 | 82.2 | 241.7364 |  | 15.12 | 80 | 95.12 | 58.0167 |  | 15.12 | 19.2 | 34.32 | 58.0167 |  | 15.12 | 19.2 | 34.32 | 58.0167 |  | 15.12 | 19.2 | 34.32 | 58.0167 |  | 15.12 | 19.2 | 34.32 | 58.0167 |  | 314.6 | 531.8201 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 531.8201 | 116.2011 | 531.8201 | [12 empty] | I
Project-A12 |  | v004 |  | 0.50177 | 2.3745 |  |  |  | 65 | 21.84 | 86.84 | 129.5411 |  | 15.6 | 91 | 106.6 | 38.324 |  | 15.6 | 21.84 | 37.44 | 31.0899 |  | 15.6 | 21.84 | 37.44 | 31.0899 |  | 15.6 | 21.84 | 37.44 | 31.0899 |  | 15.6 | 21.84 | 37.44 | 31.0899 |  | 343.2 | 292.2246 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 284.9905 | 84.3128 | 284.9905 | [12 empty] | S
Project-A13 |  | v007 |  | 0.53273 | 2.0094 |  |  |  | 96 | 9.6 | 105.6 | 180.2051 |  | 23.04 | 40 | 63.04 | 43.2492 |  | 23.04 | 9.6 | 32.64 | 43.2492 |  | 23.04 | 9.6 | 32.64 | 43.2492 |  | 23.04 | 9.6 | 32.64 | 43.2492 |  | 23.04 | 9.6 | 32.64 | 43.2492 |  | 299.2 | 396.4512 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 396.4512 | 43.7947 | 396.4512
Project-A14 |  | v006 |  | 0.50166 | 2.0139 |  |  |  | 39 | 12.72 | 51.72 | 77.7421 |  | 9.36 | 53 | 62.36 | 26.3172 |  | 9.36 | 12.72 | 22.08 | 18.6581 |  | 9.36 | 12.72 | 22.08 | 18.6581 |  | 9.36 | 12.72 | 22.08 | 18.6581 |  | 9.36 | 12.72 | 22.08 | 18.6581 |  | 202.4 | 178.6916 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 171.0325 | 57.8978 | 171.0325 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0355 | 2.2127 |  |  |  | 72 | 23.76 | 95.76 | 69.5285 |  | 17.28 | 99 | 116.28 | 44.742 |  | 17.28 | 23.76 | 41.04 | 16.6868 |  | 17.28 | 23.76 | 41.04 | 16.6868 |  | 17.28 | 23.76 | 41.04 | 16.6868 |  | 17.28 | 23.76 | 41.04 | 16.6868 |  | 376.2 | 181.0179 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 152.9627 | 98.4323 | 152.9627 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 88.157 |  | 10.544 | 63.5333 | 74.0773 | 57.9582 |  | 10.544 | 15.248 | 25.792 | 26.1042 |  | 10.544 | 15.248 | 25.792 | 26.1042 |  | 10.544 | 15.248 | 25.792 | 26.1042 |  | 10.544 | 15.248 | 25.792 | 26.1042 |  | 236.4267 | 250.5319 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 193.8014 | 122.6439 | 239.2883 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1322.3555 |  | 158.16 | 953 | 1111.16 | 869.3723 |  | 158.16 | 228.72 | 386.88 | 391.5627 |  | 158.16 | 228.72 | 386.88 | 391.5627 |  | 158.16 | 228.72 | 386.88 | 391.5627 |  | 158.16 | 228.72 | 386.88 | 391.5627 |  | 3546.4 | 3757.9787 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2907.021 | 1839.6583 | 3589.3248 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 968.43 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 280.5319 |  | <- To shorten average individual project span |  |  |  | <----------> | 239.2883
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 89.8306 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 33.6825 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1372.475 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.50025 | 1.5229 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-04 23:35 |  | 0 | 2014-02-05 23:35 | 2014-03-26 13:45 |  | 0 | 2014-03-27 13:45 | 2014-04-08 05:38 |  | 0 | 2014-04-09 05:38 | 2014-04-20 21:31 |  | 0 | 2014-04-21 21:31 | 2014-05-03 13:23 |  | 0 | 2014-05-04 13:23 | 2014-05-16 05:16 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 134.2195 | 968.43 | [14 empty] | E
Project-A02 |  | 0.51931 | 1.5287 |  |  |  | 2014-01-01 |  | 15 | 2014-01-17 | 2014-02-14 21:14 |  | 0 | 2014-02-15 21:14 | 2014-04-09 05:11 |  | 0 | 2014-04-10 05:11 | 2014-04-22 18:36 |  | 0 | 2014-04-23 18:36 | 2014-05-06 08:02 |  | 0 | 2014-05-07 08:02 | 2014-05-19 21:28 |  | 0 | 2014-05-20 21:28 | 2014-06-02 10:54 |  | v002 |  | 0.058933 |  | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 13.2599 |  | 136.4539 | [15 empty] | N
Project-A03 |  | 0.55012 | 1.5106 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-31 02:02 |  | 0 | 2014-02-01 02:02 | 2014-02-18 23:00 |  | 0 | 2014-02-19 23:00 | 2014-02-26 22:32 |  | 0 | 2014-02-27 22:32 | 2014-03-06 22:04 |  | 0 | 2014-03-07 22:04 | 2014-03-14 21:35 |  | 0 | 2014-03-15 21:35 | 2014-03-22 21:07 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 79.8798 | [15 empty] | D
Project-A04 |  | 0.50887 | 1.5147 |  |  |  | 2014-01-01 |  | 37 | 2014-02-08 | 2014-04-17 18:43 |  | 0 | 2014-04-18 18:43 | 2014-05-05 06:53 |  | 0 | 2014-05-06 06:53 | 2014-05-22 19:04 |  | 0 | 2014-05-23 19:04 | 2014-06-09 07:14 |  | 0 | 2014-06-10 07:14 | 2014-06-26 19:24 |  | 0 | 2014-06-27 19:24 | 2014-07-14 07:35 |  | v004 |  | 0.032878 |  | 37 | 0 | 0 | 0 | 0 | 0 | 37 | 18.2475 |  | 156.3157
Project-A05 |  | 0.50354 | 1.4886 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-14 21:33 |  | 0 | 2014-01-15 21:33 | 2014-03-10 15:21 |  | 0 | 2014-03-11 15:21 | 2014-03-24 12:54 |  | 0 | 2014-03-25 12:54 | 2014-04-07 10:27 |  | 0 | 2014-04-08 10:27 | 2014-04-21 08:00 |  | 0 | 2014-04-22 08:00 | 2014-05-05 05:33 |  | v002 |  | 0.05335 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 123.2315 | [15 empty] | O
Project-A06 |  | 0.50111 | 1.5151 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-04-15 18:29 |  | 0 | 2015-04-16 18:29 | 2015-05-15 19:27 |  | 0 | 2015-05-16 19:27 | 2015-06-10 17:10 |  | 1 | 2015-06-12 17:10 | 2015-07-07 14:53 |  | 365 | 2016-07-07 14:53 | 2016-08-01 12:36 |  | 0 | 2016-08-02 12:36 | 2016-08-27 10:19 |  | v003 |  | 0.059553 |  | 365 | 0 | 0 | 1 | 365 | 0 | 731 | 326.0546 |  | 603.43 | [15 empty] | F
Project-A07 |  | 0.53372 | 1.5142 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-06-25 05:56 |  | 0 | 2015-06-26 05:56 | 2015-08-20 01:27 |  | 0 | 2015-08-21 01:27 | 2015-10-01 21:07 |  | 0 | 2015-10-02 21:07 | 2015-11-13 16:47 |  | 4 | 2015-11-18 16:47 | 2015-12-30 12:27 |  | 0 | 2015-12-31 12:27 | 2016-02-11 08:06 |  | v005 |  | 0.10918 |  | 365 | 0 | 0 | 0 | 4 | 0 | 369 | 597.7667 |  | 405.3378
Project-A08 |  | 0.50667 | 1.5124 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 20:51 |  | 0 | 2014-01-12 20:51 | 2014-01-20 03:24 |  | 0 | 2014-01-21 03:24 | 2014-01-23 12:15 |  | 0 | 2014-01-24 12:15 | 2014-01-26 21:05 |  | 0 | 2014-01-27 21:05 | 2014-01-30 05:56 |  | 0 | 2014-01-31 05:56 | 2014-02-02 14:46 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 31.6155 | [15 empty] | T
Project-A09 |  | 0.54281 | 0.26831 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-04-02 06:30 |  | 0 | 2014-04-03 06:30 | 2015-02-17 19:12 |  | 0 | 2015-02-18 19:12 | 2015-05-06 17:27 |  | 0 | 2015-05-07 17:27 | 2015-07-23 15:41 |  | 0 | 2015-07-24 15:41 | 2015-10-09 13:56 |  | 0 | 2015-10-10 13:56 | 2015-12-26 12:11 |  | v003 |  | 0.083747 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 723.5077 | [15 empty] | H
Project-A10 |  | 0.50128 | 1.4994 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-04-06 19:35 |  | 0 | 2014-04-07 19:35 | 2014-06-04 20:08 |  | 0 | 2014-06-05 20:08 | 2014-06-23 01:47 |  | 0 | 2014-06-24 01:47 | 2014-07-11 07:27 |  | 0 | 2014-07-12 07:27 | 2014-07-29 13:06 |  | 0 | 2014-07-30 13:06 | 2014-08-16 18:46 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 26.3244 |  | 203.7818 | [15 empty] | I
Project-A11 |  | 0.26061 | 1.5146 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-10-04 17:40 |  | 0 | 2014-10-05 17:40 | 2014-12-02 18:05 |  | 0 | 2014-12-03 18:05 | 2015-01-30 18:29 |  | 0 | 2015-01-31 18:29 | 2015-03-30 18:53 |  | 0 | 2015-03-31 18:53 | 2015-05-28 19:17 |  | 0 | 2015-05-29 19:17 | 2015-07-26 19:41 |  | v002 |  | 0.08871 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 45.2419 |  | 536.8201 | [15 empty] | S
Project-A12 |  | 0.50177 | 2.3745 |  |  |  | 2014-01-01 |  | 47 | 2014-02-18 | 2014-06-27 12:59 |  | 0 | 2014-06-28 12:59 | 2014-08-05 20:46 |  | 0 | 2014-08-06 20:46 | 2014-09-06 22:55 |  | 0 | 2014-09-07 22:55 | 2014-10-09 01:05 |  | 0 | 2014-10-10 01:05 | 2014-11-10 03:14 |  | 0 | 2014-11-11 03:14 | 2014-12-12 05:23 |  | v004 |  | 0.096774 |  | 47 | 0 | 0 | 0 | 0 | 0 | 47 | 68.2258 |  | 297.2246
Project-A13 |  | 0.53273 | 2.0094 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-08-26 04:55 |  | 0 | 2014-08-27 04:55 | 2014-10-09 10:54 |  | 0 | 2014-10-10 10:54 | 2014-11-22 16:53 |  | 0 | 2014-11-23 16:53 | 2015-01-05 22:52 |  | 0 | 2015-01-06 22:52 | 2015-02-19 04:51 |  | 0 | 2015-02-20 04:51 | 2015-04-04 10:50 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 401.4512 | [15 empty] | W
Project-A14 |  | 0.50166 | 2.0139 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-26 17:49 |  | 0 | 2014-05-27 17:49 | 2014-06-23 01:25 |  | 0 | 2014-06-24 01:25 | 2014-07-12 17:13 |  | 0 | 2014-07-13 17:13 | 2014-08-01 09:01 |  | 0 | 2014-08-02 09:01 | 2014-08-21 00:48 |  | 0 | 2014-08-22 00:48 | 2014-09-09 16:36 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 57.3573 |  | 183.6916 | [15 empty] | O
Project-A15 |  | 1.0355 | 2.2127 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-05-29 12:41 |  | 0 | 2014-05-30 12:41 | 2014-07-14 06:29 |  | 0 | 2014-07-15 06:29 | 2014-07-31 22:59 |  | 0 | 2014-08-01 22:59 | 2014-08-18 15:28 |  | 3 | 2014-08-22 15:28 | 2014-09-08 07:57 |  | 2 | 2014-09-11 07:57 | 2014-09-28 00:26 |  | v008 |  | 0.10608 |  | 78 | 0 | 0 | 0 | 3 | 2 | 83 | 124.1129 |  | 191.0179 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 72.4667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.066667 |  |  |  | 24.8 |  |  |  | 0.13333 | [5 empty] | 0.066667 |  | 72.4667 | 0 | 0 | 0.066667 | 24.8 | 0.13333 | 97.4667 | 89.8306 | Average | 280.5319 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 1087 |  |  |  | 0 |  |  |  | 0 |  |  |  | 1 |  |  |  | 372 |  |  |  | 2 | [5 empty] | 1 |  | 1087 | 0 | 0 | 1 | 372 | 2 | 1462 | 1347.4597 | Total | 4207.9787 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 1
| Days: | 0.67365
E
N
SIT - Violation | Count: | 0 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 0
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-27 13:45 | 2014-04-08 05:38 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-10 05:11 | 2014-04-22 18:36 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-19 23:00 | 2014-02-26 22:32 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-06 06:53 | 2014-05-22 19:04 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-03-11 15:21 | 2014-03-24 12:54 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2015-05-16 19:27 | 2015-06-10 17:10 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-21 01:27 | 2015-10-01 21:07 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-21 03:24 | 2014-01-23 12:15 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2015-02-18 19:12 | 2015-05-06 17:27 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-06-05 20:08 | 2014-06-23 01:47 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-12-03 18:05 | 2015-01-30 18:29 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-06 20:46 | 2014-09-06 22:55 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-10 10:54 | 2014-11-22 16:53 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-24 01:25 | 2014-07-12 17:13 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-15 06:29 | 2014-07-31 22:59 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-09 05:38 | 2014-04-20 21:31 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-23 18:36 | 2014-05-06 08:02 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-27 22:32 | 2014-03-06 22:04 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-23 19:04 | 2014-06-09 07:14 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-25 12:54 | 2014-04-07 10:27 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-06-12 17:10 | 2015-07-07 14:53 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-02 21:07 | 2015-11-13 16:47 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-24 12:15 | 2014-01-26 21:05 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-05-07 17:27 | 2015-07-23 15:41 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-24 01:47 | 2014-07-11 07:27 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-01-31 18:29 | 2015-03-30 18:53 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-07 22:55 | 2014-10-09 01:05 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-11-23 16:53 | 2015-01-05 22:52 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-13 17:13 | 2014-08-01 09:01 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-01 22:59 | 2014-08-18 15:28 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-21 21:31 | 2014-05-03 13:23 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-07 08:02 | 2014-05-19 21:28 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-07 22:04 | 2014-03-14 21:35 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-10 07:14 | 2014-06-26 19:24 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-08 10:27 | 2014-04-21 08:00 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2016-07-07 14:53 | 2016-08-01 12:36 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-11-18 16:47 | 2015-12-30 12:27 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-27 21:05 | 2014-01-30 05:56 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-07-24 15:41 | 2015-10-09 13:56 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-12 07:27 | 2014-07-29 13:06 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-03-31 18:53 | 2015-05-28 19:17 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-10 01:05 | 2014-11-10 03:14 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-06 22:52 | 2015-02-19 04:51 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-02 09:01 | 2014-08-21 00:48 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-22 15:28 | 2014-09-08 07:57 | v008
Prod - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0.67365
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-05-04 13:23 | 2014-05-16 05:16 | v001 |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0.67365 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-20 21:28 | 2014-06-02 10:54 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-15 21:35 | 2014-03-22 21:07 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-27 19:24 | 2014-07-14 07:35 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-22 08:00 | 2014-05-05 05:33 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2016-08-02 12:36 | 2016-08-27 10:19 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-12-31 12:27 | 2016-02-11 08:06 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-31 05:56 | 2014-02-02 14:46 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-10-10 13:56 | 2015-12-26 12:11 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-30 13:06 | 2014-08-16 18:46 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-05-29 19:17 | 2015-07-26 19:41 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-11 03:14 | 2014-12-12 05:23 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-02-20 04:51 | 2015-04-04 10:50 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-22 00:48 | 2014-09-09 16:36 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-11 07:57 | 2014-09-28 00:26 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.13414 | 13.414 | 13
0.14918 | 14.9182 | 14
0.47146 | 47.1457 | 47
0.97758 | 97.7577 | 97
0.98621 | 98.6211 | 98
0.84504 | 84.5036 | 84
0.97718 | 97.7181 | 97
0.4784 | 47.8403 | 47
0.21064 | 21.064 | 21
0.93644 | 93.644 | 93
0.88185 | 88.1845 | 88
0.91493 | 91.4931 | 91
0.65029 | 65.0292 | 65
0.60697 | 60.6971 | 60
0.87338 | 87.3381 | 87
0.84095 | 84.0951 | 84
0.14665 | 14.6645 | 14
0.40227 | 40.2274 | 40
0.14534 | 14.5345 | 14
0.82805 | 82.8048 | 82
0.34242 | 34.2417 | 34
0.74816 | 74.8164 | 74
0.8821 | 88.2098 | 88
0.016342 | 1.6342 | 1
0.98933 | 98.9335 | 98
0.64951 | 64.9514 | 64
0.45171 | 45.1706 | 45
0.43573 | 43.5732 | 43
0.30793 | 30.7933 | 30
0.097622 | 9.7622 | 9
0.33341 | 33.3412 | 33
0.10627 | 10.6271 | 10
0.80447 | 80.4467 | 80
0.45463 | 45.4632 | 45
0.21028 | 21.0283 | 21
0.094032 | 9.4032 | 9
0.37293 | 37.2933 | 37
0.10321 | 10.3207 | 10
0.079281 | 7.9281 | 7

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1372.475 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH