## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.50577 | 0.26056 |  |  |  | 17 | 17.76 | 34.76 | 68.1606 |  | 4.08 | 74 | 78.08 | 284.0024 |  | 4.08 | 17.76 | 21.84 | 68.1606 |  | 4.08 | 17.76 | 21.84 | 68.1606 |  | 4.08 | 17.76 | 21.84 | 68.1606 |  | 4.08 | 17.76 | 21.84 | 68.1606 |  | 200.2 | 624.8054 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 73.9462 | 624.8054 | 624.8054
Project-A02 |  | v002 |  | 0.49972 | 1.4994 |  |  |  | 15 | 19.2 | 34.2 | 30.0169 |  | 3.6 | 80 | 83.6 | 53.3533 |  | 3.6 | 19.2 | 22.8 | 12.8048 |  | 3.6 | 19.2 | 22.8 | 12.8048 |  | 3.6 | 19.2 | 22.8 | 12.8048 |  | 3.6 | 19.2 | 22.8 | 12.8048 |  | 209 | 134.5894 | 104500 |  | 0.058933 |  | 33 | 176 |  | 66.0373 | 117.3773 | 117.3773 | [12 empty] | E
Project-A03 |  | v003 |  | 0.50495 | 3.675 |  |  |  | 16 | 6.48 | 22.48 | 31.6861 |  | 3.84 | 27 | 30.84 | 7.6047 |  | 3.84 | 6.48 | 10.32 | 7.6047 |  | 3.84 | 6.48 | 10.32 | 7.6047 |  | 3.84 | 6.48 | 10.32 | 7.6047 |  | 3.84 | 6.48 | 10.32 | 7.6047 |  | 94.6 | 69.7095 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 69.7095 | 16.1631 | 69.7095 | [12 empty] | N
Project-A04 |  | v004 |  | 0.49359 | 1.5027 |  |  |  | 35 | 4.32 | 39.32 | 70.9095 |  | 8.4 | 18 | 26.4 | 17.0183 |  | 8.4 | 4.32 | 12.72 | 17.0183 |  | 8.4 | 4.32 | 12.72 | 17.0183 |  | 8.4 | 4.32 | 12.72 | 17.0183 |  | 8.4 | 4.32 | 12.72 | 17.0183 |  | 116.6 | 156.0009 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 156.0009 | 26.3518 | 156.0009 | [12 empty] | D
Project-A05 |  | v002 |  | 0.49848 | 1.7406 |  |  |  | 6 | 19.2 | 25.2 | 12.0366 |  | 1.44 | 80 | 81.44 | 45.9605 |  | 1.44 | 19.2 | 20.64 | 11.0305 |  | 1.44 | 19.2 | 20.64 | 11.0305 |  | 1.44 | 19.2 | 20.64 | 11.0305 |  | 1.44 | 19.2 | 20.64 | 11.0305 |  | 189.2 | 102.1193 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 26.4806 | 101.1131 | 101.1131
Project-A06 |  | v003 |  | 0.51854 | 1.5158 |  |  |  | 52 | 10.56 | 62.56 | 100.2824 |  | 12.48 | 44 | 56.48 | 29.0274 |  | 12.48 | 10.56 | 23.04 | 24.0678 |  | 12.48 | 10.56 | 23.04 | 24.0678 |  | 12.48 | 10.56 | 23.04 | 24.0678 |  | 12.48 | 10.56 | 23.04 | 24.0678 |  | 211.2 | 225.5809 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 220.6213 | 63.8602 | 220.6213 | [12 empty] | O
Project-A07 |  | v005 |  | 0.49295 | 0.26865 |  |  |  | 93 | 19.92 | 112.92 | 188.6608 |  | 22.32 | 83 | 105.32 | 308.9511 |  | 22.32 | 19.92 | 42.24 | 74.1483 |  | 22.32 | 19.92 | 42.24 | 74.1483 |  | 22.32 | 19.92 | 42.24 | 74.1483 |  | 22.32 | 19.92 | 42.24 | 74.1483 |  | 387.2 | 794.2049 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 415.0538 | 679.6924 | 679.6924 | [12 empty] | F
Project-A08 |  | v006 |  | 0.49212 | 2.3704 |  |  |  | 5 | 2.64 | 7.64 | 10.16 |  | 1.2 | 11 | 12.2 | 4.6406 |  | 1.2 | 2.64 | 3.84 | 2.4384 |  | 1.2 | 2.64 | 3.84 | 2.4384 |  | 1.2 | 2.64 | 3.84 | 2.4384 |  | 1.2 | 2.64 | 3.84 | 2.4384 |  | 35.2 | 24.5543 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 22.3521 | 10.2094 | 22.3521
Project-A09 |  | v003 |  | 0.49351 | 0.25093 |  |  |  | 49 | 20.64 | 69.64 | 99.2893 |  | 11.76 | 86 | 97.76 | 342.7233 |  | 11.76 | 20.64 | 32.4 | 82.2536 |  | 11.76 | 20.64 | 32.4 | 82.2536 |  | 11.76 | 20.64 | 32.4 | 82.2536 |  | 11.76 | 20.64 | 32.4 | 82.2536 |  | 297 | 771.0271 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 218.4365 | 753.9913 | 753.9913 | [12 empty] | T
Project-A10 |  | v001 |  | 0.49659 | 1.5269 |  |  |  | 36 | 20.88 | 56.88 | 72.4943 |  | 8.64 | 87 | 95.64 | 56.9783 |  | 8.64 | 20.88 | 29.52 | 17.3986 |  | 8.64 | 20.88 | 29.52 | 17.3986 |  | 8.64 | 20.88 | 29.52 | 17.3986 |  | 8.64 | 20.88 | 29.52 | 17.3986 |  | 270.6 | 199.0671 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 159.4874 | 125.3522 | 159.4874 | [12 empty] | H
Project-A11 |  | v002 |  | 0.49416 | 1.5374 |  |  |  | 63 | 19.2 | 82.2 | 127.4903 |  | 15.12 | 80 | 95.12 | 52.0351 |  | 15.12 | 19.2 | 34.32 | 30.5977 |  | 15.12 | 19.2 | 34.32 | 30.5977 |  | 15.12 | 19.2 | 34.32 | 30.5977 |  | 15.12 | 19.2 | 34.32 | 30.5977 |  | 314.6 | 301.9161 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 280.4787 | 114.4771 | 280.4787 | [12 empty] | I
Project-A12 |  | v004 |  | 0.49155 | 1.4741 |  |  |  | 65 | 21.84 | 86.84 | 132.2352 |  | 15.6 | 91 | 106.6 | 61.7309 |  | 15.6 | 21.84 | 37.44 | 31.7364 |  | 15.6 | 21.84 | 37.44 | 31.7364 |  | 15.6 | 21.84 | 37.44 | 31.7364 |  | 15.6 | 21.84 | 37.44 | 31.7364 |  | 343.2 | 320.9118 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 290.9174 | 135.8079 | 290.9174 | [12 empty] | S
Project-A13 |  | v007 |  | 0.50493 | 1.9906 |  |  |  | 96 | 9.6 | 105.6 | 190.1238 |  | 23.04 | 40 | 63.04 | 45.6297 |  | 23.04 | 9.6 | 32.64 | 45.6297 |  | 23.04 | 9.6 | 32.64 | 45.6297 |  | 23.04 | 9.6 | 32.64 | 45.6297 |  | 23.04 | 9.6 | 32.64 | 45.6297 |  | 299.2 | 418.2723 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 418.2723 | 44.2084 | 418.2723
Project-A14 |  | v006 |  | 0.51027 | 2.0147 |  |  |  | 39 | 12.72 | 51.72 | 76.4305 |  | 9.36 | 53 | 62.36 | 26.307 |  | 9.36 | 12.72 | 22.08 | 18.3433 |  | 9.36 | 12.72 | 22.08 | 18.3433 |  | 9.36 | 12.72 | 22.08 | 18.3433 |  | 9.36 | 12.72 | 22.08 | 18.3433 |  | 202.4 | 176.1108 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 168.1471 | 57.8754 | 168.1471 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0029 | 2.3721 |  |  |  | 72 | 23.76 | 95.76 | 71.7932 |  | 17.28 | 99 | 116.28 | 41.7345 |  | 17.28 | 23.76 | 41.04 | 17.2304 |  | 17.28 | 23.76 | 41.04 | 17.2304 |  | 17.28 | 23.76 | 41.04 | 17.2304 |  | 17.28 | 23.76 | 41.04 | 17.2304 |  | 376.2 | 182.4491 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 157.945 | 91.8159 | 157.945 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 85.4513 |  | 10.544 | 63.5333 | 74.0773 | 91.8465 |  | 10.544 | 15.248 | 25.792 | 30.6975 |  | 10.544 | 15.248 | 25.792 | 30.6975 |  | 10.544 | 15.248 | 25.792 | 30.6975 |  | 10.544 | 15.248 | 25.792 | 30.6975 |  | 236.4267 | 300.0879 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 182.9257 | 197.5401 | 281.3941 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1281.7697 |  | 158.16 | 953 | 1111.16 | 1377.6971 |  | 158.16 | 228.72 | 386.88 | 460.463 |  | 158.16 | 228.72 | 386.88 | 460.463 |  | 158.16 | 228.72 | 386.88 | 460.463 |  | 158.16 | 228.72 | 386.88 | 460.463 |  | 3546.4 | 4501.3189 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2743.8862 | 2963.101 | 4220.9113 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 961.5809 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 329.7546 |  | <- To shorten average individual project span |  |  |  | <----------> | 281.3941
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 56.8257 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 509.4202 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1857.5814 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.50577 | 0.26056 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-11 03:51 |  | 0 | 2014-03-12 03:51 | 2014-12-21 03:55 |  | 0 | 2014-12-22 03:55 | 2015-02-28 07:46 |  | 0 | 2015-03-01 07:46 | 2015-05-08 11:37 |  | 0 | 2015-05-09 11:37 | 2015-07-16 15:28 |  | 0 | 2015-07-17 15:28 | 2015-09-23 19:20 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 629.8054 | 961.5809 | [14 empty] | E
Project-A02 |  | 0.49972 | 1.4994 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-02-13 00:24 |  | 0 | 2014-02-14 00:24 | 2014-04-08 08:53 |  | 0 | 2014-04-09 08:53 | 2014-04-22 04:12 |  | 0 | 2014-04-23 04:12 | 2014-05-05 23:31 |  | 0 | 2014-05-06 23:31 | 2014-05-19 18:50 |  | 0 | 2014-05-20 18:50 | 2014-06-02 14:09 |  | v002 |  | 0.058933 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 10.6079 |  | 139.5894 | [15 empty] | N
Project-A03 |  | 0.50495 | 3.675 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-02 16:28 |  | 0 | 2014-02-03 16:28 | 2014-02-11 06:59 |  | 0 | 2014-02-12 06:59 | 2014-02-19 21:30 |  | 0 | 2014-02-20 21:30 | 2014-02-28 12:00 |  | 0 | 2014-03-01 12:00 | 2014-03-09 02:31 |  | 0 | 2014-03-10 02:31 | 2014-03-17 17:02 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 74.7095 | [15 empty] | D
Project-A04 |  | 0.49359 | 1.5027 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-04-16 21:50 |  | 0 | 2014-04-17 21:50 | 2014-05-04 22:16 |  | 0 | 2014-05-05 22:16 | 2014-05-22 22:42 |  | 0 | 2014-05-23 22:42 | 2014-06-09 23:09 |  | 0 | 2014-06-10 23:09 | 2014-06-27 23:35 |  | 0 | 2014-06-28 23:35 | 2014-07-16 00:01 |  | v004 |  | 0.032878 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 16.768 |  | 161.0009
Project-A05 |  | 0.49848 | 1.7406 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-14 00:53 |  | 0 | 2014-01-15 00:53 | 2014-03-01 23:56 |  | 0 | 2014-03-02 23:56 | 2014-03-14 00:40 |  | 0 | 2014-03-15 00:40 | 2014-03-26 01:24 |  | 0 | 2014-03-27 01:24 | 2014-04-07 02:08 |  | 0 | 2014-04-08 02:08 | 2014-04-19 02:52 |  | v002 |  | 0.05335 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 107.1193 | [15 empty] | O
Project-A06 |  | 0.51854 | 1.5158 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-04-12 06:47 |  | 0 | 2015-04-13 06:47 | 2015-05-12 07:26 |  | 0 | 2015-05-13 07:26 | 2015-06-06 09:04 |  | 1 | 2015-06-08 09:04 | 2015-07-02 10:41 |  | 365 | 2016-07-02 10:41 | 2016-07-26 12:19 |  | 0 | 2016-07-27 12:19 | 2016-08-20 13:57 |  | v003 |  | 0.059553 |  | 365 | 0 | 0 | 1 | 365 | 0 | 731 | 326.0546 |  | 596.5809 | [15 empty] | F
Project-A07 |  | 0.49295 | 0.26865 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-09-14 15:52 |  | 0 | 2014-09-15 15:52 | 2015-07-21 14:41 |  | 0 | 2015-07-22 14:41 | 2015-10-04 18:15 |  | 0 | 2015-10-05 18:15 | 2015-12-18 21:48 |  | 0 | 2015-12-19 21:48 | 2016-03-03 01:22 |  | 0 | 2016-03-04 01:22 | 2016-05-17 04:55 |  | v005 |  | 0.10918 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 109.727 |  | 799.2049
Project-A08 |  | 0.49212 | 2.3704 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-12 03:50 |  | 0 | 2014-01-13 03:50 | 2014-01-17 19:13 |  | 0 | 2014-01-18 19:13 | 2014-01-21 05:44 |  | 0 | 2014-01-22 05:44 | 2014-01-24 16:16 |  | 0 | 2014-01-25 16:16 | 2014-01-28 02:47 |  | 0 | 2014-01-29 02:47 | 2014-01-31 13:18 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 29.5543 | [15 empty] | T
Project-A09 |  | 0.49351 | 0.25093 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-04-11 06:57 |  | 0 | 2014-04-12 06:57 | 2015-03-21 00:18 |  | 0 | 2015-03-22 00:18 | 2015-06-12 06:23 |  | 0 | 2015-06-13 06:23 | 2015-09-03 12:29 |  | 0 | 2015-09-04 12:29 | 2015-11-25 18:34 |  | 0 | 2015-11-26 18:34 | 2016-02-17 00:39 |  | v003 |  | 0.083747 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 776.0271 | [15 empty] | H
Project-A10 |  | 0.49659 | 1.5269 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-04-07 11:52 |  | 0 | 2014-04-08 11:52 | 2014-06-04 11:20 |  | 0 | 2014-06-05 11:20 | 2014-06-22 20:54 |  | 0 | 2014-06-23 20:54 | 2014-07-11 06:29 |  | 0 | 2014-07-12 06:29 | 2014-07-29 16:03 |  | 0 | 2014-07-30 16:03 | 2014-08-17 01:37 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 26.3244 |  | 204.0671 | [15 empty] | I
Project-A11 |  | 0.49416 | 1.5374 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-06-12 11:46 |  | 0 | 2014-06-13 11:46 | 2014-08-04 12:37 |  | 0 | 2014-08-05 12:37 | 2014-09-05 02:57 |  | 0 | 2014-09-06 02:57 | 2014-10-06 17:18 |  | 0 | 2014-10-07 17:18 | 2014-11-07 07:39 |  | 0 | 2014-11-08 07:39 | 2014-12-08 21:59 |  | v002 |  | 0.08871 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 45.2419 |  | 306.9161 | [15 empty] | S
Project-A12 |  | 0.49155 | 1.4741 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-06-28 05:39 |  | 0 | 2014-06-29 05:39 | 2014-08-29 23:11 |  | 0 | 2014-08-30 23:11 | 2014-10-01 16:52 |  | 1 | 2014-10-03 16:52 | 2014-11-04 10:32 |  | 0 | 2014-11-05 10:32 | 2014-12-07 04:13 |  | 3 | 2014-12-11 04:13 | 2015-01-11 21:53 |  | v004 |  | 0.096774 |  | 45 | 0 | 0 | 1 | 0 | 3 | 49 | 65.3226 |  | 329.9118
Project-A13 |  | 0.50493 | 1.9906 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-09-05 02:58 |  | 0 | 2014-09-06 02:58 | 2014-10-21 18:05 |  | 0 | 2014-10-22 18:05 | 2014-12-07 09:12 |  | 0 | 2014-12-08 09:12 | 2015-01-23 00:19 |  | 0 | 2015-01-24 00:19 | 2015-03-10 15:25 |  | 0 | 2015-03-11 15:25 | 2015-04-26 06:32 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 423.2723 | [15 empty] | W
Project-A14 |  | 0.51027 | 2.0147 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-25 10:20 |  | 0 | 2014-05-26 10:20 | 2014-06-21 17:42 |  | 0 | 2014-06-22 17:42 | 2014-07-11 01:56 |  | 0 | 2014-07-12 01:56 | 2014-07-30 10:11 |  | 0 | 2014-07-31 10:11 | 2014-08-18 18:25 |  | 0 | 2014-08-19 18:25 | 2014-09-07 02:39 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 57.3573 |  | 181.1108 | [15 empty] | O
Project-A15 |  | 1.0029 | 2.3721 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-05-31 19:02 |  | 0 | 2014-06-01 19:02 | 2014-07-13 12:40 |  | 0 | 2014-07-14 12:40 | 2014-07-31 18:12 |  | 0 | 2014-08-01 18:12 | 2014-08-18 23:43 |  | 0 | 2014-08-19 23:43 | 2014-09-06 05:15 |  | 0 | 2014-09-07 05:15 | 2014-09-24 10:47 |  | v008 |  | 0.10608 |  | 78 | 0 | 0 | 0 | 0 | 0 | 78 | 124.1129 |  | 187.4491 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 52.0667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.13333 |  |  |  | 24.3333 |  |  |  | 0.2 | [5 empty] | 0.066667 |  | 52.0667 | 0 | 0 | 0.13333 | 24.3333 | 0.2 | 76.7333 | 56.8257 | Average | 329.7546 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 781 |  |  |  | 0 |  |  |  | 0 |  |  |  | 2 |  |  |  | 365 |  |  |  | 3 | [5 empty] | 1 |  | 781 | 0 | 0 | 2 | 365 | 3 | 1151 | 852.3852 | Total | 4946.3189 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 4
| Days: | 10.1884
E
N
SIT - Violation | Count: | 2 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 5.2907
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-12-22 03:55 | 2015-02-28 07:46 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-09 08:53 | 2014-04-22 04:12 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-12 06:59 | 2014-02-19 21:30 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-05 22:16 | 2014-05-22 22:42 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-03-02 23:56 | 2014-03-14 00:40 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2015-05-13 07:26 | 2015-06-06 09:04 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-07-22 14:41 | 2015-10-04 18:15 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-18 19:13 | 2014-01-21 05:44 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2015-03-22 00:18 | 2015-06-12 06:23 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-06-05 11:20 | 2014-06-22 20:54 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0.13368 | 0 | K
Project-A11 | 2014-08-05 12:37 | 2014-09-05 02:57 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 5.157 | 0 | 0 | 0 | S
Project-A12 | 2014-08-30 23:11 | 2014-10-01 16:52 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-22 18:05 | 2014-12-07 09:12 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-22 17:42 | 2014-07-11 01:56 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-14 12:40 | 2014-07-31 18:12 | v008 | [31 empty] | T
UAT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 3.0182
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-03-01 07:46 | 2015-05-08 11:37 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-23 04:12 | 2014-05-05 23:31 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-20 21:30 | 2014-02-28 12:00 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-23 22:42 | 2014-06-09 23:09 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-15 00:40 | 2014-03-26 01:24 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-06-08 09:04 | 2015-07-02 10:41 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-05 18:15 | 2015-12-18 21:48 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-22 05:44 | 2014-01-24 16:16 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-06-13 06:23 | 2015-09-03 12:29 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-23 20:54 | 2014-07-11 06:29 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-06 02:57 | 2014-10-06 17:18 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 3.0182 | 0 | 0 | 0
Project-A12 | 2014-10-03 16:52 | 2014-11-04 10:32 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-08 09:12 | 2015-01-23 00:19 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-12 01:56 | 2014-07-30 10:11 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-01 18:12 | 2014-08-18 23:43 | v008
NFT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 1.8795
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-05-09 11:37 | 2015-07-16 15:28 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-06 23:31 | 2014-05-19 18:50 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-01 12:00 | 2014-03-09 02:31 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-10 23:09 | 2014-06-27 23:35 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-27 01:24 | 2014-04-07 02:08 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2016-07-02 10:41 | 2016-07-26 12:19 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-12-19 21:48 | 2016-03-03 01:22 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-25 16:16 | 2014-01-28 02:47 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-09-04 12:29 | 2015-11-25 18:34 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-12 06:29 | 2014-07-29 16:03 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-07 17:18 | 2014-11-07 07:39 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 1.8795 | 0 | 0 | 0
Project-A12 | 2014-11-05 10:32 | 2014-12-07 04:13 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-24 00:19 | 2015-03-10 15:25 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-31 10:11 | 2014-08-18 18:25 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-19 23:43 | 2014-09-06 05:15 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-07-17 15:28 | 2015-09-23 19:20 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-20 18:50 | 2014-06-02 14:09 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-10 02:31 | 2014-03-17 17:02 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-28 23:35 | 2014-07-16 00:01 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-08 02:08 | 2014-04-19 02:52 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2016-07-27 12:19 | 2016-08-20 13:57 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-03-04 01:22 | 2016-05-17 04:55 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-29 02:47 | 2014-01-31 13:18 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-11-26 18:34 | 2016-02-17 00:39 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-30 16:03 | 2014-08-17 01:37 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-11-08 07:39 | 2014-12-08 21:59 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-11 04:13 | 2015-01-11 21:53 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-11 15:25 | 2015-04-26 06:32 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-19 18:25 | 2014-09-07 02:39 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-07 05:15 | 2014-09-24 10:47 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.3986 | 39.8597 | 39
0.44516 | 44.5157 | 44
0.62121 | 62.1208 | 62
0.28795 | 28.7948 | 28
0.87958 | 87.9579 | 87
0.0046377 | 0.46377 | 0
0.64916 | 64.9161 | 64
0.59446 | 59.446 | 59
0.69328 | 69.3279 | 69
0.13794 | 13.7935 | 13
0.11522 | 11.5225 | 11
0.21668 | 21.6683 | 21
0.9228 | 92.2795 | 92
0.35599 | 35.5989 | 35
0.6987 | 69.8703 | 69
0.64943 | 64.9431 | 64
0.77325 | 77.325 | 77
0.46233 | 46.2332 | 46
0.50978 | 50.9783 | 50
0.082109 | 8.2109 | 8
0.055424 | 5.5424 | 5
0.87433 | 87.4334 | 87
0.1126 | 11.2595 | 11
0.25192 | 25.1922 | 25
0.29791 | 29.7908 | 29
0.30804 | 30.8044 | 30
0.39228 | 39.2281 | 39
0.91236 | 91.2364 | 91
0.83427 | 83.4275 | 83
0.78003 | 78.0026 | 78
0.87048 | 87.0478 | 87
0.97212 | 97.2119 | 97
0.69673 | 69.673 | 69
0.92643 | 92.6432 | 92
0.49063 | 49.0628 | 49
0.83286 | 83.2864 | 83
0.64274 | 64.2736 | 64
0.78565 | 78.5648 | 78
0.10558 | 10.5579 | 10

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1857.5814 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH