## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.53372 | 1.5165 |  |  |  | 17 | 17.76 | 34.76 | 31.8517 |  | 4.08 | 74 | 78.08 | 48.7963 |  | 4.08 | 17.76 | 21.84 | 11.7111 |  | 4.08 | 17.76 | 21.84 | 11.7111 |  | 4.08 | 17.76 | 21.84 | 11.7111 |  | 4.08 | 17.76 | 21.84 | 11.7111 |  | 200.2 | 127.4924 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 70.0737 | 107.3518 | 107.3518
Project-A02 |  | v002 |  | 0.56077 | 1.5017 |  |  |  | 15 | 19.2 | 34.2 | 26.7492 |  | 3.6 | 80 | 83.6 | 53.2739 |  | 3.6 | 19.2 | 22.8 | 12.7857 |  | 3.6 | 19.2 | 22.8 | 12.7857 |  | 3.6 | 19.2 | 22.8 | 12.7857 |  | 3.6 | 19.2 | 22.8 | 12.7857 |  | 209 | 131.1659 | 104500 |  | 0.058933 |  | 33 | 176 |  | 58.8482 | 117.2025 | 117.2025 | [12 empty] | E
Project-A03 |  | v003 |  | 0.5434 | 1.5006 |  |  |  | 16 | 6.48 | 22.48 | 29.444 |  | 3.84 | 27 | 30.84 | 17.9926 |  | 3.84 | 6.48 | 10.32 | 7.0666 |  | 3.84 | 6.48 | 10.32 | 7.0666 |  | 3.84 | 6.48 | 10.32 | 7.0666 |  | 3.84 | 6.48 | 10.32 | 7.0666 |  | 94.6 | 75.7029 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 64.7768 | 39.5838 | 64.7768 | [12 empty] | N
Project-A04 |  | v004 |  | 0.49821 | 1.5262 |  |  |  | 35 | 4.32 | 39.32 | 70.2508 |  | 8.4 | 18 | 26.4 | 16.8602 |  | 8.4 | 4.32 | 12.72 | 16.8602 |  | 8.4 | 4.32 | 12.72 | 16.8602 |  | 8.4 | 4.32 | 12.72 | 16.8602 |  | 8.4 | 4.32 | 12.72 | 16.8602 |  | 116.6 | 154.5519 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 154.5519 | 25.9462 | 154.5519 | [12 empty] | D
Project-A05 |  | v002 |  | 0.54275 | 4.1411 |  |  |  | 6 | 19.2 | 25.2 | 11.0548 |  | 1.44 | 80 | 81.44 | 19.3185 |  | 1.44 | 19.2 | 20.64 | 4.6364 |  | 1.44 | 19.2 | 20.64 | 4.6364 |  | 1.44 | 19.2 | 20.64 | 4.6364 |  | 1.44 | 19.2 | 20.64 | 4.6364 |  | 189.2 | 48.9191 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 24.3207 | 42.5006 | 42.5006
Project-A06 |  | v003 |  | 0.51776 | 1.5161 |  |  |  | 52 | 10.56 | 62.56 | 100.4335 |  | 12.48 | 44 | 56.48 | 29.0227 |  | 12.48 | 10.56 | 23.04 | 24.104 |  | 12.48 | 10.56 | 23.04 | 24.104 |  | 12.48 | 10.56 | 23.04 | 24.104 |  | 12.48 | 10.56 | 23.04 | 24.104 |  | 211.2 | 225.8724 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 220.9537 | 63.85 | 220.9537 | [12 empty] | O
Project-A07 |  | v005 |  | 0.49763 | 0.30248 |  |  |  | 93 | 19.92 | 112.92 | 186.8847 |  | 22.32 | 83 | 105.32 | 274.4019 |  | 22.32 | 19.92 | 42.24 | 65.8565 |  | 22.32 | 19.92 | 42.24 | 65.8565 |  | 22.32 | 19.92 | 42.24 | 65.8565 |  | 22.32 | 19.92 | 42.24 | 65.8565 |  | 387.2 | 724.7124 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 411.1463 | 603.6841 | 603.6841 | [12 empty] | F
Project-A08 |  | v006 |  | 0.49732 | 1.4882 |  |  |  | 5 | 2.64 | 7.64 | 10.0539 |  | 1.2 | 11 | 12.2 | 7.3914 |  | 1.2 | 2.64 | 3.84 | 2.4129 |  | 1.2 | 2.64 | 3.84 | 2.4129 |  | 1.2 | 2.64 | 3.84 | 2.4129 |  | 1.2 | 2.64 | 3.84 | 2.4129 |  | 35.2 | 27.0969 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 22.1185 | 16.2611 | 22.1185
Project-A09 |  | v003 |  | 0.53359 | 2.4063 |  |  |  | 49 | 20.64 | 69.64 | 91.8301 |  | 11.76 | 86 | 97.76 | 35.7401 |  | 11.76 | 20.64 | 32.4 | 22.0392 |  | 11.76 | 20.64 | 32.4 | 22.0392 |  | 11.76 | 20.64 | 32.4 | 22.0392 |  | 11.76 | 20.64 | 32.4 | 22.0392 |  | 297 | 215.7271 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 202.0263 | 78.6281 | 202.0263 | [12 empty] | T
Project-A10 |  | v001 |  | 0.56547 | 0.29632 |  |  |  | 36 | 20.88 | 56.88 | 70.464 |  | 8.64 | 87 | 95.64 | 293.6001 |  | 8.64 | 20.88 | 29.52 | 70.464 |  | 8.64 | 20.88 | 29.52 | 70.464 |  | 8.64 | 20.88 | 29.52 | 70.464 |  | 8.64 | 20.88 | 29.52 | 70.464 |  | 270.6 | 645.9202 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 140.0599 | 645.9202 | 645.9202 | [12 empty] | H
Project-A11 |  | v002 |  | 0.50465 | 1.488 |  |  |  | 63 | 19.2 | 82.2 | 124.8392 |  | 15.12 | 80 | 95.12 | 53.7626 |  | 15.12 | 19.2 | 34.32 | 29.9614 |  | 15.12 | 19.2 | 34.32 | 29.9614 |  | 15.12 | 19.2 | 34.32 | 29.9614 |  | 15.12 | 19.2 | 34.32 | 29.9614 |  | 314.6 | 298.4475 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 274.6463 | 118.2777 | 274.6463 | [12 empty] | I
Project-A12 |  | v004 |  | 0.30736 | 0.26592 |  |  |  | 65 | 21.84 | 86.84 | 211.4784 |  | 15.6 | 91 | 106.6 | 342.2031 |  | 15.6 | 21.84 | 37.44 | 82.1287 |  | 15.6 | 21.84 | 37.44 | 82.1287 |  | 15.6 | 21.84 | 37.44 | 82.1287 |  | 15.6 | 21.84 | 37.44 | 82.1287 |  | 343.2 | 882.1964 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 465.2524 | 752.8468 | 752.8468 | [12 empty] | S
Project-A13 |  | v007 |  | 0.49678 | 2.0022 |  |  |  | 96 | 9.6 | 105.6 | 193.2438 |  | 23.04 | 40 | 63.04 | 46.3785 |  | 23.04 | 9.6 | 32.64 | 46.3785 |  | 23.04 | 9.6 | 32.64 | 46.3785 |  | 23.04 | 9.6 | 32.64 | 46.3785 |  | 23.04 | 9.6 | 32.64 | 46.3785 |  | 299.2 | 425.1363 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 425.1363 | 43.9519 | 425.1363
Project-A14 |  | v006 |  | 0.25257 | 1.98 |  |  |  | 39 | 12.72 | 51.72 | 154.4142 |  | 9.36 | 53 | 62.36 | 37.0594 |  | 9.36 | 12.72 | 22.08 | 37.0594 |  | 9.36 | 12.72 | 22.08 | 37.0594 |  | 9.36 | 12.72 | 22.08 | 37.0594 |  | 9.36 | 12.72 | 22.08 | 37.0594 |  | 202.4 | 339.7112 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 339.7112 | 58.8879 | 339.7112 | [12 empty] | W
Project-A15 |  | v008 |  | 1.148 | 2.0684 |  |  |  | 72 | 23.76 | 95.76 | 62.7173 |  | 17.28 | 99 | 116.28 | 47.8642 |  | 17.28 | 23.76 | 41.04 | 15.0522 |  | 17.28 | 23.76 | 41.04 | 15.0522 |  | 17.28 | 23.76 | 41.04 | 15.0522 |  | 17.28 | 23.76 | 41.04 | 15.0522 |  | 376.2 | 170.7901 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 137.9781 | 105.3013 | 137.9781 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 91.714 |  | 10.544 | 63.5333 | 74.0773 | 88.2444 |  | 10.544 | 15.248 | 25.792 | 29.9011 |  | 10.544 | 15.248 | 25.792 | 29.9011 |  | 10.544 | 15.248 | 25.792 | 29.9011 |  | 10.544 | 15.248 | 25.792 | 29.9011 |  | 236.4267 | 299.5628 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 200.7733 | 188.0129 | 274.0937 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1375.7096 |  | 158.16 | 953 | 1111.16 | 1323.6654 |  | 158.16 | 228.72 | 386.88 | 448.5169 |  | 158.16 | 228.72 | 386.88 | 448.5169 |  | 158.16 | 228.72 | 386.88 | 448.5169 |  | 158.16 | 228.72 | 386.88 | 448.5169 |  | 3546.4 | 4493.4426 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3011.6 | 2820.194 | 4111.405 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 934.1964 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 305.4295 |  | <- To shorten average individual project span |  |  |  | <----------> | 274.0937
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 57.4597 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 621.2867 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1918.3723 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.53372 | 1.5165 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-02-02 20:26 |  | 0 | 2015-02-03 20:26 | 2015-03-24 15:33 |  | 0 | 2015-03-25 15:33 | 2015-04-06 08:37 |  | 0 | 2015-04-07 08:37 | 2015-04-19 01:41 |  | 4 | 2015-04-24 01:41 | 2015-05-05 18:45 |  | 3 | 2015-05-09 18:45 | 2015-05-21 11:49 |  | v001 |  | 0.056452 |  | 365 | 0 | 0 | 0 | 4 | 3 | 372 | 309.0726 |  | 139.4924 | 934.1964 | [14 empty] | E
Project-A02 |  | 0.56077 | 1.5017 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-28 17:59 |  | 0 | 2014-01-29 17:59 | 2014-03-24 00:33 |  | 0 | 2014-03-25 00:33 | 2014-04-06 19:25 |  | 0 | 2014-04-07 19:25 | 2014-04-20 14:16 |  | 0 | 2014-04-21 14:16 | 2014-05-04 09:07 |  | 0 | 2014-05-05 09:07 | 2014-05-18 03:59 |  | v002 |  | 0.058933 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 136.1659 | [15 empty] | N
Project-A03 |  | 0.5434 | 1.5006 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-31 10:39 |  | 0 | 2014-02-01 10:39 | 2014-02-19 10:29 |  | 0 | 2014-02-20 10:29 | 2014-02-27 12:05 |  | 0 | 2014-02-28 12:05 | 2014-03-07 13:40 |  | 0 | 2014-03-08 13:40 | 2014-03-15 15:16 |  | 0 | 2014-03-16 15:16 | 2014-03-23 16:52 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80.7029 | [15 empty] | D
Project-A04 |  | 0.49821 | 1.5262 |  |  |  | 2014-01-01 |  | 36 | 2014-02-07 | 2014-04-18 06:01 |  | 0 | 2014-04-19 06:01 | 2014-05-06 02:40 |  | 0 | 2014-05-07 02:40 | 2014-05-23 23:19 |  | 0 | 2014-05-24 23:19 | 2014-06-10 19:57 |  | 0 | 2014-06-11 19:57 | 2014-06-28 16:36 |  | 0 | 2014-06-29 16:36 | 2014-07-16 13:15 |  | v004 |  | 0.032878 |  | 36 | 0 | 0 | 0 | 0 | 0 | 36 | 17.7543 |  | 159.5519
Project-A05 |  | 0.54275 | 4.1411 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-02-27 01:19 |  | 0 | 2014-02-28 01:19 | 2014-03-19 08:58 |  | 0 | 2014-03-20 08:58 | 2014-03-25 00:14 |  | 0 | 2014-03-26 00:14 | 2014-03-30 15:31 |  | 0 | 2014-03-31 15:31 | 2014-04-05 06:47 |  | 0 | 2014-04-06 06:47 | 2014-04-10 22:03 |  | v002 |  | 0.05335 |  | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 36.0112 |  | 53.9191 | [15 empty] | O
Project-A06 |  | 0.51776 | 1.5161 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-04-12 10:24 |  | 0 | 2014-04-13 10:24 | 2014-05-12 10:57 |  | 0 | 2014-05-13 10:57 | 2014-06-06 13:27 |  | 6 | 2014-06-13 13:27 | 2014-07-07 15:57 |  | 0 | 2014-07-08 15:57 | 2014-08-01 18:26 |  | 0 | 2014-08-02 18:26 | 2014-08-26 20:56 |  | v003 |  | 0.059553 |  | 0 | 0 | 0 | 6 | 0 | 0 | 6 | 0 |  | 236.8724 | [15 empty] | F
Project-A07 |  | 0.49763 | 0.30248 |  |  |  | 2014-01-01 |  | 68 | 2014-03-11 | 2014-09-13 21:14 |  | 0 | 2014-09-14 21:14 | 2015-06-16 06:53 |  | 0 | 2015-06-17 06:53 | 2015-08-22 03:26 |  | 0 | 2015-08-23 03:26 | 2015-10-27 23:59 |  | 0 | 2015-10-28 23:59 | 2016-01-02 20:33 |  | 0 | 2016-01-03 20:33 | 2016-03-09 17:06 |  | v005 |  | 0.10918 |  | 68 | 0 | 0 | 0 | 0 | 0 | 68 | 111.3648 |  | 729.7124
Project-A08 |  | 0.49732 | 1.4882 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-12 01:18 |  | 0 | 2014-01-13 01:18 | 2014-01-20 10:41 |  | 0 | 2014-01-21 10:41 | 2014-01-23 20:36 |  | 0 | 2014-01-24 20:36 | 2014-01-27 06:30 |  | 0 | 2014-01-28 06:30 | 2014-01-30 16:25 |  | 0 | 2014-01-31 16:25 | 2014-02-03 02:20 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 32.0969 | [15 empty] | T
Project-A09 |  | 0.53359 | 2.4063 |  |  |  | 2014-01-01 |  | 15 | 2014-01-17 | 2014-04-18 19:55 |  | 0 | 2014-04-19 19:55 | 2014-05-25 13:41 |  | 0 | 2014-05-26 13:41 | 2014-06-17 14:38 |  | 0 | 2014-06-18 14:38 | 2014-07-10 15:34 |  | 0 | 2014-07-11 15:34 | 2014-08-02 16:31 |  | 0 | 2014-08-03 16:31 | 2014-08-25 17:27 |  | v003 |  | 0.083747 |  | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 18.8431 |  | 220.7271 | [15 empty] | H
Project-A10 |  | 0.56547 | 0.29632 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-13 11:08 |  | 0 | 2014-03-14 11:08 | 2015-01-02 01:32 |  | 0 | 2015-01-03 01:32 | 2015-03-14 12:41 |  | 0 | 2015-03-15 12:41 | 2015-05-24 23:49 |  | 0 | 2015-05-25 23:49 | 2015-08-04 10:57 |  | 0 | 2015-08-05 10:57 | 2015-10-14 22:05 |  | v001 |  | 0.076303 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 650.9202 | [15 empty] | I
Project-A11 |  | 0.50465 | 1.488 |  |  |  | 2014-01-01 |  | 35 | 2014-02-06 | 2014-06-10 20:08 |  | 0 | 2014-06-11 20:08 | 2014-08-04 14:27 |  | 0 | 2014-08-05 14:27 | 2014-09-04 13:31 |  | 0 | 2014-09-05 13:31 | 2014-10-05 12:36 |  | 0 | 2014-10-06 12:36 | 2014-11-05 11:40 |  | 0 | 2014-11-06 11:40 | 2014-12-06 10:44 |  | v002 |  | 0.08871 |  | 35 | 0 | 0 | 0 | 0 | 0 | 35 | 46.5726 |  | 303.4475 | [15 empty] | S
Project-A12 |  | 0.30736 | 0.26592 |  |  |  | 2014-01-01 |  | 47 | 2014-02-18 | 2014-09-17 11:29 |  | 0 | 2014-09-18 11:29 | 2015-08-26 16:21 |  | 0 | 2015-08-27 16:21 | 2015-11-17 19:27 |  | 0 | 2015-11-18 19:27 | 2016-02-08 22:32 |  | 0 | 2016-02-09 22:32 | 2016-05-02 01:37 |  | 0 | 2016-05-03 01:37 | 2016-07-24 04:43 |  | v004 |  | 0.096774 |  | 47 | 0 | 0 | 0 | 0 | 0 | 47 | 68.2258 |  | 887.1964
Project-A13 |  | 0.49678 | 2.0022 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-09-08 05:51 |  | 0 | 2014-09-09 05:51 | 2014-10-25 14:56 |  | 0 | 2014-10-26 14:56 | 2014-12-12 00:01 |  | 0 | 2014-12-13 00:01 | 2015-01-28 09:06 |  | 0 | 2015-01-29 09:06 | 2015-03-16 18:11 |  | 0 | 2015-03-17 18:11 | 2015-05-03 03:16 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 430.1363 | [15 empty] | W
Project-A14 |  | 0.25257 | 1.98 |  |  |  | 2014-01-01 |  | 69 | 2014-03-12 | 2014-08-13 09:56 |  | 0 | 2014-08-14 09:56 | 2014-09-20 11:22 |  | 0 | 2014-09-21 11:22 | 2014-10-28 12:47 |  | 0 | 2014-10-29 12:47 | 2014-12-05 14:13 |  | 0 | 2014-12-06 14:13 | 2015-01-12 15:39 |  | 0 | 2015-01-13 15:39 | 2015-02-19 17:04 |  | v006 |  | 0.057072 |  | 69 | 0 | 0 | 0 | 0 | 0 | 69 | 59.0695 |  | 344.7112 | [15 empty] | O
Project-A15 |  | 1.148 | 2.0684 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-05-22 17:13 |  | 0 | 2014-05-23 17:13 | 2014-07-10 13:57 |  | 0 | 2014-07-11 13:57 | 2014-07-26 15:13 |  | 0 | 2014-07-27 15:13 | 2014-08-11 16:28 |  | 0 | 2014-08-12 16:28 | 2014-08-27 17:43 |  | 0 | 2014-08-28 17:43 | 2014-09-12 18:58 |  | v008 |  | 0.10608 |  | 78 | 0 | 0 | 0 | 0 | 0 | 78 | 124.1129 |  | 175.7901 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 54.2667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.4 |  |  |  | 0.26667 |  |  |  | 0.2 | [5 empty] | 0.066667 |  | 54.2667 | 0 | 0 | 0.4 | 0.26667 | 0.2 | 55.1333 | 57.4597 | Average | 305.4295 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 814 |  |  |  | 0 |  |  |  | 0 |  |  |  | 6 |  |  |  | 4 |  |  |  | 3 | [5 empty] | 1 |  | 814 | 0 | 0 | 6 | 4 | 3 | 827 | 861.8952 | Total | 4581.4426 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 2
| Days: | 12.4257
E
N
SIT - Violation | Count: | 2 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 12.4257
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2015-03-25 15:33 | 2015-04-06 08:37 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-25 00:33 | 2014-04-06 19:25 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-20 10:29 | 2014-02-27 12:05 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-07 02:40 | 2014-05-23 23:19 | v004 | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 10.515 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-03-20 08:58 | 2014-03-25 00:14 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-05-13 10:57 | 2014-06-06 13:27 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-06-17 06:53 | 2015-08-22 03:26 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-21 10:41 | 2014-01-23 20:36 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-05-26 13:41 | 2014-06-17 14:38 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2015-01-03 01:32 | 2015-03-14 12:41 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-08-05 14:27 | 2014-09-04 13:31 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2015-08-27 16:21 | 2015-11-17 19:27 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-26 14:56 | 2014-12-12 00:01 | v007 |  | Count P-A14: 1; Count P-A15: 0 | [13 empty] | 1.9107 | 0 | E
Project-A14 | 2014-09-21 11:22 | 2014-10-28 12:47 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-11 13:57 | 2014-07-26 15:13 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-04-07 08:37 | 2015-04-19 01:41 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-07 19:25 | 2014-04-20 14:16 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-28 12:05 | 2014-03-07 13:40 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-24 23:19 | 2014-06-10 19:57 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-26 00:14 | 2014-03-30 15:31 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-06-13 13:27 | 2014-07-07 15:57 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-23 03:26 | 2015-10-27 23:59 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-24 20:36 | 2014-01-27 06:30 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-06-18 14:38 | 2014-07-10 15:34 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-03-15 12:41 | 2015-05-24 23:49 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-05 13:31 | 2014-10-05 12:36 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2015-11-18 19:27 | 2016-02-08 22:32 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-13 00:01 | 2015-01-28 09:06 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-10-29 12:47 | 2014-12-05 14:13 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-07-27 15:13 | 2014-08-11 16:28 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-04-24 01:41 | 2015-05-05 18:45 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-21 14:16 | 2014-05-04 09:07 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-08 13:40 | 2014-03-15 15:16 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-11 19:57 | 2014-06-28 16:36 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-31 15:31 | 2014-04-05 06:47 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-07-08 15:57 | 2014-08-01 18:26 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-28 23:59 | 2016-01-02 20:33 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-28 06:30 | 2014-01-30 16:25 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-11 15:34 | 2014-08-02 16:31 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-05-25 23:49 | 2015-08-04 10:57 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-06 12:36 | 2014-11-05 11:40 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2016-02-09 22:32 | 2016-05-02 01:37 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-29 09:06 | 2015-03-16 18:11 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-12-06 14:13 | 2015-01-12 15:39 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-12 16:28 | 2014-08-27 17:43 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-05-09 18:45 | 2015-05-21 11:49 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-05 09:07 | 2014-05-18 03:59 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-16 15:16 | 2014-03-23 16:52 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-29 16:36 | 2014-07-16 13:15 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-06 06:47 | 2014-04-10 22:03 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-02 18:26 | 2014-08-26 20:56 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-01-03 20:33 | 2016-03-09 17:06 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-31 16:25 | 2014-02-03 02:20 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-03 16:31 | 2014-08-25 17:27 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-08-05 10:57 | 2015-10-14 22:05 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-11-06 11:40 | 2014-12-06 10:44 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2016-05-03 01:37 | 2016-07-24 04:43 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-17 18:11 | 2015-05-03 03:16 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-01-13 15:39 | 2015-02-19 17:04 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-28 17:43 | 2014-09-12 18:58 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.31577 | 31.5771 | 31
0.21056 | 21.056 | 21
0.010281 | 1.0281 | 1
0.55568 | 55.5677 | 55
0.5592 | 55.9205 | 55
0.30843 | 30.8433 | 30
0.60657 | 60.6568 | 60
0.92903 | 92.9034 | 92
0.12094 | 12.0944 | 12
0.53718 | 53.7182 | 53
0.28751 | 28.7509 | 28
0.53826 | 53.8256 | 53
0.84104 | 84.1042 | 84
0.48743 | 48.7431 | 48
0.9469 | 94.6897 | 94
0.22493 | 22.4928 | 22
0.41744 | 41.7438 | 41
0.24926 | 24.9258 | 24
0.22591 | 22.5912 | 22
0.23548 | 23.5475 | 23
0.58879 | 58.8787 | 58
0.97804 | 97.8042 | 97
0.61312 | 61.3115 | 61
0.78668 | 78.6679 | 78
0.39142 | 39.1417 | 39
0.31969 | 31.9692 | 31
0.06474 | 6.474 | 6
0.89679 | 89.6788 | 89
0.24868 | 24.868 | 24
0.73623 | 73.6228 | 73
0.51021 | 51.0215 | 51
0.35278 | 35.2777 | 35
0.29027 | 29.0267 | 29
0.35547 | 35.5468 | 35
0.21166 | 21.1665 | 21
0.20231 | 20.2313 | 20
0.59716 | 59.7159 | 59
0.99163 | 99.1627 | 99
0.69339 | 69.3393 | 69

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1918.3723 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH