## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.55614 | 1.5027 |  |  |  | 17 | 17.76 | 34.76 | 30.5681 |  | 4.08 | 74 | 78.08 | 49.2435 |  | 4.08 | 17.76 | 21.84 | 11.8184 |  | 4.08 | 17.76 | 21.84 | 11.8184 |  | 4.08 | 17.76 | 21.84 | 11.8184 |  | 4.08 | 17.76 | 21.84 | 11.8184 |  | 200.2 | 127.0854 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 67.2498 | 108.3357 | 108.3357
Project-A02 |  | v002 |  | 0.50828 | 1.4969 |  |  |  | 15 | 19.2 | 34.2 | 29.5112 |  | 3.6 | 80 | 83.6 | 53.4427 |  | 3.6 | 19.2 | 22.8 | 12.8262 |  | 3.6 | 19.2 | 22.8 | 12.8262 |  | 3.6 | 19.2 | 22.8 | 12.8262 |  | 3.6 | 19.2 | 22.8 | 12.8262 |  | 209 | 134.2589 | 104500 |  | 0.058933 |  | 33 | 176 |  | 64.9247 | 117.5739 | 117.5739 | [12 empty] | E
Project-A03 |  | v003 |  | 0.51882 | 1.5214 |  |  |  | 16 | 6.48 | 22.48 | 30.8391 |  | 3.84 | 27 | 30.84 | 17.7468 |  | 3.84 | 6.48 | 10.32 | 7.4014 |  | 3.84 | 6.48 | 10.32 | 7.4014 |  | 3.84 | 6.48 | 10.32 | 7.4014 |  | 3.84 | 6.48 | 10.32 | 7.4014 |  | 94.6 | 78.1915 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 67.8461 | 39.043 | 67.8461 | [12 empty] | N
Project-A04 |  | v004 |  | 0.50494 | 1.489 |  |  |  | 35 | 4.32 | 39.32 | 69.315 |  | 8.4 | 18 | 26.4 | 16.6356 |  | 8.4 | 4.32 | 12.72 | 16.6356 |  | 8.4 | 4.32 | 12.72 | 16.6356 |  | 8.4 | 4.32 | 12.72 | 16.6356 |  | 8.4 | 4.32 | 12.72 | 16.6356 |  | 116.6 | 152.493 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 152.493 | 26.5957 | 152.493 | [12 empty] | D
Project-A05 |  | v002 |  | 0.56743 | 1.5255 |  |  |  | 6 | 19.2 | 25.2 | 12.5864 |  | 1.44 | 80 | 81.44 | 52.4434 |  | 1.44 | 19.2 | 20.64 | 12.5864 |  | 1.44 | 19.2 | 20.64 | 12.5864 |  | 1.44 | 19.2 | 20.64 | 12.5864 |  | 1.44 | 19.2 | 20.64 | 12.5864 |  | 189.2 | 115.3754 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 23.2628 | 115.3754 | 115.3754
Project-A06 |  | v003 |  | 0.50036 | 1.5538 |  |  |  | 52 | 10.56 | 62.56 | 103.9253 |  | 12.48 | 44 | 56.48 | 28.3169 |  | 12.48 | 10.56 | 23.04 | 24.9421 |  | 12.48 | 10.56 | 23.04 | 24.9421 |  | 12.48 | 10.56 | 23.04 | 24.9421 |  | 12.48 | 10.56 | 23.04 | 24.9421 |  | 211.2 | 232.0105 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 228.6357 | 62.2972 | 228.6357 | [12 empty] | O
Project-A07 |  | v005 |  | 0.2534 | 1.5318 |  |  |  | 93 | 19.92 | 112.92 | 367.009 |  | 22.32 | 83 | 105.32 | 88.0821 |  | 22.32 | 19.92 | 42.24 | 88.0821 |  | 22.32 | 19.92 | 42.24 | 88.0821 |  | 22.32 | 19.92 | 42.24 | 88.0821 |  | 22.32 | 19.92 | 42.24 | 88.0821 |  | 387.2 | 807.4197 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 807.4197 | 119.2068 | 807.4197 | [12 empty] | F
Project-A08 |  | v006 |  | 0.56853 | 1.5107 |  |  |  | 5 | 2.64 | 7.64 | 8.7947 |  | 1.2 | 11 | 12.2 | 7.2812 |  | 1.2 | 2.64 | 3.84 | 2.1107 |  | 1.2 | 2.64 | 3.84 | 2.1107 |  | 1.2 | 2.64 | 3.84 | 2.1107 |  | 1.2 | 2.64 | 3.84 | 2.1107 |  | 35.2 | 24.5188 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 19.3483 | 16.0186 | 19.3483
Project-A09 |  | v003 |  | 0.53008 | 0.30329 |  |  |  | 49 | 20.64 | 69.64 | 92.4389 |  | 11.76 | 86 | 97.76 | 283.5532 |  | 11.76 | 20.64 | 32.4 | 68.0528 |  | 11.76 | 20.64 | 32.4 | 68.0528 |  | 11.76 | 20.64 | 32.4 | 68.0528 |  | 11.76 | 20.64 | 32.4 | 68.0528 |  | 297 | 648.2032 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 203.3656 | 623.8171 | 623.8171 | [12 empty] | T
Project-A10 |  | v001 |  | 0.55522 | 1.5366 |  |  |  | 36 | 20.88 | 56.88 | 64.8396 |  | 8.64 | 87 | 95.64 | 56.6193 |  | 8.64 | 20.88 | 29.52 | 15.5615 |  | 8.64 | 20.88 | 29.52 | 15.5615 |  | 8.64 | 20.88 | 29.52 | 15.5615 |  | 8.64 | 20.88 | 29.52 | 15.5615 |  | 270.6 | 183.705 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 142.6471 | 124.5625 | 142.6471 | [12 empty] | H
Project-A11 |  | v002 |  | 0.51259 | 1.5281 |  |  |  | 63 | 19.2 | 82.2 | 122.9052 |  | 15.12 | 80 | 95.12 | 52.3534 |  | 15.12 | 19.2 | 34.32 | 29.4972 |  | 15.12 | 19.2 | 34.32 | 29.4972 |  | 15.12 | 19.2 | 34.32 | 29.4972 |  | 15.12 | 19.2 | 34.32 | 29.4972 |  | 314.6 | 293.2476 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 270.3914 | 115.1776 | 270.3914 | [12 empty] | I
Project-A12 |  | v004 |  | 0.28087 | 2.3829 |  |  |  | 65 | 21.84 | 86.84 | 231.4222 |  | 15.6 | 91 | 106.6 | 55.5413 |  | 15.6 | 21.84 | 37.44 | 55.5413 |  | 15.6 | 21.84 | 37.44 | 55.5413 |  | 15.6 | 21.84 | 37.44 | 55.5413 |  | 15.6 | 21.84 | 37.44 | 55.5413 |  | 343.2 | 509.1289 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 509.1289 | 84.0155 | 509.1289 | [12 empty] | S
Project-A13 |  | v007 |  | 0.58988 | 2.0087 |  |  |  | 96 | 9.6 | 105.6 | 162.7436 |  | 23.04 | 40 | 63.04 | 39.0585 |  | 23.04 | 9.6 | 32.64 | 39.0585 |  | 23.04 | 9.6 | 32.64 | 39.0585 |  | 23.04 | 9.6 | 32.64 | 39.0585 |  | 23.04 | 9.6 | 32.64 | 39.0585 |  | 299.2 | 358.036 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 358.036 | 43.8104 | 358.036
Project-A14 |  | v006 |  | 0.52908 | 2.0068 |  |  |  | 39 | 12.72 | 51.72 | 73.713 |  | 9.36 | 53 | 62.36 | 26.4097 |  | 9.36 | 12.72 | 22.08 | 17.6911 |  | 9.36 | 12.72 | 22.08 | 17.6911 |  | 9.36 | 12.72 | 22.08 | 17.6911 |  | 9.36 | 12.72 | 22.08 | 17.6911 |  | 202.4 | 170.8871 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 162.1685 | 58.1012 | 162.1685 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0244 | 2.1018 |  |  |  | 72 | 23.76 | 95.76 | 70.286 |  | 17.28 | 99 | 116.28 | 47.1025 |  | 17.28 | 23.76 | 41.04 | 16.8686 |  | 17.28 | 23.76 | 41.04 | 16.8686 |  | 17.28 | 23.76 | 41.04 | 16.8686 |  | 17.28 | 23.76 | 41.04 | 16.8686 |  | 376.2 | 184.8632 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 154.6293 | 103.6256 | 154.6293 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 98.0598 |  | 10.544 | 63.5333 | 74.0773 | 58.2553 |  | 10.544 | 15.248 | 25.792 | 27.9116 |  | 10.544 | 15.248 | 25.792 | 27.9116 |  | 10.544 | 15.248 | 25.792 | 27.9116 |  | 10.544 | 15.248 | 25.792 | 27.9116 |  | 236.4267 | 267.9616 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 215.4365 | 117.1704 | 255.8564 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1470.8974 |  | 158.16 | 953 | 1111.16 | 873.8302 |  | 158.16 | 228.72 | 386.88 | 418.6741 |  | 158.16 | 228.72 | 386.88 | 418.6741 |  | 158.16 | 228.72 | 386.88 | 418.6741 |  | 158.16 | 228.72 | 386.88 | 418.6741 |  | 3546.4 | 4019.4241 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3231.5469 | 1757.5561 | 3837.8462 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 881.4197 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 273.4283 |  | <- To shorten average individual project span |  |  |  | <----------> | 255.8564
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 59.2934 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 5.4226 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1219.564 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.55614 | 1.5027 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-01 13:38 |  | 0 | 2014-02-02 13:38 | 2014-03-23 19:29 |  | 0 | 2014-03-24 19:29 | 2014-04-05 15:07 |  | 0 | 2014-04-06 15:07 | 2014-04-18 10:46 |  | 0 | 2014-04-19 10:46 | 2014-05-01 06:24 |  | 0 | 2014-05-02 06:24 | 2014-05-14 02:03 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 132.0854 | 881.4197 | [14 empty] | E
Project-A02 |  | 0.50828 | 1.4969 |  |  |  | 2014-01-01 |  | 14 | 2014-01-16 | 2014-02-14 12:16 |  | 0 | 2014-02-15 12:16 | 2014-04-09 22:54 |  | 0 | 2014-04-10 22:54 | 2014-04-23 18:43 |  | 0 | 2014-04-24 18:43 | 2014-05-07 14:33 |  | 0 | 2014-05-08 14:33 | 2014-05-21 10:23 |  | 0 | 2014-05-22 10:23 | 2014-06-04 06:13 |  | v002 |  | 0.058933 |  | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 12.3759 |  | 139.2589 | [15 empty] | N
Project-A03 |  | 0.51882 | 1.5214 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-01 20:08 |  | 0 | 2014-02-02 20:08 | 2014-02-20 14:04 |  | 0 | 2014-02-21 14:04 | 2014-02-28 23:42 |  | 0 | 2014-03-01 23:42 | 2014-03-09 09:20 |  | 0 | 2014-03-10 09:20 | 2014-03-17 18:58 |  | 0 | 2014-03-18 18:58 | 2014-03-26 04:36 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 83.1915 | [15 empty] | D
Project-A04 |  | 0.50494 | 1.489 |  |  |  | 2014-01-01 |  | 36 | 2014-02-07 | 2014-04-17 07:34 |  | 0 | 2014-04-18 07:34 | 2014-05-04 22:49 |  | 0 | 2014-05-05 22:49 | 2014-05-22 14:04 |  | 0 | 2014-05-23 14:04 | 2014-06-09 05:19 |  | 0 | 2014-06-10 05:19 | 2014-06-26 20:35 |  | 0 | 2014-06-27 20:35 | 2014-07-14 11:50 |  | v004 |  | 0.032878 |  | 36 | 0 | 0 | 0 | 0 | 0 | 36 | 17.7543 |  | 157.493
Project-A05 |  | 0.56743 | 1.5255 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-14 14:04 |  | 0 | 2014-01-15 14:04 | 2014-03-09 00:43 |  | 0 | 2014-03-10 00:43 | 2014-03-22 14:47 |  | 0 | 2014-03-23 14:47 | 2014-04-05 04:52 |  | 0 | 2014-04-06 04:52 | 2014-04-18 18:56 |  | 0 | 2014-04-19 18:56 | 2014-05-02 09:01 |  | v002 |  | 0.05335 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 120.3754 | [15 empty] | O
Project-A06 |  | 0.50036 | 1.5538 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-04-15 22:12 |  | 0 | 2015-04-16 22:12 | 2015-05-15 05:49 |  | 0 | 2015-05-16 05:49 | 2015-06-10 04:25 |  | 0 | 2015-06-11 04:25 | 2015-07-06 03:02 |  | 0 | 2015-07-07 03:02 | 2015-08-01 01:39 |  | 0 | 2015-08-02 01:39 | 2015-08-27 00:15 |  | v003 |  | 0.059553 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 326.0546 |  | 237.0105 | [15 empty] | F
Project-A07 |  | 0.2534 | 1.5318 |  |  |  | 2014-01-01 |  | 69 | 2014-03-12 | 2015-03-14 00:13 |  | 0 | 2015-03-15 00:13 | 2015-06-11 02:11 |  | 0 | 2015-06-12 02:11 | 2015-09-08 04:09 |  | 0 | 2015-09-09 04:09 | 2015-12-06 06:08 |  | 0 | 2015-12-07 06:08 | 2016-03-04 08:06 |  | 0 | 2016-03-05 08:06 | 2016-06-01 10:04 |  | v005 |  | 0.10918 |  | 69 | 0 | 0 | 0 | 0 | 0 | 69 | 113.0025 |  | 812.4197
Project-A08 |  | 0.56853 | 1.5107 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-10 19:04 |  | 0 | 2014-01-11 19:04 | 2014-01-19 01:49 |  | 0 | 2014-01-20 01:49 | 2014-01-22 04:29 |  | 0 | 2014-01-23 04:29 | 2014-01-25 07:08 |  | 0 | 2014-01-26 07:08 | 2014-01-28 09:48 |  | 0 | 2014-01-29 09:48 | 2014-01-31 12:27 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 29.5188 | [15 empty] | T
Project-A09 |  | 0.53008 | 0.30329 |  |  |  | 2014-01-01 |  | 15 | 2014-01-17 | 2014-04-19 10:32 |  | 0 | 2014-04-20 10:32 | 2015-01-28 23:49 |  | 0 | 2015-01-29 23:49 | 2015-04-08 01:05 |  | 0 | 2015-04-09 01:05 | 2015-06-16 02:21 |  | 0 | 2015-06-17 02:21 | 2015-08-24 03:37 |  | 0 | 2015-08-25 03:37 | 2015-11-01 04:53 |  | v003 |  | 0.083747 |  | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 18.8431 |  | 653.2032 | [15 empty] | H
Project-A10 |  | 0.55522 | 1.5366 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-03-30 20:09 |  | 0 | 2014-03-31 20:09 | 2014-05-27 11:01 |  | 0 | 2014-05-28 11:01 | 2014-06-13 00:29 |  | 7 | 2014-06-21 00:29 | 2014-07-06 13:58 |  | 0 | 2014-07-07 13:58 | 2014-07-23 03:27 |  | 0 | 2014-07-24 03:27 | 2014-08-08 16:55 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 7 | 0 | 0 | 30 | 26.3244 |  | 195.705 | [15 empty] | I
Project-A11 |  | 0.51259 | 1.5281 |  |  |  | 2014-01-01 |  | 37 | 2014-02-08 | 2014-06-10 21:43 |  | 0 | 2014-06-11 21:43 | 2014-08-03 06:12 |  | 0 | 2014-08-04 06:12 | 2014-09-02 18:08 |  | 0 | 2014-09-03 18:08 | 2014-10-03 06:04 |  | 0 | 2014-10-04 06:04 | 2014-11-02 18:00 |  | 0 | 2014-11-03 18:00 | 2014-12-03 05:57 |  | v002 |  | 0.08871 |  | 37 | 0 | 0 | 0 | 0 | 0 | 37 | 49.2339 |  | 298.2476 | [15 empty] | S
Project-A12 |  | 0.28087 | 2.3829 |  |  |  | 2014-01-01 |  | 48 | 2014-02-19 | 2014-10-08 10:08 |  | 0 | 2014-10-09 10:08 | 2014-12-03 23:08 |  | 0 | 2014-12-04 23:08 | 2015-01-29 12:07 |  | 0 | 2015-01-30 12:07 | 2015-03-27 01:07 |  | 0 | 2015-03-28 01:07 | 2015-05-22 14:06 |  | 0 | 2015-05-23 14:06 | 2015-07-18 03:06 |  | v004 |  | 0.096774 |  | 48 | 0 | 0 | 0 | 0 | 0 | 48 | 69.6774 |  | 514.1289
Project-A13 |  | 0.58988 | 2.0087 |  |  |  | 2014-01-01 |  | 59 | 2014-03-02 | 2014-08-11 17:51 |  | 0 | 2014-08-12 17:51 | 2014-09-20 19:15 |  | 0 | 2014-09-21 19:15 | 2014-10-30 20:39 |  | 0 | 2014-10-31 20:39 | 2014-12-09 22:03 |  | 0 | 2014-12-10 22:03 | 2015-01-18 23:28 |  | 0 | 2015-01-19 23:28 | 2015-02-28 00:52 |  | v007 |  | 0.084367 |  | 59 | 0 | 0 | 0 | 0 | 0 | 59 | 74.665 |  | 363.036 | [15 empty] | W
Project-A14 |  | 0.52908 | 2.0068 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-22 17:07 |  | 0 | 2014-05-23 17:07 | 2014-06-19 02:57 |  | 0 | 2014-06-20 02:57 | 2014-07-07 19:32 |  | 0 | 2014-07-08 19:32 | 2014-07-26 12:07 |  | 0 | 2014-07-27 12:07 | 2014-08-14 04:42 |  | 0 | 2014-08-15 04:42 | 2014-09-01 21:17 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 57.3573 |  | 175.8871 | [15 empty] | O
Project-A15 |  | 1.0244 | 2.1018 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-05-30 06:52 |  | 0 | 2014-05-31 06:52 | 2014-07-17 09:20 |  | 0 | 2014-07-18 09:20 | 2014-08-04 06:10 |  | 0 | 2014-08-05 06:10 | 2014-08-22 03:01 |  | 0 | 2014-08-23 03:01 | 2014-09-08 23:52 |  | 0 | 2014-09-09 23:52 | 2014-09-26 20:43 |  | v008 |  | 0.10608 |  | 78 | 0 | 0 | 0 | 0 | 0 | 78 | 124.1129 |  | 189.8632 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 54.0667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.46667 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 0.066667 |  | 54.0667 | 0 | 0 | 0.46667 | 0 | 0 | 54.5333 | 59.2934 | Average | 273.4283 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 811 |  |  |  | 0 |  |  |  | 0 |  |  |  | 7 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 1 |  | 811 | 0 | 0 | 7 | 0 | 0 | 818 | 889.4014 | Total | 4101.4241 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 1
| Days: | 0.10845
E
N
SIT - Violation | Count: | 0 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 0
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-24 19:29 | 2014-04-05 15:07 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-10 22:54 | 2014-04-23 18:43 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-21 14:04 | 2014-02-28 23:42 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-05 22:49 | 2014-05-22 14:04 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-03-10 00:43 | 2014-03-22 14:47 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2015-05-16 05:49 | 2015-06-10 04:25 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-06-12 02:11 | 2015-09-08 04:09 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-20 01:49 | 2014-01-22 04:29 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2015-01-29 23:49 | 2015-04-08 01:05 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-05-28 11:01 | 2014-06-13 00:29 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-08-04 06:12 | 2014-09-02 18:08 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-12-04 23:08 | 2015-01-29 12:07 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-09-21 19:15 | 2014-10-30 20:39 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-20 02:57 | 2014-07-07 19:32 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-18 09:20 | 2014-08-04 06:10 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-06 15:07 | 2014-04-18 10:46 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-24 18:43 | 2014-05-07 14:33 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-01 23:42 | 2014-03-09 09:20 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-23 14:04 | 2014-06-09 05:19 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-23 14:47 | 2014-04-05 04:52 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-06-11 04:25 | 2015-07-06 03:02 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-09-09 04:09 | 2015-12-06 06:08 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-23 04:29 | 2014-01-25 07:08 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-04-09 01:05 | 2015-06-16 02:21 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-21 00:29 | 2014-07-06 13:58 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-03 18:08 | 2014-10-03 06:04 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2015-01-30 12:07 | 2015-03-27 01:07 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-10-31 20:39 | 2014-12-09 22:03 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-08 19:32 | 2014-07-26 12:07 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-05 06:10 | 2014-08-22 03:01 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-19 10:46 | 2014-05-01 06:24 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-08 14:33 | 2014-05-21 10:23 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-10 09:20 | 2014-03-17 18:58 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-10 05:19 | 2014-06-26 20:35 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-06 04:52 | 2014-04-18 18:56 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-07-07 03:02 | 2015-08-01 01:39 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-12-07 06:08 | 2016-03-04 08:06 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-26 07:08 | 2014-01-28 09:48 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-06-17 02:21 | 2015-08-24 03:37 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-07 13:58 | 2014-07-23 03:27 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-04 06:04 | 2014-11-02 18:00 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2015-03-28 01:07 | 2015-05-22 14:06 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-10 22:03 | 2015-01-18 23:28 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-27 12:07 | 2014-08-14 04:42 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-23 03:01 | 2014-09-08 23:52 | v008
Prod - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0.10845
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-05-02 06:24 | 2014-05-14 02:03 | v001 |  |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0.10845 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-22 10:23 | 2014-06-04 06:13 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-18 18:58 | 2014-03-26 04:36 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-27 20:35 | 2014-07-14 11:50 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-19 18:56 | 2014-05-02 09:01 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-08-02 01:39 | 2015-08-27 00:15 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-03-05 08:06 | 2016-06-01 10:04 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-29 09:48 | 2014-01-31 12:27 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-08-25 03:37 | 2015-11-01 04:53 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-24 03:27 | 2014-08-08 16:55 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-11-03 18:00 | 2014-12-03 05:57 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2015-05-23 14:06 | 2015-07-18 03:06 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-19 23:28 | 2015-02-28 00:52 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-15 04:42 | 2014-09-01 21:17 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-09 23:52 | 2014-09-26 20:43 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.91067 | 91.0669 | 91
0.94586 | 94.5858 | 94
0.55746 | 55.7461 | 55
0.936 | 93.6 | 93
0.19979 | 19.9794 | 19
0.62425 | 62.4251 | 62
0.73075 | 73.0752 | 73
0.18844 | 18.8439 | 18
0.45789 | 45.7888 | 45
0.28198 | 28.1984 | 28
0.53036 | 53.0363 | 53
0.83424 | 83.4236 | 83
0.51414 | 51.4142 | 51
0.29976 | 29.9756 | 29
0.16476 | 16.476 | 16
0.098869 | 9.8869 | 9
0.086444 | 8.6444 | 8
0.80977 | 80.977 | 80
0.66245 | 66.245 | 66
0.0046838 | 0.46838 | 0
0.49184 | 49.1844 | 49
0.3858 | 38.5805 | 38
0.54442 | 54.4423 | 54
0.37664 | 37.6636 | 37
0.83019 | 83.0191 | 83
0.9095 | 90.9499 | 90
0.18979 | 18.979 | 18
0.60503 | 60.5031 | 60
0.34597 | 34.5972 | 34
0.35965 | 35.9645 | 35
0.93443 | 93.4428 | 93
0.17581 | 17.5805 | 17
0.75875 | 75.8755 | 75
0.20148 | 20.1483 | 20
0.0211 | 2.11 | 2
0.47731 | 47.7312 | 47
0.23498 | 23.4979 | 23
0.38214 | 38.2137 | 38
0.13523 | 13.5234 | 13

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1219.564 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH