## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.513 | 1.5074 |  |  |  | 17 | 17.76 | 34.76 | 33.1382 |  | 4.08 | 74 | 78.08 | 49.0902 |  | 4.08 | 17.76 | 21.84 | 11.7816 |  | 4.08 | 17.76 | 21.84 | 11.7816 |  | 4.08 | 17.76 | 21.84 | 11.7816 |  | 4.08 | 17.76 | 21.84 | 11.7816 |  | 200.2 | 129.3549 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 72.904 | 107.9984 | 107.9984
Project-A02 |  | v002 |  | 0.52317 | 1.508 |  |  |  | 15 | 19.2 | 34.2 | 28.6712 |  | 3.6 | 80 | 83.6 | 53.0505 |  | 3.6 | 19.2 | 22.8 | 12.7321 |  | 3.6 | 19.2 | 22.8 | 12.7321 |  | 3.6 | 19.2 | 22.8 | 12.7321 |  | 3.6 | 19.2 | 22.8 | 12.7321 |  | 209 | 132.6501 | 104500 |  | 0.058933 |  | 33 | 176 |  | 63.0767 | 116.711 | 116.711 | [12 empty] | E
Project-A03 |  | v003 |  | 0.52054 | 2.3601 |  |  |  | 16 | 6.48 | 22.48 | 30.7375 |  | 3.84 | 27 | 30.84 | 11.4402 |  | 3.84 | 6.48 | 10.32 | 7.377 |  | 3.84 | 6.48 | 10.32 | 7.377 |  | 3.84 | 6.48 | 10.32 | 7.377 |  | 3.84 | 6.48 | 10.32 | 7.377 |  | 94.6 | 71.6857 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 67.6225 | 25.1684 | 67.6225 | [12 empty] | N
Project-A04 |  | v004 |  | 0.50168 | 1.5184 |  |  |  | 35 | 4.32 | 39.32 | 69.7651 |  | 8.4 | 18 | 26.4 | 16.7436 |  | 8.4 | 4.32 | 12.72 | 16.7436 |  | 8.4 | 4.32 | 12.72 | 16.7436 |  | 8.4 | 4.32 | 12.72 | 16.7436 |  | 8.4 | 4.32 | 12.72 | 16.7436 |  | 116.6 | 153.4833 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 153.4833 | 26.0805 | 153.4833 | [12 empty] | D
Project-A05 |  | v002 |  | 0.58592 | 1.9066 |  |  |  | 6 | 19.2 | 25.2 | 10.2403 |  | 1.44 | 80 | 81.44 | 41.9586 |  | 1.44 | 19.2 | 20.64 | 10.0701 |  | 1.44 | 19.2 | 20.64 | 10.0701 |  | 1.44 | 19.2 | 20.64 | 10.0701 |  | 1.44 | 19.2 | 20.64 | 10.0701 |  | 189.2 | 92.479 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 22.5286 | 92.3088 | 92.3088
Project-A06 |  | v003 |  | 0.6202 | 1.5049 |  |  |  | 52 | 10.56 | 62.56 | 83.8445 |  | 12.48 | 44 | 56.48 | 29.2382 |  | 12.48 | 10.56 | 23.04 | 20.1227 |  | 12.48 | 10.56 | 23.04 | 20.1227 |  | 12.48 | 10.56 | 23.04 | 20.1227 |  | 12.48 | 10.56 | 23.04 | 20.1227 |  | 211.2 | 193.5734 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 184.4578 | 64.3241 | 184.4578 | [12 empty] | O
Project-A07 |  | v005 |  | 0.30126 | 1.5007 |  |  |  | 93 | 19.92 | 112.92 | 308.6986 |  | 22.32 | 83 | 105.32 | 74.0877 |  | 22.32 | 19.92 | 42.24 | 74.0877 |  | 22.32 | 19.92 | 42.24 | 74.0877 |  | 22.32 | 19.92 | 42.24 | 74.0877 |  | 22.32 | 19.92 | 42.24 | 74.0877 |  | 387.2 | 679.1369 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 679.1369 | 121.6728 | 679.1369 | [12 empty] | F
Project-A08 |  | v006 |  | 0.51212 | 1.7584 |  |  |  | 5 | 2.64 | 7.64 | 9.7633 |  | 1.2 | 11 | 12.2 | 6.2556 |  | 1.2 | 2.64 | 3.84 | 2.3432 |  | 1.2 | 2.64 | 3.84 | 2.3432 |  | 1.2 | 2.64 | 3.84 | 2.3432 |  | 1.2 | 2.64 | 3.84 | 2.3432 |  | 35.2 | 25.3916 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 21.4792 | 13.7623 | 21.4792
Project-A09 |  | v003 |  | 0.50626 | 1.5566 |  |  |  | 49 | 20.64 | 69.64 | 96.7886 |  | 11.76 | 86 | 97.76 | 55.2475 |  | 11.76 | 20.64 | 32.4 | 23.2293 |  | 11.76 | 20.64 | 32.4 | 23.2293 |  | 11.76 | 20.64 | 32.4 | 23.2293 |  | 11.76 | 20.64 | 32.4 | 23.2293 |  | 297 | 244.9532 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 212.9349 | 121.5445 | 212.9349 | [12 empty] | T
Project-A10 |  | v001 |  | 0.52166 | 1.5448 |  |  |  | 36 | 20.88 | 56.88 | 69.0111 |  | 8.64 | 87 | 95.64 | 56.317 |  | 8.64 | 20.88 | 29.52 | 16.5627 |  | 8.64 | 20.88 | 29.52 | 16.5627 |  | 8.64 | 20.88 | 29.52 | 16.5627 |  | 8.64 | 20.88 | 29.52 | 16.5627 |  | 270.6 | 191.5787 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 151.8244 | 123.8974 | 151.8244 | [12 empty] | H
Project-A11 |  | v002 |  | 0.50904 | 1.5034 |  |  |  | 63 | 19.2 | 82.2 | 123.7615 |  | 15.12 | 80 | 95.12 | 53.2144 |  | 15.12 | 19.2 | 34.32 | 29.7028 |  | 15.12 | 19.2 | 34.32 | 29.7028 |  | 15.12 | 19.2 | 34.32 | 29.7028 |  | 15.12 | 19.2 | 34.32 | 29.7028 |  | 314.6 | 295.7869 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 272.2752 | 117.0716 | 272.2752 | [12 empty] | I
Project-A12 |  | v004 |  | 0.27826 | 1.5136 |  |  |  | 65 | 21.84 | 86.84 | 233.5905 |  | 15.6 | 91 | 106.6 | 60.1228 |  | 15.6 | 21.84 | 37.44 | 56.0617 |  | 15.6 | 21.84 | 37.44 | 56.0617 |  | 15.6 | 21.84 | 37.44 | 56.0617 |  | 15.6 | 21.84 | 37.44 | 56.0617 |  | 343.2 | 517.9602 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 513.8991 | 132.2702 | 513.8991 | [12 empty] | S
Project-A13 |  | v007 |  | 0.58502 | 2.0025 |  |  |  | 96 | 9.6 | 105.6 | 164.0979 |  | 23.04 | 40 | 63.04 | 39.3835 |  | 23.04 | 9.6 | 32.64 | 39.3835 |  | 23.04 | 9.6 | 32.64 | 39.3835 |  | 23.04 | 9.6 | 32.64 | 39.3835 |  | 23.04 | 9.6 | 32.64 | 39.3835 |  | 299.2 | 361.0153 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 361.0153 | 43.944 | 361.0153
Project-A14 |  | v006 |  | 0.51633 | 2.06 |  |  |  | 39 | 12.72 | 51.72 | 75.5327 |  | 9.36 | 53 | 62.36 | 25.7288 |  | 9.36 | 12.72 | 22.08 | 18.1279 |  | 9.36 | 12.72 | 22.08 | 18.1279 |  | 9.36 | 12.72 | 22.08 | 18.1279 |  | 9.36 | 12.72 | 22.08 | 18.1279 |  | 202.4 | 173.7729 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 166.172 | 56.6033 | 166.172 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0055 | 0.25451 |  |  |  | 72 | 23.76 | 95.76 | 93.3557 |  | 17.28 | 99 | 116.28 | 388.9822 |  | 17.28 | 23.76 | 41.04 | 93.3557 |  | 17.28 | 23.76 | 41.04 | 93.3557 |  | 17.28 | 23.76 | 41.04 | 93.3557 |  | 17.28 | 23.76 | 41.04 | 93.3557 |  | 376.2 | 855.7608 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 157.5291 | 855.7608 | 855.7608 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 95.3998 |  | 10.544 | 63.5333 | 74.0773 | 64.0574 |  | 10.544 | 15.248 | 25.792 | 28.7788 |  | 10.544 | 15.248 | 25.792 | 28.7788 |  | 10.544 | 15.248 | 25.792 | 28.7788 |  | 10.544 | 15.248 | 25.792 | 28.7788 |  | 236.4267 | 274.5722 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 206.6893 | 134.6079 | 263.8053 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1430.9966 |  | 158.16 | 953 | 1111.16 | 960.8606 |  | 158.16 | 228.72 | 386.88 | 431.6814 |  | 158.16 | 228.72 | 386.88 | 431.6814 |  | 158.16 | 228.72 | 386.88 | 431.6814 |  | 158.16 | 228.72 | 386.88 | 431.6814 |  | 3546.4 | 4118.5828 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3100.3391 | 2019.118 | 3957.0796 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 939.7608 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 304.4389 |  | <- To shorten average individual project span |  |  |  | <----------> | 263.8053
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 38.0192 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 3339.6581 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 4621.8769 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.513 | 1.5074 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-04 03:19 |  | 0 | 2014-02-05 03:19 | 2014-03-26 05:29 |  | 0 | 2014-03-27 05:29 | 2014-04-08 00:14 |  | 0 | 2014-04-09 00:14 | 2014-04-20 19:00 |  | 0 | 2014-04-21 19:00 | 2014-05-03 13:46 |  | 0 | 2014-05-04 13:46 | 2014-05-16 08:31 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 134.3549 | 939.7608 | [14 empty] | E
Project-A02 |  | 0.52317 | 1.508 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-02-11 16:07 |  | 0 | 2014-02-12 16:07 | 2014-04-06 17:19 |  | 0 | 2014-04-07 17:19 | 2014-04-20 10:53 |  | 2 | 2014-04-23 10:53 | 2014-05-06 04:28 |  | 0 | 2014-05-07 04:28 | 2014-05-19 22:02 |  | 0 | 2014-05-20 22:02 | 2014-06-02 15:36 |  | v002 |  | 0.058933 |  | 12 | 0 | 0 | 2 | 0 | 0 | 14 | 10.6079 |  | 139.6501 | [15 empty] | N
Project-A03 |  | 0.52054 | 2.3601 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-02-24 17:42 |  | 0 | 2014-02-25 17:42 | 2014-03-09 04:16 |  | 0 | 2014-03-10 04:16 | 2014-03-17 13:19 |  | 0 | 2014-03-18 13:19 | 2014-03-25 22:22 |  | 0 | 2014-03-26 22:22 | 2014-04-03 07:24 |  | 0 | 2014-04-04 07:24 | 2014-04-11 16:27 |  | v003 |  | 0.026675 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 9.2029 |  | 76.6857 | [15 empty] | D
Project-A04 |  | 0.50168 | 1.5184 |  |  |  | 2014-01-01 |  | 35 | 2014-02-06 | 2014-04-16 18:22 |  | 0 | 2014-04-17 18:22 | 2014-05-04 12:13 |  | 0 | 2014-05-05 12:13 | 2014-05-22 06:03 |  | 1 | 2014-05-24 06:03 | 2014-06-09 23:54 |  | 0 | 2014-06-10 23:54 | 2014-06-27 17:45 |  | 0 | 2014-06-28 17:45 | 2014-07-15 11:36 |  | v004 |  | 0.032878 |  | 35 | 0 | 0 | 1 | 0 | 0 | 36 | 17.2612 |  | 159.4833
Project-A05 |  | 0.58592 | 1.9066 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-02-26 05:46 |  | 0 | 2014-02-27 05:46 | 2014-04-10 04:46 |  | 0 | 2014-04-11 04:46 | 2014-04-21 06:27 |  | 0 | 2014-04-22 06:27 | 2014-05-02 08:08 |  | 5 | 2014-05-08 08:08 | 2014-05-18 09:49 |  | 0 | 2014-05-19 09:49 | 2014-05-29 11:30 |  | v002 |  | 0.05335 |  | 45 | 0 | 0 | 0 | 5 | 0 | 50 | 36.0112 |  | 102.479 | [15 empty] | O
Project-A06 |  | 0.6202 | 1.5049 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-05-21 20:16 |  | 0 | 2014-05-22 20:16 | 2014-06-21 01:59 |  | 0 | 2014-06-22 01:59 | 2014-07-12 04:56 |  | 0 | 2014-07-13 04:56 | 2014-08-02 07:52 |  | 0 | 2014-08-03 07:52 | 2014-08-23 10:49 |  | 0 | 2014-08-24 10:49 | 2014-09-13 13:46 |  | v003 |  | 0.059553 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 50.0248 |  | 198.5734 | [15 empty] | F
Project-A07 |  | 0.30126 | 1.5007 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2015-01-12 16:46 |  | 0 | 2015-01-13 16:46 | 2015-03-28 18:52 |  | 0 | 2015-03-29 18:52 | 2015-06-11 20:58 |  | 0 | 2015-06-12 20:58 | 2015-08-25 23:05 |  | 0 | 2015-08-26 23:05 | 2015-11-09 01:11 |  | 0 | 2015-11-10 01:11 | 2016-01-23 03:17 |  | v005 |  | 0.10918 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 109.727 |  | 684.1369
Project-A08 |  | 0.51212 | 1.7584 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 18:19 |  | 0 | 2014-01-12 18:19 | 2014-01-19 00:27 |  | 0 | 2014-01-20 00:27 | 2014-01-22 08:41 |  | 0 | 2014-01-23 08:41 | 2014-01-25 16:56 |  | 0 | 2014-01-26 16:56 | 2014-01-29 01:10 |  | 0 | 2014-01-30 01:10 | 2014-02-01 09:24 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30.3916 | [15 empty] | T
Project-A09 |  | 0.50626 | 1.5566 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-04-08 18:56 |  | 0 | 2014-04-09 18:56 | 2014-06-04 00:52 |  | 0 | 2014-06-05 00:52 | 2014-06-28 06:22 |  | 365 | 2015-06-29 06:22 | 2015-07-22 11:52 |  | 0 | 2015-07-23 11:52 | 2015-08-15 17:22 |  | 0 | 2015-08-16 17:22 | 2015-09-08 22:53 |  | v003 |  | 0.083747 |  | 0 | 0 | 0 | 365 | 0 | 0 | 365 | 0 |  | 614.9532 | [15 empty] | H
Project-A10 |  | 0.52166 | 1.5448 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-04-04 00:16 |  | 0 | 2014-04-05 00:16 | 2014-05-31 07:52 |  | 0 | 2014-06-01 07:52 | 2014-06-17 21:23 |  | 0 | 2014-06-18 21:23 | 2014-07-05 10:53 |  | 0 | 2014-07-06 10:53 | 2014-07-23 00:23 |  | 0 | 2014-07-24 00:23 | 2014-08-09 13:53 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 26.3244 |  | 196.5787 | [15 empty] | I
Project-A11 |  | 0.50904 | 1.5034 |  |  |  | 2014-01-01 |  | 37 | 2014-02-08 | 2014-06-11 18:17 |  | 0 | 2014-06-12 18:17 | 2014-08-04 23:25 |  | 0 | 2014-08-05 23:25 | 2014-09-04 16:17 |  | 0 | 2014-09-05 16:17 | 2014-10-05 09:09 |  | 0 | 2014-10-06 09:09 | 2014-11-05 02:01 |  | 0 | 2014-11-06 02:01 | 2014-12-05 18:53 |  | v002 |  | 0.08871 |  | 37 | 0 | 0 | 0 | 0 | 0 | 37 | 49.2339 |  | 300.7869 | [15 empty] | S
Project-A12 |  | 0.27826 | 1.5136 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-10-07 14:10 |  | 0 | 2014-10-08 14:10 | 2014-12-07 17:07 |  | 0 | 2014-12-08 17:07 | 2015-02-02 18:36 |  | 0 | 2015-02-03 18:36 | 2015-03-31 20:05 |  | 0 | 2015-04-01 20:05 | 2015-05-27 21:34 |  | 0 | 2015-05-28 21:34 | 2015-07-23 23:03 |  | v004 |  | 0.096774 |  | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 65.3226 |  | 522.9602
Project-A13 |  | 0.58502 | 2.0025 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-08-10 02:21 |  | 0 | 2014-08-11 02:21 | 2014-09-19 11:33 |  | 0 | 2014-09-20 11:33 | 2014-10-29 20:45 |  | 0 | 2014-10-30 20:45 | 2014-12-09 05:58 |  | 0 | 2014-12-10 05:58 | 2015-01-18 15:10 |  | 0 | 2015-01-19 15:10 | 2015-02-28 00:22 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 366.0153 | [15 empty] | W
Project-A14 |  | 0.51633 | 2.06 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-18 12:47 |  | 0 | 2014-03-19 12:47 | 2014-04-14 06:17 |  | 0 | 2014-04-15 06:17 | 2014-05-03 09:21 |  | 0 | 2014-05-04 09:21 | 2014-05-22 12:25 |  | 0 | 2014-05-23 12:25 | 2014-06-10 15:29 |  | 0 | 2014-06-11 15:29 | 2014-06-29 18:33 |  | v006 |  | 0.057072 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 178.7729 | [15 empty] | O
Project-A15 |  | 1.0055 | 0.25451 |  |  |  | 2014-01-01 |  | 79 | 2014-03-22 | 2014-06-23 08:32 |  | 0 | 2014-06-24 08:32 | 2015-07-18 08:07 |  | 0 | 2015-07-19 08:07 | 2015-10-20 16:39 |  | 0 | 2015-10-21 16:39 | 2016-01-23 01:11 |  | 0 | 2016-01-24 01:11 | 2016-04-26 09:43 |  | 0 | 2016-04-27 09:43 | 2016-07-29 18:16 |  | v008 |  | 0.10608 |  | 79 | 0 | 0 | 0 | 0 | 0 | 79 | 125.7041 |  | 860.7608 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 31.8667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 24.5333 |  |  |  | 0.33333 |  |  |  | 0 | [5 empty] | 0.066667 |  | 31.8667 | 0 | 0 | 24.5333 | 0.33333 | 0 | 56.7333 | 38.0192 | Average | 304.4389 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 478 |  |  |  | 0 |  |  |  | 0 |  |  |  | 368 |  |  |  | 5 |  |  |  | 0 | [5 empty] | 1 |  | 478 | 0 | 0 | 368 | 5 | 0 | 851 | 570.2885 | Total | 4566.5828 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 7
| Days: | 66.7932
E
N
SIT - Violation | Count: | 4 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 24.3427
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-27 05:29 | 2014-04-08 00:14 | v001 |  |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.28832 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-07 17:19 | 2014-04-20 10:53 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.1923 | 0 | T
Project-A03 | 2014-03-10 04:16 | 2014-03-17 13:19 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-05 12:13 | 2014-05-22 06:03 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-04-11 04:46 | 2014-04-21 06:27 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.0074 | 0 | S
Project-A06 | 2014-06-22 01:59 | 2014-07-12 04:56 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-03-29 18:52 | 2015-06-11 20:58 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-20 00:27 | 2014-01-22 08:41 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-05 00:52 | 2014-06-28 06:22 | v003 |  | Count P-A10: 1; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 12.8547 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-06-01 07:52 | 2014-06-17 21:23 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-08-05 23:25 | 2014-09-04 16:17 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-12-08 17:07 | 2015-02-02 18:36 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-09-20 11:33 | 2014-10-29 20:45 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-04-15 06:17 | 2014-05-03 09:21 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2015-07-19 08:07 | 2015-10-20 16:39 | v008 | [31 empty] | T
UAT - Violation | Count: | 2 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 41.4173
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-09 00:14 | 2014-04-20 19:00 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-23 10:53 | 2014-05-06 04:28 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.7966 | 0
Project-A03 | 2014-03-18 13:19 | 2014-03-25 22:22 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-24 06:03 | 2014-06-09 23:54 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-22 06:27 | 2014-05-02 08:08 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-07-13 04:56 | 2014-08-02 07:52 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-06-12 20:58 | 2015-08-25 23:05 | v005 |  | Count P-A08: 0; Count P-A09: 1; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 39.6207 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-23 08:41 | 2014-01-25 16:56 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-06-29 06:22 | 2015-07-22 11:52 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-18 21:23 | 2014-07-05 10:53 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-05 16:17 | 2014-10-05 09:09 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2015-02-03 18:36 | 2015-03-31 20:05 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-10-30 20:45 | 2014-12-09 05:58 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-05-04 09:21 | 2014-05-22 12:25 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-10-21 16:39 | 2016-01-23 01:11 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-21 19:00 | 2014-05-03 13:46 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-07 04:28 | 2014-05-19 22:02 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-26 22:22 | 2014-04-03 07:24 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-10 23:54 | 2014-06-27 17:45 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-08 08:08 | 2014-05-18 09:49 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-03 07:52 | 2014-08-23 10:49 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-26 23:05 | 2015-11-09 01:11 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-26 16:56 | 2014-01-29 01:10 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-07-23 11:52 | 2015-08-15 17:22 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-06 10:53 | 2014-07-23 00:23 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-06 09:09 | 2014-11-05 02:01 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2015-04-01 20:05 | 2015-05-27 21:34 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-10 05:58 | 2015-01-18 15:10 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-05-23 12:25 | 2014-06-10 15:29 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-01-24 01:11 | 2016-04-26 09:43 | v008
Prod - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 1.0332
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-05-04 13:46 | 2014-05-16 08:31 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-20 22:02 | 2014-06-02 15:36 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-04-04 07:24 | 2014-04-11 16:27 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-28 17:45 | 2014-07-15 11:36 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.0332 | 0
Project-A05 | 2014-05-19 09:49 | 2014-05-29 11:30 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-24 10:49 | 2014-09-13 13:46 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-11-10 01:11 | 2016-01-23 03:17 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-30 01:10 | 2014-02-01 09:24 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-08-16 17:22 | 2015-09-08 22:53 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-24 00:23 | 2014-08-09 13:53 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-11-06 02:01 | 2014-12-05 18:53 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2015-05-28 21:34 | 2015-07-23 23:03 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-19 15:10 | 2015-02-28 00:22 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-06-11 15:29 | 2014-06-29 18:33 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-04-27 09:43 | 2016-07-29 18:16 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.23173 | 23.1728 | 23
0.81606 | 81.606 | 81
0.40747 | 40.7465 | 40
0.79532 | 79.532 | 79
0.22112 | 22.1118 | 22
0.99643 | 99.643 | 99
0.43404 | 43.4036 | 43
0.941 | 94.1005 | 94
0.69577 | 69.5766 | 69
0.69118 | 69.1184 | 69
0.59573 | 59.5733 | 59
0.79116 | 79.1159 | 79
0.7362 | 73.62 | 73
0.46035 | 46.0352 | 46
0.62318 | 62.3178 | 62
0.86631 | 86.6308 | 86
0.75592 | 75.5924 | 75
0.7254 | 72.5395 | 72
0.47227 | 47.2265 | 47
0.81083 | 81.0828 | 81
0.48634 | 48.6339 | 48
0.89575 | 89.5749 | 89
0.88642 | 88.6418 | 88
0.17904 | 17.9043 | 17
0.74962 | 74.962 | 74
0.0086627 | 0.86627 | 0
0.58792 | 58.7924 | 58
0.34019 | 34.0193 | 34
0.47548 | 47.5482 | 47
0.030535 | 3.0535 | 3
0.21128 | 21.1278 | 21
0.66789 | 66.7894 | 66
0.74249 | 74.249 | 74
0.19819 | 19.8193 | 19
0.76151 | 76.151 | 76
0.55396 | 55.3964 | 55
0.75042 | 75.0422 | 75
0.22073 | 22.0733 | 22
0.1851 | 18.5098 | 18

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 4621.8769 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH