## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.50083 | 0.2544 |  |  |  | 17 | 17.76 | 34.76 | 69.8123 |  | 4.08 | 74 | 78.08 | 290.8848 |  | 4.08 | 17.76 | 21.84 | 69.8123 |  | 4.08 | 17.76 | 21.84 | 69.8123 |  | 4.08 | 17.76 | 21.84 | 69.8123 |  | 4.08 | 17.76 | 21.84 | 69.8123 |  | 200.2 | 639.9465 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 74.6764 | 639.9465 | 639.9465
Project-A02 |  | v002 |  | 0.5016 | 1.5001 |  |  |  | 15 | 19.2 | 34.2 | 29.9046 |  | 3.6 | 80 | 83.6 | 53.3305 |  | 3.6 | 19.2 | 22.8 | 12.7993 |  | 3.6 | 19.2 | 22.8 | 12.7993 |  | 3.6 | 19.2 | 22.8 | 12.7993 |  | 3.6 | 19.2 | 22.8 | 12.7993 |  | 209 | 134.4324 | 104500 |  | 0.058933 |  | 33 | 176 |  | 65.7901 | 117.3272 | 117.3272 | [12 empty] | E
Project-A03 |  | v003 |  | 0.497 | 3.2655 |  |  |  | 16 | 6.48 | 22.48 | 32.1932 |  | 3.84 | 27 | 30.84 | 8.2682 |  | 3.84 | 6.48 | 10.32 | 7.7264 |  | 3.84 | 6.48 | 10.32 | 7.7264 |  | 3.84 | 6.48 | 10.32 | 7.7264 |  | 3.84 | 6.48 | 10.32 | 7.7264 |  | 94.6 | 71.3668 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 70.825 | 18.19 | 70.825 | [12 empty] | N
Project-A04 |  | v004 |  | 0.50084 | 1.5263 |  |  |  | 35 | 4.32 | 39.32 | 69.8829 |  | 8.4 | 18 | 26.4 | 16.7719 |  | 8.4 | 4.32 | 12.72 | 16.7719 |  | 8.4 | 4.32 | 12.72 | 16.7719 |  | 8.4 | 4.32 | 12.72 | 16.7719 |  | 8.4 | 4.32 | 12.72 | 16.7719 |  | 116.6 | 153.7424 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 153.7424 | 25.9447 | 153.7424 | [12 empty] | D
Project-A05 |  | v002 |  | 0.49908 | 1.5073 |  |  |  | 6 | 19.2 | 25.2 | 12.7377 |  | 1.44 | 80 | 81.44 | 53.0737 |  | 1.44 | 19.2 | 20.64 | 12.7377 |  | 1.44 | 19.2 | 20.64 | 12.7377 |  | 1.44 | 19.2 | 20.64 | 12.7377 |  | 1.44 | 19.2 | 20.64 | 12.7377 |  | 189.2 | 116.7622 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 26.4487 | 116.7622 | 116.7622
Project-A06 |  | v003 |  | 0.50284 | 1.4978 |  |  |  | 52 | 10.56 | 62.56 | 103.4126 |  | 12.48 | 44 | 56.48 | 29.3768 |  | 12.48 | 10.56 | 23.04 | 24.819 |  | 12.48 | 10.56 | 23.04 | 24.819 |  | 12.48 | 10.56 | 23.04 | 24.819 |  | 12.48 | 10.56 | 23.04 | 24.819 |  | 211.2 | 232.0655 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 227.5077 | 64.6291 | 227.5077 | [12 empty] | O
Project-A07 |  | v005 |  | 0.50388 | 0.25087 |  |  |  | 93 | 19.92 | 112.92 | 184.5668 |  | 22.32 | 83 | 105.32 | 330.8525 |  | 22.32 | 19.92 | 42.24 | 79.4046 |  | 22.32 | 19.92 | 42.24 | 79.4046 |  | 22.32 | 19.92 | 42.24 | 79.4046 |  | 22.32 | 19.92 | 42.24 | 79.4046 |  | 387.2 | 833.0376 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 406.0469 | 727.8754 | 727.8754 | [12 empty] | F
Project-A08 |  | v006 |  | 0.50035 | 1.5008 |  |  |  | 5 | 2.64 | 7.64 | 9.9931 |  | 1.2 | 11 | 12.2 | 7.3294 |  | 1.2 | 2.64 | 3.84 | 2.3983 |  | 1.2 | 2.64 | 3.84 | 2.3983 |  | 1.2 | 2.64 | 3.84 | 2.3983 |  | 1.2 | 2.64 | 3.84 | 2.3983 |  | 35.2 | 26.9158 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 21.9848 | 16.1246 | 21.9848
Project-A09 |  | v003 |  | 0.49696 | 3.2691 |  |  |  | 49 | 20.64 | 69.64 | 98.5999 |  | 11.76 | 86 | 97.76 | 26.3068 |  | 11.76 | 20.64 | 32.4 | 23.664 |  | 11.76 | 20.64 | 32.4 | 23.664 |  | 11.76 | 20.64 | 32.4 | 23.664 |  | 11.76 | 20.64 | 32.4 | 23.664 |  | 297 | 219.5626 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 216.9198 | 57.8749 | 216.9198 | [12 empty] | T
Project-A10 |  | v001 |  | 0.49914 | 0.2524 |  |  |  | 36 | 20.88 | 56.88 | 82.7256 |  | 8.64 | 87 | 95.64 | 344.6899 |  | 8.64 | 20.88 | 29.52 | 82.7256 |  | 8.64 | 20.88 | 29.52 | 82.7256 |  | 8.64 | 20.88 | 29.52 | 82.7256 |  | 8.64 | 20.88 | 29.52 | 82.7256 |  | 270.6 | 758.3178 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 158.6719 | 758.3178 | 758.3178 | [12 empty] | H
Project-A11 |  | v002 |  | 0.50106 | 1.5 |  |  |  | 63 | 19.2 | 82.2 | 125.7341 |  | 15.12 | 80 | 95.12 | 53.3339 |  | 15.12 | 19.2 | 34.32 | 30.1762 |  | 15.12 | 19.2 | 34.32 | 30.1762 |  | 15.12 | 19.2 | 34.32 | 30.1762 |  | 15.12 | 19.2 | 34.32 | 30.1762 |  | 314.6 | 299.7727 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 276.615 | 117.3345 | 276.615 | [12 empty] | I
Project-A12 |  | v004 |  | 0.49782 | 1.4864 |  |  |  | 65 | 21.84 | 86.84 | 130.5686 |  | 15.6 | 91 | 106.6 | 61.2229 |  | 15.6 | 21.84 | 37.44 | 31.3365 |  | 15.6 | 21.84 | 37.44 | 31.3365 |  | 15.6 | 21.84 | 37.44 | 31.3365 |  | 15.6 | 21.84 | 37.44 | 31.3365 |  | 343.2 | 317.1373 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 287.2508 | 134.6904 | 287.2508 | [12 empty] | S
Project-A13 |  | v007 |  | 0.50221 | 2.0053 |  |  |  | 96 | 9.6 | 105.6 | 191.1544 |  | 23.04 | 40 | 63.04 | 45.8771 |  | 23.04 | 9.6 | 32.64 | 45.8771 |  | 23.04 | 9.6 | 32.64 | 45.8771 |  | 23.04 | 9.6 | 32.64 | 45.8771 |  | 23.04 | 9.6 | 32.64 | 45.8771 |  | 299.2 | 420.5397 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 420.5397 | 43.8838 | 420.5397
Project-A14 |  | v006 |  | 0.49896 | 2.0121 |  |  |  | 39 | 12.72 | 51.72 | 78.1633 |  | 9.36 | 53 | 62.36 | 26.3407 |  | 9.36 | 12.72 | 22.08 | 18.7592 |  | 9.36 | 12.72 | 22.08 | 18.7592 |  | 9.36 | 12.72 | 22.08 | 18.7592 |  | 9.36 | 12.72 | 22.08 | 18.7592 |  | 202.4 | 179.5408 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 171.9593 | 57.9496 | 171.9593 | [12 empty] | W
Project-A15 |  | v008 |  | 0.99744 | 2.1716 |  |  |  | 72 | 23.76 | 95.76 | 72.1844 |  | 17.28 | 99 | 116.28 | 45.5885 |  | 17.28 | 23.76 | 41.04 | 17.3243 |  | 17.28 | 23.76 | 41.04 | 17.3243 |  | 17.28 | 23.76 | 41.04 | 17.3243 |  | 17.28 | 23.76 | 41.04 | 17.3243 |  | 376.2 | 187.0699 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 158.8058 | 100.2946 | 158.8058 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 86.1089 |  | 10.544 | 63.5333 | 74.0773 | 92.8832 |  | 10.544 | 15.248 | 25.792 | 31.7555 |  | 10.544 | 15.248 | 25.792 | 31.7555 |  | 10.544 | 15.248 | 25.792 | 31.7555 |  | 10.544 | 15.248 | 25.792 | 31.7555 |  | 236.4267 | 306.014 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 182.519 | 199.8097 | 291.092 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1291.6335 |  | 158.16 | 953 | 1111.16 | 1393.2475 |  | 158.16 | 228.72 | 386.88 | 476.3323 |  | 158.16 | 228.72 | 386.88 | 476.3323 |  | 158.16 | 228.72 | 386.88 | 476.3323 |  | 158.16 | 228.72 | 386.88 | 476.3323 |  | 3546.4 | 4590.2102 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2737.7844 | 2997.1454 | 4366.3795 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 905.0376 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 335.6807 |  | <- To shorten average individual project span |  |  |  | <----------> | 291.092
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 35.7531 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 657.1374 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1933.6088 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.50083 | 0.2544 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-12 19:30 |  | 0 | 2014-03-13 19:30 | 2014-12-29 16:44 |  | 0 | 2014-12-30 16:44 | 2015-03-10 12:14 |  | 0 | 2015-03-11 12:14 | 2015-05-20 07:43 |  | 0 | 2015-05-21 07:43 | 2015-07-30 03:13 |  | 0 | 2015-07-31 03:13 | 2015-10-08 22:43 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 644.9465 | 905.0376 | [14 empty] | E
Project-A02 |  | 0.5016 | 1.5001 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-31 21:43 |  | 0 | 2014-02-01 21:43 | 2014-03-27 05:39 |  | 0 | 2014-03-28 05:39 | 2014-04-10 00:50 |  | 0 | 2014-04-11 00:50 | 2014-04-23 20:01 |  | 0 | 2014-04-24 20:01 | 2014-05-07 15:12 |  | 0 | 2014-05-08 15:12 | 2014-05-21 10:23 |  | v002 |  | 0.058933 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 139.4324 | [15 empty] | N
Project-A03 |  | 0.497 | 3.2655 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-03 04:38 |  | 0 | 2014-02-04 04:38 | 2014-02-12 11:04 |  | 0 | 2014-02-13 11:04 | 2014-02-21 04:30 |  | 0 | 2014-02-22 04:30 | 2014-03-01 21:56 |  | 0 | 2014-03-02 21:56 | 2014-03-10 15:22 |  | 0 | 2014-03-11 15:22 | 2014-03-19 08:48 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 76.3668 | [15 empty] | D
Project-A04 |  | 0.50084 | 1.5263 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-04-15 21:11 |  | 0 | 2014-04-16 21:11 | 2014-05-03 15:43 |  | 0 | 2014-05-04 15:43 | 2014-05-21 10:14 |  | 0 | 2014-05-22 10:14 | 2014-06-08 04:46 |  | 0 | 2014-06-09 04:46 | 2014-06-25 23:17 |  | 0 | 2014-06-26 23:17 | 2014-07-13 17:49 |  | v004 |  | 0.032878 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 16.768 |  | 158.7424
Project-A05 |  | 0.49908 | 1.5073 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-14 17:42 |  | 0 | 2014-01-15 17:42 | 2014-03-09 19:28 |  | 0 | 2014-03-10 19:28 | 2014-03-23 13:11 |  | 0 | 2014-03-24 13:11 | 2014-04-06 06:53 |  | 0 | 2014-04-07 06:53 | 2014-04-20 00:35 |  | 0 | 2014-04-21 00:35 | 2014-05-03 18:18 |  | v002 |  | 0.05335 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 121.7622 | [15 empty] | O
Project-A06 |  | 0.50284 | 1.4978 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-04-15 09:54 |  | 0 | 2014-04-16 09:54 | 2014-05-15 18:57 |  | 0 | 2014-05-16 18:57 | 2014-06-10 14:36 |  | 0 | 2014-06-11 14:36 | 2014-07-06 10:16 |  | 0 | 2014-07-07 10:16 | 2014-08-01 05:55 |  | 0 | 2014-08-02 05:55 | 2014-08-27 01:34 |  | v003 |  | 0.059553 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 237.0655 | [15 empty] | F
Project-A07 |  | 0.50388 | 0.25087 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-09-10 13:36 |  | 0 | 2014-09-11 13:36 | 2015-08-08 10:04 |  | 0 | 2015-08-09 10:04 | 2015-10-27 19:46 |  | 0 | 2015-10-28 19:46 | 2016-01-16 05:29 |  | 0 | 2016-01-17 05:29 | 2016-04-05 15:12 |  | 0 | 2016-04-06 15:12 | 2016-06-25 00:54 |  | v005 |  | 0.10918 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 109.727 |  | 838.0376
Project-A08 |  | 0.50035 | 1.5008 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 23:50 |  | 0 | 2014-01-12 23:50 | 2014-01-20 07:44 |  | 0 | 2014-01-21 07:44 | 2014-01-23 17:18 |  | 0 | 2014-01-24 17:18 | 2014-01-27 02:52 |  | 0 | 2014-01-28 02:52 | 2014-01-30 12:25 |  | 0 | 2014-01-31 12:25 | 2014-02-02 21:59 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 31.9158 | [15 empty] | T
Project-A09 |  | 0.49696 | 3.2691 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-04-22 14:24 |  | 0 | 2014-04-23 14:24 | 2014-05-19 21:46 |  | 0 | 2014-05-20 21:46 | 2014-06-13 13:42 |  | 0 | 2014-06-14 13:42 | 2014-07-08 05:38 |  | 0 | 2014-07-09 05:38 | 2014-08-01 21:34 |  | 0 | 2014-08-02 21:34 | 2014-08-26 13:30 |  | v003 |  | 0.083747 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 15.0744 |  | 224.5626 | [15 empty] | H
Project-A10 |  | 0.49914 | 0.2524 |  |  |  | 2014-01-01 |  | 24 | 2014-01-26 | 2014-04-18 17:25 |  | 0 | 2014-04-19 17:25 | 2015-03-30 09:58 |  | 0 | 2015-03-31 09:58 | 2015-06-22 03:23 |  | 0 | 2015-06-23 03:23 | 2015-09-13 20:48 |  | 0 | 2015-09-14 20:48 | 2015-12-06 14:13 |  | 0 | 2015-12-07 14:13 | 2016-02-28 07:38 |  | v001 |  | 0.076303 |  | 24 | 0 | 0 | 0 | 0 | 0 | 24 | 27.469 |  | 763.3178 | [15 empty] | I
Project-A11 |  | 0.50106 | 1.5 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-06-10 17:37 |  | 0 | 2014-06-11 17:37 | 2014-08-04 01:38 |  | 0 | 2014-08-05 01:38 | 2014-09-04 05:52 |  | 0 | 2014-09-05 05:52 | 2014-10-05 10:05 |  | 0 | 2014-10-06 10:05 | 2014-11-05 14:19 |  | 365 | 2015-11-06 14:19 | 2015-12-06 18:33 |  | v002 |  | 0.08871 |  | 34 | 0 | 0 | 0 | 0 | 365 | 399 | 45.2419 |  | 669.7727 | [15 empty] | S
Project-A12 |  | 0.49782 | 1.4864 |  |  |  | 2014-01-01 |  | 48 | 2014-02-19 | 2014-06-29 13:39 |  | 0 | 2014-06-30 13:39 | 2014-08-30 19:00 |  | 0 | 2014-08-31 19:00 | 2014-10-02 03:04 |  | 1 | 2014-10-04 03:04 | 2014-11-04 11:09 |  | 0 | 2014-11-05 11:09 | 2014-12-06 19:13 |  | 0 | 2014-12-07 19:13 | 2015-01-08 03:18 |  | v004 |  | 0.096774 |  | 48 | 0 | 0 | 1 | 0 | 0 | 49 | 69.6774 |  | 323.1373
Project-A13 |  | 0.50221 | 2.0053 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-09-06 03:42 |  | 0 | 2014-09-07 03:42 | 2014-10-23 00:45 |  | 0 | 2014-10-24 00:45 | 2014-12-08 21:48 |  | 0 | 2014-12-09 21:48 | 2015-01-24 18:51 |  | 0 | 2015-01-25 18:51 | 2015-03-12 15:54 |  | 0 | 2015-03-13 15:54 | 2015-04-28 12:57 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 425.5397 | [15 empty] | W
Project-A14 |  | 0.49896 | 2.0121 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-27 03:55 |  | 0 | 2014-05-28 03:55 | 2014-06-23 12:06 |  | 0 | 2014-06-24 12:06 | 2014-07-13 06:19 |  | 1 | 2014-07-15 06:19 | 2014-08-03 00:32 |  | 0 | 2014-08-04 00:32 | 2014-08-22 18:46 |  | 3 | 2014-08-26 18:46 | 2014-09-14 12:59 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 1 | 0 | 3 | 71 | 57.3573 |  | 188.5408 | [15 empty] | O
Project-A15 |  | 0.99744 | 2.1716 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-06-01 04:26 |  | 0 | 2014-06-02 04:26 | 2014-07-17 18:33 |  | 0 | 2014-07-18 18:33 | 2014-08-05 02:20 |  | 0 | 2014-08-06 02:20 | 2014-08-23 10:07 |  | 0 | 2014-08-24 10:07 | 2014-09-10 17:54 |  | 0 | 2014-09-11 17:54 | 2014-09-29 01:41 |  | v008 |  | 0.10608 |  | 78 | 0 | 0 | 0 | 0 | 0 | 78 | 124.1129 |  | 192.0699 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 28 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.13333 |  |  |  | 0 |  |  |  | 24.5333 | [5 empty] | 0.066667 |  | 28 | 0 | 0 | 0.13333 | 0 | 24.5333 | 52.6667 | 35.7531 | Average | 335.6807 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 420 |  |  |  | 0 |  |  |  | 0 |  |  |  | 2 |  |  |  | 0 |  |  |  | 368 | [5 empty] | 1 |  | 420 | 0 | 0 | 2 | 0 | 368 | 790 | 536.2965 | Total | 5035.2102 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 8
| Days: | 13.1427
E
N
SIT - Violation | Count: | 4 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 8.6392
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-12-30 16:44 | 2015-03-10 12:14 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-28 05:39 | 2014-04-10 00:50 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-13 11:04 | 2014-02-21 04:30 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-04 15:43 | 2014-05-21 10:14 | v004 | [5 empty] | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 4.6373 | 0 | 0 | 0.52001 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-03-10 19:28 | 2014-03-23 13:11 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-05-16 18:57 | 2014-06-10 14:36 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-09 10:04 | 2015-10-27 19:46 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-21 07:44 | 2014-01-23 17:18 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-05-20 21:46 | 2014-06-13 13:42 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2015-03-31 09:58 | 2015-06-22 03:23 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-08-05 01:38 | 2014-09-04 05:52 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 1 | [11 empty] | 3.4527 | 0 | 0 | 0.029188 | S
Project-A12 | 2014-08-31 19:00 | 2014-10-02 03:04 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-24 00:45 | 2014-12-08 21:48 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-24 12:06 | 2014-07-13 06:19 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-18 18:33 | 2014-08-05 02:20 | v008 | [31 empty] | T
UAT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 1.2924
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-03-11 12:14 | 2015-05-20 07:43 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-11 00:50 | 2014-04-23 20:01 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-22 04:30 | 2014-03-01 21:56 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-22 10:14 | 2014-06-08 04:46 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-24 13:11 | 2014-04-06 06:53 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-06-11 14:36 | 2014-07-06 10:16 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-28 19:46 | 2016-01-16 05:29 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-24 17:18 | 2014-01-27 02:52 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-06-14 13:42 | 2014-07-08 05:38 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-06-23 03:23 | 2015-09-13 20:48 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-05 05:52 | 2014-10-05 10:05 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 1.2924 | 0 | 0 | 0
Project-A12 | 2014-10-04 03:04 | 2014-11-04 11:09 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-09 21:48 | 2015-01-24 18:51 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-15 06:19 | 2014-08-03 00:32 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-06 02:20 | 2014-08-23 10:07 | v008
NFT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0.13215
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-05-21 07:43 | 2015-07-30 03:13 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-24 20:01 | 2014-05-07 15:12 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-02 21:56 | 2014-03-10 15:22 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-09 04:46 | 2014-06-25 23:17 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-07 06:53 | 2014-04-20 00:35 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-07-07 10:16 | 2014-08-01 05:55 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-01-17 05:29 | 2016-04-05 15:12 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-28 02:52 | 2014-01-30 12:25 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-09 05:38 | 2014-08-01 21:34 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-09-14 20:48 | 2015-12-06 14:13 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-06 10:05 | 2014-11-05 14:19 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0.13215 | 0 | 0 | 0
Project-A12 | 2014-11-05 11:09 | 2014-12-06 19:13 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-25 18:51 | 2015-03-12 15:54 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-04 00:32 | 2014-08-22 18:46 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-24 10:07 | 2014-09-10 17:54 | v008
Prod - Violation | Count: | 2 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 3.079
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-07-31 03:13 | 2015-10-08 22:43 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-08 15:12 | 2014-05-21 10:23 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-11 15:22 | 2014-03-19 08:48 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-26 23:17 | 2014-07-13 17:49 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-21 00:35 | 2014-05-03 18:18 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-02 05:55 | 2014-08-27 01:34 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.28386 | 0
Project-A07 | 2016-04-06 15:12 | 2016-06-25 00:54 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-31 12:25 | 2014-02-02 21:59 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-02 21:34 | 2014-08-26 13:30 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-12-07 14:13 | 2016-02-28 07:38 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-11-06 14:19 | 2015-12-06 18:33 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-07 19:13 | 2015-01-08 03:18 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-13 15:54 | 2015-04-28 12:57 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-26 18:46 | 2014-09-14 12:59 | v006 | [30 empty] | 2.7952 | bar: Count P-A15
Project-A15 | 2014-09-11 17:54 | 2014-09-29 01:41 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.77986 | 77.9856 | 77
0.22831 | 22.8314 | 22
0.48361 | 48.3613 | 48
0.48698 | 48.6983 | 48
0.68056 | 68.0565 | 68
0.98581 | 98.5807 | 98
0.19547 | 19.5467 | 19
0.45735 | 45.7353 | 45
0.77518 | 77.5183 | 77
0.48879 | 48.8795 | 48
0.30039 | 30.0387 | 30
0.69077 | 69.0769 | 69
0.30873 | 30.8734 | 30
0.43906 | 43.9057 | 43
0.65895 | 65.8952 | 65
0.40664 | 40.6641 | 40
0.11988 | 11.9879 | 11
0.65953 | 65.9534 | 65
0.79195 | 79.1945 | 79
0.97558 | 97.5577 | 97
0.62523 | 62.5229 | 62
0.65456 | 65.4564 | 65
0.32107 | 32.1068 | 32
0.337 | 33.7001 | 33
0.67254 | 67.254 | 67
0.91641 | 91.6405 | 91
0.29709 | 29.7086 | 29
0.43342 | 43.3422 | 43
0.085813 | 8.5813 | 8
0.96479 | 96.4785 | 96
0.43645 | 43.6447 | 43
0.57619 | 57.6189 | 57
0.67902 | 67.9016 | 67
0.020662 | 2.0662 | 2
0.99469 | 99.4688 | 99
0.87475 | 87.4751 | 87
0.76671 | 76.6713 | 76
0.41105 | 41.105 | 41
0.70608 | 70.608 | 70

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1933.6088 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH