## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.53879 | 1.507 |  |  |  | 17 | 17.76 | 34.76 | 31.552 |  | 4.08 | 74 | 78.08 | 49.1051 |  | 4.08 | 17.76 | 21.84 | 11.7852 |  | 4.08 | 17.76 | 21.84 | 11.7852 |  | 4.08 | 17.76 | 21.84 | 11.7852 |  | 4.08 | 17.76 | 21.84 | 11.7852 |  | 200.2 | 127.7979 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 69.4143 | 108.0311 | 108.0311
Project-A02 |  | v002 |  | 0.5124 | 1.4937 |  |  |  | 15 | 19.2 | 34.2 | 29.2742 |  | 3.6 | 80 | 83.6 | 53.5582 |  | 3.6 | 19.2 | 22.8 | 12.854 |  | 3.6 | 19.2 | 22.8 | 12.854 |  | 3.6 | 19.2 | 22.8 | 12.854 |  | 3.6 | 19.2 | 22.8 | 12.854 |  | 209 | 134.2483 | 104500 |  | 0.058933 |  | 33 | 176 |  | 64.4032 | 117.8281 | 117.8281 | [12 empty] | E
Project-A03 |  | v003 |  | 0.5395 | 1.6154 |  |  |  | 16 | 6.48 | 22.48 | 29.657 |  | 3.84 | 27 | 30.84 | 16.7142 |  | 3.84 | 6.48 | 10.32 | 7.1177 |  | 3.84 | 6.48 | 10.32 | 7.1177 |  | 3.84 | 6.48 | 10.32 | 7.1177 |  | 3.84 | 6.48 | 10.32 | 7.1177 |  | 94.6 | 74.842 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 65.2455 | 36.7712 | 65.2455 | [12 empty] | N
Project-A04 |  | v004 |  | 0.26218 | 1.5105 |  |  |  | 35 | 4.32 | 39.32 | 133.4938 |  | 8.4 | 18 | 26.4 | 32.0385 |  | 8.4 | 4.32 | 12.72 | 32.0385 |  | 8.4 | 4.32 | 12.72 | 32.0385 |  | 8.4 | 4.32 | 12.72 | 32.0385 |  | 8.4 | 4.32 | 12.72 | 32.0385 |  | 116.6 | 293.6864 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 293.6864 | 26.2167 | 293.6864 | [12 empty] | D
Project-A05 |  | v002 |  | 0.55178 | 1.9893 |  |  |  | 6 | 19.2 | 25.2 | 10.8738 |  | 1.44 | 80 | 81.44 | 40.2144 |  | 1.44 | 19.2 | 20.64 | 9.6515 |  | 1.44 | 19.2 | 20.64 | 9.6515 |  | 1.44 | 19.2 | 20.64 | 9.6515 |  | 1.44 | 19.2 | 20.64 | 9.6515 |  | 189.2 | 89.694 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 23.9224 | 88.4717 | 88.4717
Project-A06 |  | v003 |  | 0.65372 | 1.5288 |  |  |  | 52 | 10.56 | 62.56 | 79.5443 |  | 12.48 | 44 | 56.48 | 28.7801 |  | 12.48 | 10.56 | 23.04 | 19.0906 |  | 12.48 | 10.56 | 23.04 | 19.0906 |  | 12.48 | 10.56 | 23.04 | 19.0906 |  | 12.48 | 10.56 | 23.04 | 19.0906 |  | 211.2 | 184.687 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 174.9976 | 63.3162 | 174.9976 | [12 empty] | O
Project-A07 |  | v005 |  | 0.30458 | 1.4618 |  |  |  | 93 | 19.92 | 112.92 | 305.3342 |  | 22.32 | 83 | 105.32 | 73.2802 |  | 22.32 | 19.92 | 42.24 | 73.2802 |  | 22.32 | 19.92 | 42.24 | 73.2802 |  | 22.32 | 19.92 | 42.24 | 73.2802 |  | 22.32 | 19.92 | 42.24 | 73.2802 |  | 387.2 | 671.7353 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 671.7353 | 124.9149 | 671.7353 | [12 empty] | F
Project-A08 |  | v006 |  | 0.57944 | 1.5365 |  |  |  | 5 | 2.64 | 7.64 | 8.629 |  | 1.2 | 11 | 12.2 | 7.1592 |  | 1.2 | 2.64 | 3.84 | 2.071 |  | 1.2 | 2.64 | 3.84 | 2.071 |  | 1.2 | 2.64 | 3.84 | 2.071 |  | 1.2 | 2.64 | 3.84 | 2.071 |  | 35.2 | 24.0719 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 18.9837 | 15.7501 | 18.9837
Project-A09 |  | v003 |  | 0.57562 | 1.5398 |  |  |  | 49 | 20.64 | 69.64 | 85.1255 |  | 11.76 | 86 | 97.76 | 55.8504 |  | 11.76 | 20.64 | 32.4 | 20.4301 |  | 11.76 | 20.64 | 32.4 | 20.4301 |  | 11.76 | 20.64 | 32.4 | 20.4301 |  | 11.76 | 20.64 | 32.4 | 20.4301 |  | 297 | 222.6962 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 187.276 | 122.8708 | 187.276 | [12 empty] | T
Project-A10 |  | v001 |  | 0.58569 | 1.5767 |  |  |  | 36 | 20.88 | 56.88 | 61.4663 |  | 8.64 | 87 | 95.64 | 55.1801 |  | 8.64 | 20.88 | 29.52 | 14.7519 |  | 8.64 | 20.88 | 29.52 | 14.7519 |  | 8.64 | 20.88 | 29.52 | 14.7519 |  | 8.64 | 20.88 | 29.52 | 14.7519 |  | 270.6 | 175.654 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 135.2258 | 121.3963 | 135.2258 | [12 empty] | H
Project-A11 |  | v002 |  | 0.25698 | 1.5178 |  |  |  | 63 | 19.2 | 82.2 | 245.1596 |  | 15.12 | 80 | 95.12 | 58.8383 |  | 15.12 | 19.2 | 34.32 | 58.8383 |  | 15.12 | 19.2 | 34.32 | 58.8383 |  | 15.12 | 19.2 | 34.32 | 58.8383 |  | 15.12 | 19.2 | 34.32 | 58.8383 |  | 314.6 | 539.3511 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 539.3511 | 115.958 | 539.3511 | [12 empty] | I
Project-A12 |  | v004 |  | 0.59284 | 2.406 |  |  |  | 65 | 21.84 | 86.84 | 109.6408 |  | 15.6 | 91 | 106.6 | 37.8213 |  | 15.6 | 21.84 | 37.44 | 26.3138 |  | 15.6 | 21.84 | 37.44 | 26.3138 |  | 15.6 | 21.84 | 37.44 | 26.3138 |  | 15.6 | 21.84 | 37.44 | 26.3138 |  | 343.2 | 252.7174 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 241.2098 | 83.207 | 241.2098 | [12 empty] | S
Project-A13 |  | v007 |  | 0.50564 | 1.9781 |  |  |  | 96 | 9.6 | 105.6 | 189.86 |  | 23.04 | 40 | 63.04 | 45.5664 |  | 23.04 | 9.6 | 32.64 | 45.5664 |  | 23.04 | 9.6 | 32.64 | 45.5664 |  | 23.04 | 9.6 | 32.64 | 45.5664 |  | 23.04 | 9.6 | 32.64 | 45.5664 |  | 299.2 | 417.6921 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 417.6921 | 44.4874 | 417.6921
Project-A14 |  | v006 |  | 0.27418 | 2.0687 |  |  |  | 39 | 12.72 | 51.72 | 142.2443 |  | 9.36 | 53 | 62.36 | 34.1386 |  | 9.36 | 12.72 | 22.08 | 34.1386 |  | 9.36 | 12.72 | 22.08 | 34.1386 |  | 9.36 | 12.72 | 22.08 | 34.1386 |  | 9.36 | 12.72 | 22.08 | 34.1386 |  | 202.4 | 312.9375 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 312.9375 | 56.3636 | 312.9375 | [12 empty] | W
Project-A15 |  | v008 |  | 1.2666 | 0.26986 |  |  |  | 72 | 23.76 | 95.76 | 88.0448 |  | 17.28 | 99 | 116.28 | 366.8533 |  | 17.28 | 23.76 | 41.04 | 88.0448 |  | 17.28 | 23.76 | 41.04 | 88.0448 |  | 17.28 | 23.76 | 41.04 | 88.0448 |  | 17.28 | 23.76 | 41.04 | 88.0448 |  | 376.2 | 807.0772 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 125.0546 | 807.0772 | 807.0772 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 103.3266 |  | 10.544 | 63.5333 | 74.0773 | 63.6732 |  | 10.544 | 15.248 | 25.792 | 30.3982 |  | 10.544 | 15.248 | 25.792 | 30.3982 |  | 10.544 | 15.248 | 25.792 | 30.3982 |  | 10.544 | 15.248 | 25.792 | 30.3982 |  | 236.4267 | 288.5926 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 222.7423 | 128.844 | 278.6499 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1549.8996 |  | 158.16 | 953 | 1111.16 | 955.0983 |  | 158.16 | 228.72 | 386.88 | 455.9726 |  | 158.16 | 228.72 | 386.88 | 455.9726 |  | 158.16 | 228.72 | 386.88 | 455.9726 |  | 158.16 | 228.72 | 386.88 | 455.9726 |  | 3546.4 | 4328.8883 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3341.1351 | 1932.6603 | 4179.7488 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 889.0772 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 317.7926 |  | <- To shorten average individual project span |  |  |  | <----------> | 278.6499
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 44.7618 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 0 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1251.6315 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | TRUE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.53879 | 1.507 |  |  |  | 2014-01-01 |  | 3 | 2014-01-05 | 2014-02-05 13:15 |  | 0 | 2014-02-06 13:15 | 2014-03-27 15:46 |  | 0 | 2014-03-28 15:46 | 2014-04-09 10:37 |  | 0 | 2014-04-10 10:37 | 2014-04-22 05:28 |  | 0 | 2014-04-23 05:28 | 2014-05-05 00:18 |  | 0 | 2014-05-06 00:18 | 2014-05-17 19:09 |  | v001 |  | 0.056452 |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 2.5403 |  | 132.7979 | 889.0772 | [14 empty] | E
Project-A02 |  | 0.5124 | 1.4937 |  |  |  | 2014-01-01 |  | 15 | 2014-01-17 | 2014-02-15 06:35 |  | 0 | 2014-02-16 06:35 | 2014-04-10 19:59 |  | 0 | 2014-04-11 19:59 | 2014-04-24 16:28 |  | 0 | 2014-04-25 16:28 | 2014-05-08 12:58 |  | 0 | 2014-05-09 12:58 | 2014-05-22 09:28 |  | 0 | 2014-05-23 09:28 | 2014-06-05 05:58 |  | v002 |  | 0.058933 |  | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 13.2599 |  | 139.2483 | [15 empty] | N
Project-A03 |  | 0.5395 | 1.6154 |  |  |  | 2014-01-01 |  | 24 | 2014-01-26 | 2014-02-24 15:46 |  | 0 | 2014-02-25 15:46 | 2014-03-14 08:55 |  | 0 | 2014-03-15 08:55 | 2014-03-22 11:44 |  | 0 | 2014-03-23 11:44 | 2014-03-30 14:34 |  | 0 | 2014-03-31 14:34 | 2014-04-07 17:23 |  | 0 | 2014-04-08 17:23 | 2014-04-15 20:12 |  | v003 |  | 0.026675 |  | 24 | 0 | 0 | 0 | 0 | 0 | 24 | 9.603 |  | 79.842 | [15 empty] | D
Project-A04 |  | 0.26218 | 1.5105 |  |  |  | 2014-01-01 |  | 39 | 2014-02-10 | 2014-06-23 11:51 |  | 0 | 2014-06-24 11:51 | 2014-07-26 12:47 |  | 0 | 2014-07-27 12:47 | 2014-08-28 13:42 |  | 0 | 2014-08-29 13:42 | 2014-09-30 14:37 |  | 0 | 2014-10-01 14:37 | 2014-11-02 15:33 |  | 0 | 2014-11-03 15:33 | 2014-12-05 16:28 |  | v004 |  | 0.032878 |  | 39 | 0 | 0 | 0 | 0 | 0 | 39 | 19.2339 |  | 298.6864
Project-A05 |  | 0.55178 | 1.9893 |  |  |  | 2014-01-01 |  | 51 | 2014-02-22 | 2014-03-04 20:58 |  | 0 | 2014-03-05 20:58 | 2014-04-15 02:07 |  | 0 | 2014-04-16 02:07 | 2014-04-25 17:45 |  | 363 | 2015-04-24 17:45 | 2015-05-04 09:23 |  | 0 | 2015-05-05 09:23 | 2015-05-15 01:01 |  | 0 | 2015-05-16 01:01 | 2015-05-25 16:39 |  | v002 |  | 0.05335 |  | 51 | 0 | 0 | 363 | 0 | 0 | 414 | 40.8127 |  | 457.694 | [15 empty] | O
Project-A06 |  | 0.65372 | 1.5288 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-05-17 13:04 |  | 0 | 2014-05-18 13:04 | 2014-06-16 07:47 |  | 0 | 2014-06-17 07:47 | 2014-07-06 09:58 |  | 0 | 2014-07-07 09:58 | 2014-07-26 12:08 |  | 0 | 2014-07-27 12:08 | 2014-08-15 14:19 |  | 0 | 2014-08-16 14:19 | 2014-09-04 16:29 |  | v003 |  | 0.059553 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 50.0248 |  | 189.687 | [15 empty] | F
Project-A07 |  | 0.30458 | 1.4618 |  |  |  | 2014-01-01 |  | 69 | 2014-03-12 | 2015-01-11 08:01 |  | 0 | 2015-01-12 08:01 | 2015-03-26 14:45 |  | 0 | 2015-03-27 14:45 | 2015-06-08 21:28 |  | 0 | 2015-06-09 21:28 | 2015-08-22 04:12 |  | 0 | 2015-08-23 04:12 | 2015-11-04 10:55 |  | 0 | 2015-11-05 10:55 | 2016-01-17 17:39 |  | v005 |  | 0.10918 |  | 69 | 0 | 0 | 0 | 0 | 0 | 69 | 113.0025 |  | 676.7353
Project-A08 |  | 0.57944 | 1.5365 |  |  |  | 2014-01-01 |  | 3 | 2014-01-05 | 2014-01-13 15:06 |  | 0 | 2014-01-14 15:06 | 2014-01-21 18:55 |  | 0 | 2014-01-22 18:55 | 2014-01-24 20:37 |  | 0 | 2014-01-25 20:37 | 2014-01-27 22:19 |  | 0 | 2014-01-28 22:19 | 2014-01-31 00:01 |  | 0 | 2014-02-01 00:01 | 2014-02-03 01:44 |  | v006 |  | 0.0099256 |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 0.44665 |  | 29.0719 | [15 empty] | T
Project-A09 |  | 0.57562 | 1.5398 |  |  |  | 2014-01-01 |  | 16 | 2014-01-18 | 2014-04-13 03:01 |  | 0 | 2014-04-14 03:01 | 2014-06-08 23:25 |  | 0 | 2014-06-09 23:25 | 2014-06-30 09:45 |  | 0 | 2014-07-01 09:45 | 2014-07-21 20:04 |  | 0 | 2014-07-22 20:04 | 2014-08-12 06:23 |  | 0 | 2014-08-13 06:23 | 2014-09-02 16:43 |  | v003 |  | 0.083747 |  | 16 | 0 | 0 | 0 | 0 | 0 | 16 | 20.0993 |  | 227.6962 | [15 empty] | H
Project-A10 |  | 0.58569 | 1.5767 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-03-27 11:11 |  | 0 | 2014-03-28 11:11 | 2014-05-22 15:31 |  | 0 | 2014-05-23 15:31 | 2014-06-07 09:34 |  | 0 | 2014-06-08 09:34 | 2014-06-23 03:36 |  | 0 | 2014-06-24 03:36 | 2014-07-08 21:39 |  | 0 | 2014-07-09 21:39 | 2014-07-24 15:42 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 26.3244 |  | 180.654 | [15 empty] | I
Project-A11 |  | 0.25698 | 1.5178 |  |  |  | 2014-01-01 |  | 36 | 2014-02-07 | 2014-10-10 03:50 |  | 0 | 2014-10-11 03:50 | 2014-12-08 23:57 |  | 0 | 2014-12-09 23:57 | 2015-02-06 20:04 |  | 0 | 2015-02-07 20:04 | 2015-04-07 16:11 |  | 0 | 2015-04-08 16:11 | 2015-06-06 12:18 |  | 0 | 2015-06-07 12:18 | 2015-08-05 08:26 |  | v002 |  | 0.08871 |  | 36 | 0 | 0 | 0 | 0 | 0 | 36 | 47.9032 |  | 544.3511 | [15 empty] | S
Project-A12 |  | 0.59284 | 2.406 |  |  |  | 2014-01-01 |  | 48 | 2014-02-19 | 2014-06-08 15:23 |  | 0 | 2014-06-09 15:23 | 2014-07-17 11:06 |  | 0 | 2014-07-18 11:06 | 2014-08-13 18:37 |  | 0 | 2014-08-14 18:37 | 2014-09-10 02:09 |  | 0 | 2014-09-11 02:09 | 2014-10-07 09:41 |  | 0 | 2014-10-08 09:41 | 2014-11-03 17:13 |  | v004 |  | 0.096774 |  | 48 | 0 | 0 | 0 | 0 | 0 | 48 | 69.6774 |  | 257.7174
Project-A13 |  | 0.50564 | 1.9781 |  |  |  | 2014-01-01 |  | 57 | 2014-02-28 | 2014-09-05 20:38 |  | 0 | 2014-09-06 20:38 | 2014-10-22 10:14 |  | 0 | 2014-10-23 10:14 | 2014-12-07 23:50 |  | 0 | 2014-12-08 23:50 | 2015-01-23 13:25 |  | 0 | 2015-01-24 13:25 | 2015-03-11 03:01 |  | 0 | 2015-03-12 03:01 | 2015-04-26 16:37 |  | v007 |  | 0.084367 |  | 57 | 0 | 0 | 0 | 0 | 0 | 57 | 72.134 |  | 422.6921 | [15 empty] | W
Project-A14 |  | 0.27418 | 2.0687 |  |  |  | 2014-01-01 |  | 69 | 2014-03-12 | 2014-08-01 05:52 |  | 0 | 2014-08-02 05:52 | 2014-09-05 09:11 |  | 0 | 2014-09-06 09:11 | 2014-10-10 12:31 |  | 0 | 2014-10-11 12:31 | 2014-11-14 15:51 |  | 0 | 2014-11-15 15:51 | 2014-12-19 19:10 |  | 0 | 2014-12-20 19:10 | 2015-01-23 22:30 |  | v006 |  | 0.057072 |  | 69 | 0 | 0 | 0 | 0 | 0 | 69 | 59.0695 |  | 317.9375 | [15 empty] | O
Project-A15 |  | 1.2666 | 0.26986 |  |  |  | 2014-01-01 |  | 80 | 2014-03-23 | 2014-06-19 01:04 |  | 0 | 2014-06-20 01:04 | 2015-06-21 21:33 |  | 0 | 2015-06-22 21:33 | 2015-09-18 22:38 |  | 0 | 2015-09-19 22:38 | 2015-12-16 23:42 |  | 0 | 2015-12-17 23:42 | 2016-03-15 00:47 |  | 0 | 2016-03-16 00:47 | 2016-06-12 01:51 |  | v008 |  | 0.10608 |  | 80 | 0 | 0 | 0 | 0 | 0 | 80 | 127.2953 |  | 812.0772 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 39.2667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 24.2 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 0.066667 |  | 39.2667 | 0 | 0 | 24.2 | 0 | 0 | 63.4667 | 44.7618 | Average | 317.7926 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 589 |  |  |  | 0 |  |  |  | 0 |  |  |  | 363 |  |  |  | 0 |  |  |  | 0 | [5 empty] | 1 |  | 589 | 0 | 0 | 363 | 0 | 0 | 952 | 671.4268 | Total | 4766.8883 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 0
| Days: | 0
E
N
SIT - Violation | Count: | 0 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 0
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-28 15:46 | 2014-04-09 10:37 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-11 19:59 | 2014-04-24 16:28 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-03-15 08:55 | 2014-03-22 11:44 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-07-27 12:47 | 2014-08-28 13:42 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-04-16 02:07 | 2014-04-25 17:45 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-06-17 07:47 | 2014-07-06 09:58 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-03-27 14:45 | 2015-06-08 21:28 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-22 18:55 | 2014-01-24 20:37 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-09 23:25 | 2014-06-30 09:45 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-05-23 15:31 | 2014-06-07 09:34 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-12-09 23:57 | 2015-02-06 20:04 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-07-18 11:06 | 2014-08-13 18:37 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-23 10:14 | 2014-12-07 23:50 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-09-06 09:11 | 2014-10-10 12:31 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2015-06-22 21:33 | 2015-09-18 22:38 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-10 10:37 | 2014-04-22 05:28 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-25 16:28 | 2014-05-08 12:58 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-23 11:44 | 2014-03-30 14:34 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-08-29 13:42 | 2014-09-30 14:37 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-04-24 17:45 | 2015-05-04 09:23 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-07-07 09:58 | 2014-07-26 12:08 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-06-09 21:28 | 2015-08-22 04:12 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-25 20:37 | 2014-01-27 22:19 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-01 09:45 | 2014-07-21 20:04 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-08 09:34 | 2014-06-23 03:36 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-02-07 20:04 | 2015-04-07 16:11 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-08-14 18:37 | 2014-09-10 02:09 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-08 23:50 | 2015-01-23 13:25 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-10-11 12:31 | 2014-11-14 15:51 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-09-19 22:38 | 2015-12-16 23:42 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-23 05:28 | 2014-05-05 00:18 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-09 12:58 | 2014-05-22 09:28 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-31 14:34 | 2014-04-07 17:23 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-10-01 14:37 | 2014-11-02 15:33 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-05-05 09:23 | 2015-05-15 01:01 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-07-27 12:08 | 2014-08-15 14:19 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-23 04:12 | 2015-11-04 10:55 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-28 22:19 | 2014-01-31 00:01 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-22 20:04 | 2014-08-12 06:23 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-24 03:36 | 2014-07-08 21:39 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-04-08 16:11 | 2015-06-06 12:18 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-11 02:09 | 2014-10-07 09:41 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-24 13:25 | 2015-03-11 03:01 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-11-15 15:51 | 2014-12-19 19:10 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-12-17 23:42 | 2016-03-15 00:47 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-05-06 00:18 | 2014-05-17 19:09 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-23 09:28 | 2014-06-05 05:58 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-04-08 17:23 | 2014-04-15 20:12 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-11-03 15:33 | 2014-12-05 16:28 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-05-16 01:01 | 2015-05-25 16:39 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-16 14:19 | 2014-09-04 16:29 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-11-05 10:55 | 2016-01-17 17:39 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-02-01 00:01 | 2014-02-03 01:44 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-13 06:23 | 2014-09-02 16:43 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-09 21:39 | 2014-07-24 15:42 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-06-07 12:18 | 2015-08-05 08:26 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-08 09:41 | 2014-11-03 17:13 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-12 03:01 | 2015-04-26 16:37 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-12-20 19:10 | 2015-01-23 22:30 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-03-16 00:47 | 2016-06-12 01:51 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.013245 | 1.3245 | 1
0.47258 | 47.2578 | 47
0.16162 | 16.1618 | 16
0.75046 | 75.0465 | 75
0.96443 | 96.443 | 96
0.22317 | 22.3169 | 22
0.24899 | 24.8988 | 24
0.18447 | 18.4469 | 18
0.26124 | 26.1236 | 26
0.069591 | 6.9591 | 6
0.82834 | 82.834 | 82
0.7689 | 76.8905 | 76
0.05845 | 5.845 | 5
0.52667 | 52.6672 | 52
0.046644 | 4.6644 | 4
0.085044 | 8.5044 | 8
0.36136 | 36.1361 | 36
0.74469 | 74.4685 | 74
0.78461 | 78.4613 | 78
0.70543 | 70.5431 | 70
0.4934 | 49.3404 | 49
0.6058 | 60.5797 | 60
0.93619 | 93.6189 | 93
0.7579 | 75.7897 | 75
0.34225 | 34.2252 | 34
0.041634 | 4.1634 | 4
0.89441 | 89.4409 | 89
0.66818 | 66.8176 | 66
0.42629 | 42.6294 | 42
0.85596 | 85.5956 | 85
0.91812 | 91.8118 | 91
0.7836 | 78.3598 | 78
0.8981 | 89.8096 | 89
0.026259 | 2.6259 | 2
0.1864 | 18.6403 | 18
0.6736 | 67.3604 | 67
0.95809 | 95.8091 | 95
0.35983 | 35.9829 | 35
0.10446 | 10.4456 | 10

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1251.6315 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH