## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.49723 | 0.25106 |  |  |  | 17 | 17.76 | 34.76 | 70.7407 |  | 4.08 | 74 | 78.08 | 294.7529 |  | 4.08 | 17.76 | 21.84 | 70.7407 |  | 4.08 | 17.76 | 21.84 | 70.7407 |  | 4.08 | 17.76 | 21.84 | 70.7407 |  | 4.08 | 17.76 | 21.84 | 70.7407 |  | 200.2 | 648.4564 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 75.2162 | 648.4564 | 648.4564
Project-A02 |  | v002 |  | 0.50404 | 1.5018 |  |  |  | 15 | 19.2 | 34.2 | 29.7594 |  | 3.6 | 80 | 83.6 | 53.2704 |  | 3.6 | 19.2 | 22.8 | 12.7849 |  | 3.6 | 19.2 | 22.8 | 12.7849 |  | 3.6 | 19.2 | 22.8 | 12.7849 |  | 3.6 | 19.2 | 22.8 | 12.7849 |  | 209 | 134.1695 | 104500 |  | 0.058933 |  | 33 | 176 |  | 65.4707 | 117.195 | 117.195 | [12 empty] | E
Project-A03 |  | v003 |  | 0.49785 | 4.9994 |  |  |  | 16 | 6.48 | 22.48 | 32.1382 |  | 3.84 | 27 | 30.84 | 7.7132 |  | 3.84 | 6.48 | 10.32 | 7.7132 |  | 3.84 | 6.48 | 10.32 | 7.7132 |  | 3.84 | 6.48 | 10.32 | 7.7132 |  | 3.84 | 6.48 | 10.32 | 7.7132 |  | 94.6 | 70.704 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 70.704 | 11.8815 | 70.704 | [12 empty] | N
Project-A04 |  | v004 |  | 0.49963 | 1.5129 |  |  |  | 35 | 4.32 | 39.32 | 70.0518 |  | 8.4 | 18 | 26.4 | 16.8124 |  | 8.4 | 4.32 | 12.72 | 16.8124 |  | 8.4 | 4.32 | 12.72 | 16.8124 |  | 8.4 | 4.32 | 12.72 | 16.8124 |  | 8.4 | 4.32 | 12.72 | 16.8124 |  | 116.6 | 154.1139 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 154.1139 | 26.1742 | 154.1139 | [12 empty] | D
Project-A05 |  | v002 |  | 0.50377 | 3.3556 |  |  |  | 6 | 19.2 | 25.2 | 11.9103 |  | 1.44 | 80 | 81.44 | 23.841 |  | 1.44 | 19.2 | 20.64 | 5.7218 |  | 1.44 | 19.2 | 20.64 | 5.7218 |  | 1.44 | 19.2 | 20.64 | 5.7218 |  | 1.44 | 19.2 | 20.64 | 5.7218 |  | 189.2 | 58.6387 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 26.2026 | 52.4503 | 52.4503
Project-A06 |  | v003 |  | 0.49824 | 1.5048 |  |  |  | 52 | 10.56 | 62.56 | 104.3665 |  | 12.48 | 44 | 56.48 | 29.2394 |  | 12.48 | 10.56 | 23.04 | 25.048 |  | 12.48 | 10.56 | 23.04 | 25.048 |  | 12.48 | 10.56 | 23.04 | 25.048 |  | 12.48 | 10.56 | 23.04 | 25.048 |  | 211.2 | 233.7977 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 229.6063 | 64.3266 | 229.6063 | [12 empty] | O
Project-A07 |  | v005 |  | 0.49927 | 1.5026 |  |  |  | 93 | 19.92 | 112.92 | 186.2712 |  | 22.32 | 83 | 105.32 | 55.2379 |  | 22.32 | 19.92 | 42.24 | 44.7051 |  | 22.32 | 19.92 | 42.24 | 44.7051 |  | 22.32 | 19.92 | 42.24 | 44.7051 |  | 22.32 | 19.92 | 42.24 | 44.7051 |  | 387.2 | 420.3296 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 409.7967 | 121.5235 | 409.7967 | [12 empty] | F
Project-A08 |  | v006 |  | 0.49819 | 1.9437 |  |  |  | 5 | 2.64 | 7.64 | 10.0364 |  | 1.2 | 11 | 12.2 | 5.6593 |  | 1.2 | 2.64 | 3.84 | 2.4087 |  | 1.2 | 2.64 | 3.84 | 2.4087 |  | 1.2 | 2.64 | 3.84 | 2.4087 |  | 1.2 | 2.64 | 3.84 | 2.4087 |  | 35.2 | 25.3307 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 22.0801 | 12.4505 | 22.0801
Project-A09 |  | v003 |  | 0.50398 | 1.5052 |  |  |  | 49 | 20.64 | 69.64 | 97.2258 |  | 11.76 | 86 | 97.76 | 57.1345 |  | 11.76 | 20.64 | 32.4 | 23.3342 |  | 11.76 | 20.64 | 32.4 | 23.3342 |  | 11.76 | 20.64 | 32.4 | 23.3342 |  | 11.76 | 20.64 | 32.4 | 23.3342 |  | 297 | 247.697 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 213.8967 | 125.696 | 213.8967 | [12 empty] | T
Project-A10 |  | v001 |  | 0.50363 | 1.6133 |  |  |  | 36 | 20.88 | 56.88 | 71.4806 |  | 8.64 | 87 | 95.64 | 53.9264 |  | 8.64 | 20.88 | 29.52 | 17.1553 |  | 8.64 | 20.88 | 29.52 | 17.1553 |  | 8.64 | 20.88 | 29.52 | 17.1553 |  | 8.64 | 20.88 | 29.52 | 17.1553 |  | 270.6 | 194.0283 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 157.2573 | 118.638 | 157.2573 | [12 empty] | H
Project-A11 |  | v002 |  | 0.49809 | 0.25369 |  |  |  | 63 | 19.2 | 82.2 | 126.4841 |  | 15.12 | 80 | 95.12 | 315.3491 |  | 15.12 | 19.2 | 34.32 | 75.6838 |  | 15.12 | 19.2 | 34.32 | 75.6838 |  | 15.12 | 19.2 | 34.32 | 75.6838 |  | 15.12 | 19.2 | 34.32 | 75.6838 |  | 314.6 | 744.5684 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 278.2651 | 693.7681 | 693.7681 | [12 empty] | I
Project-A12 |  | v004 |  | 0.49865 | 1.5042 |  |  |  | 65 | 21.84 | 86.84 | 130.353 |  | 15.6 | 91 | 106.6 | 60.4983 |  | 15.6 | 21.84 | 37.44 | 31.2847 |  | 15.6 | 21.84 | 37.44 | 31.2847 |  | 15.6 | 21.84 | 37.44 | 31.2847 |  | 15.6 | 21.84 | 37.44 | 31.2847 |  | 343.2 | 315.9901 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 286.7766 | 133.0962 | 286.7766 | [12 empty] | S
Project-A13 |  | v007 |  | 0.50069 | 0.25 |  |  |  | 96 | 9.6 | 105.6 | 191.7365 |  | 23.04 | 40 | 63.04 | 160 |  | 23.04 | 9.6 | 32.64 | 46.0168 |  | 23.04 | 9.6 | 32.64 | 46.0168 |  | 23.04 | 9.6 | 32.64 | 46.0168 |  | 23.04 | 9.6 | 32.64 | 46.0168 |  | 299.2 | 535.8035 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 421.8203 | 352 | 421.8203
Project-A14 |  | v006 |  | 0.49843 | 2.048 |  |  |  | 39 | 12.72 | 51.72 | 78.2455 |  | 9.36 | 53 | 62.36 | 25.8787 |  | 9.36 | 12.72 | 22.08 | 18.7789 |  | 9.36 | 12.72 | 22.08 | 18.7789 |  | 9.36 | 12.72 | 22.08 | 18.7789 |  | 9.36 | 12.72 | 22.08 | 18.7789 |  | 202.4 | 179.24 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 172.1402 | 56.9332 | 172.1402 | [12 empty] | W
Project-A15 |  | v008 |  | 0.99831 | 0.25378 |  |  |  | 72 | 23.76 | 95.76 | 93.6248 |  | 17.28 | 99 | 116.28 | 390.1033 |  | 17.28 | 23.76 | 41.04 | 93.6248 |  | 17.28 | 23.76 | 41.04 | 93.6248 |  | 17.28 | 23.76 | 41.04 | 93.6248 |  | 17.28 | 23.76 | 41.04 | 93.6248 |  | 376.2 | 858.2272 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 158.6681 | 858.2272 | 858.2272 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 86.9617 |  | 10.544 | 63.5333 | 74.0773 | 103.2945 |  | 10.544 | 15.248 | 25.792 | 32.7876 |  | 10.544 | 15.248 | 25.792 | 32.7876 |  | 10.544 | 15.248 | 25.792 | 32.7876 |  | 10.544 | 15.248 | 25.792 | 32.7876 |  | 236.4267 | 321.4063 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 182.801 | 226.1878 | 300.5526 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1304.4248 |  | 158.16 | 953 | 1111.16 | 1549.4169 |  | 158.16 | 228.72 | 386.88 | 491.8133 |  | 158.16 | 228.72 | 386.88 | 491.8133 |  | 158.16 | 228.72 | 386.88 | 491.8133 |  | 158.16 | 228.72 | 386.88 | 491.8133 |  | 3546.4 | 4821.095 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2742.0148 | 3392.8165 | 4508.2889 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 1114.5684 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 326.473 |  | <- To shorten average individual project span |  |  |  | <----------> | 300.5526
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 115.9132 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 97.0642 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1654.0188 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.49723 | 0.25106 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-03-13 17:47 |  | 0 | 2015-03-14 17:47 | 2016-01-03 11:51 |  | 0 | 2016-01-04 11:51 | 2016-03-15 05:37 |  | 0 | 2016-03-16 05:37 | 2016-05-25 23:24 |  | 1 | 2016-05-27 23:24 | 2016-08-06 17:11 |  | 0 | 2016-08-07 17:11 | 2016-10-17 10:57 |  | v001 |  | 0.056452 |  | 365 | 0 | 0 | 0 | 1 | 0 | 366 | 309.0726 |  | 654.4564 | 1114.5684 | [14 empty] | E
Project-A02 |  | 0.50404 | 1.5018 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-31 18:14 |  | 0 | 2014-02-01 18:14 | 2014-03-27 00:43 |  | 0 | 2014-03-28 00:43 | 2014-04-09 19:33 |  | 0 | 2014-04-10 19:33 | 2014-04-23 14:24 |  | 0 | 2014-04-24 14:24 | 2014-05-07 09:14 |  | 0 | 2014-05-08 09:14 | 2014-05-21 04:04 |  | v002 |  | 0.058933 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 139.1695 | [15 empty] | N
Project-A03 |  | 0.49785 | 4.9994 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-03 03:19 |  | 0 | 2014-02-04 03:19 | 2014-02-11 20:26 |  | 0 | 2014-02-12 20:26 | 2014-02-20 13:33 |  | 0 | 2014-02-21 13:33 | 2014-03-01 06:40 |  | 0 | 2014-03-02 06:40 | 2014-03-09 23:47 |  | 0 | 2014-03-10 23:47 | 2014-03-18 16:54 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 75.704 | [15 empty] | D
Project-A04 |  | 0.49963 | 1.5129 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-04-16 01:15 |  | 0 | 2014-04-17 01:15 | 2014-05-03 20:44 |  | 0 | 2014-05-04 20:44 | 2014-05-21 16:14 |  | 0 | 2014-05-22 16:14 | 2014-06-08 11:44 |  | 0 | 2014-06-09 11:44 | 2014-06-26 07:14 |  | 0 | 2014-06-27 07:14 | 2014-07-14 02:44 |  | v004 |  | 0.032878 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 16.768 |  | 159.1139
Project-A05 |  | 0.50377 | 3.3556 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-02-27 21:51 |  | 0 | 2014-02-28 21:51 | 2014-03-24 18:02 |  | 0 | 2014-03-25 18:02 | 2014-03-31 11:21 |  | 0 | 2014-04-01 11:21 | 2014-04-07 04:41 |  | 0 | 2014-04-08 04:41 | 2014-04-13 22:00 |  | 0 | 2014-04-14 22:00 | 2014-04-20 15:20 |  | v002 |  | 0.05335 |  | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 36.0112 |  | 63.6387 | [15 empty] | O
Project-A06 |  | 0.49824 | 1.5048 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-06-11 08:48 |  | 0 | 2014-06-12 08:48 | 2014-07-11 14:32 |  | 0 | 2014-07-12 14:32 | 2014-08-06 15:41 |  | 0 | 2014-08-07 15:41 | 2014-09-01 16:51 |  | 0 | 2014-09-02 16:51 | 2014-09-27 18:00 |  | 0 | 2014-09-28 18:00 | 2014-10-23 19:09 |  | v003 |  | 0.059553 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 50.0248 |  | 238.7977 | [15 empty] | F
Project-A07 |  | 0.49927 | 1.5026 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-09-12 06:31 |  | 0 | 2014-09-13 06:31 | 2014-11-07 12:13 |  | 0 | 2014-11-08 12:13 | 2014-12-23 05:09 |  | 0 | 2014-12-24 05:09 | 2015-02-06 22:04 |  | 0 | 2015-02-07 22:04 | 2015-03-24 14:59 |  | 0 | 2015-03-25 14:59 | 2015-05-09 07:55 |  | v005 |  | 0.10918 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 109.727 |  | 425.3296
Project-A08 |  | 0.49819 | 1.9437 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-12 00:52 |  | 0 | 2014-01-13 00:52 | 2014-01-18 16:42 |  | 0 | 2014-01-19 16:42 | 2014-01-22 02:30 |  | 0 | 2014-01-23 02:30 | 2014-01-25 12:19 |  | 0 | 2014-01-26 12:19 | 2014-01-28 22:08 |  | 0 | 2014-01-29 22:08 | 2014-02-01 07:56 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30.3307 | [15 empty] | T
Project-A09 |  | 0.50398 | 1.5052 |  |  |  | 2014-01-01 |  | 363 | 2014-12-31 | 2015-04-07 05:25 |  | 0 | 2015-04-08 05:25 | 2015-06-04 08:39 |  | 0 | 2015-06-05 08:39 | 2015-06-28 16:40 |  | 0 | 2015-06-29 16:40 | 2015-07-23 00:41 |  | 0 | 2015-07-24 00:41 | 2015-08-16 08:43 |  | 0 | 2015-08-17 08:43 | 2015-09-09 16:44 |  | v003 |  | 0.083747 |  | 363 | 0 | 0 | 0 | 0 | 0 | 363 | 456.0019 |  | 252.697 | [15 empty] | H
Project-A10 |  | 0.50363 | 1.6133 |  |  |  | 2014-01-01 |  | 25 | 2014-01-27 | 2014-04-08 11:32 |  | 0 | 2014-04-09 11:32 | 2014-06-02 09:46 |  | 0 | 2014-06-03 09:46 | 2014-06-20 13:30 |  | 0 | 2014-06-21 13:30 | 2014-07-08 17:13 |  | 0 | 2014-07-09 17:13 | 2014-07-26 20:57 |  | 0 | 2014-07-27 20:57 | 2014-08-14 00:41 |  | v001 |  | 0.076303 |  | 25 | 0 | 0 | 0 | 0 | 0 | 25 | 28.6135 |  | 199.0283 | [15 empty] | I
Project-A11 |  | 0.49809 | 0.25369 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-05-08 11:37 |  | 0 | 2015-05-09 11:37 | 2016-03-19 20:00 |  | 0 | 2016-03-20 20:00 | 2016-06-04 12:25 |  | 0 | 2016-06-05 12:25 | 2016-08-20 04:49 |  | 0 | 2016-08-21 04:49 | 2016-11-04 21:14 |  | 0 | 2016-11-05 21:14 | 2017-01-20 13:39 |  | v002 |  | 0.08871 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 485.6855 |  | 749.5684 | [15 empty] | S
Project-A12 |  | 0.49865 | 1.5042 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-06-26 08:28 |  | 0 | 2014-06-27 08:28 | 2014-08-26 20:26 |  | 0 | 2014-08-27 20:26 | 2014-09-28 03:16 |  | 0 | 2014-09-29 03:16 | 2014-10-30 10:06 |  | 0 | 2014-10-31 10:06 | 2014-12-01 16:56 |  | 0 | 2014-12-02 16:56 | 2015-01-02 23:46 |  | v004 |  | 0.096774 |  | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 65.3226 |  | 320.9901
Project-A13 |  | 0.50069 | 0.25 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-07-12 17:41 |  | 0 | 2014-07-13 17:41 | 2014-12-20 17:41 |  | 0 | 2014-12-21 17:41 | 2015-02-05 18:05 |  | 0 | 2015-02-06 18:05 | 2015-03-24 18:29 |  | 0 | 2015-03-25 18:29 | 2015-05-10 18:53 |  | 0 | 2015-05-11 18:53 | 2015-06-26 19:17 |  | v007 |  | 0.084367 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 540.8035 | [15 empty] | W
Project-A14 |  | 0.49843 | 2.048 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-27 05:54 |  | 0 | 2014-05-28 05:54 | 2014-06-23 02:59 |  | 0 | 2014-06-24 02:59 | 2014-07-12 21:41 |  | 0 | 2014-07-13 21:41 | 2014-08-01 16:22 |  | 0 | 2014-08-02 16:22 | 2014-08-21 11:04 |  | 0 | 2014-08-22 11:04 | 2014-09-10 05:46 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 0 | 0 | 0 | 67 | 57.3573 |  | 184.24 | [15 empty] | O
Project-A15 |  | 0.99831 | 0.25378 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-06-22 15:00 |  | 0 | 2014-06-23 15:00 | 2015-07-18 17:28 |  | 0 | 2015-07-19 17:28 | 2015-10-21 08:28 |  | 0 | 2015-10-22 08:28 | 2016-01-23 23:28 |  | 0 | 2016-01-24 23:28 | 2016-04-27 14:27 |  | 0 | 2016-04-28 14:27 | 2016-07-31 05:27 |  | v008 |  | 0.10608 |  | 78 | 0 | 0 | 0 | 0 | 0 | 78 | 124.1129 |  | 863.2272 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 100.6667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.066667 |  |  |  | 0 | [5 empty] | 0.066667 |  | 100.6667 | 0 | 0 | 0 | 0.066667 | 0 | 100.7333 | 115.9132 | Average | 326.473 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 1510 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0 |  |  |  | 1 |  |  |  | 0 | [5 empty] | 1 |  | 1510 | 0 | 0 | 0 | 1 | 0 | 1511 | 1738.6973 | Total | 4897.095 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 3
| Days: | 1.9413
E
N
SIT - Violation | Count: | 2 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 1.7752
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2016-01-04 11:51 | 2016-03-15 05:37 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-28 00:43 | 2014-04-09 19:33 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-12 20:26 | 2014-02-20 13:33 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-04 20:44 | 2014-05-21 16:14 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-03-25 18:02 | 2014-03-31 11:21 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-12 14:32 | 2014-08-06 15:41 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.29736 | 0
Project-A07 | 2014-11-08 12:13 | 2014-12-23 05:09 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 1; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 1.4778 | 0 | 0 | W
Project-A08 | 2014-01-19 16:42 | 2014-01-22 02:30 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2015-06-05 08:39 | 2015-06-28 16:40 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-06-03 09:46 | 2014-06-20 13:30 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2016-03-20 20:00 | 2016-06-04 12:25 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-27 20:26 | 2014-09-28 03:16 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-12-21 17:41 | 2015-02-05 18:05 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-24 02:59 | 2014-07-12 21:41 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2015-07-19 17:28 | 2015-10-21 08:28 | v008 | [31 empty] | T
UAT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0.16613
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-03-16 05:37 | 2016-05-25 23:24 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-10 19:33 | 2014-04-23 14:24 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-21 13:33 | 2014-03-01 06:40 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-22 16:14 | 2014-06-08 11:44 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-01 11:21 | 2014-04-07 04:41 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-07 15:41 | 2014-09-01 16:51 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2014-12-24 05:09 | 2015-02-06 22:04 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 1; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0.16613 | 0 | 0
Project-A08 | 2014-01-23 02:30 | 2014-01-25 12:19 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-06-29 16:40 | 2015-07-23 00:41 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-21 13:30 | 2014-07-08 17:13 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2016-06-05 12:25 | 2016-08-20 04:49 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-29 03:16 | 2014-10-30 10:06 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-02-06 18:05 | 2015-03-24 18:29 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-13 21:41 | 2014-08-01 16:22 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-10-22 08:28 | 2016-01-23 23:28 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-05-27 23:24 | 2016-08-06 17:11 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-24 14:24 | 2014-05-07 09:14 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-02 06:40 | 2014-03-09 23:47 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-09 11:44 | 2014-06-26 07:14 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-08 04:41 | 2014-04-13 22:00 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-02 16:51 | 2014-09-27 18:00 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-02-07 22:04 | 2015-03-24 14:59 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-26 12:19 | 2014-01-28 22:08 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-07-24 00:41 | 2015-08-16 08:43 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-09 17:13 | 2014-07-26 20:57 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2016-08-21 04:49 | 2016-11-04 21:14 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-31 10:06 | 2014-12-01 16:56 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-25 18:29 | 2015-05-10 18:53 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-02 16:22 | 2014-08-21 11:04 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-01-24 23:28 | 2016-04-27 14:27 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-08-07 17:11 | 2016-10-17 10:57 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-08 09:14 | 2014-05-21 04:04 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-10 23:47 | 2014-03-18 16:54 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-27 07:14 | 2014-07-14 02:44 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-14 22:00 | 2014-04-20 15:20 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-28 18:00 | 2014-10-23 19:09 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-03-25 14:59 | 2015-05-09 07:55 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-29 22:08 | 2014-02-01 07:56 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-08-17 08:43 | 2015-09-09 16:44 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-27 20:57 | 2014-08-14 00:41 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2016-11-05 21:14 | 2017-01-20 13:39 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-02 16:56 | 2015-01-02 23:46 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-05-11 18:53 | 2015-06-26 19:17 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-22 11:04 | 2014-09-10 05:46 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-04-28 14:27 | 2016-07-31 05:27 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.53002 | 53.0023 | 53
0.36633 | 36.6327 | 36
0.96639 | 96.6386 | 96
0.91397 | 91.3975 | 91
0.18529 | 18.5292 | 18
0.30689 | 30.6889 | 30
0.44253 | 44.253 | 44
0.6938 | 69.3797 | 69
0.15205 | 15.2047 | 15
0.43388 | 43.388 | 43
0.94707 | 94.7073 | 94
0.96657 | 96.657 | 96
0.83912 | 83.9122 | 83
0.17773 | 17.7729 | 17
0.86781 | 86.7811 | 86
0.19424 | 19.4238 | 19
0.1042 | 10.4203 | 10
0.70692 | 70.692 | 70
0.69268 | 69.2682 | 69
0.33179 | 33.1785 | 33
0.73303 | 73.3029 | 73
0.33229 | 33.2293 | 33
0.77825 | 77.8253 | 77
0.88284 | 88.2839 | 88
0.30527 | 30.5266 | 30
0.40376 | 40.3764 | 40
0.4055 | 40.5498 | 40
0.3421 | 34.21 | 34
0.47832 | 47.8316 | 47
0.31266 | 31.266 | 31
0.47298 | 47.2979 | 47
0.072674 | 7.2674 | 7
0.12889 | 12.8893 | 12
0.63526 | 63.526 | 63
0.2659 | 26.5897 | 26
0.56038 | 56.0376 | 56
0.28815 | 28.8149 | 28
0.4559 | 45.5896 | 45
0.31226 | 31.2257 | 31

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1654.0188 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH