## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.5025 | 0.38062 |  |  |  | 17 | 17.76 | 34.76 | 46.6606 |  | 4.08 | 74 | 78.08 | 194.419 |  | 4.08 | 17.76 | 21.84 | 46.6606 |  | 4.08 | 17.76 | 21.84 | 46.6606 |  | 4.08 | 17.76 | 21.84 | 46.6606 |  | 4.08 | 17.76 | 21.84 | 46.6606 |  | 200.2 | 427.7218 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 74.428 | 427.7218 | 427.7218
Project-A02 |  | v002 |  | 0.54892 | 1.6538 |  |  |  | 15 | 19.2 | 34.2 | 27.3264 |  | 3.6 | 80 | 83.6 | 48.3732 |  | 3.6 | 19.2 | 22.8 | 11.6096 |  | 3.6 | 19.2 | 22.8 | 11.6096 |  | 3.6 | 19.2 | 22.8 | 11.6096 |  | 3.6 | 19.2 | 22.8 | 11.6096 |  | 209 | 122.1378 | 104500 |  | 0.058933 |  | 33 | 176 |  | 60.118 | 106.421 | 106.421 | [12 empty] | E
Project-A03 |  | v003 |  | 0.51407 | 1.5151 |  |  |  | 16 | 6.48 | 22.48 | 31.124 |  | 3.84 | 27 | 30.84 | 17.8207 |  | 3.84 | 6.48 | 10.32 | 7.4698 |  | 3.84 | 6.48 | 10.32 | 7.4698 |  | 3.84 | 6.48 | 10.32 | 7.4698 |  | 3.84 | 6.48 | 10.32 | 7.4698 |  | 94.6 | 78.8237 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 68.4728 | 39.2055 | 68.4728 | [12 empty] | N
Project-A04 |  | v004 |  | 0.50288 | 1.5076 |  |  |  | 35 | 4.32 | 39.32 | 69.599 |  | 8.4 | 18 | 26.4 | 16.7038 |  | 8.4 | 4.32 | 12.72 | 16.7038 |  | 8.4 | 4.32 | 12.72 | 16.7038 |  | 8.4 | 4.32 | 12.72 | 16.7038 |  | 8.4 | 4.32 | 12.72 | 16.7038 |  | 116.6 | 153.1178 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 153.1178 | 26.2673 | 153.1178 | [12 empty] | D
Project-A05 |  | v002 |  | 0.52975 | 2.0831 |  |  |  | 6 | 19.2 | 25.2 | 11.326 |  | 1.44 | 80 | 81.44 | 38.4048 |  | 1.44 | 19.2 | 20.64 | 9.2172 |  | 1.44 | 19.2 | 20.64 | 9.2172 |  | 1.44 | 19.2 | 20.64 | 9.2172 |  | 1.44 | 19.2 | 20.64 | 9.2172 |  | 189.2 | 86.5995 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 24.9173 | 84.4907 | 84.4907
Project-A06 |  | v003 |  | 0.50557 | 1.7198 |  |  |  | 52 | 10.56 | 62.56 | 102.8535 |  | 12.48 | 44 | 56.48 | 25.5841 |  | 12.48 | 10.56 | 23.04 | 24.6848 |  | 12.48 | 10.56 | 23.04 | 24.6848 |  | 12.48 | 10.56 | 23.04 | 24.6848 |  | 12.48 | 10.56 | 23.04 | 24.6848 |  | 211.2 | 227.1768 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 226.2776 | 56.2849 | 226.2776 | [12 empty] | O
Project-A07 |  | v005 |  | 0.51582 | 0.29061 |  |  |  | 93 | 19.92 | 112.92 | 180.2962 |  | 22.32 | 83 | 105.32 | 285.6077 |  | 22.32 | 19.92 | 42.24 | 68.5458 |  | 22.32 | 19.92 | 42.24 | 68.5458 |  | 22.32 | 19.92 | 42.24 | 68.5458 |  | 22.32 | 19.92 | 42.24 | 68.5458 |  | 387.2 | 740.0873 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 396.6517 | 628.3369 | 628.3369 | [12 empty] | F
Project-A08 |  | v006 |  | 0.51186 | 2.367 |  |  |  | 5 | 2.64 | 7.64 | 9.7684 |  | 1.2 | 11 | 12.2 | 4.6472 |  | 1.2 | 2.64 | 3.84 | 2.3444 |  | 1.2 | 2.64 | 3.84 | 2.3444 |  | 1.2 | 2.64 | 3.84 | 2.3444 |  | 1.2 | 2.64 | 3.84 | 2.3444 |  | 35.2 | 23.7932 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 21.4905 | 10.2237 | 21.4905
Project-A09 |  | v003 |  | 0.49014 | 0.30487 |  |  |  | 49 | 20.64 | 69.64 | 99.9724 |  | 11.76 | 86 | 97.76 | 282.0877 |  | 11.76 | 20.64 | 32.4 | 67.7011 |  | 11.76 | 20.64 | 32.4 | 67.7011 |  | 11.76 | 20.64 | 32.4 | 67.7011 |  | 11.76 | 20.64 | 32.4 | 67.7011 |  | 297 | 652.8643 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 219.9393 | 620.593 | 620.593 | [12 empty] | T
Project-A10 |  | v001 |  | 0.51992 | 1.569 |  |  |  | 36 | 20.88 | 56.88 | 69.2408 |  | 8.64 | 87 | 95.64 | 55.4509 |  | 8.64 | 20.88 | 29.52 | 16.6178 |  | 8.64 | 20.88 | 29.52 | 16.6178 |  | 8.64 | 20.88 | 29.52 | 16.6178 |  | 8.64 | 20.88 | 29.52 | 16.6178 |  | 270.6 | 191.1628 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 152.3298 | 121.9919 | 152.3298 | [12 empty] | H
Project-A11 |  | v002 |  | 0.26112 | 1.5161 |  |  |  | 63 | 19.2 | 82.2 | 241.265 |  | 15.12 | 80 | 95.12 | 57.9036 |  | 15.12 | 19.2 | 34.32 | 57.9036 |  | 15.12 | 19.2 | 34.32 | 57.9036 |  | 15.12 | 19.2 | 34.32 | 57.9036 |  | 15.12 | 19.2 | 34.32 | 57.9036 |  | 314.6 | 530.7831 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 530.7831 | 116.0885 | 530.7831 | [12 empty] | I
Project-A12 |  | v004 |  | 0.546 | 1.4816 |  |  |  | 65 | 21.84 | 86.84 | 119.0483 |  | 15.6 | 91 | 106.6 | 61.4195 |  | 15.6 | 21.84 | 37.44 | 28.5716 |  | 15.6 | 21.84 | 37.44 | 28.5716 |  | 15.6 | 21.84 | 37.44 | 28.5716 |  | 15.6 | 21.84 | 37.44 | 28.5716 |  | 343.2 | 294.7542 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 261.9063 | 135.123 | 261.9063 | [12 empty] | S
Project-A13 |  | v007 |  | 0.4955 | 2.1113 |  |  |  | 96 | 9.6 | 105.6 | 193.7447 |  | 23.04 | 40 | 63.04 | 46.4987 |  | 23.04 | 9.6 | 32.64 | 46.4987 |  | 23.04 | 9.6 | 32.64 | 46.4987 |  | 23.04 | 9.6 | 32.64 | 46.4987 |  | 23.04 | 9.6 | 32.64 | 46.4987 |  | 299.2 | 426.2384 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 426.2384 | 41.6806 | 426.2384
Project-A14 |  | v006 |  | 0.55274 | 1.992 |  |  |  | 39 | 12.72 | 51.72 | 70.5573 |  | 9.36 | 53 | 62.36 | 26.6066 |  | 9.36 | 12.72 | 22.08 | 16.9337 |  | 9.36 | 12.72 | 22.08 | 16.9337 |  | 9.36 | 12.72 | 22.08 | 16.9337 |  | 9.36 | 12.72 | 22.08 | 16.9337 |  | 202.4 | 164.8989 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 155.226 | 58.5346 | 155.226 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0032 | 3.5076 |  |  |  | 72 | 23.76 | 95.76 | 71.7699 |  | 17.28 | 99 | 116.28 | 28.2248 |  | 17.28 | 23.76 | 41.04 | 17.2248 |  | 17.28 | 23.76 | 41.04 | 17.2248 |  | 17.28 | 23.76 | 41.04 | 17.2248 |  | 17.28 | 23.76 | 41.04 | 17.2248 |  | 376.2 | 168.8937 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 157.8937 | 62.0945 | 157.8937 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 89.6368 |  | 10.544 | 63.5333 | 74.0773 | 79.3168 |  | 10.544 | 15.248 | 25.792 | 29.2458 |  | 10.544 | 15.248 | 25.792 | 29.2458 |  | 10.544 | 15.248 | 25.792 | 29.2458 |  | 10.544 | 15.248 | 25.792 | 29.2458 |  | 236.4267 | 285.9369 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 195.3193 | 169.0039 | 268.0866 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1344.5524 |  | 158.16 | 953 | 1111.16 | 1189.7522 |  | 158.16 | 228.72 | 386.88 | 438.6872 |  | 158.16 | 228.72 | 386.88 | 438.6872 |  | 158.16 | 228.72 | 386.88 | 438.6872 |  | 158.16 | 228.72 | 386.88 | 438.6872 |  | 3546.4 | 4289.0534 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2929.79 | 2535.058 | 4021.2992 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 900.7831 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 291.0702 |  | <- To shorten average individual project span |  |  |  | <----------> | 268.0866
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 92.1768 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 543.7444 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1827.7745 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.5025 | 0.38062 |  |  |  | 2014-01-01 |  | 5 | 2014-01-07 | 2014-02-22 15:51 |  | 0 | 2014-02-23 15:51 | 2014-09-06 01:55 |  | 0 | 2014-09-07 01:55 | 2014-10-23 17:46 |  | 0 | 2014-10-24 17:46 | 2014-12-10 09:37 |  | 0 | 2014-12-11 09:37 | 2015-01-27 01:28 |  | 0 | 2015-01-28 01:28 | 2015-03-15 17:19 |  | v001 |  | 0.056452 |  | 5 | 0 | 0 | 0 | 0 | 0 | 5 | 4.2339 |  | 432.7218 | 900.7831 | [14 empty] | E
Project-A02 |  | 0.54892 | 1.6538 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-29 07:50 |  | 0 | 2014-01-30 07:50 | 2014-03-19 16:47 |  | 0 | 2014-03-20 16:47 | 2014-04-01 07:25 |  | 0 | 2014-04-02 07:25 | 2014-04-13 22:03 |  | 0 | 2014-04-14 22:03 | 2014-04-26 12:41 |  | 0 | 2014-04-27 12:41 | 2014-05-09 03:18 |  | v002 |  | 0.058933 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 127.1378 | [15 empty] | N
Project-A03 |  | 0.51407 | 1.5151 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-02 02:59 |  | 0 | 2014-02-03 02:59 | 2014-02-20 22:40 |  | 0 | 2014-02-21 22:40 | 2014-03-01 09:57 |  | 0 | 2014-03-02 09:57 | 2014-03-09 21:13 |  | 0 | 2014-03-10 21:13 | 2014-03-18 08:30 |  | 0 | 2014-03-19 08:30 | 2014-03-26 19:46 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 83.8237 | [15 empty] | D
Project-A04 |  | 0.50288 | 1.5076 |  |  |  | 2014-01-01 |  | 33 | 2014-02-04 | 2014-04-14 14:23 |  | 0 | 2014-04-15 14:23 | 2014-05-02 07:16 |  | 0 | 2014-05-03 07:16 | 2014-05-20 00:09 |  | 0 | 2014-05-21 00:09 | 2014-06-06 17:03 |  | 0 | 2014-06-07 17:03 | 2014-06-24 09:56 |  | 0 | 2014-06-25 09:56 | 2014-07-12 02:50 |  | v004 |  | 0.032878 |  | 33 | 0 | 0 | 0 | 0 | 0 | 33 | 16.2748 |  | 158.1178
Project-A05 |  | 0.52975 | 2.0831 |  |  |  | 2014-01-01 |  | 48 | 2014-02-19 | 2014-03-02 07:49 |  | 0 | 2014-03-03 07:49 | 2014-04-10 17:32 |  | 0 | 2014-04-11 17:32 | 2014-04-20 22:45 |  | 0 | 2014-04-21 22:45 | 2014-05-01 03:58 |  | 0 | 2014-05-02 03:58 | 2014-05-11 09:11 |  | 0 | 2014-05-12 09:11 | 2014-05-21 14:23 |  | v002 |  | 0.05335 |  | 48 | 0 | 0 | 0 | 0 | 0 | 48 | 38.4119 |  | 91.5995 | [15 empty] | O
Project-A06 |  | 0.50557 | 1.7198 |  |  |  | 2014-01-01 |  | 364 | 2015-01-01 | 2015-04-13 20:29 |  | 0 | 2015-04-14 20:29 | 2015-05-10 10:30 |  | 0 | 2015-05-11 10:30 | 2015-06-05 02:56 |  | 0 | 2015-06-06 02:56 | 2015-06-30 19:22 |  | 0 | 2015-07-01 19:22 | 2015-07-26 11:48 |  | 0 | 2015-07-27 11:48 | 2015-08-21 04:15 |  | v003 |  | 0.059553 |  | 364 | 0 | 0 | 0 | 0 | 0 | 364 | 325.1613 |  | 232.1768 | [15 empty] | F
Project-A07 |  | 0.51582 | 0.29061 |  |  |  | 2014-01-01 |  | 81 | 2014-03-24 | 2014-09-20 07:07 |  | 0 | 2014-09-21 07:07 | 2015-07-03 21:42 |  | 0 | 2015-07-04 21:42 | 2015-09-11 10:48 |  | 0 | 2015-09-12 10:48 | 2015-11-19 23:54 |  | 0 | 2015-11-20 23:54 | 2016-01-28 13:00 |  | 0 | 2016-01-29 13:00 | 2016-04-07 02:06 |  | v005 |  | 0.10918 |  | 81 | 0 | 0 | 0 | 0 | 0 | 81 | 132.6551 |  | 745.0873
Project-A08 |  | 0.51186 | 2.367 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 18:26 |  | 0 | 2014-01-12 18:26 | 2014-01-17 09:58 |  | 0 | 2014-01-18 09:58 | 2014-01-20 18:14 |  | 0 | 2014-01-21 18:14 | 2014-01-24 02:30 |  | 0 | 2014-01-25 02:30 | 2014-01-27 10:46 |  | 0 | 2014-01-28 10:46 | 2014-01-30 19:02 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28.7932 | [15 empty] | T
Project-A09 |  | 0.49014 | 0.30487 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-04-23 23:20 |  | 0 | 2014-04-24 23:20 | 2015-02-01 01:27 |  | 0 | 2015-02-02 01:27 | 2015-04-10 18:16 |  | 0 | 2015-04-11 18:16 | 2015-06-18 11:06 |  | 0 | 2015-06-19 11:06 | 2015-08-26 03:55 |  | 0 | 2015-08-27 03:55 | 2015-11-02 20:45 |  | v003 |  | 0.083747 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 15.0744 |  | 657.8643 | [15 empty] | H
Project-A10 |  | 0.51992 | 1.569 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-04-04 05:47 |  | 0 | 2014-04-05 05:47 | 2014-05-30 16:36 |  | 0 | 2014-05-31 16:36 | 2014-06-17 07:26 |  | 0 | 2014-06-18 07:26 | 2014-07-04 22:15 |  | 0 | 2014-07-05 22:15 | 2014-07-22 13:05 |  | 0 | 2014-07-23 13:05 | 2014-08-09 03:55 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 26.3244 |  | 196.1628 | [15 empty] | I
Project-A11 |  | 0.26112 | 1.5161 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-08-31 06:22 |  | 0 | 2015-09-01 06:22 | 2015-10-29 04:03 |  | 0 | 2015-10-30 04:03 | 2015-12-27 01:44 |  | 0 | 2015-12-28 01:44 | 2016-02-23 23:25 |  | 0 | 2016-02-24 23:25 | 2016-04-22 21:06 |  | 0 | 2016-04-23 21:06 | 2016-06-20 18:48 |  | v002 |  | 0.08871 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 485.6855 |  | 535.7831 | [15 empty] | S
Project-A12 |  | 0.546 | 1.4816 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-06-15 01:10 |  | 0 | 2014-06-16 01:10 | 2014-08-16 11:14 |  | 0 | 2014-08-17 11:14 | 2014-09-15 00:57 |  | 0 | 2014-09-16 00:57 | 2014-10-14 14:40 |  | 0 | 2014-10-15 14:40 | 2014-11-13 04:23 |  | 0 | 2014-11-14 04:23 | 2014-12-12 18:06 |  | v004 |  | 0.096774 |  | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 65.3226 |  | 299.7542
Project-A13 |  | 0.4955 | 2.1113 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-09-08 17:52 |  | 0 | 2014-09-09 17:52 | 2014-10-26 05:51 |  | 0 | 2014-10-27 05:51 | 2014-12-12 17:49 |  | 0 | 2014-12-13 17:49 | 2015-01-29 05:47 |  | 0 | 2015-01-30 05:47 | 2015-03-17 17:45 |  | 0 | 2015-03-18 17:45 | 2015-05-04 05:43 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 0 | 0 | 56 | 70.8685 |  | 431.2384 | [15 empty] | W
Project-A14 |  | 0.55274 | 1.992 |  |  |  | 2014-01-01 |  | 75 | 2014-03-18 | 2014-05-27 13:22 |  | 0 | 2014-05-28 13:22 | 2014-06-24 03:56 |  | 0 | 2014-06-25 03:56 | 2014-07-12 02:21 |  | 0 | 2014-07-13 02:21 | 2014-07-30 00:45 |  | 0 | 2014-07-31 00:45 | 2014-08-16 23:10 |  | 0 | 2014-08-17 23:10 | 2014-09-03 21:34 |  | v006 |  | 0.057072 |  | 75 | 0 | 0 | 0 | 0 | 0 | 75 | 64.206 |  | 169.8989 | [15 empty] | O
Project-A15 |  | 1.0032 | 3.5076 |  |  |  | 2014-01-01 |  | 87 | 2014-03-30 | 2014-06-09 18:29 |  | 0 | 2014-06-10 18:29 | 2014-07-08 23:52 |  | 0 | 2014-07-09 23:52 | 2014-07-27 05:16 |  | 1 | 2014-07-29 05:16 | 2014-08-15 10:40 |  | 1 | 2014-08-17 10:40 | 2014-09-03 16:03 |  | 0 | 2014-09-04 16:03 | 2014-09-21 21:27 |  | v008 |  | 0.10608 |  | 87 | 0 | 0 | 1 | 1 | 0 | 89 | 138.4336 |  | 175.8937 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 79.6 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.066667 |  |  |  | 0.066667 |  |  |  | 0 | [5 empty] | 0.066667 |  | 79.6 | 0 | 0 | 0.066667 | 0.066667 | 0 | 79.7333 | 92.1768 | Average | 291.0702 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 1194 |  |  |  | 0 |  |  |  | 0 |  |  |  | 1 |  |  |  | 1 |  |  |  | 0 | [5 empty] | 1 |  | 1194 | 0 | 0 | 1 | 1 | 0 | 1196 | 1382.652 | Total | 4366.0534 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 3
| Days: | 10.8749
E
N
SIT - Violation | Count: | 2 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 10.0629
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-09-07 01:55 | 2014-10-23 17:46 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7.9599 | 0 | 0 | 0
Project-A02 | 2014-03-20 16:47 | 2014-04-01 07:25 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-21 22:40 | 2014-03-01 09:57 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-03 07:16 | 2014-05-20 00:09 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-04-11 17:32 | 2014-04-20 22:45 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2015-05-11 10:30 | 2015-06-05 02:56 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-07-04 21:42 | 2015-09-11 10:48 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-18 09:58 | 2014-01-20 18:14 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2015-02-02 01:27 | 2015-04-10 18:16 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-05-31 16:36 | 2014-06-17 07:26 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2015-10-30 04:03 | 2015-12-27 01:44 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-17 11:14 | 2014-09-15 00:57 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-27 05:51 | 2014-12-12 17:49 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-25 03:56 | 2014-07-12 02:21 | v006 | [30 empty] | 2.103 | E | bar: Count P-A15
Project-A15 | 2014-07-09 23:52 | 2014-07-27 05:16 | v008 | [31 empty] | T
UAT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0.812
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-10-24 17:46 | 2014-12-10 09:37 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-02 07:25 | 2014-04-13 22:03 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-02 09:57 | 2014-03-09 21:13 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-21 00:09 | 2014-06-06 17:03 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-21 22:45 | 2014-05-01 03:58 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-06-06 02:56 | 2015-06-30 19:22 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-09-12 10:48 | 2015-11-19 23:54 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-21 18:14 | 2014-01-24 02:30 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-04-11 18:16 | 2015-06-18 11:06 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-18 07:26 | 2014-07-04 22:15 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-12-28 01:44 | 2016-02-23 23:25 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-16 00:57 | 2014-10-14 14:40 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-13 17:49 | 2015-01-29 05:47 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-13 02:21 | 2014-07-30 00:45 | v006 | [30 empty] | 0.812 | bar: Count P-A15
Project-A15 | 2014-07-29 05:16 | 2014-08-15 10:40 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-12-11 09:37 | 2015-01-27 01:28 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-14 22:03 | 2014-04-26 12:41 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-10 21:13 | 2014-03-18 08:30 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-07 17:03 | 2014-06-24 09:56 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-02 03:58 | 2014-05-11 09:11 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-07-01 19:22 | 2015-07-26 11:48 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-11-20 23:54 | 2016-01-28 13:00 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-25 02:30 | 2014-01-27 10:46 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-06-19 11:06 | 2015-08-26 03:55 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-05 22:15 | 2014-07-22 13:05 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2016-02-24 23:25 | 2016-04-22 21:06 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-15 14:40 | 2014-11-13 04:23 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-30 05:47 | 2015-03-17 17:45 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-31 00:45 | 2014-08-16 23:10 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-17 10:40 | 2014-09-03 16:03 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-01-28 01:28 | 2015-03-15 17:19 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-27 12:41 | 2014-05-09 03:18 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-19 08:30 | 2014-03-26 19:46 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-25 09:56 | 2014-07-12 02:50 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-12 09:11 | 2014-05-21 14:23 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-07-27 11:48 | 2015-08-21 04:15 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-01-29 13:00 | 2016-04-07 02:06 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-28 10:46 | 2014-01-30 19:02 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-08-27 03:55 | 2015-11-02 20:45 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-23 13:05 | 2014-08-09 03:55 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2016-04-23 21:06 | 2016-06-20 18:48 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-14 04:23 | 2014-12-12 18:06 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-18 17:45 | 2015-05-04 05:43 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-17 23:10 | 2014-09-03 21:34 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-04 16:03 | 2014-09-21 21:27 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.70857 | 70.8566 | 70
0.82682 | 82.6816 | 82
0.84192 | 84.1919 | 84
0.54429 | 54.4286 | 54
0.65558 | 65.5582 | 65
0.2694 | 26.9403 | 26
0.78993 | 78.9926 | 78
0.78478 | 78.4784 | 78
0.18884 | 18.884 | 18
0.53682 | 53.6823 | 53
0.34416 | 34.416 | 34
0.22727 | 22.7272 | 22
0.037463 | 3.7463 | 3
0.88864 | 88.8642 | 88
0.13319 | 13.3187 | 13
0.044282 | 4.4282 | 4
0.04738 | 4.738 | 4
0.64915 | 64.9146 | 64
0.10621 | 10.6214 | 10
0.20612 | 20.6122 | 20
0.21297 | 21.2968 | 21
0.61843 | 61.8426 | 61
0.80199 | 80.1994 | 80
0.18599 | 18.5988 | 18
0.48967 | 48.9667 | 48
0.23468 | 23.4679 | 23
0.90958 | 90.9578 | 90
0.30187 | 30.1867 | 30
0.41881 | 41.8808 | 41
0.76528 | 76.5276 | 76
0.27327 | 27.3268 | 27
0.20381 | 20.3813 | 20
0.12731 | 12.7313 | 12
0.67621 | 67.6212 | 67
0.59525 | 59.5246 | 59
0.55926 | 55.9265 | 55
0.49192 | 49.1925 | 49
0.41817 | 41.8165 | 41
0.45245 | 45.2454 | 45

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1827.7745 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH