## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.7481 | 1.4787 |  |  |  | 17 | 17.76 | 34.76 | 22.7243 |  | 4.08 | 74 | 78.08 | 50.044 |  | 4.08 | 17.76 | 21.84 | 12.0106 |  | 4.08 | 17.76 | 21.84 | 12.0106 |  | 4.08 | 17.76 | 21.84 | 12.0106 |  | 4.08 | 17.76 | 21.84 | 12.0106 |  | 200.2 | 120.8106 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 49.9936 | 110.0968 | 110.0968
Project-A02 |  | v002 |  | 0.5418 | 1.4656 |  |  |  | 15 | 19.2 | 34.2 | 27.6856 |  | 3.6 | 80 | 83.6 | 54.5857 |  | 3.6 | 19.2 | 22.8 | 13.1006 |  | 3.6 | 19.2 | 22.8 | 13.1006 |  | 3.6 | 19.2 | 22.8 | 13.1006 |  | 3.6 | 19.2 | 22.8 | 13.1006 |  | 209 | 134.6736 | 104500 |  | 0.058933 |  | 33 | 176 |  | 60.9083 | 120.0886 | 120.0886 | [12 empty] | E
Project-A03 |  | v003 |  | 0.54931 | 1.4923 |  |  |  | 16 | 6.48 | 22.48 | 29.1275 |  | 3.84 | 27 | 30.84 | 18.0924 |  | 3.84 | 6.48 | 10.32 | 6.9906 |  | 3.84 | 6.48 | 10.32 | 6.9906 |  | 3.84 | 6.48 | 10.32 | 6.9906 |  | 3.84 | 6.48 | 10.32 | 6.9906 |  | 94.6 | 75.1823 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 64.0804 | 39.8033 | 64.0804 | [12 empty] | N
Project-A04 |  | v004 |  | 0.48671 | 1.4137 |  |  |  | 35 | 4.32 | 39.32 | 71.9117 |  | 8.4 | 18 | 26.4 | 17.2588 |  | 8.4 | 4.32 | 12.72 | 17.2588 |  | 8.4 | 4.32 | 12.72 | 17.2588 |  | 8.4 | 4.32 | 12.72 | 17.2588 |  | 8.4 | 4.32 | 12.72 | 17.2588 |  | 116.6 | 158.2057 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 158.2057 | 28.0126 | 158.2057 | [12 empty] | D
Project-A05 |  | v002 |  | 0.65767 | 4.8535 |  |  |  | 6 | 19.2 | 25.2 | 9.1231 |  | 1.44 | 80 | 81.44 | 16.4831 |  | 1.44 | 19.2 | 20.64 | 3.9559 |  | 1.44 | 19.2 | 20.64 | 3.9559 |  | 1.44 | 19.2 | 20.64 | 3.9559 |  | 1.44 | 19.2 | 20.64 | 3.9559 |  | 189.2 | 41.4299 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 20.0709 | 36.2627 | 36.2627
Project-A06 |  | v003 |  | 0.28113 | 1.3894 |  |  |  | 52 | 10.56 | 62.56 | 184.9694 |  | 12.48 | 44 | 56.48 | 44.3927 |  | 12.48 | 10.56 | 23.04 | 44.3927 |  | 12.48 | 10.56 | 23.04 | 44.3927 |  | 12.48 | 10.56 | 23.04 | 44.3927 |  | 12.48 | 10.56 | 23.04 | 44.3927 |  | 211.2 | 406.9327 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 406.9327 | 69.6725 | 406.9327 | [12 empty] | O
Project-A07 |  | v005 |  | 0.28362 | 1.4325 |  |  |  | 93 | 19.92 | 112.92 | 327.9026 |  | 22.32 | 83 | 105.32 | 78.6966 |  | 22.32 | 19.92 | 42.24 | 78.6966 |  | 22.32 | 19.92 | 42.24 | 78.6966 |  | 22.32 | 19.92 | 42.24 | 78.6966 |  | 22.32 | 19.92 | 42.24 | 78.6966 |  | 387.2 | 721.3858 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 721.3858 | 127.4725 | 721.3858 | [12 empty] | F
Project-A08 |  | v006 |  | 0.54267 | 2.0145 |  |  |  | 5 | 2.64 | 7.64 | 9.2137 |  | 1.2 | 11 | 12.2 | 5.4604 |  | 1.2 | 2.64 | 3.84 | 2.2113 |  | 1.2 | 2.64 | 3.84 | 2.2113 |  | 1.2 | 2.64 | 3.84 | 2.2113 |  | 1.2 | 2.64 | 3.84 | 2.2113 |  | 35.2 | 23.5193 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 20.2702 | 12.0129 | 20.2702
Project-A09 |  | v003 |  | 0.25 | 1.4211 |  |  |  | 49 | 20.64 | 69.64 | 196 |  | 11.76 | 86 | 97.76 | 60.5161 |  | 11.76 | 20.64 | 32.4 | 47.04 |  | 11.76 | 20.64 | 32.4 | 47.04 |  | 11.76 | 20.64 | 32.4 | 47.04 |  | 11.76 | 20.64 | 32.4 | 47.04 |  | 297 | 444.6761 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 431.2 | 133.1353 | 431.2 | [12 empty] | T
Project-A10 |  | v001 |  | 0.51023 | 1.6147 |  |  |  | 36 | 20.88 | 56.88 | 70.5569 |  | 8.64 | 87 | 95.64 | 53.8797 |  | 8.64 | 20.88 | 29.52 | 16.9337 |  | 8.64 | 20.88 | 29.52 | 16.9337 |  | 8.64 | 20.88 | 29.52 | 16.9337 |  | 8.64 | 20.88 | 29.52 | 16.9337 |  | 270.6 | 192.1713 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 155.2253 | 118.5353 | 155.2253 | [12 empty] | H
Project-A11 |  | v002 |  | 0.51968 | 1.5059 |  |  |  | 63 | 19.2 | 82.2 | 121.2293 |  | 15.12 | 80 | 95.12 | 53.1257 |  | 15.12 | 19.2 | 34.32 | 29.095 |  | 15.12 | 19.2 | 34.32 | 29.095 |  | 15.12 | 19.2 | 34.32 | 29.095 |  | 15.12 | 19.2 | 34.32 | 29.095 |  | 314.6 | 290.735 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 266.7044 | 116.8765 | 266.7044 | [12 empty] | I
Project-A12 |  | v004 |  | 0.53461 | 1.3766 |  |  |  | 65 | 21.84 | 86.84 | 121.583 |  | 15.6 | 91 | 106.6 | 66.103 |  | 15.6 | 21.84 | 37.44 | 29.1799 |  | 15.6 | 21.84 | 37.44 | 29.1799 |  | 15.6 | 21.84 | 37.44 | 29.1799 |  | 15.6 | 21.84 | 37.44 | 29.1799 |  | 343.2 | 304.4056 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 267.4825 | 145.4266 | 267.4825 | [12 empty] | S
Project-A13 |  | v007 |  | 0.48389 | 0.28471 |  |  |  | 96 | 9.6 | 105.6 | 198.3933 |  | 23.04 | 40 | 63.04 | 140.4955 |  | 23.04 | 9.6 | 32.64 | 47.6144 |  | 23.04 | 9.6 | 32.64 | 47.6144 |  | 23.04 | 9.6 | 32.64 | 47.6144 |  | 23.04 | 9.6 | 32.64 | 47.6144 |  | 299.2 | 529.3463 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 436.4652 | 309.0901 | 436.4652
Project-A14 |  | v006 |  | 0.49679 | 0.25885 |  |  |  | 39 | 12.72 | 51.72 | 78.5032 |  | 9.36 | 53 | 62.36 | 204.7552 |  | 9.36 | 12.72 | 22.08 | 49.1412 |  | 9.36 | 12.72 | 22.08 | 49.1412 |  | 9.36 | 12.72 | 22.08 | 49.1412 |  | 9.36 | 12.72 | 22.08 | 49.1412 |  | 202.4 | 479.8234 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 172.7071 | 450.4614 | 450.4614 | [12 empty] | W
Project-A15 |  | v008 |  | 1.1138 | 1.9981 |  |  |  | 72 | 23.76 | 95.76 | 64.6435 |  | 17.28 | 99 | 116.28 | 49.5481 |  | 17.28 | 23.76 | 41.04 | 15.5145 |  | 17.28 | 23.76 | 41.04 | 15.5145 |  | 17.28 | 23.76 | 41.04 | 15.5145 |  | 17.28 | 23.76 | 41.04 | 15.5145 |  | 376.2 | 176.2494 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 142.2158 | 109.0058 | 142.2158 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 102.2378 |  | 10.544 | 63.5333 | 74.0773 | 60.8958 |  | 10.544 | 15.248 | 25.792 | 27.5424 |  | 10.544 | 15.248 | 25.792 | 27.5424 |  | 10.544 | 15.248 | 25.792 | 27.5424 |  | 10.544 | 15.248 | 25.792 | 27.5424 |  | 236.4267 | 273.3031 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 224.9232 | 128.3969 | 252.4718 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1533.5671 |  | 158.16 | 953 | 1111.16 | 913.4369 |  | 158.16 | 228.72 | 386.88 | 413.1357 |  | 158.16 | 228.72 | 386.88 | 413.1357 |  | 158.16 | 228.72 | 386.88 | 413.1357 |  | 158.16 | 228.72 | 386.88 | 413.1357 |  | 3546.4 | 4099.5469 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3373.8477 | 1925.9529 | 3787.0775 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 792.3858 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 281.8365 |  | <- To shorten average individual project span |  |  |  | <----------> | 252.4718
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 46.7314 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 17.4908 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1138.4445 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.7481 | 1.4787 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-24 17:23 |  | 0 | 2014-01-25 17:23 | 2014-03-16 18:26 |  | 0 | 2014-03-17 18:26 | 2014-03-29 18:42 |  | 0 | 2014-03-30 18:42 | 2014-04-11 18:57 |  | 0 | 2014-04-12 18:57 | 2014-04-24 19:12 |  | 0 | 2014-04-25 19:12 | 2014-05-07 19:27 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 125.8106 | 792.3858 | [14 empty] | E
Project-A02 |  | 0.5418 | 1.4656 |  |  |  | 2014-01-01 |  | 14 | 2014-01-16 | 2014-02-12 16:27 |  | 0 | 2014-02-13 16:27 | 2014-04-09 06:31 |  | 0 | 2014-04-10 06:31 | 2014-04-23 08:56 |  | 0 | 2014-04-24 08:56 | 2014-05-07 11:20 |  | 5 | 2014-05-13 11:20 | 2014-05-26 13:45 |  | 0 | 2014-05-27 13:45 | 2014-06-09 16:10 |  | v002 |  | 0.058933 |  | 14 | 0 | 0 | 0 | 5 | 0 | 19 | 12.3759 |  | 144.6736 | [15 empty] | N
Project-A03 |  | 0.54931 | 1.4923 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-31 03:04 |  | 0 | 2014-02-01 03:04 | 2014-02-19 05:17 |  | 0 | 2014-02-20 05:17 | 2014-02-27 05:03 |  | 0 | 2014-02-28 05:03 | 2014-03-07 04:50 |  | 0 | 2014-03-08 04:50 | 2014-03-15 04:36 |  | 0 | 2014-03-16 04:36 | 2014-03-23 04:22 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 80.1823 | [15 empty] | D
Project-A04 |  | 0.48671 | 1.4137 |  |  |  | 2014-01-01 |  | 35 | 2014-02-06 | 2014-04-18 21:53 |  | 0 | 2014-04-19 21:53 | 2014-05-07 04:06 |  | 0 | 2014-05-08 04:06 | 2014-05-25 10:18 |  | 18 | 2014-06-13 10:18 | 2014-06-30 16:31 |  | 0 | 2014-07-01 16:31 | 2014-07-18 22:44 |  | 0 | 2014-07-19 22:44 | 2014-08-06 04:56 |  | v004 |  | 0.032878 |  | 35 | 0 | 0 | 18 | 0 | 0 | 53 | 17.2612 |  | 181.2057
Project-A05 |  | 0.65767 | 4.8535 |  |  |  | 2014-01-01 |  | 43 | 2014-02-14 | 2014-02-23 02:57 |  | 0 | 2014-02-24 02:57 | 2014-03-12 14:33 |  | 0 | 2014-03-13 14:33 | 2014-03-17 13:29 |  | 0 | 2014-03-18 13:29 | 2014-03-22 12:26 |  | 0 | 2014-03-23 12:26 | 2014-03-27 11:23 |  | 0 | 2014-03-28 11:23 | 2014-04-01 10:19 |  | v002 |  | 0.05335 |  | 43 | 0 | 0 | 0 | 0 | 0 | 43 | 34.4107 |  | 46.4299 | [15 empty] | O
Project-A06 |  | 0.28113 | 1.3894 |  |  |  | 2014-01-01 |  | 53 | 2014-02-24 | 2014-08-27 23:16 |  | 0 | 2014-08-28 23:16 | 2014-10-12 08:41 |  | 0 | 2014-10-13 08:41 | 2014-11-26 18:07 |  | 2 | 2014-11-29 18:07 | 2015-01-13 03:32 |  | 0 | 2015-01-14 03:32 | 2015-02-27 12:58 |  | 0 | 2015-02-28 12:58 | 2015-04-13 22:23 |  | v003 |  | 0.059553 |  | 53 | 0 | 0 | 2 | 0 | 0 | 55 | 47.3449 |  | 413.9327 | [15 empty] | F
Project-A07 |  | 0.28362 | 1.4325 |  |  |  | 2014-01-01 |  | 66 | 2014-03-09 | 2015-01-30 21:40 |  | 0 | 2015-01-31 21:40 | 2015-04-20 14:23 |  | 0 | 2015-04-21 14:23 | 2015-07-09 07:06 |  | 0 | 2015-07-10 07:06 | 2015-09-26 23:49 |  | 0 | 2015-09-27 23:49 | 2015-12-15 16:32 |  | 0 | 2015-12-16 16:32 | 2016-03-04 09:16 |  | v005 |  | 0.10918 |  | 66 | 0 | 0 | 0 | 0 | 0 | 66 | 108.0893 |  | 726.3858
Project-A08 |  | 0.54267 | 2.0145 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 05:08 |  | 0 | 2014-01-12 05:08 | 2014-01-17 16:11 |  | 0 | 2014-01-18 16:11 | 2014-01-20 21:15 |  | 0 | 2014-01-21 21:15 | 2014-01-24 02:19 |  | 0 | 2014-01-25 02:19 | 2014-01-27 07:24 |  | 0 | 2014-01-28 07:24 | 2014-01-30 12:28 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28.5193 | [15 empty] | T
Project-A09 |  | 0.25 | 1.4211 |  |  |  | 2014-01-01 |  | 24 | 2014-01-26 | 2014-08-10 |  | 0 | 2014-08-11 | 2014-10-10 12:23 |  | 0 | 2014-10-11 12:23 | 2014-11-27 13:21 |  | 4 | 2014-12-02 13:21 | 2015-01-18 14:18 |  | 0 | 2015-01-19 14:18 | 2015-03-07 15:16 |  | 0 | 2015-03-08 15:16 | 2015-04-24 16:14 |  | v003 |  | 0.083747 |  | 24 | 0 | 0 | 4 | 0 | 0 | 28 | 30.1489 |  | 453.6761 | [15 empty] | H
Project-A10 |  | 0.51023 | 1.6147 |  |  |  | 2014-01-01 |  | 26 | 2014-01-28 | 2014-04-08 13:22 |  | 0 | 2014-04-09 13:22 | 2014-06-02 10:29 |  | 0 | 2014-06-03 10:29 | 2014-06-20 08:53 |  | 13 | 2014-07-04 08:53 | 2014-07-21 07:18 |  | 0 | 2014-07-22 07:18 | 2014-08-08 05:42 |  | 0 | 2014-08-09 05:42 | 2014-08-26 04:07 |  | v001 |  | 0.076303 |  | 26 | 0 | 0 | 13 | 0 | 0 | 39 | 29.7581 |  | 210.1713 | [15 empty] | I
Project-A11 |  | 0.51968 | 1.5059 |  |  |  | 2014-01-01 |  | 47 | 2014-02-18 | 2014-06-19 05:30 |  | 0 | 2014-06-20 05:30 | 2014-08-12 08:31 |  | 0 | 2014-08-13 08:31 | 2014-09-11 10:48 |  | 0 | 2014-09-12 10:48 | 2014-10-11 13:05 |  | 0 | 2014-10-12 13:05 | 2014-11-10 15:22 |  | 0 | 2014-11-11 15:22 | 2014-12-10 17:38 |  | v002 |  | 0.08871 |  | 47 | 0 | 0 | 0 | 0 | 0 | 47 | 62.5403 |  | 295.735 | [15 empty] | S
Project-A12 |  | 0.53461 | 1.3766 |  |  |  | 2014-01-01 |  | 64 | 2014-03-07 | 2014-07-06 13:59 |  | 0 | 2014-07-07 13:59 | 2014-09-11 16:28 |  | 0 | 2014-09-12 16:28 | 2014-10-11 20:47 |  | 0 | 2014-10-12 20:47 | 2014-11-11 01:06 |  | 0 | 2014-11-12 01:06 | 2014-12-11 05:25 |  | 0 | 2014-12-12 05:25 | 2015-01-10 09:44 |  | v004 |  | 0.096774 |  | 64 | 0 | 0 | 0 | 0 | 0 | 64 | 92.9032 |  | 309.4056
Project-A13 |  | 0.48389 | 0.28471 |  |  |  | 2014-01-01 |  | 73 | 2014-03-16 | 2014-09-30 09:26 |  | 0 | 2014-10-01 09:26 | 2015-02-18 21:20 |  | 0 | 2015-02-19 21:20 | 2015-04-08 12:05 |  | 11 | 2015-04-20 12:05 | 2015-06-07 02:49 |  | 0 | 2015-06-08 02:49 | 2015-07-25 17:34 |  | 0 | 2015-07-26 17:34 | 2015-09-12 08:19 |  | v007 |  | 0.084367 |  | 73 | 0 | 0 | 11 | 0 | 0 | 84 | 92.3821 |  | 545.3463 | [15 empty] | W
Project-A14 |  | 0.49679 | 0.25885 |  |  |  | 2014-01-01 |  | 71 | 2014-03-14 | 2014-05-31 12:05 |  | 0 | 2014-06-01 12:05 | 2014-12-23 06:12 |  | 0 | 2014-12-24 06:12 | 2015-02-11 09:36 |  | 0 | 2015-02-12 09:36 | 2015-04-02 12:59 |  | 0 | 2015-04-03 12:59 | 2015-05-22 16:22 |  | 0 | 2015-05-23 16:22 | 2015-07-11 19:46 |  | v006 |  | 0.057072 |  | 71 | 0 | 0 | 0 | 0 | 0 | 71 | 60.7816 |  | 484.8234 | [15 empty] | O
Project-A15 |  | 1.1138 | 1.9981 |  |  |  | 2014-01-01 |  | 71 | 2014-03-14 | 2014-05-17 15:27 |  | 0 | 2014-05-18 15:27 | 2014-07-07 04:36 |  | 0 | 2014-07-08 04:36 | 2014-07-23 16:57 |  | 0 | 2014-07-24 16:57 | 2014-08-09 05:18 |  | 0 | 2014-08-10 05:18 | 2014-08-25 17:38 |  | 0 | 2014-08-26 17:38 | 2014-09-11 05:59 |  | v008 |  | 0.10608 |  | 71 | 0 | 0 | 0 | 0 | 0 | 71 | 112.9746 |  | 181.2494 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 39.1333 |  |  |  | 0 |  |  |  | 0 |  |  |  | 3.2 |  |  |  | 0.33333 |  |  |  | 0 | [5 empty] | 0.066667 |  | 39.1333 | 0 | 0 | 3.2 | 0.33333 | 0 | 42.6667 | 46.7314 | Average | 281.8365 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 587 |  |  |  | 0 |  |  |  | 0 |  |  |  | 48 |  |  |  | 5 |  |  |  | 0 | [5 empty] | 1 |  | 587 | 0 | 0 | 48 | 5 | 0 | 640 | 700.9708 | Total | 4227.5469 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 1
| Days: | 0.34982
E
N
SIT - Violation | Count: | 1 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 0.34982
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-17 18:26 | 2014-03-29 18:42 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-10 06:31 | 2014-04-23 08:56 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-20 05:17 | 2014-02-27 05:03 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-08 04:06 | 2014-05-25 10:18 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-03-13 14:33 | 2014-03-17 13:29 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-10-13 08:41 | 2014-11-26 18:07 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-04-21 14:23 | 2015-07-09 07:06 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-18 16:11 | 2014-01-20 21:15 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-10-11 12:23 | 2014-11-27 13:21 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0.34982 | 0 | 0 | 0 | R
Project-A10 | 2014-06-03 10:29 | 2014-06-20 08:53 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-08-13 08:31 | 2014-09-11 10:48 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-09-12 16:28 | 2014-10-11 20:47 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2015-02-19 21:20 | 2015-04-08 12:05 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-12-24 06:12 | 2015-02-11 09:36 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-08 04:36 | 2014-07-23 16:57 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-03-30 18:42 | 2014-04-11 18:57 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-24 08:56 | 2014-05-07 11:20 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-28 05:03 | 2014-03-07 04:50 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-13 10:18 | 2014-06-30 16:31 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-18 13:29 | 2014-03-22 12:26 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-11-29 18:07 | 2015-01-13 03:32 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-07-10 07:06 | 2015-09-26 23:49 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-21 21:15 | 2014-01-24 02:19 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-12-02 13:21 | 2015-01-18 14:18 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-04 08:53 | 2014-07-21 07:18 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-12 10:48 | 2014-10-11 13:05 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-12 20:47 | 2014-11-11 01:06 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-04-20 12:05 | 2015-06-07 02:49 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-02-12 09:36 | 2015-04-02 12:59 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-07-24 16:57 | 2014-08-09 05:18 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-12 18:57 | 2014-04-24 19:12 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-13 11:20 | 2014-05-26 13:45 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-08 04:50 | 2014-03-15 04:36 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-07-01 16:31 | 2014-07-18 22:44 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-23 12:26 | 2014-03-27 11:23 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-01-14 03:32 | 2015-02-27 12:58 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-09-27 23:49 | 2015-12-15 16:32 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-25 02:19 | 2014-01-27 07:24 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-01-19 14:18 | 2015-03-07 15:16 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-22 07:18 | 2014-08-08 05:42 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-12 13:05 | 2014-11-10 15:22 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-12 01:06 | 2014-12-11 05:25 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-06-08 02:49 | 2015-07-25 17:34 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-04-03 12:59 | 2015-05-22 16:22 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-10 05:18 | 2014-08-25 17:38 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-25 19:12 | 2014-05-07 19:27 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-27 13:45 | 2014-06-09 16:10 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-16 04:36 | 2014-03-23 04:22 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-07-19 22:44 | 2014-08-06 04:56 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-28 11:23 | 2014-04-01 10:19 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-02-28 12:58 | 2015-04-13 22:23 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-12-16 16:32 | 2016-03-04 09:16 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-28 07:24 | 2014-01-30 12:28 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-03-08 15:16 | 2015-04-24 16:14 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-08-09 05:42 | 2014-08-26 04:07 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-11-11 15:22 | 2014-12-10 17:38 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-12 05:25 | 2015-01-10 09:44 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-07-26 17:34 | 2015-09-12 08:19 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-05-23 16:22 | 2015-07-11 19:46 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-26 17:38 | 2014-09-11 05:59 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.48683 | 48.6826 | 48
0.15978 | 15.9781 | 15
0.72382 | 72.3817 | 72
0.21948 | 21.9478 | 21
0.61758 | 61.7577 | 61
0.59628 | 59.6282 | 59
0.9764 | 97.6402 | 97
0.98108 | 98.1081 | 98
0.049192 | 4.9192 | 4
0.61891 | 61.8906 | 61
0.31368 | 31.3681 | 31
0.70143 | 70.1435 | 70
0.55854 | 55.8545 | 55
0.53202 | 53.202 | 53
0.54104 | 54.1037 | 54
0.98068 | 98.0677 | 98
0.40655 | 40.6549 | 40
0.92438 | 92.4381 | 92
0.54125 | 54.1245 | 54
0.16951 | 16.9508 | 16
0.6627 | 66.2704 | 66
0.25268 | 25.2679 | 25
0.50216 | 50.2161 | 50
0.67968 | 67.9677 | 67
0.71788 | 71.7882 | 71
0.8337 | 83.3696 | 83
0.88048 | 88.0483 | 88
0.068685 | 6.8685 | 6
0.19166 | 19.1665 | 19
0.98692 | 98.6922 | 98
0.35934 | 35.9336 | 35
0.51369 | 51.3686 | 51
0.99448 | 99.4483 | 99
0.063856 | 6.3856 | 6
0.697 | 69.7 | 69
0.084815 | 8.4815 | 8
0.34928 | 34.9281 | 34
0.82093 | 82.0926 | 82
0.16032 | 16.0316 | 16

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1138.4445 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 5 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH