## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.47499 | 0.36981 |  |  |  | 17 | 17.76 | 34.76 | 48.0253 |  | 4.08 | 74 | 78.08 | 200.1052 |  | 4.08 | 17.76 | 21.84 | 48.0253 |  | 4.08 | 17.76 | 21.84 | 48.0253 |  | 4.08 | 17.76 | 21.84 | 48.0253 |  | 4.08 | 17.76 | 21.84 | 48.0253 |  | 200.2 | 440.2315 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 78.7382 | 440.2315 | 440.2315
Project-A02 |  | v002 |  | 0.47922 | 1.5305 |  |  |  | 15 | 19.2 | 34.2 | 31.3011 |  | 3.6 | 80 | 83.6 | 52.2721 |  | 3.6 | 19.2 | 22.8 | 12.5453 |  | 3.6 | 19.2 | 22.8 | 12.5453 |  | 3.6 | 19.2 | 22.8 | 12.5453 |  | 3.6 | 19.2 | 22.8 | 12.5453 |  | 209 | 133.7545 | 104500 |  | 0.058933 |  | 33 | 176 |  | 68.8624 | 114.9987 | 114.9987 | [12 empty] | E
Project-A03 |  | v003 |  | 0.49127 | 2.3526 |  |  |  | 16 | 6.48 | 22.48 | 32.5684 |  | 3.84 | 27 | 30.84 | 11.4769 |  | 3.84 | 6.48 | 10.32 | 7.8164 |  | 3.84 | 6.48 | 10.32 | 7.8164 |  | 3.84 | 6.48 | 10.32 | 7.8164 |  | 3.84 | 6.48 | 10.32 | 7.8164 |  | 94.6 | 75.311 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 71.6506 | 25.2492 | 71.6506 | [12 empty] | N
Project-A04 |  | v004 |  | 0.4815 | 1.5243 |  |  |  | 35 | 4.32 | 39.32 | 72.6896 |  | 8.4 | 18 | 26.4 | 17.4455 |  | 8.4 | 4.32 | 12.72 | 17.4455 |  | 8.4 | 4.32 | 12.72 | 17.4455 |  | 8.4 | 4.32 | 12.72 | 17.4455 |  | 8.4 | 4.32 | 12.72 | 17.4455 |  | 116.6 | 159.9171 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 159.9171 | 25.9789 | 159.9171 | [12 empty] | D
Project-A05 |  | v002 |  | 0.48516 | 1.7246 |  |  |  | 6 | 19.2 | 25.2 | 12.367 |  | 1.44 | 80 | 81.44 | 46.3886 |  | 1.44 | 19.2 | 20.64 | 11.1333 |  | 1.44 | 19.2 | 20.64 | 11.1333 |  | 1.44 | 19.2 | 20.64 | 11.1333 |  | 1.44 | 19.2 | 20.64 | 11.1333 |  | 189.2 | 103.2888 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 27.2074 | 102.055 | 102.055
Project-A06 |  | v003 |  | 0.57048 | 1.5044 |  |  |  | 52 | 10.56 | 62.56 | 91.1519 |  | 12.48 | 44 | 56.48 | 29.2484 |  | 12.48 | 10.56 | 23.04 | 21.8765 |  | 12.48 | 10.56 | 23.04 | 21.8765 |  | 12.48 | 10.56 | 23.04 | 21.8765 |  | 12.48 | 10.56 | 23.04 | 21.8765 |  | 211.2 | 207.9061 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 200.5341 | 64.3465 | 200.5341 | [12 empty] | O
Project-A07 |  | v005 |  | 0.47736 | 0.37267 |  |  |  | 93 | 19.92 | 112.92 | 194.8207 |  | 22.32 | 83 | 105.32 | 222.7166 |  | 22.32 | 19.92 | 42.24 | 53.452 |  | 22.32 | 19.92 | 42.24 | 53.452 |  | 22.32 | 19.92 | 42.24 | 53.452 |  | 22.32 | 19.92 | 42.24 | 53.452 |  | 387.2 | 631.3451 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 428.6055 | 489.9764 | 489.9764 | [12 empty] | F
Project-A08 |  | v006 |  | 0.47411 | 2.3055 |  |  |  | 5 | 2.64 | 7.64 | 10.5462 |  | 1.2 | 11 | 12.2 | 4.7713 |  | 1.2 | 2.64 | 3.84 | 2.5311 |  | 1.2 | 2.64 | 3.84 | 2.5311 |  | 1.2 | 2.64 | 3.84 | 2.5311 |  | 1.2 | 2.64 | 3.84 | 2.5311 |  | 35.2 | 25.4418 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 23.2015 | 10.4969 | 23.2015
Project-A09 |  | v003 |  | 0.47107 | 1.5042 |  |  |  | 49 | 20.64 | 69.64 | 104.0188 |  | 11.76 | 86 | 97.76 | 57.1746 |  | 11.76 | 20.64 | 32.4 | 24.9645 |  | 11.76 | 20.64 | 32.4 | 24.9645 |  | 11.76 | 20.64 | 32.4 | 24.9645 |  | 11.76 | 20.64 | 32.4 | 24.9645 |  | 297 | 261.0515 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 228.8414 | 125.7842 | 228.8414 | [12 empty] | T
Project-A10 |  | v001 |  | 0.46175 | 0.32571 |  |  |  | 36 | 20.88 | 56.88 | 77.9636 |  | 8.64 | 87 | 95.64 | 267.1051 |  | 8.64 | 20.88 | 29.52 | 64.1052 |  | 8.64 | 20.88 | 29.52 | 64.1052 |  | 8.64 | 20.88 | 29.52 | 64.1052 |  | 8.64 | 20.88 | 29.52 | 64.1052 |  | 270.6 | 601.4896 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 171.52 | 587.6312 | 587.6312 | [12 empty] | H
Project-A11 |  | v002 |  | 0.57384 | 1.4773 |  |  |  | 63 | 19.2 | 82.2 | 109.786 |  | 15.12 | 80 | 95.12 | 54.1538 |  | 15.12 | 19.2 | 34.32 | 26.3487 |  | 15.12 | 19.2 | 34.32 | 26.3487 |  | 15.12 | 19.2 | 34.32 | 26.3487 |  | 15.12 | 19.2 | 34.32 | 26.3487 |  | 314.6 | 269.3344 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 241.5293 | 119.1383 | 241.5293 | [12 empty] | I
Project-A12 |  | v004 |  | 0.54721 | 1.4979 |  |  |  | 65 | 21.84 | 86.84 | 118.7847 |  | 15.6 | 91 | 106.6 | 60.7518 |  | 15.6 | 21.84 | 37.44 | 28.5083 |  | 15.6 | 21.84 | 37.44 | 28.5083 |  | 15.6 | 21.84 | 37.44 | 28.5083 |  | 15.6 | 21.84 | 37.44 | 28.5083 |  | 343.2 | 293.5698 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 261.3263 | 133.654 | 261.3263 | [12 empty] | S
Project-A13 |  | v007 |  | 0.4902 | 1.9806 |  |  |  | 96 | 9.6 | 105.6 | 195.837 |  | 23.04 | 40 | 63.04 | 47.0009 |  | 23.04 | 9.6 | 32.64 | 47.0009 |  | 23.04 | 9.6 | 32.64 | 47.0009 |  | 23.04 | 9.6 | 32.64 | 47.0009 |  | 23.04 | 9.6 | 32.64 | 47.0009 |  | 299.2 | 430.8414 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 430.8414 | 44.4308 | 430.8414
Project-A14 |  | v006 |  | 0.25794 | 3.4702 |  |  |  | 39 | 12.72 | 51.72 | 151.1956 |  | 9.36 | 53 | 62.36 | 36.2869 |  | 9.36 | 12.72 | 22.08 | 36.2869 |  | 9.36 | 12.72 | 22.08 | 36.2869 |  | 9.36 | 12.72 | 22.08 | 36.2869 |  | 9.36 | 12.72 | 22.08 | 36.2869 |  | 202.4 | 332.6303 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 332.6303 | 33.6003 | 332.6303 | [12 empty] | W
Project-A15 |  | v008 |  | 1.2639 | 2.06 |  |  |  | 72 | 23.76 | 95.76 | 56.967 |  | 17.28 | 99 | 116.28 | 48.059 |  | 17.28 | 23.76 | 41.04 | 13.6721 |  | 17.28 | 23.76 | 41.04 | 13.6721 |  | 17.28 | 23.76 | 41.04 | 13.6721 |  | 17.28 | 23.76 | 41.04 | 13.6721 |  | 376.2 | 159.7142 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 125.3273 | 105.7298 | 125.3273 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 87.2015 |  | 10.544 | 63.5333 | 74.0773 | 76.9971 |  | 10.544 | 15.248 | 25.792 | 27.7141 |  | 10.544 | 15.248 | 25.792 | 27.7141 |  | 10.544 | 15.248 | 25.792 | 27.7141 |  | 10.544 | 15.248 | 25.792 | 27.7141 |  | 236.4267 | 275.0551 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 190.0489 | 161.5534 | 254.0461 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1308.0229 |  | 158.16 | 953 | 1111.16 | 1154.9568 |  | 158.16 | 228.72 | 386.88 | 415.7119 |  | 158.16 | 228.72 | 386.88 | 415.7119 |  | 158.16 | 228.72 | 386.88 | 415.7119 |  | 158.16 | 228.72 | 386.88 | 415.7119 |  | 3546.4 | 4125.8271 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2850.7329 | 2423.3016 | 3810.6921 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 889.7142 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 307.7218 |  | <- To shorten average individual project span |  |  |  | <----------> | 254.0461
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 88.9045 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 0 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1286.3405 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | TRUE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.47499 | 0.36981 |  |  |  | 2014-01-01 |  | 364 | 2015-01-01 | 2015-02-18 00:36 |  | 0 | 2015-02-19 00:36 | 2015-09-07 03:08 |  | 0 | 2015-09-08 03:08 | 2015-10-26 03:44 |  | 2 | 2015-10-29 03:44 | 2015-12-16 04:21 |  | 2 | 2015-12-19 04:21 | 2016-02-05 04:57 |  | 0 | 2016-02-06 04:57 | 2016-03-25 05:33 |  | v001 |  | 0.056452 |  | 364 | 0 | 0 | 2 | 2 | 0 | 368 | 308.2258 |  | 449.2315 | 889.7142 | [14 empty] | E
Project-A02 |  | 0.47922 | 1.5305 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-02-14 07:14 |  | 0 | 2014-02-15 07:14 | 2014-04-08 13:45 |  | 0 | 2014-04-09 13:45 | 2014-04-22 02:51 |  | 1 | 2014-04-24 02:51 | 2014-05-06 15:56 |  | 4 | 2014-05-11 15:56 | 2014-05-24 05:01 |  | 0 | 2014-05-25 05:01 | 2014-06-06 18:06 |  | v002 |  | 0.058933 |  | 12 | 0 | 0 | 1 | 4 | 0 | 17 | 10.6079 |  | 143.7545 | [15 empty] | N
Project-A03 |  | 0.49127 | 2.3526 |  |  |  | 2014-01-01 |  | 3 | 2014-01-05 | 2014-02-06 13:39 |  | 0 | 2014-02-07 13:39 | 2014-02-19 01:05 |  | 0 | 2014-02-20 01:05 | 2014-02-27 20:41 |  | 0 | 2014-02-28 20:41 | 2014-03-08 16:17 |  | 0 | 2014-03-09 16:17 | 2014-03-17 11:52 |  | 0 | 2014-03-18 11:52 | 2014-03-26 07:28 |  | v003 |  | 0.026675 |  | 3 | 0 | 0 | 0 | 0 | 0 | 3 | 1.2004 |  | 80.311 | [15 empty] | D
Project-A04 |  | 0.4815 | 1.5243 |  |  |  | 2014-01-01 |  | 38 | 2014-02-09 | 2014-04-22 16:33 |  | 0 | 2014-04-23 16:33 | 2014-05-11 03:15 |  | 0 | 2014-05-12 03:15 | 2014-05-29 13:56 |  | 0 | 2014-05-30 13:56 | 2014-06-17 00:38 |  | 0 | 2014-06-18 00:38 | 2014-07-05 11:19 |  | 2 | 2014-07-08 11:19 | 2014-07-25 22:01 |  | v004 |  | 0.032878 |  | 38 | 0 | 0 | 0 | 0 | 2 | 40 | 18.7407 |  | 166.9171
Project-A05 |  | 0.48516 | 1.7246 |  |  |  | 2014-01-01 |  | 4 | 2014-01-06 | 2014-01-18 08:48 |  | 0 | 2014-01-19 08:48 | 2014-03-06 18:08 |  | 0 | 2014-03-07 18:08 | 2014-03-18 21:20 |  | 2 | 2014-03-21 21:20 | 2014-04-02 00:32 |  | 0 | 2014-04-03 00:32 | 2014-04-14 03:44 |  | 3 | 2014-04-18 03:44 | 2014-04-29 06:56 |  | v002 |  | 0.05335 |  | 4 | 0 | 0 | 2 | 0 | 3 | 9 | 3.201 |  | 113.2888 | [15 empty] | O
Project-A06 |  | 0.57048 | 1.5044 |  |  |  | 2014-01-01 |  | 59 | 2014-03-02 | 2014-06-01 03:39 |  | 0 | 2014-06-02 03:39 | 2014-07-01 09:36 |  | 0 | 2014-07-02 09:36 | 2014-07-24 06:39 |  | 0 | 2014-07-25 06:39 | 2014-08-16 03:41 |  | 0 | 2014-08-17 03:41 | 2014-09-08 00:43 |  | 0 | 2014-09-09 00:43 | 2014-09-30 21:45 |  | v003 |  | 0.059553 |  | 59 | 0 | 0 | 0 | 0 | 0 | 59 | 52.7047 |  | 212.9061 | [15 empty] | F
Project-A07 |  | 0.47736 | 0.37267 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-09-20 19:42 |  | 0 | 2014-09-21 19:42 | 2015-05-02 12:54 |  | 0 | 2015-05-03 12:54 | 2015-06-25 23:44 |  | 2 | 2015-06-28 23:44 | 2015-08-21 10:35 |  | 1 | 2015-08-23 10:35 | 2015-10-15 21:26 |  | 0 | 2015-10-16 21:26 | 2015-12-09 08:17 |  | v005 |  | 0.10918 |  | 67 | 0 | 0 | 2 | 1 | 0 | 70 | 109.727 |  | 639.3451
Project-A08 |  | 0.47411 | 2.3055 |  |  |  | 2014-01-01 |  | 2 | 2014-01-04 | 2014-01-14 13:06 |  | 0 | 2014-01-15 13:06 | 2014-01-20 07:37 |  | 0 | 2014-01-21 07:37 | 2014-01-23 20:22 |  | 1 | 2014-01-25 20:22 | 2014-01-28 09:07 |  | 3 | 2014-02-01 09:07 | 2014-02-03 21:51 |  | 3 | 2014-02-07 21:51 | 2014-02-10 10:36 |  | v006 |  | 0.0099256 |  | 2 | 0 | 0 | 1 | 3 | 3 | 9 | 0.29777 |  | 37.4418 | [15 empty] | T
Project-A09 |  | 0.47107 | 1.5042 |  |  |  | 2014-01-01 |  | 1 | 2014-01-03 | 2014-04-17 00:27 |  | 0 | 2014-04-18 00:27 | 2014-06-14 04:39 |  | 0 | 2014-06-15 04:39 | 2014-07-10 03:48 |  | 1 | 2014-07-12 03:48 | 2014-08-06 02:56 |  | 1 | 2014-08-08 02:56 | 2014-09-02 02:05 |  | 0 | 2014-09-03 02:05 | 2014-09-28 01:14 |  | v003 |  | 0.083747 |  | 1 | 0 | 0 | 1 | 1 | 0 | 3 | 1.2562 |  | 268.0515 | [15 empty] | H
Project-A10 |  | 0.46175 | 0.32571 |  |  |  | 2014-01-01 |  | 2 | 2014-01-04 | 2014-03-22 23:08 |  | 0 | 2014-03-23 23:08 | 2014-12-16 01:39 |  | 0 | 2014-12-17 01:39 | 2015-02-19 04:10 |  | 0 | 2015-02-20 04:10 | 2015-04-25 06:42 |  | 1 | 2015-04-27 06:42 | 2015-06-30 09:14 |  | 0 | 2015-07-01 09:14 | 2015-09-03 11:45 |  | v001 |  | 0.076303 |  | 2 | 0 | 0 | 0 | 1 | 0 | 3 | 2.2891 |  | 607.4896 | [15 empty] | I
Project-A11 |  | 0.57384 | 1.4773 |  |  |  | 2014-01-01 |  | 38 | 2014-02-09 | 2014-05-29 18:52 |  | 0 | 2014-05-30 18:52 | 2014-07-23 22:33 |  | 0 | 2014-07-24 22:33 | 2014-08-20 06:55 |  | 2 | 2014-08-23 06:55 | 2014-09-18 15:17 |  | 0 | 2014-09-19 15:17 | 2014-10-15 23:40 |  | 1 | 2014-10-17 23:40 | 2014-11-13 08:02 |  | v002 |  | 0.08871 |  | 38 | 0 | 0 | 2 | 0 | 1 | 41 | 50.5645 |  | 277.3344 | [15 empty] | S
Project-A12 |  | 0.54721 | 1.4979 |  |  |  | 2014-01-01 |  | 49 | 2014-02-20 | 2014-06-18 18:50 |  | 0 | 2014-06-19 18:50 | 2014-08-19 12:53 |  | 0 | 2014-08-20 12:53 | 2014-09-18 01:05 |  | 3 | 2014-09-22 01:05 | 2014-10-20 13:17 |  | 1 | 2014-10-22 13:17 | 2014-11-20 01:29 |  | 1 | 2014-11-22 01:29 | 2014-12-20 13:41 |  | v004 |  | 0.096774 |  | 49 | 0 | 0 | 3 | 1 | 1 | 54 | 71.129 |  | 303.5698
Project-A13 |  | 0.4902 | 1.9806 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-09-10 20:05 |  | 0 | 2014-09-11 20:05 | 2014-10-28 20:07 |  | 0 | 2014-10-29 20:07 | 2014-12-15 20:08 |  | 2 | 2014-12-18 20:08 | 2015-02-03 20:09 |  | 3 | 2015-02-07 20:09 | 2015-03-26 20:10 |  | 0 | 2015-03-27 20:10 | 2015-05-13 20:12 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 2 | 3 | 0 | 61 | 70.8685 |  | 440.8414 | [15 empty] | W
Project-A14 |  | 0.25794 | 3.4702 |  |  |  | 2014-01-01 |  | 70 | 2014-03-13 | 2014-08-11 04:42 |  | 0 | 2014-08-12 04:42 | 2014-09-17 11:35 |  | 0 | 2014-09-18 11:35 | 2014-10-24 18:28 |  | 3 | 2014-10-28 18:28 | 2014-12-04 01:21 |  | 1 | 2014-12-06 01:21 | 2015-01-11 08:14 |  | 3 | 2015-01-15 08:14 | 2015-02-20 15:08 |  | v006 |  | 0.057072 |  | 70 | 0 | 0 | 3 | 1 | 3 | 77 | 59.9256 |  | 344.6303 | [15 empty] | O
Project-A15 |  | 1.2639 | 2.06 |  |  |  | 2014-01-01 |  | 360 | 2014-12-28 | 2015-02-22 23:12 |  | 0 | 2015-02-23 23:12 | 2015-04-13 00:37 |  | 0 | 2015-04-14 00:37 | 2015-04-27 16:45 |  | 363 | 2016-04-25 16:45 | 2016-05-09 08:53 |  | 1 | 2016-05-11 08:53 | 2016-05-25 01:01 |  | 2 | 2016-05-28 01:01 | 2016-06-10 17:09 |  | v008 |  | 0.10608 |  | 360 | 0 | 0 | 363 | 1 | 2 | 726 | 572.8288 |  | 530.7142 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 75 |  |  |  | 0 |  |  |  | 0 |  |  |  | 25.4667 |  |  |  | 1.2 |  |  |  | 1 | [5 empty] | 0.066667 |  | 75 | 0 | 0 | 25.4667 | 1.2 | 1 | 102.6667 | 88.9045 | Average | 307.7218 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 1125 |  |  |  | 0 |  |  |  | 0 |  |  |  | 382 |  |  |  | 18 |  |  |  | 15 | [5 empty] | 1 |  | 1125 | 0 | 0 | 382 | 18 | 15 | 1540 | 1333.567 | Total | 4615.8271 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 0
| Days: | 0
E
N
SIT - Violation | Count: | 0 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 0
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2015-09-08 03:08 | 2015-10-26 03:44 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-09 13:45 | 2014-04-22 02:51 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-20 01:05 | 2014-02-27 20:41 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-12 03:15 | 2014-05-29 13:56 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-03-07 18:08 | 2014-03-18 21:20 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-02 09:36 | 2014-07-24 06:39 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-05-03 12:54 | 2015-06-25 23:44 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-21 07:37 | 2014-01-23 20:22 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-15 04:39 | 2014-07-10 03:48 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-12-17 01:39 | 2015-02-19 04:10 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-07-24 22:33 | 2014-08-20 06:55 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-20 12:53 | 2014-09-18 01:05 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-29 20:07 | 2014-12-15 20:08 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-09-18 11:35 | 2014-10-24 18:28 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2015-04-14 00:37 | 2015-04-27 16:45 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-10-29 03:44 | 2015-12-16 04:21 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-24 02:51 | 2014-05-06 15:56 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-28 20:41 | 2014-03-08 16:17 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-30 13:56 | 2014-06-17 00:38 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-21 21:20 | 2014-04-02 00:32 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-07-25 06:39 | 2014-08-16 03:41 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-06-28 23:44 | 2015-08-21 10:35 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-25 20:22 | 2014-01-28 09:07 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-12 03:48 | 2014-08-06 02:56 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-02-20 04:10 | 2015-04-25 06:42 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-08-23 06:55 | 2014-09-18 15:17 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-22 01:05 | 2014-10-20 13:17 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-18 20:08 | 2015-02-03 20:09 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-10-28 18:28 | 2014-12-04 01:21 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-04-25 16:45 | 2016-05-09 08:53 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-12-19 04:21 | 2016-02-05 04:57 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-11 15:56 | 2014-05-24 05:01 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-09 16:17 | 2014-03-17 11:52 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-18 00:38 | 2014-07-05 11:19 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-03 00:32 | 2014-04-14 03:44 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-17 03:41 | 2014-09-08 00:43 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-23 10:35 | 2015-10-15 21:26 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-02-01 09:07 | 2014-02-03 21:51 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-08 02:56 | 2014-09-02 02:05 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-04-27 06:42 | 2015-06-30 09:14 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-19 15:17 | 2014-10-15 23:40 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-22 13:17 | 2014-11-20 01:29 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-02-07 20:09 | 2015-03-26 20:10 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-12-06 01:21 | 2015-01-11 08:14 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-05-11 08:53 | 2016-05-25 01:01 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-02-06 04:57 | 2016-03-25 05:33 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-25 05:01 | 2014-06-06 18:06 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-18 11:52 | 2014-03-26 07:28 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-07-08 11:19 | 2014-07-25 22:01 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-18 03:44 | 2014-04-29 06:56 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-09 00:43 | 2014-09-30 21:45 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-16 21:26 | 2015-12-09 08:17 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-02-07 21:51 | 2014-02-10 10:36 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-09-03 02:05 | 2014-09-28 01:14 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-07-01 09:14 | 2015-09-03 11:45 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-17 23:40 | 2014-11-13 08:02 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-22 01:29 | 2014-12-20 13:41 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-27 20:10 | 2015-05-13 20:12 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-01-15 08:14 | 2015-02-20 15:08 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-05-28 01:01 | 2016-06-10 17:09 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.27035 | 27.0349 | 27
0.60036 | 60.0362 | 60
0.66487 | 66.4867 | 66
0.67117 | 67.1169 | 67
0.81915 | 81.9146 | 81
0.11144 | 11.1444 | 11
0.055356 | 5.5356 | 5
0.15498 | 15.4983 | 15
0.33122 | 33.122 | 33
0.35208 | 35.2079 | 35
0.53615 | 53.6146 | 53
0.5936 | 59.3601 | 59
0.96162 | 96.1615 | 96
0.69491 | 69.4906 | 69
0.8317 | 83.1703 | 83
0.1947 | 19.4701 | 19
0.085018 | 8.5018 | 8
0.24623 | 24.6225 | 24
0.79265 | 79.2647 | 79
0.64214 | 64.2136 | 64
0.61715 | 61.7155 | 61
0.46259 | 46.2587 | 46
0.86474 | 86.4735 | 86
0.74409 | 74.409 | 74
0.15799 | 15.7991 | 15
0.58196 | 58.1964 | 58
0.17597 | 17.5973 | 17
0.088886 | 8.8886 | 8
0.26139 | 26.1387 | 26
0.10894 | 10.8937 | 10
0.87619 | 87.6194 | 87
0.74248 | 74.2482 | 74
0.027546 | 2.7546 | 2
0.67576 | 67.5762 | 67
0.28826 | 28.8259 | 28
0.46564 | 46.564 | 46
0.78176 | 78.1755 | 78
0.38454 | 38.4543 | 38
0.85178 | 85.1775 | 85

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1286.3405 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 2 | 1 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH