## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.62706 | 0.25025 |  |  |  | 17 | 17.76 | 34.76 | 70.9704 |  | 4.08 | 74 | 78.08 | 295.7101 |  | 4.08 | 17.76 | 21.84 | 70.9704 |  | 4.08 | 17.76 | 21.84 | 70.9704 |  | 4.08 | 17.76 | 21.84 | 70.9704 |  | 4.08 | 17.76 | 21.84 | 70.9704 |  | 200.2 | 650.5623 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 59.643 | 650.5623 | 650.5623
Project-A02 |  | v002 |  | 0.50275 | 3.1084 |  |  |  | 15 | 19.2 | 34.2 | 29.836 |  | 3.6 | 80 | 83.6 | 25.7364 |  | 3.6 | 19.2 | 22.8 | 7.1606 |  | 3.6 | 19.2 | 22.8 | 7.1606 |  | 3.6 | 19.2 | 22.8 | 7.1606 |  | 3.6 | 19.2 | 22.8 | 7.1606 |  | 209 | 84.2149 | 104500 |  | 0.058933 |  | 33 | 176 |  | 65.6392 | 56.62 | 65.6392 | [12 empty] | E
Project-A03 |  | v003 |  | 0.49376 | 2.7927 |  |  |  | 16 | 6.48 | 22.48 | 32.4045 |  | 3.84 | 27 | 30.84 | 9.668 |  | 3.84 | 6.48 | 10.32 | 7.7771 |  | 3.84 | 6.48 | 10.32 | 7.7771 |  | 3.84 | 6.48 | 10.32 | 7.7771 |  | 3.84 | 6.48 | 10.32 | 7.7771 |  | 94.6 | 73.1808 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 71.2898 | 21.2697 | 71.2898 | [12 empty] | N
Project-A04 |  | v004 |  | 0.55294 | 1.5116 |  |  |  | 35 | 4.32 | 39.32 | 63.2984 |  | 8.4 | 18 | 26.4 | 15.1916 |  | 8.4 | 4.32 | 12.72 | 15.1916 |  | 8.4 | 4.32 | 12.72 | 15.1916 |  | 8.4 | 4.32 | 12.72 | 15.1916 |  | 8.4 | 4.32 | 12.72 | 15.1916 |  | 116.6 | 139.2565 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 139.2565 | 26.1981 | 139.2565 | [12 empty] | D
Project-A05 |  | v002 |  | 0.54702 | 0.25251 |  |  |  | 6 | 19.2 | 25.2 | 76.0381 |  | 1.44 | 80 | 81.44 | 316.8253 |  | 1.44 | 19.2 | 20.64 | 76.0381 |  | 1.44 | 19.2 | 20.64 | 76.0381 |  | 1.44 | 19.2 | 20.64 | 76.0381 |  | 1.44 | 19.2 | 20.64 | 76.0381 |  | 189.2 | 697.0156 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 24.1307 | 697.0156 | 697.0156
Project-A06 |  | v003 |  | 0.52137 | 1.3885 |  |  |  | 52 | 10.56 | 62.56 | 99.7378 |  | 12.48 | 44 | 56.48 | 31.6894 |  | 12.48 | 10.56 | 23.04 | 23.9371 |  | 12.48 | 10.56 | 23.04 | 23.9371 |  | 12.48 | 10.56 | 23.04 | 23.9371 |  | 12.48 | 10.56 | 23.04 | 23.9371 |  | 211.2 | 227.1755 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 219.4232 | 69.7166 | 219.4232 | [12 empty] | O
Project-A07 |  | v005 |  | 0.53608 | 1.5399 |  |  |  | 93 | 19.92 | 112.92 | 173.4818 |  | 22.32 | 83 | 105.32 | 53.8979 |  | 22.32 | 19.92 | 42.24 | 41.6356 |  | 22.32 | 19.92 | 42.24 | 41.6356 |  | 22.32 | 19.92 | 42.24 | 41.6356 |  | 22.32 | 19.92 | 42.24 | 41.6356 |  | 387.2 | 393.9223 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 381.66 | 118.5754 | 381.66 | [12 empty] | F
Project-A08 |  | v006 |  | 0.49569 | 1.1321 |  |  |  | 5 | 2.64 | 7.64 | 10.0869 |  | 1.2 | 11 | 12.2 | 9.7165 |  | 1.2 | 2.64 | 3.84 | 2.4209 |  | 1.2 | 2.64 | 3.84 | 2.4209 |  | 1.2 | 2.64 | 3.84 | 2.4209 |  | 1.2 | 2.64 | 3.84 | 2.4209 |  | 35.2 | 29.4869 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 22.1913 | 21.3762 | 22.1913
Project-A09 |  | v003 |  | 0.55835 | 1.4707 |  |  |  | 49 | 20.64 | 69.64 | 87.7579 |  | 11.76 | 86 | 97.76 | 58.4754 |  | 11.76 | 20.64 | 32.4 | 21.0619 |  | 11.76 | 20.64 | 32.4 | 21.0619 |  | 11.76 | 20.64 | 32.4 | 21.0619 |  | 11.76 | 20.64 | 32.4 | 21.0619 |  | 297 | 230.4808 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 193.0673 | 128.6459 | 193.0673 | [12 empty] | T
Project-A10 |  | v001 |  | 0.5164 | 2.2216 |  |  |  | 36 | 20.88 | 56.88 | 69.7139 |  | 8.64 | 87 | 95.64 | 39.1612 |  | 8.64 | 20.88 | 29.52 | 16.7313 |  | 8.64 | 20.88 | 29.52 | 16.7313 |  | 8.64 | 20.88 | 29.52 | 16.7313 |  | 8.64 | 20.88 | 29.52 | 16.7313 |  | 270.6 | 175.8005 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 153.3707 | 86.1547 | 153.3707 | [12 empty] | H
Project-A11 |  | v002 |  | 0.38464 | 0.28039 |  |  |  | 63 | 19.2 | 82.2 | 163.7909 |  | 15.12 | 80 | 95.12 | 285.3172 |  | 15.12 | 19.2 | 34.32 | 68.4761 |  | 15.12 | 19.2 | 34.32 | 68.4761 |  | 15.12 | 19.2 | 34.32 | 68.4761 |  | 15.12 | 19.2 | 34.32 | 68.4761 |  | 314.6 | 723.0125 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 360.3399 | 627.6978 | 627.6978 | [12 empty] | I
Project-A12 |  | v004 |  | 0.52595 | 1.5134 |  |  |  | 65 | 21.84 | 86.84 | 123.5869 |  | 15.6 | 91 | 106.6 | 60.1294 |  | 15.6 | 21.84 | 37.44 | 29.6609 |  | 15.6 | 21.84 | 37.44 | 29.6609 |  | 15.6 | 21.84 | 37.44 | 29.6609 |  | 15.6 | 21.84 | 37.44 | 29.6609 |  | 343.2 | 302.3597 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 271.8912 | 132.2847 | 271.8912 | [12 empty] | S
Project-A13 |  | v007 |  | 0.27067 | 2.0156 |  |  |  | 96 | 9.6 | 105.6 | 354.68 |  | 23.04 | 40 | 63.04 | 85.1232 |  | 23.04 | 9.6 | 32.64 | 85.1232 |  | 23.04 | 9.6 | 32.64 | 85.1232 |  | 23.04 | 9.6 | 32.64 | 85.1232 |  | 23.04 | 9.6 | 32.64 | 85.1232 |  | 299.2 | 780.2961 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 780.2961 | 43.6592 | 780.2961
Project-A14 |  | v006 |  | 0.52898 | 1.9788 |  |  |  | 39 | 12.72 | 51.72 | 73.7273 |  | 9.36 | 53 | 62.36 | 26.7844 |  | 9.36 | 12.72 | 22.08 | 17.6945 |  | 9.36 | 12.72 | 22.08 | 17.6945 |  | 9.36 | 12.72 | 22.08 | 17.6945 |  | 9.36 | 12.72 | 22.08 | 17.6945 |  | 202.4 | 171.2899 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 162.2 | 58.9258 | 162.2 | [12 empty] | W
Project-A15 |  | v008 |  | 0.93836 | 2.5436 |  |  |  | 72 | 23.76 | 95.76 | 76.7298 |  | 17.28 | 99 | 116.28 | 38.9218 |  | 17.28 | 23.76 | 41.04 | 18.4152 |  | 17.28 | 23.76 | 41.04 | 18.4152 |  | 17.28 | 23.76 | 41.04 | 18.4152 |  | 17.28 | 23.76 | 41.04 | 18.4152 |  | 376.2 | 189.3122 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 168.8056 | 85.6279 | 168.8056 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 100.3894 |  | 10.544 | 63.5333 | 74.0773 | 90.1565 |  | 10.544 | 15.248 | 25.792 | 33.4863 |  | 10.544 | 15.248 | 25.792 | 33.4863 |  | 10.544 | 15.248 | 25.792 | 33.4863 |  | 10.544 | 15.248 | 25.792 | 33.4863 |  | 236.4267 | 324.4911 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 204.8803 | 188.2887 | 306.9578 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1505.8406 |  | 158.16 | 953 | 1111.16 | 1352.3479 |  | 158.16 | 228.72 | 386.88 | 502.2945 |  | 158.16 | 228.72 | 386.88 | 502.2945 |  | 158.16 | 228.72 | 386.88 | 502.2945 |  | 158.16 | 228.72 | 386.88 | 502.2945 |  | 3546.4 | 4867.3665 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3073.2043 | 2824.3299 | 4604.3663 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 918.2961 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 348.6911 |  | <- To shorten average individual project span |  |  |  | <----------> | 306.9578
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 58.5775 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 41.327 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1366.8917 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.62706 | 0.25025 |  |  |  | 2014-01-01 |  | 3 | 2014-01-05 | 2014-03-16 23:17 |  | 0 | 2014-03-17 23:17 | 2015-01-07 16:20 |  | 0 | 2015-01-08 16:20 | 2015-03-20 15:37 |  | 2 | 2015-03-23 15:37 | 2015-06-02 14:55 |  | 32 | 2015-07-05 14:55 | 2015-09-14 14:12 |  | 0 | 2015-09-15 14:12 | 2015-11-25 13:30 |  | v001 |  | 0.056452 |  | 3 | 0 | 0 | 2 | 32 | 0 | 37 | 2.5403 |  | 689.5623 | 918.2961 | [14 empty] | E
Project-A02 |  | 0.50275 | 3.1084 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-31 20:04 |  | 0 | 2014-02-01 20:04 | 2014-02-27 13:44 |  | 0 | 2014-02-28 13:44 | 2014-03-07 17:36 |  | 0 | 2014-03-08 17:36 | 2014-03-15 21:27 |  | 0 | 2014-03-16 21:27 | 2014-03-24 01:18 |  | 0 | 2014-03-25 01:18 | 2014-04-01 05:10 |  | v002 |  | 0.058933 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 89.2149 | [15 empty] | N
Project-A03 |  | 0.49376 | 2.7927 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-03 09:42 |  | 0 | 2014-02-04 09:42 | 2014-02-14 01:44 |  | 0 | 2014-02-15 01:44 | 2014-02-22 20:23 |  | 0 | 2014-02-23 20:23 | 2014-03-03 15:02 |  | 0 | 2014-03-04 15:02 | 2014-03-12 09:41 |  | 0 | 2014-03-13 09:41 | 2014-03-21 04:20 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 78.1808 | [15 empty] | D
Project-A04 |  | 0.55294 | 1.5116 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-04-09 07:10 |  | 0 | 2014-04-10 07:10 | 2014-04-25 11:46 |  | 0 | 2014-04-26 11:46 | 2014-05-11 16:22 |  | 0 | 2014-05-12 16:22 | 2014-05-27 20:57 |  | 0 | 2014-05-28 20:57 | 2014-06-13 01:33 |  | 0 | 2014-06-14 01:33 | 2014-06-29 06:09 |  | v004 |  | 0.032878 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 16.768 |  | 144.2565
Project-A05 |  | 0.54702 | 0.25251 |  |  |  | 2014-01-01 |  | 49 | 2014-02-20 | 2014-05-07 00:55 |  | 0 | 2014-05-08 00:55 | 2015-03-20 20:43 |  | 0 | 2015-03-21 20:43 | 2015-06-05 21:38 |  | 0 | 2015-06-06 21:38 | 2015-08-21 22:33 |  | 69 | 2015-10-30 22:33 | 2016-01-14 23:28 |  | 0 | 2016-01-15 23:28 | 2016-04-01 00:22 |  | v002 |  | 0.05335 |  | 49 | 0 | 0 | 0 | 69 | 0 | 118 | 39.2122 |  | 771.0156 | [15 empty] | O
Project-A06 |  | 0.52137 | 1.3885 |  |  |  | 2014-01-01 |  | 128 | 2014-05-10 | 2014-08-17 17:42 |  | 0 | 2014-08-18 17:42 | 2014-09-19 10:15 |  | 0 | 2014-09-20 10:15 | 2014-10-14 08:45 |  | 43 | 2014-11-27 08:45 | 2014-12-21 07:14 |  | 70 | 2015-03-02 07:14 | 2015-03-26 05:43 |  | 0 | 2015-03-27 05:43 | 2015-04-20 04:13 |  | v003 |  | 0.059553 |  | 128 | 0 | 0 | 43 | 70 | 0 | 241 | 114.3424 |  | 345.1755 | [15 empty] | F
Project-A07 |  | 0.53608 | 1.5399 |  |  |  | 2014-01-01 |  | 73 | 2014-03-16 | 2014-09-05 11:34 |  | 0 | 2014-09-06 11:34 | 2014-10-30 09:07 |  | 0 | 2014-10-31 09:07 | 2014-12-12 00:22 |  | 59 | 2015-02-10 00:22 | 2015-03-23 15:37 |  | 2 | 2015-03-26 15:37 | 2015-05-07 06:53 |  | 0 | 2015-05-08 06:53 | 2015-06-18 22:08 |  | v005 |  | 0.10918 |  | 73 | 0 | 0 | 59 | 2 | 0 | 134 | 119.5533 |  | 459.9223
Project-A08 |  | 0.49569 | 1.1321 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-12 02:05 |  | 0 | 2014-01-13 02:05 | 2014-01-22 19:17 |  | 0 | 2014-01-23 19:17 | 2014-01-26 05:23 |  | 0 | 2014-01-27 05:23 | 2014-01-29 15:29 |  | 0 | 2014-01-30 15:29 | 2014-02-02 01:35 |  | 0 | 2014-02-03 01:35 | 2014-02-05 11:41 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 34.4869 | [15 empty] | T
Project-A09 |  | 0.55835 | 1.4707 |  |  |  | 2014-01-01 |  | 20 | 2014-01-22 | 2014-04-19 18:11 |  | 0 | 2014-04-20 18:11 | 2014-06-18 05:36 |  | 0 | 2014-06-19 05:36 | 2014-07-10 07:05 |  | 0 | 2014-07-11 07:05 | 2014-08-01 08:34 |  | 0 | 2014-08-02 08:34 | 2014-08-23 10:03 |  | 0 | 2014-08-24 10:03 | 2014-09-14 11:32 |  | v003 |  | 0.083747 |  | 20 | 0 | 0 | 0 | 0 | 0 | 20 | 25.1241 |  | 235.4808 | [15 empty] | H
Project-A10 |  | 0.5164 | 2.2216 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-04-04 17:08 |  | 0 | 2014-04-05 17:08 | 2014-05-14 21:00 |  | 0 | 2014-05-15 21:00 | 2014-06-01 14:33 |  | 0 | 2014-06-02 14:33 | 2014-06-19 08:07 |  | 0 | 2014-06-20 08:07 | 2014-07-07 01:40 |  | 0 | 2014-07-08 01:40 | 2014-07-24 19:13 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 0 | 0 | 0 | 23 | 26.3244 |  | 180.8005 | [15 empty] | I
Project-A11 |  | 0.38464 | 0.28039 |  |  |  | 2014-01-01 |  | 32 | 2014-02-03 | 2014-07-16 18:59 |  | 0 | 2014-07-17 18:59 | 2015-04-29 02:36 |  | 0 | 2015-04-30 02:36 | 2015-07-07 14:01 |  | 0 | 2015-07-08 14:01 | 2015-09-15 01:27 |  | 4 | 2015-09-20 01:27 | 2015-11-27 12:52 |  | 0 | 2015-11-28 12:52 | 2016-02-05 00:18 |  | v002 |  | 0.08871 |  | 32 | 0 | 0 | 0 | 4 | 0 | 36 | 42.5806 |  | 732.0125 | [15 empty] | S
Project-A12 |  | 0.52595 | 1.5134 |  |  |  | 2014-01-01 |  | 33 | 2014-02-04 | 2014-06-07 14:05 |  | 0 | 2014-06-08 14:05 | 2014-08-07 17:11 |  | 0 | 2014-08-08 17:11 | 2014-09-07 09:03 |  | 0 | 2014-09-08 09:03 | 2014-10-08 00:55 |  | 0 | 2014-10-09 00:55 | 2014-11-07 16:46 |  | 0 | 2014-11-08 16:46 | 2014-12-08 08:38 |  | v004 |  | 0.096774 |  | 33 | 0 | 0 | 0 | 0 | 0 | 33 | 47.9032 |  | 307.3597
Project-A13 |  | 0.27067 | 2.0156 |  |  |  | 2014-01-01 |  | 133 | 2014-05-15 | 2015-05-04 16:19 |  | 0 | 2015-05-05 16:19 | 2015-07-29 19:17 |  | 0 | 2015-07-30 19:17 | 2015-10-23 22:14 |  | 0 | 2015-10-24 22:14 | 2016-01-18 01:11 |  | 0 | 2016-01-19 01:11 | 2016-04-13 04:09 |  | 0 | 2016-04-14 04:09 | 2016-07-08 07:06 |  | v007 |  | 0.084367 |  | 133 | 0 | 0 | 0 | 0 | 0 | 133 | 168.3127 |  | 785.2961 | [15 empty] | W
Project-A14 |  | 0.52898 | 1.9788 |  |  |  | 2014-01-01 |  | 183 | 2014-07-04 | 2014-09-15 17:27 |  | 0 | 2014-09-16 17:27 | 2014-10-13 12:17 |  | 0 | 2014-10-14 12:17 | 2014-11-01 04:57 |  | 0 | 2014-11-02 04:57 | 2014-11-19 21:37 |  | 0 | 2014-11-20 21:37 | 2014-12-08 14:17 |  | 0 | 2014-12-09 14:17 | 2014-12-27 06:57 |  | v006 |  | 0.057072 |  | 183 | 0 | 0 | 0 | 0 | 0 | 183 | 156.6625 |  | 176.2899 | [15 empty] | O
Project-A15 |  | 0.93836 | 2.5436 |  |  |  | 2014-01-01 |  | 75 | 2014-03-18 | 2014-06-02 17:31 |  | 0 | 2014-06-03 17:31 | 2014-07-12 15:38 |  | 0 | 2014-07-13 15:38 | 2014-08-01 01:36 |  | 4 | 2014-08-06 01:36 | 2014-08-24 11:34 |  | 3 | 2014-08-28 11:34 | 2014-09-15 21:32 |  | 0 | 2014-09-16 21:32 | 2014-10-05 07:30 |  | v008 |  | 0.10608 |  | 75 | 0 | 0 | 4 | 3 | 0 | 82 | 119.3393 |  | 201.3122 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 52.4 |  |  |  | 0 |  |  |  | 0 |  |  |  | 7.2 |  |  |  | 12 |  |  |  | 0 | [5 empty] | 0.066667 |  | 52.4 | 0 | 0 | 7.2 | 12 | 0 | 71.6 | 58.5775 | Average | 348.6911 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 786 |  |  |  | 0 |  |  |  | 0 |  |  |  | 108 |  |  |  | 180 |  |  |  | 0 | [5 empty] | 1 |  | 786 | 0 | 0 | 108 | 180 | 0 | 1074 | 878.6632 | Total | 5230.3665 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 1
| Days: | 0.82654
E
N
SIT - Violation | Count: | 1 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 0.82654
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2015-01-08 16:20 | 2015-03-20 15:37 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-02-28 13:44 | 2014-03-07 17:36 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-15 01:44 | 2014-02-22 20:23 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-04-26 11:46 | 2014-05-11 16:22 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2015-03-21 20:43 | 2015-06-05 21:38 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-09-20 10:15 | 2014-10-14 08:45 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2014-10-31 09:07 | 2014-12-12 00:22 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0.82654 | 0 | W
Project-A08 | 2014-01-23 19:17 | 2014-01-26 05:23 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-19 05:36 | 2014-07-10 07:05 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-05-15 21:00 | 2014-06-01 14:33 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2015-04-30 02:36 | 2015-07-07 14:01 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-08 17:11 | 2014-09-07 09:03 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2015-07-30 19:17 | 2015-10-23 22:14 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-10-14 12:17 | 2014-11-01 04:57 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-13 15:38 | 2014-08-01 01:36 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-03-23 15:37 | 2015-06-02 14:55 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-08 17:36 | 2014-03-15 21:27 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-23 20:23 | 2014-03-03 15:02 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-12 16:22 | 2014-05-27 20:57 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-06-06 21:38 | 2015-08-21 22:33 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-11-27 08:45 | 2014-12-21 07:14 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-02-10 00:22 | 2015-03-23 15:37 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-27 05:23 | 2014-01-29 15:29 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-11 07:05 | 2014-08-01 08:34 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-02 14:33 | 2014-06-19 08:07 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-07-08 14:01 | 2015-09-15 01:27 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-08 09:03 | 2014-10-08 00:55 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-10-24 22:14 | 2016-01-18 01:11 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-11-02 04:57 | 2014-11-19 21:37 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-06 01:36 | 2014-08-24 11:34 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-07-05 14:55 | 2015-09-14 14:12 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-16 21:27 | 2014-03-24 01:18 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-04 15:02 | 2014-03-12 09:41 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-28 20:57 | 2014-06-13 01:33 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-10-30 22:33 | 2016-01-14 23:28 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-03-02 07:14 | 2015-03-26 05:43 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-03-26 15:37 | 2015-05-07 06:53 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-30 15:29 | 2014-02-02 01:35 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-02 08:34 | 2014-08-23 10:03 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-20 08:07 | 2014-07-07 01:40 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-09-20 01:27 | 2015-11-27 12:52 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-09 00:55 | 2014-11-07 16:46 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2016-01-19 01:11 | 2016-04-13 04:09 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-11-20 21:37 | 2014-12-08 14:17 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-28 11:34 | 2014-09-15 21:32 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-09-15 14:12 | 2015-11-25 13:30 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-25 01:18 | 2014-04-01 05:10 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-13 09:41 | 2014-03-21 04:20 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-14 01:33 | 2014-06-29 06:09 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2016-01-15 23:28 | 2016-04-01 00:22 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-03-27 05:43 | 2015-04-20 04:13 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-05-08 06:53 | 2015-06-18 22:08 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-02-03 01:35 | 2014-02-05 11:41 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-24 10:03 | 2014-09-14 11:32 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-08 01:40 | 2014-07-24 19:13 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-11-28 12:52 | 2016-02-05 00:18 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-08 16:46 | 2014-12-08 08:38 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2016-04-14 04:09 | 2016-07-08 07:06 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-12-09 14:17 | 2014-12-27 06:57 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-16 21:32 | 2014-10-05 07:30 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.97538 | 97.5384 | 97
0.86689 | 86.689 | 86
0.45017 | 45.0166 | 45
0.52171 | 52.1715 | 52
0.79793 | 79.7928 | 79
0.84592 | 84.592 | 84
0.66339 | 66.3394 | 66
0.53838 | 53.8379 | 53
0.23097 | 23.0967 | 23
0.92906 | 92.9063 | 92
0.33658 | 33.6585 | 33
0.066357 | 6.6357 | 6
0.95165 | 95.1651 | 95
0.38942 | 38.9423 | 38
0.19962 | 19.962 | 19
0.61989 | 61.9889 | 61
0.38059 | 38.0593 | 38
0.65974 | 65.9739 | 65
0.18597 | 18.597 | 18
0.064888 | 6.4888 | 6
0.023743 | 2.3743 | 2
0.92946 | 92.9457 | 92
0.54354 | 54.3542 | 54
0.96872 | 96.8723 | 96
0.65863 | 65.8629 | 65
0.37265 | 37.2646 | 37
0.63555 | 63.5547 | 63
0.61664 | 61.6639 | 61
0.21249 | 21.249 | 21
0.92402 | 92.4019 | 92
0.32673 | 32.6733 | 32
0.17677 | 17.6774 | 17
0.99506 | 99.5059 | 99
0.16491 | 16.4908 | 16
0.92588 | 92.5878 | 92
0.26914 | 26.9143 | 26
0.72161 | 72.1613 | 72
0.81334 | 81.3336 | 81
0.32354 | 32.3538 | 32

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1366.8917 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 4 | 1 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH