## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.49466 | 1.5336 |  |  |  | 17 | 17.76 | 34.76 | 34.3671 |  | 4.08 | 74 | 78.08 | 48.2534 |  | 4.08 | 17.76 | 21.84 | 11.5808 |  | 4.08 | 17.76 | 21.84 | 11.5808 |  | 4.08 | 17.76 | 21.84 | 11.5808 |  | 4.08 | 17.76 | 21.84 | 11.5808 |  | 200.2 | 128.9438 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 75.6077 | 106.1575 | 106.1575
Project-A02 |  | v002 |  | 0.49854 | 1.5175 |  |  |  | 15 | 19.2 | 34.2 | 30.0881 |  | 3.6 | 80 | 83.6 | 52.7199 |  | 3.6 | 19.2 | 22.8 | 12.6528 |  | 3.6 | 19.2 | 22.8 | 12.6528 |  | 3.6 | 19.2 | 22.8 | 12.6528 |  | 3.6 | 19.2 | 22.8 | 12.6528 |  | 209 | 133.4191 | 104500 |  | 0.058933 |  | 33 | 176 |  | 66.1939 | 115.9837 | 115.9837 | [12 empty] | E
Project-A03 |  | v003 |  | 0.5411 | 1.4849 |  |  |  | 16 | 6.48 | 22.48 | 29.5694 |  | 3.84 | 27 | 30.84 | 18.183 |  | 3.84 | 6.48 | 10.32 | 7.0967 |  | 3.84 | 6.48 | 10.32 | 7.0967 |  | 3.84 | 6.48 | 10.32 | 7.0967 |  | 3.84 | 6.48 | 10.32 | 7.0967 |  | 94.6 | 76.139 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 65.0527 | 40.0025 | 65.0527 | [12 empty] | N
Project-A04 |  | v004 |  | 0.25 | 1.58 |  |  |  | 35 | 4.32 | 39.32 | 139.999 |  | 8.4 | 18 | 26.4 | 33.5998 |  | 8.4 | 4.32 | 12.72 | 33.5998 |  | 8.4 | 4.32 | 12.72 | 33.5998 |  | 8.4 | 4.32 | 12.72 | 33.5998 |  | 8.4 | 4.32 | 12.72 | 33.5998 |  | 116.6 | 307.9978 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 307.9978 | 25.0636 | 307.9978 | [12 empty] | D
Project-A05 |  | v002 |  | 0.49309 | 1.5275 |  |  |  | 6 | 19.2 | 25.2 | 12.5692 |  | 1.44 | 80 | 81.44 | 52.3717 |  | 1.44 | 19.2 | 20.64 | 12.5692 |  | 1.44 | 19.2 | 20.64 | 12.5692 |  | 1.44 | 19.2 | 20.64 | 12.5692 |  | 1.44 | 19.2 | 20.64 | 12.5692 |  | 189.2 | 115.2178 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 26.7698 | 115.2178 | 115.2178
Project-A06 |  | v003 |  | 0.52296 | 1.5017 |  |  |  | 52 | 10.56 | 62.56 | 99.4339 |  | 12.48 | 44 | 56.48 | 29.3009 |  | 12.48 | 10.56 | 23.04 | 23.8641 |  | 12.48 | 10.56 | 23.04 | 23.8641 |  | 12.48 | 10.56 | 23.04 | 23.8641 |  | 12.48 | 10.56 | 23.04 | 23.8641 |  | 211.2 | 224.1913 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 218.7545 | 64.4619 | 218.7545 | [12 empty] | O
Project-A07 |  | v005 |  | 0.31098 | 1.4983 |  |  |  | 93 | 19.92 | 112.92 | 299.0556 |  | 22.32 | 83 | 105.32 | 71.7734 |  | 22.32 | 19.92 | 42.24 | 71.7734 |  | 22.32 | 19.92 | 42.24 | 71.7734 |  | 22.32 | 19.92 | 42.24 | 71.7734 |  | 22.32 | 19.92 | 42.24 | 71.7734 |  | 387.2 | 657.9224 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 657.9224 | 121.87 | 657.9224 | [12 empty] | F
Project-A08 |  | v006 |  | 0.6272 | 1.5057 |  |  |  | 5 | 2.64 | 7.64 | 7.9719 |  | 1.2 | 11 | 12.2 | 7.3057 |  | 1.2 | 2.64 | 3.84 | 1.9133 |  | 1.2 | 2.64 | 3.84 | 1.9133 |  | 1.2 | 2.64 | 3.84 | 1.9133 |  | 1.2 | 2.64 | 3.84 | 1.9133 |  | 35.2 | 22.9307 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 17.5383 | 16.0726 | 17.5383
Project-A09 |  | v003 |  | 0.66733 | 0.29387 |  |  |  | 49 | 20.64 | 69.64 | 73.427 |  | 11.76 | 86 | 97.76 | 292.6513 |  | 11.76 | 20.64 | 32.4 | 70.2363 |  | 11.76 | 20.64 | 32.4 | 70.2363 |  | 11.76 | 20.64 | 32.4 | 70.2363 |  | 11.76 | 20.64 | 32.4 | 70.2363 |  | 297 | 647.0236 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 161.5394 | 643.8329 | 643.8329 | [12 empty] | T
Project-A10 |  | v001 |  | 0.57487 | 1.5251 |  |  |  | 36 | 20.88 | 56.88 | 62.6228 |  | 8.64 | 87 | 95.64 | 57.0449 |  | 8.64 | 20.88 | 29.52 | 15.0295 |  | 8.64 | 20.88 | 29.52 | 15.0295 |  | 8.64 | 20.88 | 29.52 | 15.0295 |  | 8.64 | 20.88 | 29.52 | 15.0295 |  | 270.6 | 179.7856 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 137.7701 | 125.4989 | 137.7701 | [12 empty] | H
Project-A11 |  | v002 |  | 0.28424 | 1.5125 |  |  |  | 63 | 19.2 | 82.2 | 221.6471 |  | 15.12 | 80 | 95.12 | 53.1953 |  | 15.12 | 19.2 | 34.32 | 53.1953 |  | 15.12 | 19.2 | 34.32 | 53.1953 |  | 15.12 | 19.2 | 34.32 | 53.1953 |  | 15.12 | 19.2 | 34.32 | 53.1953 |  | 314.6 | 487.6237 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 487.6237 | 116.3627 | 487.6237 | [12 empty] | I
Project-A12 |  | v004 |  | 0.48788 | 1.6094 |  |  |  | 65 | 21.84 | 86.84 | 133.2286 |  | 15.6 | 91 | 106.6 | 56.543 |  | 15.6 | 21.84 | 37.44 | 31.9749 |  | 15.6 | 21.84 | 37.44 | 31.9749 |  | 15.6 | 21.84 | 37.44 | 31.9749 |  | 15.6 | 21.84 | 37.44 | 31.9749 |  | 343.2 | 317.671 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 293.1029 | 124.3945 | 293.1029 | [12 empty] | S
Project-A13 |  | v007 |  | 0.56646 | 2.007 |  |  |  | 96 | 9.6 | 105.6 | 169.474 |  | 23.04 | 40 | 63.04 | 40.6738 |  | 23.04 | 9.6 | 32.64 | 40.6738 |  | 23.04 | 9.6 | 32.64 | 40.6738 |  | 23.04 | 9.6 | 32.64 | 40.6738 |  | 23.04 | 9.6 | 32.64 | 40.6738 |  | 299.2 | 372.8428 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 372.8428 | 43.8471 | 372.8428
Project-A14 |  | v006 |  | 0.57928 | 2.0019 |  |  |  | 39 | 12.72 | 51.72 | 67.3253 |  | 9.36 | 53 | 62.36 | 26.4755 |  | 9.36 | 12.72 | 22.08 | 16.1581 |  | 9.36 | 12.72 | 22.08 | 16.1581 |  | 9.36 | 12.72 | 22.08 | 16.1581 |  | 9.36 | 12.72 | 22.08 | 16.1581 |  | 202.4 | 158.4331 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 148.1157 | 58.2461 | 148.1157 | [12 empty] | W
Project-A15 |  | v008 |  | 1.1014 | 2.9012 |  |  |  | 72 | 23.76 | 95.76 | 65.3704 |  | 17.28 | 99 | 116.28 | 34.124 |  | 17.28 | 23.76 | 41.04 | 15.6889 |  | 17.28 | 23.76 | 41.04 | 15.6889 |  | 17.28 | 23.76 | 41.04 | 15.6889 |  | 17.28 | 23.76 | 41.04 | 15.6889 |  | 376.2 | 162.2499 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 143.8148 | 75.0729 | 143.8148 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 96.41 |  | 10.544 | 63.5333 | 74.0773 | 58.281 |  | 10.544 | 15.248 | 25.792 | 27.8671 |  | 10.544 | 15.248 | 25.792 | 27.8671 |  | 10.544 | 15.248 | 25.792 | 27.8671 |  | 10.544 | 15.248 | 25.792 | 27.8671 |  | 236.4267 | 266.1594 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 212.0431 | 119.4723 | 255.4485 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1446.1495 |  | 158.16 | 953 | 1111.16 | 874.2155 |  | 158.16 | 228.72 | 386.88 | 418.0066 |  | 158.16 | 228.72 | 386.88 | 418.0066 |  | 158.16 | 228.72 | 386.88 | 418.0066 |  | 158.16 | 228.72 | 386.88 | 418.0066 |  | 3546.4 | 3992.3916 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3180.6464 | 1792.0846 | 3831.7275 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 728.9224 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 271.6928 |  | <- To shorten average individual project span |  |  |  | <----------> | 255.4485
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 42.745 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 272.4305 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1315.7908 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.49466 | 1.5336 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-05 08:49 |  | 0 | 2014-02-06 08:49 | 2014-03-26 14:54 |  | 0 | 2014-03-27 14:54 | 2014-04-08 04:50 |  | 0 | 2014-04-09 04:50 | 2014-04-20 18:46 |  | 0 | 2014-04-21 18:46 | 2014-05-03 08:43 |  | 0 | 2014-05-04 08:43 | 2014-05-15 22:39 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 133.9438 | 728.9224 | [14 empty] | E
Project-A02 |  | 0.49854 | 1.5175 |  |  |  | 2014-01-01 |  | 14 | 2014-01-16 | 2014-02-15 02:07 |  | 0 | 2014-02-16 02:07 | 2014-04-09 19:24 |  | 0 | 2014-04-10 19:24 | 2014-04-23 11:04 |  | 0 | 2014-04-24 11:04 | 2014-05-07 02:44 |  | 0 | 2014-05-08 02:44 | 2014-05-20 18:23 |  | 0 | 2014-05-21 18:23 | 2014-06-03 10:03 |  | v002 |  | 0.058933 |  | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 12.3759 |  | 138.4191 | [15 empty] | N
Project-A03 |  | 0.5411 | 1.4849 |  |  |  | 2014-01-01 |  | 26 | 2014-01-28 | 2014-02-26 13:40 |  | 0 | 2014-02-27 13:40 | 2014-03-17 18:03 |  | 0 | 2014-03-18 18:03 | 2014-03-25 20:23 |  | 0 | 2014-03-26 20:23 | 2014-04-02 22:42 |  | 0 | 2014-04-03 22:42 | 2014-04-11 01:01 |  | 0 | 2014-04-12 01:01 | 2014-04-19 03:20 |  | v003 |  | 0.026675 |  | 26 | 0 | 0 | 0 | 0 | 0 | 26 | 10.4032 |  | 81.139 | [15 empty] | D
Project-A04 |  | 0.25 | 1.58 |  |  |  | 2014-01-01 |  | 37 | 2014-02-08 | 2014-06-27 23:59 |  | 0 | 2014-06-28 23:59 | 2014-08-01 14:22 |  | 0 | 2014-08-02 14:22 | 2014-09-05 04:46 |  | 0 | 2014-09-06 04:46 | 2014-10-09 19:10 |  | 0 | 2014-10-10 19:10 | 2014-11-13 09:33 |  | 0 | 2014-11-14 09:33 | 2014-12-17 23:57 |  | v004 |  | 0.032878 |  | 37 | 0 | 0 | 0 | 0 | 0 | 37 | 18.2475 |  | 312.9978
Project-A05 |  | 0.49309 | 1.5275 |  |  |  | 2014-01-01 |  | 46 | 2014-02-17 | 2014-03-01 13:40 |  | 0 | 2014-03-02 13:40 | 2014-04-23 22:35 |  | 0 | 2014-04-24 22:35 | 2014-05-07 12:15 |  | 0 | 2014-05-08 12:15 | 2014-05-21 01:54 |  | 0 | 2014-05-22 01:54 | 2014-06-03 15:34 |  | 0 | 2014-06-04 15:34 | 2014-06-17 05:14 |  | v002 |  | 0.05335 |  | 46 | 0 | 0 | 0 | 0 | 0 | 46 | 36.8114 |  | 120.2178 | [15 empty] | O
Project-A06 |  | 0.52296 | 1.5017 |  |  |  | 2014-01-01 |  | 58 | 2014-03-01 | 2014-06-08 10:25 |  | 0 | 2014-06-09 10:25 | 2014-07-08 17:38 |  | 0 | 2014-07-09 17:38 | 2014-08-02 14:22 |  | 7 | 2014-08-10 14:22 | 2014-09-03 11:07 |  | 0 | 2014-09-04 11:07 | 2014-09-28 07:51 |  | 0 | 2014-09-29 07:51 | 2014-10-23 04:35 |  | v003 |  | 0.059553 |  | 58 | 0 | 0 | 7 | 0 | 0 | 65 | 51.8114 |  | 236.1913 | [15 empty] | F
Project-A07 |  | 0.31098 | 1.4983 |  |  |  | 2014-01-01 |  | 66 | 2014-03-09 | 2015-01-02 01:20 |  | 0 | 2015-01-03 01:20 | 2015-03-15 19:54 |  | 0 | 2015-03-16 19:54 | 2015-05-27 14:27 |  | 0 | 2015-05-28 14:27 | 2015-08-08 09:01 |  | 0 | 2015-08-09 09:01 | 2015-10-20 03:35 |  | 0 | 2015-10-21 03:35 | 2015-12-31 22:08 |  | v005 |  | 0.10918 |  | 66 | 0 | 0 | 0 | 0 | 0 | 66 | 108.0893 |  | 662.9224
Project-A08 |  | 0.6272 | 1.5057 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-09 23:20 |  | 0 | 2014-01-10 23:20 | 2014-01-18 06:40 |  | 0 | 2014-01-19 06:40 | 2014-01-21 04:35 |  | 0 | 2014-01-22 04:35 | 2014-01-24 02:30 |  | 0 | 2014-01-25 02:30 | 2014-01-27 00:25 |  | 0 | 2014-01-28 00:25 | 2014-01-29 22:20 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27.9307 | [15 empty] | T
Project-A09 |  | 0.66733 | 0.29387 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-16 10:15 |  | 0 | 2014-03-17 10:15 | 2015-01-04 01:53 |  | 0 | 2015-01-05 01:53 | 2015-03-16 07:33 |  | 0 | 2015-03-17 07:33 | 2015-05-26 13:13 |  | 0 | 2015-05-27 13:13 | 2015-08-05 18:54 |  | 0 | 2015-08-06 18:54 | 2015-10-16 00:34 |  | v003 |  | 0.083747 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 652.0236 | [15 empty] | H
Project-A10 |  | 0.57487 | 1.5251 |  |  |  | 2014-01-01 |  | 25 | 2014-01-27 | 2014-03-30 14:57 |  | 0 | 2014-03-31 14:57 | 2014-05-27 16:02 |  | 0 | 2014-05-28 16:02 | 2014-06-12 16:44 |  | 0 | 2014-06-13 16:44 | 2014-06-28 17:26 |  | 0 | 2014-06-29 17:26 | 2014-07-14 18:09 |  | 0 | 2014-07-15 18:09 | 2014-07-30 18:51 |  | v001 |  | 0.076303 |  | 25 | 0 | 0 | 0 | 0 | 0 | 25 | 28.6135 |  | 184.7856 | [15 empty] | I
Project-A11 |  | 0.28424 | 1.5125 |  |  |  | 2014-01-01 |  | 38 | 2014-02-09 | 2014-09-18 15:32 |  | 0 | 2014-09-19 15:32 | 2014-11-11 20:13 |  | 0 | 2014-11-12 20:13 | 2015-01-05 00:54 |  | 0 | 2015-01-06 00:54 | 2015-02-28 05:36 |  | 0 | 2015-03-01 05:36 | 2015-04-23 10:17 |  | 0 | 2015-04-24 10:17 | 2015-06-16 14:58 |  | v002 |  | 0.08871 |  | 38 | 0 | 0 | 0 | 0 | 0 | 38 | 50.5645 |  | 492.6237 | [15 empty] | S
Project-A12 |  | 0.48788 | 1.6094 |  |  |  | 2014-01-01 |  | 46 | 2014-02-17 | 2014-06-30 05:29 |  | 0 | 2014-07-01 05:29 | 2014-08-26 18:31 |  | 0 | 2014-08-27 18:31 | 2014-09-28 17:55 |  | 0 | 2014-09-29 17:55 | 2014-10-31 17:19 |  | 0 | 2014-11-01 17:19 | 2014-12-03 16:42 |  | 0 | 2014-12-04 16:42 | 2015-01-05 16:06 |  | v004 |  | 0.096774 |  | 46 | 0 | 0 | 0 | 0 | 0 | 46 | 66.7742 |  | 322.671
Project-A13 |  | 0.56646 | 2.007 |  |  |  | 2014-01-01 |  | 62 | 2014-03-05 | 2014-08-21 11:23 |  | 0 | 2014-08-22 11:23 | 2014-10-02 03:33 |  | 0 | 2014-10-03 03:33 | 2014-11-12 19:43 |  | 0 | 2014-11-13 19:43 | 2014-12-24 11:53 |  | 0 | 2014-12-25 11:53 | 2015-02-04 04:03 |  | 0 | 2015-02-05 04:03 | 2015-03-17 20:14 |  | v007 |  | 0.084367 |  | 62 | 0 | 0 | 0 | 0 | 0 | 62 | 78.4615 |  | 377.8428 | [15 empty] | W
Project-A14 |  | 0.57928 | 2.0019 |  |  |  | 2014-01-01 |  | 66 | 2014-03-09 | 2014-05-15 07:48 |  | 0 | 2014-05-16 07:48 | 2014-06-11 19:13 |  | 0 | 2014-06-12 19:13 | 2014-06-28 23:01 |  | 0 | 2014-06-29 23:01 | 2014-07-16 02:48 |  | 0 | 2014-07-17 02:48 | 2014-08-02 06:36 |  | 0 | 2014-08-03 06:36 | 2014-08-19 10:24 |  | v006 |  | 0.057072 |  | 66 | 0 | 0 | 0 | 0 | 0 | 66 | 56.5012 |  | 163.4331 | [15 empty] | O
Project-A15 |  | 1.1014 | 2.9012 |  |  |  | 2014-01-01 |  | 77 | 2014-03-20 | 2014-05-24 08:53 |  | 0 | 2014-05-25 08:53 | 2014-06-28 11:52 |  | 0 | 2014-06-29 11:52 | 2014-07-15 04:24 |  | 0 | 2014-07-16 04:24 | 2014-07-31 20:56 |  | 1 | 2014-08-02 20:56 | 2014-08-18 13:28 |  | 0 | 2014-08-19 13:28 | 2014-09-04 06:00 |  | v008 |  | 0.10608 |  | 77 | 0 | 0 | 0 | 1 | 0 | 78 | 122.5217 |  | 168.2499 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 37.4 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.46667 |  |  |  | 0.066667 |  |  |  | 0 | [5 empty] | 0.066667 |  | 37.4 | 0 | 0 | 0.46667 | 0.066667 | 0 | 37.9333 | 42.745 | Average | 271.6928 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 561 |  |  |  | 0 |  |  |  | 0 |  |  |  | 7 |  |  |  | 1 |  |  |  | 0 | [5 empty] | 1 |  | 561 | 0 | 0 | 7 | 1 | 0 | 569 | 641.1756 | Total | 4075.3916 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 2
| Days: | 5.4486
E
N
SIT - Violation | Count: | 2 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 5.4486
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-27 14:54 | 2014-04-08 04:50 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-10 19:24 | 2014-04-23 11:04 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-03-18 18:03 | 2014-03-25 20:23 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-08-02 14:22 | 2014-09-05 04:46 | v004 | [5 empty] | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 9.3978e-05 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-04-24 22:35 | 2014-05-07 12:15 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-09 17:38 | 2014-08-02 14:22 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5.4485
Project-A07 | 2015-03-16 19:54 | 2015-05-27 14:27 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-19 06:40 | 2014-01-21 04:35 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2015-01-05 01:53 | 2015-03-16 07:33 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-05-28 16:02 | 2014-06-12 16:44 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-11-12 20:13 | 2015-01-05 00:54 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-27 18:31 | 2014-09-28 17:55 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-03 03:33 | 2014-11-12 19:43 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-12 19:13 | 2014-06-28 23:01 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-06-29 11:52 | 2014-07-15 04:24 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-09 04:50 | 2014-04-20 18:46 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-24 11:04 | 2014-05-07 02:44 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-26 20:23 | 2014-04-02 22:42 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-09-06 04:46 | 2014-10-09 19:10 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-08 12:15 | 2014-05-21 01:54 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-10 14:22 | 2014-09-03 11:07 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-05-28 14:27 | 2015-08-08 09:01 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-22 04:35 | 2014-01-24 02:30 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-03-17 07:33 | 2015-05-26 13:13 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-13 16:44 | 2014-06-28 17:26 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-01-06 00:54 | 2015-02-28 05:36 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-29 17:55 | 2014-10-31 17:19 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-11-13 19:43 | 2014-12-24 11:53 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-06-29 23:01 | 2014-07-16 02:48 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-07-16 04:24 | 2014-07-31 20:56 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-21 18:46 | 2014-05-03 08:43 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-08 02:44 | 2014-05-20 18:23 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-04-03 22:42 | 2014-04-11 01:01 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-10-10 19:10 | 2014-11-13 09:33 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-22 01:54 | 2014-06-03 15:34 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-04 11:07 | 2014-09-28 07:51 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-09 09:01 | 2015-10-20 03:35 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-25 02:30 | 2014-01-27 00:25 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-05-27 13:13 | 2015-08-05 18:54 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-29 17:26 | 2014-07-14 18:09 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-03-01 05:36 | 2015-04-23 10:17 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-01 17:19 | 2014-12-03 16:42 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-25 11:53 | 2015-02-04 04:03 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-17 02:48 | 2014-08-02 06:36 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-02 20:56 | 2014-08-18 13:28 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-05-04 08:43 | 2014-05-15 22:39 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-21 18:23 | 2014-06-03 10:03 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-04-12 01:01 | 2014-04-19 03:20 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-11-14 09:33 | 2014-12-17 23:57 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-06-04 15:34 | 2014-06-17 05:14 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-29 07:51 | 2014-10-23 04:35 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-21 03:35 | 2015-12-31 22:08 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-28 00:25 | 2014-01-29 22:20 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-08-06 18:54 | 2015-10-16 00:34 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-15 18:09 | 2014-07-30 18:51 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-04-24 10:17 | 2015-06-16 14:58 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-04 16:42 | 2015-01-05 16:06 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-02-05 04:03 | 2015-03-17 20:14 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-03 06:36 | 2014-08-19 10:24 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-19 13:28 | 2014-09-04 06:00 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.22347 | 22.3465 | 22
0.26667 | 26.6674 | 26
0.25759 | 25.7588 | 25
0.62287 | 62.2875 | 62
0.66698 | 66.6978 | 66
0.50643 | 50.6429 | 50
0.12569 | 12.5692 | 12
0.46034 | 46.0339 | 46
0.9029 | 90.2899 | 90
0.93574 | 93.5744 | 93
0.22737 | 22.7367 | 22
0.72923 | 72.9234 | 72
0.95428 | 95.4284 | 95
0.98159 | 98.159 | 98
0.34078 | 34.0778 | 34
0.31742 | 31.7418 | 31
0.013475 | 1.3475 | 1
0.76586 | 76.5861 | 76
0.050285 | 5.0285 | 5
0.14994 | 14.9941 | 14
0.59203 | 59.2031 | 59
0.76052 | 76.0518 | 76
0.14265 | 14.2649 | 14
0.738 | 73.8 | 73
0.69917 | 69.9174 | 69
0.93794 | 93.794 | 93
0.42617 | 42.6169 | 42
0.88599 | 88.5985 | 88
0.26624 | 26.624 | 26
0.69033 | 69.0335 | 69
0.75567 | 75.5667 | 75
0.23281 | 23.2813 | 23
0.79851 | 79.8512 | 79
0.29756 | 29.756 | 29
0.08218 | 8.218 | 8
0.72471 | 72.4712 | 72
0.37135 | 37.1349 | 37
0.84748 | 84.7481 | 84
0.17502 | 17.502 | 17

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1315.7908 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 6 | 1 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH