## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.52439 | 1.5449 |  |  |  | 17 | 17.76 | 34.76 | 32.4184 |  | 4.08 | 74 | 78.08 | 47.9002 |  | 4.08 | 17.76 | 21.84 | 11.496 |  | 4.08 | 17.76 | 21.84 | 11.496 |  | 4.08 | 17.76 | 21.84 | 11.496 |  | 4.08 | 17.76 | 21.84 | 11.496 |  | 200.2 | 126.3027 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 71.3204 | 105.3803 | 105.3803
Project-A02 |  | v002 |  | 0.51046 | 1.567 |  |  |  | 15 | 19.2 | 34.2 | 29.3854 |  | 3.6 | 80 | 83.6 | 51.0521 |  | 3.6 | 19.2 | 22.8 | 12.2525 |  | 3.6 | 19.2 | 22.8 | 12.2525 |  | 3.6 | 19.2 | 22.8 | 12.2525 |  | 3.6 | 19.2 | 22.8 | 12.2525 |  | 209 | 129.4476 | 104500 |  | 0.058933 |  | 33 | 176 |  | 64.6479 | 112.3147 | 112.3147 | [12 empty] | E
Project-A03 |  | v003 |  | 0.4998 | 1.8979 |  |  |  | 16 | 6.48 | 22.48 | 32.0129 |  | 3.84 | 27 | 30.84 | 14.2263 |  | 3.84 | 6.48 | 10.32 | 7.6831 |  | 3.84 | 6.48 | 10.32 | 7.6831 |  | 3.84 | 6.48 | 10.32 | 7.6831 |  | 3.84 | 6.48 | 10.32 | 7.6831 |  | 94.6 | 76.9715 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 70.4283 | 31.2978 | 70.4283 | [12 empty] | N
Project-A04 |  | v004 |  | 0.48558 | 1.4929 |  |  |  | 35 | 4.32 | 39.32 | 72.0786 |  | 8.4 | 18 | 26.4 | 17.2989 |  | 8.4 | 4.32 | 12.72 | 17.2989 |  | 8.4 | 4.32 | 12.72 | 17.2989 |  | 8.4 | 4.32 | 12.72 | 17.2989 |  | 8.4 | 4.32 | 12.72 | 17.2989 |  | 116.6 | 158.573 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 158.573 | 26.5253 | 158.573 | [12 empty] | D
Project-A05 |  | v002 |  | 0.51455 | 1.4554 |  |  |  | 6 | 19.2 | 25.2 | 13.192 |  | 1.44 | 80 | 81.44 | 54.9667 |  | 1.44 | 19.2 | 20.64 | 13.192 |  | 1.44 | 19.2 | 20.64 | 13.192 |  | 1.44 | 19.2 | 20.64 | 13.192 |  | 1.44 | 19.2 | 20.64 | 13.192 |  | 189.2 | 120.9268 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 25.6535 | 120.9268 | 120.9268
Project-A06 |  | v003 |  | 0.62312 | 1.5178 |  |  |  | 52 | 10.56 | 62.56 | 83.4507 |  | 12.48 | 44 | 56.48 | 28.9885 |  | 12.48 | 10.56 | 23.04 | 20.0282 |  | 12.48 | 10.56 | 23.04 | 20.0282 |  | 12.48 | 10.56 | 23.04 | 20.0282 |  | 12.48 | 10.56 | 23.04 | 20.0282 |  | 211.2 | 192.5519 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 183.5916 | 63.7747 | 183.5916 | [12 empty] | O
Project-A07 |  | v005 |  | 0.44555 | 0.37945 |  |  |  | 93 | 19.92 | 112.92 | 208.7308 |  | 22.32 | 83 | 105.32 | 218.7369 |  | 22.32 | 19.92 | 42.24 | 52.4969 |  | 22.32 | 19.92 | 42.24 | 52.4969 |  | 22.32 | 19.92 | 42.24 | 52.4969 |  | 22.32 | 19.92 | 42.24 | 52.4969 |  | 387.2 | 637.4551 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 459.2078 | 481.2212 | 481.2212 | [12 empty] | F
Project-A08 |  | v006 |  | 0.47258 | 1.9535 |  |  |  | 5 | 2.64 | 7.64 | 10.5802 |  | 1.2 | 11 | 12.2 | 5.631 |  | 1.2 | 2.64 | 3.84 | 2.5393 |  | 1.2 | 2.64 | 3.84 | 2.5393 |  | 1.2 | 2.64 | 3.84 | 2.5393 |  | 1.2 | 2.64 | 3.84 | 2.5393 |  | 35.2 | 26.3683 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 23.2765 | 12.3882 | 23.2765
Project-A09 |  | v003 |  | 0.52992 | 0.30636 |  |  |  | 49 | 20.64 | 69.64 | 92.467 |  | 11.76 | 86 | 97.76 | 280.714 |  | 11.76 | 20.64 | 32.4 | 67.3714 |  | 11.76 | 20.64 | 32.4 | 67.3714 |  | 11.76 | 20.64 | 32.4 | 67.3714 |  | 11.76 | 20.64 | 32.4 | 67.3714 |  | 297 | 642.6665 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 203.4275 | 617.5708 | 617.5708 | [12 empty] | T
Project-A10 |  | v001 |  | 0.52997 | 1.5474 |  |  |  | 36 | 20.88 | 56.88 | 67.9285 |  | 8.64 | 87 | 95.64 | 56.2218 |  | 8.64 | 20.88 | 29.52 | 16.3028 |  | 8.64 | 20.88 | 29.52 | 16.3028 |  | 8.64 | 20.88 | 29.52 | 16.3028 |  | 8.64 | 20.88 | 29.52 | 16.3028 |  | 270.6 | 189.3617 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 149.4427 | 123.6879 | 149.4427 | [12 empty] | H
Project-A11 |  | v002 |  | 0.50201 | 1.6712 |  |  |  | 63 | 19.2 | 82.2 | 125.4959 |  | 15.12 | 80 | 95.12 | 47.8684 |  | 15.12 | 19.2 | 34.32 | 30.119 |  | 15.12 | 19.2 | 34.32 | 30.119 |  | 15.12 | 19.2 | 34.32 | 30.119 |  | 15.12 | 19.2 | 34.32 | 30.119 |  | 314.6 | 293.8403 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 276.091 | 105.3104 | 276.091 | [12 empty] | I
Project-A12 |  | v004 |  | 0.49659 | 1.5108 |  |  |  | 65 | 21.84 | 86.84 | 130.8935 |  | 15.6 | 91 | 106.6 | 60.2325 |  | 15.6 | 21.84 | 37.44 | 31.4144 |  | 15.6 | 21.84 | 37.44 | 31.4144 |  | 15.6 | 21.84 | 37.44 | 31.4144 |  | 15.6 | 21.84 | 37.44 | 31.4144 |  | 343.2 | 316.7836 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 287.9656 | 132.5114 | 287.9656 | [12 empty] | S
Project-A13 |  | v007 |  | 0.47512 | 1.9853 |  |  |  | 96 | 9.6 | 105.6 | 202.0523 |  | 23.04 | 40 | 63.04 | 48.4926 |  | 23.04 | 9.6 | 32.64 | 48.4926 |  | 23.04 | 9.6 | 32.64 | 48.4926 |  | 23.04 | 9.6 | 32.64 | 48.4926 |  | 23.04 | 9.6 | 32.64 | 48.4926 |  | 299.2 | 444.5151 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 444.5151 | 44.3259 | 444.5151
Project-A14 |  | v006 |  | 0.47145 | 2.2389 |  |  |  | 39 | 12.72 | 51.72 | 82.723 |  | 9.36 | 53 | 62.36 | 23.6723 |  | 9.36 | 12.72 | 22.08 | 19.8535 |  | 9.36 | 12.72 | 22.08 | 19.8535 |  | 9.36 | 12.72 | 22.08 | 19.8535 |  | 9.36 | 12.72 | 22.08 | 19.8535 |  | 202.4 | 185.8094 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 181.9906 | 52.0791 | 181.9906 | [12 empty] | W
Project-A15 |  | v008 |  | 0.91891 | 2.0602 |  |  |  | 72 | 23.76 | 95.76 | 78.3539 |  | 17.28 | 99 | 116.28 | 48.0526 |  | 17.28 | 23.76 | 41.04 | 18.8049 |  | 17.28 | 23.76 | 41.04 | 18.8049 |  | 17.28 | 23.76 | 41.04 | 18.8049 |  | 17.28 | 23.76 | 41.04 | 18.8049 |  | 376.2 | 201.6263 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 172.3786 | 105.7157 | 172.3786 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.5419 |  |  |  | 43.9333 | 15.248 | 59.1813 | 84.1175 |  | 10.544 | 63.5333 | 74.0773 | 66.937 |  | 10.544 | 15.248 | 25.792 | 24.623 |  | 10.544 | 15.248 | 25.792 | 24.623 |  | 10.544 | 15.248 | 25.792 | 24.623 |  | 10.544 | 15.248 | 25.792 | 24.623 |  | 236.4267 | 249.5467 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 184.834 | 142.3354 | 225.7111 | [12 empty] | S
|  | Total |  | 8 | 23.1292 |  |  |  | 659 | 228.72 | 887.72 | 1261.7632 |  | 158.16 | 953 | 1111.16 | 1004.0547 |  | 158.16 | 228.72 | 386.88 | 369.3455 |  | 158.16 | 228.72 | 386.88 | 369.3455 |  | 158.16 | 228.72 | 386.88 | 369.3455 |  | 158.16 | 228.72 | 386.88 | 369.3455 |  | 3546.4 | 3743.1998 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2772.5101 | 2135.0304 | 3385.6668 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 712.4551 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 267.7467 |  | <- To shorten average individual project span |  |  |  | <----------> | 225.7111
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 69.2382 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 0 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1049.44 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | TRUE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.52439 | 1.5449 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-03 10:02 |  | 0 | 2014-02-04 10:02 | 2014-03-24 07:39 |  | 0 | 2014-03-25 07:39 | 2014-04-05 19:33 |  | 0 | 2014-04-06 19:33 | 2014-04-18 07:27 |  | 0 | 2014-04-19 07:27 | 2014-04-30 19:22 |  | 0 | 2014-05-01 19:22 | 2014-05-13 07:16 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 131.3027 | 712.4551 | [14 empty] | E
Project-A02 |  | 0.51046 | 1.567 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-02-12 09:15 |  | 0 | 2014-02-13 09:15 | 2014-04-05 10:30 |  | 0 | 2014-04-06 10:30 | 2014-04-18 16:34 |  | 0 | 2014-04-19 16:34 | 2014-05-01 22:37 |  | 0 | 2014-05-02 22:37 | 2014-05-15 04:41 |  | 0 | 2014-05-16 04:41 | 2014-05-28 10:45 |  | v002 |  | 0.058933 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 10.6079 |  | 134.4476 | [15 empty] | N
Project-A03 |  | 0.4998 | 1.8979 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-03 00:19 |  | 0 | 2014-02-04 00:19 | 2014-02-18 05:44 |  | 0 | 2014-02-19 05:44 | 2014-02-26 22:08 |  | 0 | 2014-02-27 22:08 | 2014-03-07 14:32 |  | 0 | 2014-03-08 14:32 | 2014-03-16 06:55 |  | 0 | 2014-03-17 06:55 | 2014-03-24 23:19 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 81.9715 | [15 empty] | D
Project-A04 |  | 0.48558 | 1.4929 |  |  |  | 2014-01-01 |  | 30 | 2014-02-01 | 2014-04-14 01:53 |  | 0 | 2014-04-15 01:53 | 2014-05-02 09:04 |  | 0 | 2014-05-03 09:04 | 2014-05-20 16:14 |  | 0 | 2014-05-21 16:14 | 2014-06-07 23:24 |  | 0 | 2014-06-08 23:24 | 2014-06-26 06:35 |  | 0 | 2014-06-27 06:35 | 2014-07-14 13:45 |  | v004 |  | 0.032878 |  | 30 | 0 | 0 | 0 | 0 | 0 | 30 | 14.7953 |  | 163.573
Project-A05 |  | 0.51455 | 1.4554 |  |  |  | 2014-01-01 |  | 38 | 2014-02-09 | 2014-02-22 04:37 |  | 0 | 2014-02-23 04:37 | 2014-04-19 03:49 |  | 0 | 2014-04-20 03:49 | 2014-05-03 08:25 |  | 0 | 2014-05-04 08:25 | 2014-05-17 13:02 |  | 39 | 2014-06-26 13:02 | 2014-07-09 17:38 |  | 34 | 2014-08-13 17:38 | 2014-08-26 22:15 |  | v002 |  | 0.05335 |  | 38 | 0 | 0 | 0 | 39 | 34 | 111 | 30.4094 |  | 198.9268 | [15 empty] | O
Project-A06 |  | 0.62312 | 1.5178 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-03-26 10:49 |  | 0 | 2015-03-27 10:49 | 2015-04-25 10:32 |  | 0 | 2015-04-26 10:32 | 2015-05-16 11:13 |  | 0 | 2015-05-17 11:13 | 2015-06-06 11:54 |  | 0 | 2015-06-07 11:54 | 2015-06-27 12:34 |  | 0 | 2015-06-28 12:34 | 2015-07-18 13:15 |  | v003 |  | 0.059553 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 326.0546 |  | 197.5519 | [15 empty] | F
Project-A07 |  | 0.44555 | 0.37945 |  |  |  | 2014-01-01 |  | 70 | 2014-03-13 | 2014-10-07 17:32 |  | 0 | 2014-10-08 17:32 | 2015-05-15 11:13 |  | 0 | 2015-05-16 11:13 | 2015-07-07 23:09 |  | 0 | 2015-07-08 23:09 | 2015-08-30 11:04 |  | 0 | 2015-08-31 11:04 | 2015-10-22 23:00 |  | 0 | 2015-10-23 23:00 | 2015-12-15 10:55 |  | v005 |  | 0.10918 |  | 70 | 0 | 0 | 0 | 0 | 0 | 70 | 114.6402 |  | 642.4551
Project-A08 |  | 0.47258 | 1.9535 |  |  |  | 2014-01-01 |  | 354 | 2014-12-22 | 2015-01-01 13:56 |  | 0 | 2015-01-02 13:56 | 2015-01-08 05:04 |  | 0 | 2015-01-09 05:04 | 2015-01-11 18:01 |  | 0 | 2015-01-12 18:01 | 2015-01-15 06:57 |  | 0 | 2015-01-16 06:57 | 2015-01-18 19:54 |  | 0 | 2015-01-19 19:54 | 2015-01-22 08:50 |  | v006 |  | 0.0099256 |  | 354 | 0 | 0 | 0 | 0 | 0 | 354 | 52.7047 |  | 31.3683 | [15 empty] | T
Project-A09 |  | 0.52992 | 0.30636 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-04-04 11:13 |  | 0 | 2014-04-05 11:13 | 2015-01-11 04:21 |  | 0 | 2015-01-12 04:21 | 2015-03-20 13:15 |  | 0 | 2015-03-21 13:15 | 2015-05-27 22:10 |  | 0 | 2015-05-28 22:10 | 2015-08-04 07:05 |  | 0 | 2015-08-05 07:05 | 2015-10-11 16:00 |  | v003 |  | 0.083747 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 647.6665 | [15 empty] | H
Project-A10 |  | 0.52997 | 1.5474 |  |  |  | 2014-01-01 |  | 25 | 2014-01-27 | 2014-04-04 22:17 |  | 0 | 2014-04-05 22:17 | 2014-06-01 03:36 |  | 0 | 2014-06-02 03:36 | 2014-06-18 10:53 |  | 0 | 2014-06-19 10:53 | 2014-07-05 18:09 |  | 4 | 2014-07-10 18:09 | 2014-07-27 01:25 |  | 0 | 2014-07-28 01:25 | 2014-08-13 08:41 |  | v001 |  | 0.076303 |  | 25 | 0 | 0 | 0 | 4 | 0 | 29 | 28.6135 |  | 198.3617 | [15 empty] | I
Project-A11 |  | 0.50201 | 1.6712 |  |  |  | 2014-01-01 |  | 68 | 2014-03-11 | 2014-07-14 11:54 |  | 0 | 2014-07-15 11:54 | 2014-09-01 08:45 |  | 0 | 2014-09-02 08:45 | 2014-10-02 11:36 |  | 0 | 2014-10-03 11:36 | 2014-11-02 14:27 |  | 0 | 2014-11-03 14:27 | 2014-12-03 17:19 |  | 0 | 2014-12-04 17:19 | 2015-01-03 20:10 |  | v002 |  | 0.08871 |  | 68 | 0 | 0 | 0 | 0 | 0 | 68 | 90.4839 |  | 298.8403 | [15 empty] | S
Project-A12 |  | 0.49659 | 1.5108 |  |  |  | 2014-01-01 |  | 85 | 2014-03-28 | 2014-08-05 21:27 |  | 0 | 2014-08-06 21:27 | 2014-10-06 03:01 |  | 0 | 2014-10-07 03:01 | 2014-11-07 12:58 |  | 4 | 2014-11-12 12:58 | 2014-12-13 22:55 |  | 0 | 2014-12-14 22:55 | 2015-01-15 08:52 |  | 6 | 2015-01-22 08:52 | 2015-02-22 18:48 |  | v004 |  | 0.096774 |  | 85 | 0 | 0 | 4 | 0 | 6 | 95 | 123.3871 |  | 331.7836
Project-A13 |  | 0.47512 | 1.9853 |  |  |  | 2014-01-01 |  | 57 | 2014-02-28 | 2014-09-18 01:15 |  | 0 | 2014-09-19 01:15 | 2014-11-06 13:05 |  | 0 | 2014-11-07 13:05 | 2014-12-26 00:54 |  | 36 | 2015-02-01 00:54 | 2015-03-21 12:43 |  | 0 | 2015-03-22 12:43 | 2015-05-10 00:32 |  | 0 | 2015-05-11 00:32 | 2015-06-28 12:22 |  | v007 |  | 0.084367 |  | 57 | 0 | 0 | 36 | 0 | 0 | 93 | 72.134 |  | 485.5151 | [15 empty] | W
Project-A14 |  | 0.47145 | 2.2389 |  |  |  | 2014-01-01 |  | 61 | 2014-03-04 | 2014-05-25 17:21 |  | 0 | 2014-05-26 17:21 | 2014-06-19 09:29 |  | 0 | 2014-06-20 09:29 | 2014-07-10 05:58 |  | 0 | 2014-07-11 05:58 | 2014-07-31 02:27 |  | 0 | 2014-08-01 02:27 | 2014-08-20 22:57 |  | 38 | 2014-09-28 22:57 | 2014-10-18 19:26 |  | v006 |  | 0.057072 |  | 61 | 0 | 0 | 0 | 0 | 38 | 99 | 52.2208 |  | 228.8094 | [15 empty] | O
Project-A15 |  | 0.91891 | 2.0602 |  |  |  | 2014-01-01 |  | 77 | 2014-03-20 | 2014-06-06 08:30 |  | 0 | 2014-06-07 08:30 | 2014-07-25 09:45 |  | 0 | 2014-07-26 09:45 | 2014-08-14 05:04 |  | 0 | 2014-08-15 05:04 | 2014-09-03 00:24 |  | 37 | 2014-10-11 00:24 | 2014-10-29 19:43 |  | 0 | 2014-10-30 19:43 | 2014-11-18 15:02 |  | v008 |  | 0.10608 |  | 77 | 0 | 0 | 0 | 37 | 0 | 114 | 122.5217 |  | 243.6263 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.5419 | [5 empty] | 82.8 |  |  |  | 0 |  |  |  | 0 |  |  |  | 2.6667 |  |  |  | 5.3333 |  |  |  | 5.2 | [5 empty] | 0.066667 |  | 82.8 | 0 | 0 | 2.6667 | 5.3333 | 5.2 | 96 | 69.2382 | Average | 267.7467 | [15 empty] | H
Total |  | 8 | 23.1292 | [5 empty] | 1242 |  |  |  | 0 |  |  |  | 0 |  |  |  | 40 |  |  |  | 80 |  |  |  | 78 | [5 empty] | 1 |  | 1242 | 0 | 0 | 40 | 80 | 78 | 1440 | 1038.5732 | Total | 4016.1998 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 0
| Days: | 0
E
N
SIT - Violation | Count: | 0 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 0
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-25 07:39 | 2014-04-05 19:33 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-06 10:30 | 2014-04-18 16:34 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-19 05:44 | 2014-02-26 22:08 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-03 09:04 | 2014-05-20 16:14 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-04-20 03:49 | 2014-05-03 08:25 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2015-04-26 10:32 | 2015-05-16 11:13 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-05-16 11:13 | 2015-07-07 23:09 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2015-01-09 05:04 | 2015-01-11 18:01 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2015-01-12 04:21 | 2015-03-20 13:15 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-06-02 03:36 | 2014-06-18 10:53 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-09-02 08:45 | 2014-10-02 11:36 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-10-07 03:01 | 2014-11-07 12:58 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-11-07 13:05 | 2014-12-26 00:54 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-20 09:29 | 2014-07-10 05:58 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-26 09:45 | 2014-08-14 05:04 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-06 19:33 | 2014-04-18 07:27 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-19 16:34 | 2014-05-01 22:37 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-27 22:08 | 2014-03-07 14:32 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-21 16:14 | 2014-06-07 23:24 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-04 08:25 | 2014-05-17 13:02 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-05-17 11:13 | 2015-06-06 11:54 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-07-08 23:09 | 2015-08-30 11:04 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2015-01-12 18:01 | 2015-01-15 06:57 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-03-21 13:15 | 2015-05-27 22:10 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-19 10:53 | 2014-07-05 18:09 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-03 11:36 | 2014-11-02 14:27 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-12 12:58 | 2014-12-13 22:55 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-02-01 00:54 | 2015-03-21 12:43 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-11 05:58 | 2014-07-31 02:27 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-15 05:04 | 2014-09-03 00:24 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-19 07:27 | 2014-04-30 19:22 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-02 22:37 | 2014-05-15 04:41 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-08 14:32 | 2014-03-16 06:55 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-08 23:24 | 2014-06-26 06:35 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-06-26 13:02 | 2014-07-09 17:38 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-06-07 11:54 | 2015-06-27 12:34 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-31 11:04 | 2015-10-22 23:00 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2015-01-16 06:57 | 2015-01-18 19:54 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-05-28 22:10 | 2015-08-04 07:05 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-10 18:09 | 2014-07-27 01:25 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-11-03 14:27 | 2014-12-03 17:19 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-14 22:55 | 2015-01-15 08:52 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-22 12:43 | 2015-05-10 00:32 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-01 02:27 | 2014-08-20 22:57 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-10-11 00:24 | 2014-10-29 19:43 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-05-01 19:22 | 2014-05-13 07:16 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-16 04:41 | 2014-05-28 10:45 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-17 06:55 | 2014-03-24 23:19 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-27 06:35 | 2014-07-14 13:45 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-08-13 17:38 | 2014-08-26 22:15 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-06-28 12:34 | 2015-07-18 13:15 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-23 23:00 | 2015-12-15 10:55 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2015-01-19 19:54 | 2015-01-22 08:50 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-08-05 07:05 | 2015-10-11 16:00 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-28 01:25 | 2014-08-13 08:41 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-12-04 17:19 | 2015-01-03 20:10 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2015-01-22 08:52 | 2015-02-22 18:48 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-05-11 00:32 | 2015-06-28 12:22 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-09-28 22:57 | 2014-10-18 19:26 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-10-30 19:43 | 2014-11-18 15:02 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.13071 | 13.0715 | 13
0.96254 | 96.2535 | 96
0.73235 | 73.2346 | 73
0.30095 | 30.0946 | 30
0.45609 | 45.6085 | 45
0.46515 | 46.5149 | 46
0.83251 | 83.2512 | 83
0.48813 | 48.8128 | 48
0.92417 | 92.4165 | 92
0.24369 | 24.3695 | 24
0.78613 | 78.6131 | 78
0.52332 | 52.3321 | 52
0.76138 | 76.1382 | 76
0.24782 | 24.7817 | 24
0.31504 | 31.504 | 31
0.83269 | 83.2689 | 83
0.33005 | 33.0053 | 33
0.21658 | 21.6584 | 21
0.76634 | 76.6341 | 76
0.52058 | 52.0583 | 52
0.073021 | 7.3021 | 7
0.41712 | 41.7118 | 41
0.65766 | 65.7664 | 65
0.60882 | 60.8819 | 60
0.50914 | 50.9137 | 50
0.02087 | 2.087 | 2
0.42373 | 42.3734 | 42
0.29405 | 29.4053 | 29
0.37732 | 37.7323 | 37
0.9273 | 92.7295 | 92
0.52038 | 52.0383 | 52
0.55725 | 55.7255 | 55
0.16422 | 16.4222 | 16
0.6474 | 64.7405 | 64
0.081927 | 8.1927 | 8
0.92578 | 92.5785 | 92
0.35813 | 35.8126 | 35
0.9397 | 93.9698 | 93
0.5311 | 53.1096 | 53

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1049.44 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 8 | 1 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 23.1292 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH