## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.70256 | 1.5389 |  |  |  | 17 | 17.76 | 34.76 | 24.1972 |  | 4.08 | 74 | 78.08 | 48.0866 |  | 4.08 | 17.76 | 21.84 | 11.5408 |  | 4.08 | 17.76 | 21.84 | 11.5408 |  | 4.08 | 17.76 | 21.84 | 11.5408 |  | 4.08 | 17.76 | 21.84 | 11.5408 |  | 200.2 | 118.4469 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 53.2339 | 105.7905 | 105.7905
Project-A02 |  | v002 |  | 0.58341 | 1.5267 |  |  |  | 15 | 19.2 | 34.2 | 25.7111 |  | 3.6 | 80 | 83.6 | 52.3995 |  | 3.6 | 19.2 | 22.8 | 12.5759 |  | 3.6 | 19.2 | 22.8 | 12.5759 |  | 3.6 | 19.2 | 22.8 | 12.5759 |  | 3.6 | 19.2 | 22.8 | 12.5759 |  | 209 | 128.4142 | 104500 |  | 0.058933 |  | 33 | 176 |  | 56.5644 | 115.279 | 115.279 | [12 empty] | E
Project-A03 |  | v003 |  | 0.63104 | 1.4889 |  |  |  | 16 | 6.48 | 22.48 | 25.3549 |  | 3.84 | 27 | 30.84 | 18.1336 |  | 3.84 | 6.48 | 10.32 | 6.0852 |  | 3.84 | 6.48 | 10.32 | 6.0852 |  | 3.84 | 6.48 | 10.32 | 6.0852 |  | 3.84 | 6.48 | 10.32 | 6.0852 |  | 94.6 | 67.8292 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 55.7807 | 39.894 | 55.7807 | [12 empty] | N
Project-A04 |  | v004 |  | 0.25548 | 1.4771 |  |  |  | 35 | 4.32 | 39.32 | 136.9974 |  | 8.4 | 18 | 26.4 | 32.8794 |  | 8.4 | 4.32 | 12.72 | 32.8794 |  | 8.4 | 4.32 | 12.72 | 32.8794 |  | 8.4 | 4.32 | 12.72 | 32.8794 |  | 8.4 | 4.32 | 12.72 | 32.8794 |  | 116.6 | 301.3942 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 301.3942 | 26.8085 | 301.3942 | [12 empty] | D
Project-A05 |  | v002 |  | 0.54618 | 1.5325 |  |  |  | 6 | 19.2 | 25.2 | 12.5285 |  | 1.44 | 80 | 81.44 | 52.2023 |  | 1.44 | 19.2 | 20.64 | 12.5285 |  | 1.44 | 19.2 | 20.64 | 12.5285 |  | 1.44 | 19.2 | 20.64 | 12.5285 |  | 1.44 | 19.2 | 20.64 | 12.5285 |  | 189.2 | 114.845 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 24.1677 | 114.845 | 114.845
Project-A06 |  | v003 |  | 0.56976 | 1.4937 |  |  |  | 52 | 10.56 | 62.56 | 91.266 |  | 12.48 | 44 | 56.48 | 29.4576 |  | 12.48 | 10.56 | 23.04 | 21.9038 |  | 12.48 | 10.56 | 23.04 | 21.9038 |  | 12.48 | 10.56 | 23.04 | 21.9038 |  | 12.48 | 10.56 | 23.04 | 21.9038 |  | 211.2 | 208.3389 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 200.7852 | 64.8068 | 200.7852 | [12 empty] | O
Project-A07 |  | v005 |  | 0.64736 | 1.5124 |  |  |  | 93 | 19.92 | 112.92 | 143.661 |  | 22.32 | 83 | 105.32 | 54.881 |  | 22.32 | 19.92 | 42.24 | 34.4786 |  | 22.32 | 19.92 | 42.24 | 34.4786 |  | 22.32 | 19.92 | 42.24 | 34.4786 |  | 22.32 | 19.92 | 42.24 | 34.4786 |  | 387.2 | 336.4565 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 316.0541 | 120.7383 | 316.0541 | [12 empty] | F
Project-A08 |  | v006 |  | 0.52515 | 1.5158 |  |  |  | 5 | 2.64 | 7.64 | 9.521 |  | 1.2 | 11 | 12.2 | 7.2568 |  | 1.2 | 2.64 | 3.84 | 2.285 |  | 1.2 | 2.64 | 3.84 | 2.285 |  | 1.2 | 2.64 | 3.84 | 2.285 |  | 1.2 | 2.64 | 3.84 | 2.285 |  | 35.2 | 25.918 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 20.9462 | 15.9649 | 20.9462
Project-A09 |  | v003 |  | 0.53241 | 1.4888 |  |  |  | 49 | 20.64 | 69.64 | 92.0345 |  | 11.76 | 86 | 97.76 | 57.7629 |  | 11.76 | 20.64 | 32.4 | 22.0883 |  | 11.76 | 20.64 | 32.4 | 22.0883 |  | 11.76 | 20.64 | 32.4 | 22.0883 |  | 11.76 | 20.64 | 32.4 | 22.0883 |  | 297 | 238.1505 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 202.476 | 127.0783 | 202.476 | [12 empty] | T
Project-A10 |  | v001 |  | 0.51778 | 1.4951 |  |  |  | 36 | 20.88 | 56.88 | 69.5271 |  | 8.64 | 87 | 95.64 | 58.1905 |  | 8.64 | 20.88 | 29.52 | 16.6865 |  | 8.64 | 20.88 | 29.52 | 16.6865 |  | 8.64 | 20.88 | 29.52 | 16.6865 |  | 8.64 | 20.88 | 29.52 | 16.6865 |  | 270.6 | 194.4636 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 152.9596 | 128.0191 | 152.9596 | [12 empty] | H
Project-A11 |  | v002 |  | 0.30064 | 1.4634 |  |  |  | 63 | 19.2 | 82.2 | 209.5533 |  | 15.12 | 80 | 95.12 | 54.6662 |  | 15.12 | 19.2 | 34.32 | 50.2928 |  | 15.12 | 19.2 | 34.32 | 50.2928 |  | 15.12 | 19.2 | 34.32 | 50.2928 |  | 15.12 | 19.2 | 34.32 | 50.2928 |  | 314.6 | 465.3907 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 461.0174 | 120.2656 | 461.0174 | [12 empty] | I
Project-A12 |  | v004 |  | 0.6652 | 1.4909 |  |  |  | 65 | 21.84 | 86.84 | 97.7154 |  | 15.6 | 91 | 106.6 | 61.0352 |  | 15.6 | 21.84 | 37.44 | 23.4517 |  | 15.6 | 21.84 | 37.44 | 23.4517 |  | 15.6 | 21.84 | 37.44 | 23.4517 |  | 15.6 | 21.84 | 37.44 | 23.4517 |  | 343.2 | 252.5573 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 214.9738 | 134.2775 | 214.9738 | [12 empty] | S
Project-A13 |  | v007 |  | 0.32102 | 1.9984 |  |  |  | 96 | 9.6 | 105.6 | 299.0423 |  | 23.04 | 40 | 63.04 | 71.7702 |  | 23.04 | 9.6 | 32.64 | 71.7702 |  | 23.04 | 9.6 | 32.64 | 71.7702 |  | 23.04 | 9.6 | 32.64 | 71.7702 |  | 23.04 | 9.6 | 32.64 | 71.7702 |  | 299.2 | 657.8931 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 657.8931 | 44.0363 | 657.8931
Project-A14 |  | v006 |  | 0.89109 | 2.0117 |  |  |  | 39 | 12.72 | 51.72 | 43.7666 |  | 9.36 | 53 | 62.36 | 26.3455 |  | 9.36 | 12.72 | 22.08 | 10.504 |  | 9.36 | 12.72 | 22.08 | 10.504 |  | 9.36 | 12.72 | 22.08 | 10.504 |  | 9.36 | 12.72 | 22.08 | 10.504 |  | 202.4 | 112.1281 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 96.2866 | 57.96 | 96.2866 | [12 empty] | W
Project-A15 |  | v008 |  | 0.31091 | 1.9655 |  |  |  | 72 | 23.76 | 95.76 | 231.5784 |  | 17.28 | 99 | 116.28 | 55.5788 |  | 17.28 | 23.76 | 41.04 | 55.5788 |  | 17.28 | 23.76 | 41.04 | 55.5788 |  | 17.28 | 23.76 | 41.04 | 55.5788 |  | 17.28 | 23.76 | 41.04 | 55.5788 |  | 376.2 | 509.4725 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 509.4725 | 110.8089 | 509.4725 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 100.8303 |  | 10.544 | 63.5333 | 74.0773 | 45.3764 |  | 10.544 | 15.248 | 25.792 | 25.6433 |  | 10.544 | 15.248 | 25.792 | 25.6433 |  | 10.544 | 15.248 | 25.792 | 25.6433 |  | 10.544 | 15.248 | 25.792 | 25.6433 |  | 236.4267 | 248.7799 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 221.6004 | 88.4382 | 235.0636 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1512.4548 |  | 158.16 | 953 | 1111.16 | 680.646 |  | 158.16 | 228.72 | 386.88 | 384.6495 |  | 158.16 | 228.72 | 386.88 | 384.6495 |  | 158.16 | 228.72 | 386.88 | 384.6495 |  | 158.16 | 228.72 | 386.88 | 384.6495 |  | 3546.4 | 3731.6989 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3324.0054 | 1326.5727 | 3525.9539 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 725.8931 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 254.9799 |  | <- To shorten average individual project span |  |  |  | <----------> | 235.0636
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 46.6873 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 0 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1027.5604 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | TRUE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.70256 | 1.5389 |  |  |  | 2014-01-01 |  | 6 | 2014-01-08 | 2014-02-01 04:44 |  | 0 | 2014-02-02 04:44 | 2014-03-22 06:49 |  | 0 | 2014-03-23 06:49 | 2014-04-03 19:47 |  | 0 | 2014-04-04 19:47 | 2014-04-16 08:46 |  | 0 | 2014-04-17 08:46 | 2014-04-28 21:45 |  | 0 | 2014-04-29 21:45 | 2014-05-11 10:44 |  | v001 |  | 0.056452 |  | 6 | 0 | 0 | 0 | 0 | 0 | 6 | 5.0806 |  | 123.4469 | 725.8931 | [14 empty] | E
Project-A02 |  | 0.58341 | 1.5267 |  |  |  | 2014-01-01 |  | 19 | 2014-01-21 | 2014-02-15 17:04 |  | 0 | 2014-02-16 17:04 | 2014-04-10 02:39 |  | 0 | 2014-04-11 02:39 | 2014-04-23 16:29 |  | 0 | 2014-04-24 16:29 | 2014-05-07 06:18 |  | 0 | 2014-05-08 06:18 | 2014-05-20 20:07 |  | 0 | 2014-05-21 20:07 | 2014-06-03 09:56 |  | v002 |  | 0.058933 |  | 19 | 0 | 0 | 0 | 0 | 0 | 19 | 16.7959 |  | 133.4142 | [15 empty] | N
Project-A03 |  | 0.63104 | 1.4889 |  |  |  | 2014-01-01 |  | 24 | 2014-01-26 | 2014-02-20 08:31 |  | 0 | 2014-02-21 08:31 | 2014-03-11 11:43 |  | 0 | 2014-03-12 11:43 | 2014-03-18 13:46 |  | 0 | 2014-03-19 13:46 | 2014-03-25 15:49 |  | 0 | 2014-03-26 15:49 | 2014-04-01 17:51 |  | 0 | 2014-04-02 17:51 | 2014-04-08 19:54 |  | v003 |  | 0.026675 |  | 24 | 0 | 0 | 0 | 0 | 0 | 24 | 9.603 |  | 72.8292 | [15 empty] | D
Project-A04 |  | 0.25548 | 1.4771 |  |  |  | 2014-01-01 |  | 38 | 2014-02-09 | 2014-06-25 23:56 |  | 0 | 2014-06-26 23:56 | 2014-07-29 21:03 |  | 0 | 2014-07-30 21:03 | 2014-09-01 18:09 |  | 0 | 2014-09-02 18:09 | 2014-10-05 15:15 |  | 0 | 2014-10-06 15:15 | 2014-11-08 12:21 |  | 0 | 2014-11-09 12:21 | 2014-12-12 09:28 |  | v004 |  | 0.032878 |  | 38 | 0 | 0 | 0 | 0 | 0 | 38 | 18.7407 |  | 306.3942
Project-A05 |  | 0.54618 | 1.5325 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-02-28 12:41 |  | 0 | 2014-03-01 12:41 | 2014-04-22 17:32 |  | 0 | 2014-04-23 17:32 | 2014-05-06 06:14 |  | 0 | 2014-05-07 06:14 | 2014-05-19 18:55 |  | 0 | 2014-05-20 18:55 | 2014-06-02 07:36 |  | 0 | 2014-06-03 07:36 | 2014-06-15 20:17 |  | v002 |  | 0.05335 |  | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 36.0112 |  | 119.845 | [15 empty] | O
Project-A06 |  | 0.56976 | 1.4937 |  |  |  | 2014-01-01 |  | 57 | 2014-02-28 | 2014-05-30 06:23 |  | 0 | 2014-05-31 06:23 | 2014-06-29 17:22 |  | 0 | 2014-06-30 17:22 | 2014-07-22 15:04 |  | 0 | 2014-07-23 15:04 | 2014-08-14 12:45 |  | 0 | 2014-08-15 12:45 | 2014-09-06 10:27 |  | 0 | 2014-09-07 10:27 | 2014-09-29 08:08 |  | v003 |  | 0.059553 |  | 57 | 0 | 0 | 0 | 0 | 0 | 57 | 50.9181 |  | 213.3389 | [15 empty] | F
Project-A07 |  | 0.64736 | 1.5124 |  |  |  | 2014-01-01 |  | 68 | 2014-03-11 | 2014-08-01 15:52 |  | 0 | 2014-08-02 15:52 | 2014-09-26 13:00 |  | 0 | 2014-09-27 13:00 | 2014-11-01 00:30 |  | 0 | 2014-11-02 00:30 | 2014-12-06 11:59 |  | 0 | 2014-12-07 11:59 | 2015-01-10 23:28 |  | 0 | 2015-01-11 23:28 | 2015-02-15 10:57 |  | v005 |  | 0.10918 |  | 68 | 0 | 0 | 0 | 0 | 0 | 68 | 111.3648 |  | 341.4565
Project-A08 |  | 0.52515 | 1.5158 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 12:30 |  | 0 | 2014-01-12 12:30 | 2014-01-19 18:40 |  | 0 | 2014-01-20 18:40 | 2014-01-23 01:31 |  | 0 | 2014-01-24 01:31 | 2014-01-26 08:21 |  | 0 | 2014-01-27 08:21 | 2014-01-29 15:11 |  | 0 | 2014-01-30 15:11 | 2014-02-01 22:02 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 30.918 | [15 empty] | T
Project-A09 |  | 0.53241 | 1.4888 |  |  |  | 2014-01-01 |  | 22 | 2014-01-24 | 2014-04-26 00:50 |  | 0 | 2014-04-27 00:50 | 2014-06-23 19:08 |  | 0 | 2014-06-24 19:08 | 2014-07-16 21:15 |  | 3 | 2014-07-20 21:15 | 2014-08-11 23:23 |  | 0 | 2014-08-12 23:23 | 2014-09-04 01:30 |  | 0 | 2014-09-05 01:30 | 2014-09-27 03:37 |  | v003 |  | 0.083747 |  | 22 | 0 | 0 | 3 | 0 | 0 | 25 | 27.6365 |  | 246.1505 | [15 empty] | H
Project-A10 |  | 0.51778 | 1.4951 |  |  |  | 2014-01-01 |  | 27 | 2014-01-29 | 2014-04-08 12:39 |  | 0 | 2014-04-09 12:39 | 2014-06-06 17:13 |  | 0 | 2014-06-07 17:13 | 2014-06-24 09:42 |  | 0 | 2014-06-25 09:42 | 2014-07-12 02:10 |  | 0 | 2014-07-13 02:10 | 2014-07-29 18:39 |  | 0 | 2014-07-30 18:39 | 2014-08-16 11:08 |  | v001 |  | 0.076303 |  | 27 | 0 | 0 | 0 | 0 | 0 | 27 | 30.9026 |  | 199.4636 | [15 empty] | I
Project-A11 |  | 0.30064 | 1.4634 |  |  |  | 2014-01-01 |  | 38 | 2014-02-09 | 2014-09-06 13:17 |  | 0 | 2014-09-07 13:17 | 2014-11-01 05:16 |  | 0 | 2014-11-02 05:16 | 2014-12-22 12:18 |  | 0 | 2014-12-23 12:18 | 2015-02-11 19:19 |  | 0 | 2015-02-12 19:19 | 2015-04-04 02:21 |  | 0 | 2015-04-05 02:21 | 2015-05-25 09:23 |  | v002 |  | 0.08871 |  | 38 | 0 | 0 | 0 | 0 | 0 | 38 | 50.5645 |  | 470.3907 | [15 empty] | S
Project-A12 |  | 0.6652 | 1.4909 |  |  |  | 2014-01-01 |  | 51 | 2014-02-22 | 2014-05-30 17:10 |  | 0 | 2014-05-31 17:10 | 2014-07-31 18:01 |  | 0 | 2014-08-01 18:01 | 2014-08-25 04:51 |  | 0 | 2014-08-26 04:51 | 2014-09-18 15:42 |  | 0 | 2014-09-19 15:42 | 2014-10-13 02:32 |  | 0 | 2014-10-14 02:32 | 2014-11-06 13:23 |  | v004 |  | 0.096774 |  | 51 | 0 | 0 | 0 | 0 | 0 | 51 | 74.0323 |  | 257.5573
Project-A13 |  | 0.32102 | 1.9984 |  |  |  | 2014-01-01 |  | 63 | 2014-03-06 | 2014-12-30 01:01 |  | 0 | 2014-12-31 01:01 | 2015-03-12 19:30 |  | 0 | 2015-03-13 19:30 | 2015-05-24 13:59 |  | 0 | 2015-05-25 13:59 | 2015-08-05 08:28 |  | 0 | 2015-08-06 08:28 | 2015-10-17 02:57 |  | 0 | 2015-10-18 02:57 | 2015-12-28 21:26 |  | v007 |  | 0.084367 |  | 63 | 0 | 0 | 0 | 0 | 0 | 63 | 79.727 |  | 662.8931 | [15 empty] | W
Project-A14 |  | 0.89109 | 2.0117 |  |  |  | 2014-01-01 |  | 72 | 2014-03-15 | 2014-04-27 18:24 |  | 0 | 2014-04-28 18:24 | 2014-05-25 02:41 |  | 0 | 2014-05-26 02:41 | 2014-06-05 14:47 |  | 0 | 2014-06-06 14:47 | 2014-06-17 02:53 |  | 7 | 2014-06-25 02:53 | 2014-07-05 14:59 |  | 8 | 2014-07-14 14:59 | 2014-07-25 03:04 |  | v006 |  | 0.057072 |  | 72 | 0 | 0 | 0 | 7 | 8 | 87 | 61.6377 |  | 132.1281 | [15 empty] | O
Project-A15 |  | 0.31091 | 1.9655 |  |  |  | 2014-01-01 |  | 80 | 2014-03-23 | 2014-11-09 13:53 |  | 0 | 2014-11-10 13:53 | 2015-01-05 03:46 |  | 0 | 2015-01-06 03:46 | 2015-03-02 17:40 |  | 0 | 2015-03-03 17:40 | 2015-04-28 07:33 |  | 0 | 2015-04-29 07:33 | 2015-06-23 21:27 |  | 0 | 2015-06-24 21:27 | 2015-08-19 11:20 |  | v008 |  | 0.10608 |  | 80 | 0 | 0 | 0 | 0 | 0 | 80 | 127.2953 |  | 514.4725 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 40.6667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.2 |  |  |  | 0.46667 |  |  |  | 0.53333 | [5 empty] | 0.066667 |  | 40.6667 | 0 | 0 | 0.2 | 0.46667 | 0.53333 | 41.8667 | 46.6873 | Average | 254.9799 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 610 |  |  |  | 0 |  |  |  | 0 |  |  |  | 3 |  |  |  | 7 |  |  |  | 8 | [5 empty] | 1 |  | 610 | 0 | 0 | 3 | 7 | 8 | 628 | 700.3102 | Total | 3824.6989 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 0
| Days: | 0
E
N
SIT - Violation | Count: | 0 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 0
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-23 06:49 | 2014-04-03 19:47 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-11 02:39 | 2014-04-23 16:29 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-03-12 11:43 | 2014-03-18 13:46 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-07-30 21:03 | 2014-09-01 18:09 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-04-23 17:32 | 2014-05-06 06:14 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-06-30 17:22 | 2014-07-22 15:04 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2014-09-27 13:00 | 2014-11-01 00:30 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-20 18:40 | 2014-01-23 01:31 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-24 19:08 | 2014-07-16 21:15 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-06-07 17:13 | 2014-06-24 09:42 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-11-02 05:16 | 2014-12-22 12:18 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-01 18:01 | 2014-08-25 04:51 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2015-03-13 19:30 | 2015-05-24 13:59 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-05-26 02:41 | 2014-06-05 14:47 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2015-01-06 03:46 | 2015-03-02 17:40 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-04 19:47 | 2014-04-16 08:46 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-24 16:29 | 2014-05-07 06:18 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-19 13:46 | 2014-03-25 15:49 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-09-02 18:09 | 2014-10-05 15:15 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-07 06:14 | 2014-05-19 18:55 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-07-23 15:04 | 2014-08-14 12:45 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2014-11-02 00:30 | 2014-12-06 11:59 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-24 01:31 | 2014-01-26 08:21 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-20 21:15 | 2014-08-11 23:23 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-25 09:42 | 2014-07-12 02:10 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-12-23 12:18 | 2015-02-11 19:19 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-08-26 04:51 | 2014-09-18 15:42 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-05-25 13:59 | 2015-08-05 08:28 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-06-06 14:47 | 2014-06-17 02:53 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-03-03 17:40 | 2015-04-28 07:33 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-17 08:46 | 2014-04-28 21:45 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-08 06:18 | 2014-05-20 20:07 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-26 15:49 | 2014-04-01 17:51 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-10-06 15:15 | 2014-11-08 12:21 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-20 18:55 | 2014-06-02 07:36 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-15 12:45 | 2014-09-06 10:27 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2014-12-07 11:59 | 2015-01-10 23:28 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-27 08:21 | 2014-01-29 15:11 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-12 23:23 | 2014-09-04 01:30 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-13 02:10 | 2014-07-29 18:39 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-02-12 19:19 | 2015-04-04 02:21 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-19 15:42 | 2014-10-13 02:32 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-08-06 08:28 | 2015-10-17 02:57 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-06-25 02:53 | 2014-07-05 14:59 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-04-29 07:33 | 2015-06-23 21:27 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-29 21:45 | 2014-05-11 10:44 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-21 20:07 | 2014-06-03 09:56 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-04-02 17:51 | 2014-04-08 19:54 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-11-09 12:21 | 2014-12-12 09:28 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-06-03 07:36 | 2014-06-15 20:17 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-07 10:27 | 2014-09-29 08:08 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-01-11 23:28 | 2015-02-15 10:57 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-30 15:11 | 2014-02-01 22:02 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-09-05 01:30 | 2014-09-27 03:37 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-30 18:39 | 2014-08-16 11:08 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-04-05 02:21 | 2015-05-25 09:23 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-14 02:32 | 2014-11-06 13:23 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-10-18 02:57 | 2015-12-28 21:26 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-14 14:59 | 2014-07-25 03:04 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-06-24 21:27 | 2015-08-19 11:20 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.15899 | 15.8994 | 15
0.11032 | 11.0316 | 11
0.78885 | 78.8853 | 78
0.73361 | 73.3614 | 73
0.27486 | 27.4863 | 27
0.892 | 89.1996 | 89
0.62688 | 62.6884 | 62
0.53017 | 53.0171 | 53
0.18881 | 18.8808 | 18
0.96589 | 96.589 | 96
0.37106 | 37.1057 | 37
0.14726 | 14.7265 | 14
0.71108 | 71.1076 | 71
0.21116 | 21.1158 | 21
0.58601 | 58.6008 | 58
0.21009 | 21.0089 | 21
0.53056 | 53.0564 | 53
0.92357 | 92.3566 | 92
0.27631 | 27.6309 | 27
0.87407 | 87.4065 | 87
0.31562 | 31.5617 | 31
0.65172 | 65.1719 | 65
0.9868 | 98.6797 | 98
0.15167 | 15.1669 | 15
0.60099 | 60.0994 | 60
0.21495 | 21.4945 | 21
0.37011 | 37.0113 | 37
0.91034 | 91.0345 | 91
0.083028 | 8.3028 | 8
0.40462 | 40.4623 | 40
0.86011 | 86.0109 | 86
0.39585 | 39.5852 | 39
0.50159 | 50.1585 | 50
0.57899 | 57.8995 | 57
0.82292 | 82.2918 | 82
0.60704 | 60.7041 | 60
0.13551 | 13.5508 | 13
0.73151 | 73.1514 | 73
0.72825 | 72.8253 | 72

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1027.5604 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 10 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH