## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.51395 | 0.30662 |  |  |  | 17 | 17.76 | 34.76 | 57.9209 |  | 4.08 | 74 | 78.08 | 241.3372 |  | 4.08 | 17.76 | 21.84 | 57.9209 |  | 4.08 | 17.76 | 21.84 | 57.9209 |  | 4.08 | 17.76 | 21.84 | 57.9209 |  | 4.08 | 17.76 | 21.84 | 57.9209 |  | 200.2 | 530.9419 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 72.7693 | 530.9419 | 530.9419
Project-A02 |  | v002 |  | 0.53353 | 3.2751 |  |  |  | 15 | 19.2 | 34.2 | 28.1147 |  | 3.6 | 80 | 83.6 | 24.4269 |  | 3.6 | 19.2 | 22.8 | 6.7475 |  | 3.6 | 19.2 | 22.8 | 6.7475 |  | 3.6 | 19.2 | 22.8 | 6.7475 |  | 3.6 | 19.2 | 22.8 | 6.7475 |  | 209 | 79.5316 | 104500 |  | 0.058933 |  | 33 | 176 |  | 61.8523 | 53.7391 | 61.8523 | [12 empty] | E
Project-A03 |  | v003 |  | 0.52279 | 2.3503 |  |  |  | 16 | 6.48 | 22.48 | 30.6048 |  | 3.84 | 27 | 30.84 | 11.4877 |  | 3.84 | 6.48 | 10.32 | 7.3451 |  | 3.84 | 6.48 | 10.32 | 7.3451 |  | 3.84 | 6.48 | 10.32 | 7.3451 |  | 3.84 | 6.48 | 10.32 | 7.3451 |  | 94.6 | 71.4731 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 67.3305 | 25.273 | 67.3305 | [12 empty] | N
Project-A04 |  | v004 |  | 0.51621 | 1.5076 |  |  |  | 35 | 4.32 | 39.32 | 67.8024 |  | 8.4 | 18 | 26.4 | 16.2726 |  | 8.4 | 4.32 | 12.72 | 16.2726 |  | 8.4 | 4.32 | 12.72 | 16.2726 |  | 8.4 | 4.32 | 12.72 | 16.2726 |  | 8.4 | 4.32 | 12.72 | 16.2726 |  | 116.6 | 149.1652 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 149.1652 | 26.2671 | 149.1652 | [12 empty] | D
Project-A05 |  | v002 |  | 0.52816 | 0.27905 |  |  |  | 6 | 19.2 | 25.2 | 68.8047 |  | 1.44 | 80 | 81.44 | 286.6862 |  | 1.44 | 19.2 | 20.64 | 68.8047 |  | 1.44 | 19.2 | 20.64 | 68.8047 |  | 1.44 | 19.2 | 20.64 | 68.8047 |  | 1.44 | 19.2 | 20.64 | 68.8047 |  | 189.2 | 630.7097 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 24.9926 | 630.7097 | 630.7097
Project-A06 |  | v003 |  | 0.49095 | 1.8578 |  |  |  | 52 | 10.56 | 62.56 | 105.9175 |  | 12.48 | 44 | 56.48 | 25.4202 |  | 12.48 | 10.56 | 23.04 | 25.4202 |  | 12.48 | 10.56 | 23.04 | 25.4202 |  | 12.48 | 10.56 | 23.04 | 25.4202 |  | 12.48 | 10.56 | 23.04 | 25.4202 |  | 211.2 | 233.0185 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 233.0185 | 52.1046 | 233.0185 | [12 empty] | O
Project-A07 |  | v005 |  | 0.27239 | 1.4928 |  |  |  | 93 | 19.92 | 112.92 | 341.4281 |  | 22.32 | 83 | 105.32 | 81.9427 |  | 22.32 | 19.92 | 42.24 | 81.9427 |  | 22.32 | 19.92 | 42.24 | 81.9427 |  | 22.32 | 19.92 | 42.24 | 81.9427 |  | 22.32 | 19.92 | 42.24 | 81.9427 |  | 387.2 | 751.1418 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 751.1418 | 122.3217 | 751.1418 | [12 empty] | F
Project-A08 |  | v006 |  | 0.53322 | 2.4405 |  |  |  | 5 | 2.64 | 7.64 | 9.377 |  | 1.2 | 11 | 12.2 | 4.5073 |  | 1.2 | 2.64 | 3.84 | 2.2505 |  | 1.2 | 2.64 | 3.84 | 2.2505 |  | 1.2 | 2.64 | 3.84 | 2.2505 |  | 1.2 | 2.64 | 3.84 | 2.2505 |  | 35.2 | 22.8861 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 20.6293 | 9.916 | 20.6293
Project-A09 |  | v003 |  | 0.53446 | 1.5016 |  |  |  | 49 | 20.64 | 69.64 | 91.6819 |  | 11.76 | 86 | 97.76 | 57.2706 |  | 11.76 | 20.64 | 32.4 | 22.0037 |  | 11.76 | 20.64 | 32.4 | 22.0037 |  | 11.76 | 20.64 | 32.4 | 22.0037 |  | 11.76 | 20.64 | 32.4 | 22.0037 |  | 297 | 236.9671 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 201.7002 | 125.9953 | 201.7002 | [12 empty] | T
Project-A10 |  | v001 |  | 0.51558 | 1.5616 |  |  |  | 36 | 20.88 | 56.88 | 69.8249 |  | 8.64 | 87 | 95.64 | 55.7133 |  | 8.64 | 20.88 | 29.52 | 16.758 |  | 8.64 | 20.88 | 29.52 | 16.758 |  | 8.64 | 20.88 | 29.52 | 16.758 |  | 8.64 | 20.88 | 29.52 | 16.758 |  | 270.6 | 192.5701 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 153.6147 | 122.5692 | 153.6147 | [12 empty] | H
Project-A11 |  | v002 |  | 0.49367 | 1.5606 |  |  |  | 63 | 19.2 | 82.2 | 127.6156 |  | 15.12 | 80 | 95.12 | 51.2616 |  | 15.12 | 19.2 | 34.32 | 30.6278 |  | 15.12 | 19.2 | 34.32 | 30.6278 |  | 15.12 | 19.2 | 34.32 | 30.6278 |  | 15.12 | 19.2 | 34.32 | 30.6278 |  | 314.6 | 301.3882 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 280.7544 | 112.7755 | 280.7544 | [12 empty] | I
Project-A12 |  | v004 |  | 0.49336 | 1.5603 |  |  |  | 65 | 21.84 | 86.84 | 131.7503 |  | 15.6 | 91 | 106.6 | 58.3218 |  | 15.6 | 21.84 | 37.44 | 31.6201 |  | 15.6 | 21.84 | 37.44 | 31.6201 |  | 15.6 | 21.84 | 37.44 | 31.6201 |  | 15.6 | 21.84 | 37.44 | 31.6201 |  | 343.2 | 316.5525 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 289.8507 | 128.308 | 289.8507 | [12 empty] | S
Project-A13 |  | v007 |  | 0.51037 | 2.0507 |  |  |  | 96 | 9.6 | 105.6 | 188.0971 |  | 23.04 | 40 | 63.04 | 45.1433 |  | 23.04 | 9.6 | 32.64 | 45.1433 |  | 23.04 | 9.6 | 32.64 | 45.1433 |  | 23.04 | 9.6 | 32.64 | 45.1433 |  | 23.04 | 9.6 | 32.64 | 45.1433 |  | 299.2 | 413.8135 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 413.8135 | 42.9116 | 413.8135
Project-A14 |  | v006 |  | 0.52343 | 2.0026 |  |  |  | 39 | 12.72 | 51.72 | 74.5078 |  | 9.36 | 53 | 62.36 | 26.4651 |  | 9.36 | 12.72 | 22.08 | 17.8819 |  | 9.36 | 12.72 | 22.08 | 17.8819 |  | 9.36 | 12.72 | 22.08 | 17.8819 |  | 9.36 | 12.72 | 22.08 | 17.8819 |  | 202.4 | 172.5005 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 163.9173 | 58.2233 | 163.9173 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0179 | 0.25274 |  |  |  | 72 | 23.76 | 95.76 | 94.0107 |  | 17.28 | 99 | 116.28 | 391.7111 |  | 17.28 | 23.76 | 41.04 | 94.0107 |  | 17.28 | 23.76 | 41.04 | 94.0107 |  | 17.28 | 23.76 | 41.04 | 94.0107 |  | 17.28 | 23.76 | 41.04 | 94.0107 |  | 376.2 | 861.7644 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 155.6088 | 861.7644 | 861.7644 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 99.1639 |  | 10.544 | 63.5333 | 74.0773 | 91.8645 |  | 10.544 | 15.248 | 25.792 | 34.9833 |  | 10.544 | 15.248 | 25.792 | 34.9833 |  | 10.544 | 15.248 | 25.792 | 34.9833 |  | 10.544 | 15.248 | 25.792 | 34.9833 |  | 236.4267 | 330.9616 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 202.6773 | 193.588 | 320.6803 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1487.4583 |  | 158.16 | 953 | 1111.16 | 1377.9677 |  | 158.16 | 228.72 | 386.88 | 524.7496 |  | 158.16 | 228.72 | 386.88 | 524.7496 |  | 158.16 | 228.72 | 386.88 | 524.7496 |  | 158.16 | 228.72 | 386.88 | 524.7496 |  | 3546.4 | 4964.4244 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3040.1592 | 2903.8205 | 4810.2045 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 1231.7644 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 360.5616 |  | <- To shorten average individual project span |  |  |  | <----------> | 320.6803
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 87.6799 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 0 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1680.0059 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | TRUE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.51395 | 0.30662 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-02-28 22:06 |  | 0 | 2015-03-01 22:06 | 2015-10-29 06:12 |  | 0 | 2015-10-30 06:12 | 2015-12-27 04:18 |  | 0 | 2015-12-28 04:18 | 2016-02-24 02:24 |  | 0 | 2016-02-25 02:24 | 2016-04-23 00:30 |  | 0 | 2016-04-24 00:30 | 2016-06-20 22:36 |  | v001 |  | 0.056452 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 309.0726 |  | 535.9419 | 1231.7644 | [14 empty] | E
Project-A02 |  | 0.53353 | 3.2751 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-02-11 02:45 |  | 0 | 2014-02-12 02:45 | 2014-03-08 13:00 |  | 0 | 2014-03-09 13:00 | 2014-03-16 06:56 |  | 0 | 2014-03-17 06:56 | 2014-03-24 00:53 |  | 0 | 2014-03-25 00:53 | 2014-03-31 18:49 |  | 0 | 2014-04-01 18:49 | 2014-04-08 12:46 |  | v002 |  | 0.058933 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 10.6079 |  | 84.5316 | [15 empty] | N
Project-A03 |  | 0.52279 | 2.3503 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-01 14:31 |  | 0 | 2014-02-02 14:31 | 2014-02-14 02:13 |  | 0 | 2014-02-15 02:13 | 2014-02-22 10:30 |  | 0 | 2014-02-23 10:30 | 2014-03-02 18:47 |  | 0 | 2014-03-03 18:47 | 2014-03-11 03:04 |  | 0 | 2014-03-12 03:04 | 2014-03-19 11:21 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 76.4731 | [15 empty] | D
Project-A04 |  | 0.51621 | 1.5076 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-10 19:15 |  | 0 | 2014-03-11 19:15 | 2014-03-28 01:48 |  | 0 | 2014-03-29 01:48 | 2014-04-14 08:20 |  | 0 | 2014-04-15 08:20 | 2014-05-01 14:53 |  | 0 | 2014-05-02 14:53 | 2014-05-18 21:25 |  | 0 | 2014-05-19 21:25 | 2014-06-05 03:58 |  | v004 |  | 0.032878 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 154.1652
Project-A05 |  | 0.52816 | 0.27905 |  |  |  | 2014-01-01 |  | 51 | 2014-02-22 | 2014-05-01 19:19 |  | 0 | 2014-05-02 19:19 | 2015-02-13 11:47 |  | 0 | 2015-02-14 11:47 | 2015-04-24 07:06 |  | 365 | 2016-04-24 07:06 | 2016-07-02 02:24 |  | 0 | 2016-07-03 02:24 | 2016-09-09 21:43 |  | 0 | 2016-09-10 21:43 | 2016-11-18 17:02 |  | v002 |  | 0.05335 |  | 51 | 0 | 0 | 365 | 0 | 0 | 416 | 40.8127 |  | 1000.7097 | [15 empty] | O
Project-A06 |  | 0.49095 | 1.8578 |  |  |  | 2014-01-01 |  | 58 | 2014-03-01 | 2014-06-14 22:01 |  | 0 | 2014-06-15 22:01 | 2014-07-11 08:06 |  | 0 | 2014-07-12 08:06 | 2014-08-06 18:11 |  | 0 | 2014-08-07 18:11 | 2014-09-02 04:16 |  | 0 | 2014-09-03 04:16 | 2014-09-28 14:22 |  | 0 | 2014-09-29 14:22 | 2014-10-25 00:27 |  | v003 |  | 0.059553 |  | 58 | 0 | 0 | 0 | 0 | 0 | 58 | 51.8114 |  | 238.0185 | [15 empty] | F
Project-A07 |  | 0.27239 | 1.4928 |  |  |  | 2014-01-01 |  | 68 | 2014-03-11 | 2015-02-15 10:16 |  | 0 | 2015-02-16 10:16 | 2015-05-09 08:54 |  | 0 | 2015-05-10 08:54 | 2015-07-31 07:32 |  | 0 | 2015-08-01 07:32 | 2015-10-22 06:09 |  | 0 | 2015-10-23 06:09 | 2016-01-13 04:47 |  | 0 | 2016-01-14 04:47 | 2016-04-05 03:24 |  | v005 |  | 0.10918 |  | 68 | 0 | 0 | 0 | 0 | 0 | 68 | 111.3648 |  | 756.1418
Project-A08 |  | 0.53322 | 2.4405 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-11 09:03 |  | 0 | 2014-01-12 09:03 | 2014-01-16 21:13 |  | 0 | 2014-01-17 21:13 | 2014-01-20 03:14 |  | 0 | 2014-01-21 03:14 | 2014-01-23 09:15 |  | 0 | 2014-01-24 09:15 | 2014-01-26 15:15 |  | 0 | 2014-01-27 15:15 | 2014-01-29 21:16 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 27.8861 | [15 empty] | T
Project-A09 |  | 0.53446 | 1.5016 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-04-03 16:22 |  | 0 | 2014-04-04 16:22 | 2014-05-31 22:52 |  | 0 | 2014-06-01 22:52 | 2014-06-23 22:57 |  | 0 | 2014-06-24 22:57 | 2014-07-16 23:02 |  | 0 | 2014-07-17 23:02 | 2014-08-08 23:07 |  | 0 | 2014-08-09 23:07 | 2014-08-31 23:13 |  | v003 |  | 0.083747 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 241.9671 | [15 empty] | H
Project-A10 |  | 0.51558 | 1.5616 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-12 19:48 |  | 0 | 2014-03-13 19:48 | 2014-05-08 12:55 |  | 0 | 2014-05-09 12:55 | 2014-05-26 07:06 |  | 0 | 2014-05-27 07:06 | 2014-06-13 01:18 |  | 0 | 2014-06-14 01:18 | 2014-06-30 19:29 |  | 0 | 2014-07-01 19:29 | 2014-07-18 13:41 |  | v001 |  | 0.076303 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 197.5701 | [15 empty] | I
Project-A11 |  | 0.49367 | 1.5606 |  |  |  | 2014-01-01 |  | 36 | 2014-02-07 | 2014-06-14 14:47 |  | 0 | 2014-06-15 14:47 | 2014-08-05 21:03 |  | 0 | 2014-08-06 21:03 | 2014-09-06 12:07 |  | 1 | 2014-09-08 12:07 | 2014-10-09 03:11 |  | 0 | 2014-10-10 03:11 | 2014-11-09 18:15 |  | 0 | 2014-11-10 18:15 | 2014-12-11 09:19 |  | v002 |  | 0.08871 |  | 36 | 0 | 0 | 1 | 0 | 0 | 37 | 47.9032 |  | 307.3882 | [15 empty] | S
Project-A12 |  | 0.49336 | 1.5603 |  |  |  | 2014-01-01 |  | 59 | 2014-03-02 | 2014-07-11 18:00 |  | 0 | 2014-07-12 18:00 | 2014-09-09 01:44 |  | 0 | 2014-09-10 01:44 | 2014-10-11 16:37 |  | 0 | 2014-10-12 16:37 | 2014-11-13 07:30 |  | 0 | 2014-11-14 07:30 | 2014-12-15 22:23 |  | 3 | 2014-12-19 22:23 | 2015-01-20 13:16 |  | v004 |  | 0.096774 |  | 59 | 0 | 0 | 0 | 0 | 3 | 62 | 85.6452 |  | 324.5525
Project-A13 |  | 0.51037 | 2.0507 |  |  |  | 2014-01-01 |  | 61 | 2014-03-04 | 2014-09-08 02:20 |  | 0 | 2014-09-09 02:20 | 2014-10-24 05:46 |  | 0 | 2014-10-25 05:46 | 2014-12-09 09:12 |  | 0 | 2014-12-10 09:12 | 2015-01-24 12:39 |  | 0 | 2015-01-25 12:39 | 2015-03-11 16:05 |  | 0 | 2015-03-12 16:05 | 2015-04-26 19:32 |  | v007 |  | 0.084367 |  | 61 | 0 | 0 | 0 | 0 | 0 | 61 | 77.196 |  | 418.8135 | [15 empty] | W
Project-A14 |  | 0.52343 | 2.0026 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-17 12:11 |  | 0 | 2014-03-18 12:11 | 2014-04-13 23:21 |  | 0 | 2014-04-14 23:21 | 2014-05-02 20:31 |  | 0 | 2014-05-03 20:31 | 2014-05-21 17:41 |  | 0 | 2014-05-22 17:41 | 2014-06-09 14:51 |  | 0 | 2014-06-10 14:51 | 2014-06-28 12:01 |  | v006 |  | 0.057072 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 177.5005 | [15 empty] | O
Project-A15 |  | 1.0179 | 0.25274 |  |  |  | 2014-01-01 |  | 365 | 2015-01-02 | 2015-04-06 00:15 |  | 0 | 2015-04-07 00:15 | 2016-05-02 17:19 |  | 0 | 2016-05-03 17:19 | 2016-08-05 17:35 |  | 0 | 2016-08-06 17:35 | 2016-11-08 17:50 |  | 0 | 2016-11-09 17:50 | 2017-02-11 18:05 |  | 0 | 2017-02-12 18:05 | 2017-05-17 18:21 |  | v008 |  | 0.10608 |  | 365 | 0 | 0 | 0 | 0 | 0 | 365 | 580.7847 |  | 866.7644 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 71.6667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 24.4 |  |  |  | 0 |  |  |  | 0.2 | [5 empty] | 0.066667 |  | 71.6667 | 0 | 0 | 24.4 | 0 | 0.2 | 96.2667 | 87.6799 | Average | 360.5616 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 1075 |  |  |  | 0 |  |  |  | 0 |  |  |  | 366 |  |  |  | 0 |  |  |  | 3 | [5 empty] | 1 |  | 1075 | 0 | 0 | 366 | 0 | 3 | 1444 | 1315.1985 | Total | 5408.4244 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 0
| Days: | 0
E
N
SIT - Violation | Count: | 0 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 0
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2015-10-30 06:12 | 2015-12-27 04:18 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-09 13:00 | 2014-03-16 06:56 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-15 02:13 | 2014-02-22 10:30 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-03-29 01:48 | 2014-04-14 08:20 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2015-02-14 11:47 | 2015-04-24 07:06 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-12 08:06 | 2014-08-06 18:11 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-05-10 08:54 | 2015-07-31 07:32 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-17 21:13 | 2014-01-20 03:14 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-01 22:52 | 2014-06-23 22:57 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-05-09 12:55 | 2014-05-26 07:06 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-08-06 21:03 | 2014-09-06 12:07 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-09-10 01:44 | 2014-10-11 16:37 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-25 05:46 | 2014-12-09 09:12 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-04-14 23:21 | 2014-05-02 20:31 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2016-05-03 17:19 | 2016-08-05 17:35 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-12-28 04:18 | 2016-02-24 02:24 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-17 06:56 | 2014-03-24 00:53 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-23 10:30 | 2014-03-02 18:47 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-04-15 08:20 | 2014-05-01 14:53 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2016-04-24 07:06 | 2016-07-02 02:24 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-07 18:11 | 2014-09-02 04:16 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-01 07:32 | 2015-10-22 06:09 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-21 03:14 | 2014-01-23 09:15 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-06-24 22:57 | 2014-07-16 23:02 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-05-27 07:06 | 2014-06-13 01:18 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-08 12:07 | 2014-10-09 03:11 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-12 16:37 | 2014-11-13 07:30 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-10 09:12 | 2015-01-24 12:39 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-05-03 20:31 | 2014-05-21 17:41 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-08-06 17:35 | 2016-11-08 17:50 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-02-25 02:24 | 2016-04-23 00:30 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-25 00:53 | 2014-03-31 18:49 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-03 18:47 | 2014-03-11 03:04 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-02 14:53 | 2014-05-18 21:25 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2016-07-03 02:24 | 2016-09-09 21:43 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-03 04:16 | 2014-09-28 14:22 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-23 06:09 | 2016-01-13 04:47 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-24 09:15 | 2014-01-26 15:15 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-17 23:02 | 2014-08-08 23:07 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-14 01:18 | 2014-06-30 19:29 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-10 03:11 | 2014-11-09 18:15 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-14 07:30 | 2014-12-15 22:23 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-25 12:39 | 2015-03-11 16:05 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-05-22 17:41 | 2014-06-09 14:51 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-11-09 17:50 | 2017-02-11 18:05 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-04-24 00:30 | 2016-06-20 22:36 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-01 18:49 | 2014-04-08 12:46 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-12 03:04 | 2014-03-19 11:21 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-19 21:25 | 2014-06-05 03:58 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2016-09-10 21:43 | 2016-11-18 17:02 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-29 14:22 | 2014-10-25 00:27 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-01-14 04:47 | 2016-04-05 03:24 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-27 15:15 | 2014-01-29 21:16 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-09 23:07 | 2014-08-31 23:13 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-01 19:29 | 2014-07-18 13:41 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-11-10 18:15 | 2014-12-11 09:19 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-19 22:23 | 2015-01-20 13:16 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-12 16:05 | 2015-04-26 19:32 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-06-10 14:51 | 2014-06-28 12:01 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2017-02-12 18:05 | 2017-05-17 18:21 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.2634 | 26.34 | 26
0.37174 | 37.1737 | 37
0.46638 | 46.6379 | 46
0.42129 | 42.1292 | 42
0.70044 | 70.0436 | 70
0.83897 | 83.8974 | 83
0.72381 | 72.3807 | 72
0.18912 | 18.9124 | 18
0.20987 | 20.9868 | 20
0.44972 | 44.9721 | 44
0.21235 | 21.2353 | 21
0.29928 | 29.9275 | 29
0.98167 | 98.1672 | 98
0.59014 | 59.0136 | 59
0.33683 | 33.6831 | 33
0.86646 | 86.6456 | 86
0.95288 | 95.2884 | 95
0.39601 | 39.6012 | 39
0.72605 | 72.6045 | 72
0.015579 | 1.5579 | 1
0.49265 | 49.2651 | 49
0.56546 | 56.5458 | 56
0.30097 | 30.0971 | 30
0.58813 | 58.813 | 58
0.56697 | 56.6971 | 56
0.53938 | 53.938 | 53
0.72073 | 72.0733 | 72
0.15116 | 15.1158 | 15
0.37295 | 37.2953 | 37
0.42067 | 42.0666 | 42
0.6557 | 65.57 | 65
0.24061 | 24.0607 | 24
0.59991 | 59.991 | 59
0.56349 | 56.3493 | 56
0.64986 | 64.9863 | 64
0.22614 | 22.6138 | 22
0.44906 | 44.9057 | 44
0.048822 | 4.8822 | 4
0.027482 | 2.7482 | 2

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1680.0059 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 20 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH