## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.30413 | 0.28061 |  |  |  | 17 | 17.76 | 34.76 | 63.2901 |  | 4.08 | 74 | 78.08 | 263.7085 |  | 4.08 | 17.76 | 21.84 | 63.2901 |  | 4.08 | 17.76 | 21.84 | 63.2901 |  | 4.08 | 17.76 | 21.84 | 63.2901 |  | 4.08 | 17.76 | 21.84 | 63.2901 |  | 200.2 | 580.1588 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 122.9742 | 580.1588 | 580.1588
Project-A02 |  | v002 |  | 0.54858 | 4.148 |  |  |  | 15 | 19.2 | 34.2 | 27.3435 |  | 3.6 | 80 | 83.6 | 19.2866 |  | 3.6 | 19.2 | 22.8 | 6.5624 |  | 3.6 | 19.2 | 22.8 | 6.5624 |  | 3.6 | 19.2 | 22.8 | 6.5624 |  | 3.6 | 19.2 | 22.8 | 6.5624 |  | 209 | 72.8798 | 104500 |  | 0.058933 |  | 33 | 176 |  | 60.1556 | 42.4306 | 60.1556 | [12 empty] | E
Project-A03 |  | v003 |  | 0.51195 | 2.3436 |  |  |  | 16 | 6.48 | 22.48 | 31.2529 |  | 3.84 | 27 | 30.84 | 11.5208 |  | 3.84 | 6.48 | 10.32 | 7.5007 |  | 3.84 | 6.48 | 10.32 | 7.5007 |  | 3.84 | 6.48 | 10.32 | 7.5007 |  | 3.84 | 6.48 | 10.32 | 7.5007 |  | 94.6 | 72.7764 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 68.7563 | 25.3457 | 68.7563 | [12 empty] | N
Project-A04 |  | v004 |  | 0.51536 | 1.5236 |  |  |  | 35 | 4.32 | 39.32 | 67.914 |  | 8.4 | 18 | 26.4 | 16.2994 |  | 8.4 | 4.32 | 12.72 | 16.2994 |  | 8.4 | 4.32 | 12.72 | 16.2994 |  | 8.4 | 4.32 | 12.72 | 16.2994 |  | 8.4 | 4.32 | 12.72 | 16.2994 |  | 116.6 | 149.4108 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 149.4108 | 25.9914 | 149.4108 | [12 empty] | D
Project-A05 |  | v002 |  | 0.59827 | 0.28059 |  |  |  | 6 | 19.2 | 25.2 | 68.4263 |  | 1.44 | 80 | 81.44 | 285.1094 |  | 1.44 | 19.2 | 20.64 | 68.4263 |  | 1.44 | 19.2 | 20.64 | 68.4263 |  | 1.44 | 19.2 | 20.64 | 68.4263 |  | 1.44 | 19.2 | 20.64 | 68.4263 |  | 189.2 | 627.2407 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 22.0638 | 627.2407 | 627.2407
Project-A06 |  | v003 |  | 0.55109 | 1.7907 |  |  |  | 52 | 10.56 | 62.56 | 94.359 |  | 12.48 | 44 | 56.48 | 24.5719 |  | 12.48 | 10.56 | 23.04 | 22.6462 |  | 12.48 | 10.56 | 23.04 | 22.6462 |  | 12.48 | 10.56 | 23.04 | 22.6462 |  | 12.48 | 10.56 | 23.04 | 22.6462 |  | 211.2 | 209.5155 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 207.5897 | 54.0581 | 207.5897 | [12 empty] | O
Project-A07 |  | v005 |  | 0.31567 | 1.5742 |  |  |  | 93 | 19.92 | 112.92 | 294.6126 |  | 22.32 | 83 | 105.32 | 70.707 |  | 22.32 | 19.92 | 42.24 | 70.707 |  | 22.32 | 19.92 | 42.24 | 70.707 |  | 22.32 | 19.92 | 42.24 | 70.707 |  | 22.32 | 19.92 | 42.24 | 70.707 |  | 387.2 | 648.1477 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 648.1477 | 115.9976 | 648.1477 | [12 empty] | F
Project-A08 |  | v006 |  | 0.60264 | 1.5426 |  |  |  | 5 | 2.64 | 7.64 | 8.2968 |  | 1.2 | 11 | 12.2 | 7.1308 |  | 1.2 | 2.64 | 3.84 | 1.9912 |  | 1.2 | 2.64 | 3.84 | 1.9912 |  | 1.2 | 2.64 | 3.84 | 1.9912 |  | 1.2 | 2.64 | 3.84 | 1.9912 |  | 35.2 | 23.3926 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 18.253 | 15.6877 | 18.253
Project-A09 |  | v003 |  | 0.54531 | 1.5386 |  |  |  | 49 | 20.64 | 69.64 | 89.8576 |  | 11.76 | 86 | 97.76 | 55.8956 |  | 11.76 | 20.64 | 32.4 | 21.5658 |  | 11.76 | 20.64 | 32.4 | 21.5658 |  | 11.76 | 20.64 | 32.4 | 21.5658 |  | 11.76 | 20.64 | 32.4 | 21.5658 |  | 297 | 232.0165 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 197.6867 | 122.9703 | 197.6867 | [12 empty] | T
Project-A10 |  | v001 |  | 0.56261 | 1.6373 |  |  |  | 36 | 20.88 | 56.88 | 63.988 |  | 8.64 | 87 | 95.64 | 53.1356 |  | 8.64 | 20.88 | 29.52 | 15.3571 |  | 8.64 | 20.88 | 29.52 | 15.3571 |  | 8.64 | 20.88 | 29.52 | 15.3571 |  | 8.64 | 20.88 | 29.52 | 15.3571 |  | 270.6 | 178.5521 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 140.7737 | 116.8982 | 140.7737 | [12 empty] | H
Project-A11 |  | v002 |  | 0.52829 | 1.5328 |  |  |  | 63 | 19.2 | 82.2 | 119.2537 |  | 15.12 | 80 | 95.12 | 52.1928 |  | 15.12 | 19.2 | 34.32 | 28.6209 |  | 15.12 | 19.2 | 34.32 | 28.6209 |  | 15.12 | 19.2 | 34.32 | 28.6209 |  | 15.12 | 19.2 | 34.32 | 28.6209 |  | 314.6 | 285.9299 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 262.3581 | 114.8241 | 262.3581 | [12 empty] | I
Project-A12 |  | v004 |  | 0.50897 | 1.5559 |  |  |  | 65 | 21.84 | 86.84 | 127.7092 |  | 15.6 | 91 | 106.6 | 58.486 |  | 15.6 | 21.84 | 37.44 | 30.6502 |  | 15.6 | 21.84 | 37.44 | 30.6502 |  | 15.6 | 21.84 | 37.44 | 30.6502 |  | 15.6 | 21.84 | 37.44 | 30.6502 |  | 343.2 | 308.7961 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 280.9603 | 128.6691 | 280.9603 | [12 empty] | S
Project-A13 |  | v007 |  | 0.52661 | 2.0136 |  |  |  | 96 | 9.6 | 105.6 | 182.2996 |  | 23.04 | 40 | 63.04 | 43.7519 |  | 23.04 | 9.6 | 32.64 | 43.7519 |  | 23.04 | 9.6 | 32.64 | 43.7519 |  | 23.04 | 9.6 | 32.64 | 43.7519 |  | 23.04 | 9.6 | 32.64 | 43.7519 |  | 299.2 | 401.0592 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 401.0592 | 43.7031 | 401.0592
Project-A14 |  | v006 |  | 0.25028 | 1.9775 |  |  |  | 39 | 12.72 | 51.72 | 155.8285 |  | 9.36 | 53 | 62.36 | 37.3988 |  | 9.36 | 12.72 | 22.08 | 37.3988 |  | 9.36 | 12.72 | 22.08 | 37.3988 |  | 9.36 | 12.72 | 22.08 | 37.3988 |  | 9.36 | 12.72 | 22.08 | 37.3988 |  | 202.4 | 342.8227 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 342.8227 | 58.9641 | 342.8227 | [12 empty] | W
Project-A15 |  | v008 |  | 1.1303 | 0.26055 |  |  |  | 72 | 23.76 | 95.76 | 91.1921 |  | 17.28 | 99 | 116.28 | 379.9672 |  | 17.28 | 23.76 | 41.04 | 91.1921 |  | 17.28 | 23.76 | 41.04 | 91.1921 |  | 17.28 | 23.76 | 41.04 | 91.1921 |  | 17.28 | 23.76 | 41.04 | 91.1921 |  | 376.2 | 835.9279 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 140.1429 | 835.9279 | 835.9279 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 99.0416 |  | 10.544 | 63.5333 | 74.0773 | 91.9441 |  | 10.544 | 15.248 | 25.792 | 35.064 |  | 10.544 | 15.248 | 25.792 | 35.064 |  | 10.544 | 15.248 | 25.792 | 35.064 |  | 10.544 | 15.248 | 25.792 | 35.064 |  | 236.4267 | 331.2418 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 204.2103 | 193.9245 | 321.4201 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1485.6239 |  | 158.16 | 953 | 1111.16 | 1379.1622 |  | 158.16 | 228.72 | 386.88 | 525.9601 |  | 158.16 | 228.72 | 386.88 | 525.9601 |  | 158.16 | 228.72 | 386.88 | 525.9601 |  | 158.16 | 228.72 | 386.88 | 525.9601 |  | 3546.4 | 4968.6267 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3063.1548 | 2908.8673 | 4821.3013 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 1017.1477 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 337.1084 |  | <- To shorten average individual project span |  |  |  | <----------> | 321.4201
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 67.5813 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 612.5801 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 2034.4176 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.30413 | 0.28061 |  |  |  | 2014-01-01 |  | 7 | 2014-01-09 | 2014-03-13 06:58 |  | 0 | 2014-03-14 06:58 | 2014-12-02 23:58 |  | 0 | 2014-12-03 23:58 | 2015-02-05 06:56 |  | 0 | 2015-02-06 06:56 | 2015-04-10 13:53 |  | 0 | 2015-04-11 13:53 | 2015-06-13 20:51 |  | 0 | 2015-06-14 20:51 | 2015-08-17 03:49 |  | v001 |  | 0.056452 |  | 7 | 0 | 0 | 0 | 0 | 0 | 7 | 5.9274 |  | 585.1588 | 1017.1477 | [14 empty] | E
Project-A02 |  | 0.54858 | 4.148 |  |  |  | 2014-01-01 |  | 14 | 2014-01-16 | 2014-02-12 08:15 |  | 0 | 2014-02-13 08:15 | 2014-03-04 15:07 |  | 0 | 2014-03-05 15:07 | 2014-03-12 04:37 |  | 0 | 2014-03-13 04:37 | 2014-03-19 18:07 |  | 0 | 2014-03-20 18:07 | 2014-03-27 07:37 |  | 0 | 2014-03-28 07:37 | 2014-04-03 21:07 |  | v002 |  | 0.058933 |  | 14 | 0 | 0 | 0 | 0 | 0 | 14 | 12.3759 |  | 77.8798 | [15 empty] | N
Project-A03 |  | 0.51195 | 2.3436 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-02 06:04 |  | 0 | 2014-02-03 06:04 | 2014-02-14 18:34 |  | 0 | 2014-02-15 18:34 | 2014-02-23 06:35 |  | 0 | 2014-02-24 06:35 | 2014-03-03 18:36 |  | 0 | 2014-03-04 18:36 | 2014-03-12 06:37 |  | 0 | 2014-03-13 06:37 | 2014-03-20 18:38 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 77.7764 | [15 empty] | D
Project-A04 |  | 0.51536 | 1.5236 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-03-10 21:56 |  | 0 | 2014-03-11 21:56 | 2014-03-28 05:07 |  | 0 | 2014-03-29 05:07 | 2014-04-14 12:18 |  | 0 | 2014-04-15 12:18 | 2014-05-01 19:29 |  | 0 | 2014-05-02 19:29 | 2014-05-19 02:41 |  | 0 | 2014-05-20 02:41 | 2014-06-05 09:52 |  | v004 |  | 0.032878 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 154.4108
Project-A05 |  | 0.59827 | 0.28059 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-04-25 10:14 |  | 0 | 2014-04-26 10:14 | 2015-02-05 12:51 |  | 0 | 2015-02-06 12:51 | 2015-04-15 23:05 |  | 0 | 2015-04-16 23:05 | 2015-06-24 09:19 |  | 0 | 2015-06-25 09:19 | 2015-09-01 19:33 |  | 0 | 2015-09-02 19:33 | 2015-11-10 05:47 |  | v002 |  | 0.05335 |  | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 36.0112 |  | 632.2407 | [15 empty] | O
Project-A06 |  | 0.55109 | 1.7907 |  |  |  | 2014-01-01 |  | 61 | 2014-03-04 | 2014-06-06 08:37 |  | 0 | 2014-06-07 08:37 | 2014-07-01 22:20 |  | 0 | 2014-07-02 22:20 | 2014-07-25 13:51 |  | 0 | 2014-07-26 13:51 | 2014-08-18 05:21 |  | 0 | 2014-08-19 05:21 | 2014-09-10 20:52 |  | 7 | 2014-09-18 20:52 | 2014-10-11 12:22 |  | v003 |  | 0.059553 |  | 61 | 0 | 0 | 0 | 0 | 7 | 68 | 54.4913 |  | 221.5155 | [15 empty] | F
Project-A07 |  | 0.31567 | 1.5742 |  |  |  | 2014-01-01 |  | 364 | 2015-01-01 | 2015-10-22 14:42 |  | 0 | 2015-10-23 14:42 | 2016-01-02 07:40 |  | 0 | 2016-01-03 07:40 | 2016-03-14 00:38 |  | 0 | 2016-03-15 00:38 | 2016-05-24 17:37 |  | 0 | 2016-05-25 17:37 | 2016-08-04 10:35 |  | 0 | 2016-08-05 10:35 | 2016-10-15 03:33 |  | v005 |  | 0.10918 |  | 364 | 0 | 0 | 0 | 0 | 0 | 364 | 596.129 |  | 653.1477
Project-A08 |  | 0.60264 | 1.5426 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-10 07:07 |  | 0 | 2014-01-11 07:07 | 2014-01-18 10:16 |  | 0 | 2014-01-19 10:16 | 2014-01-21 10:03 |  | 0 | 2014-01-22 10:03 | 2014-01-24 09:51 |  | 0 | 2014-01-25 09:51 | 2014-01-27 09:38 |  | 0 | 2014-01-28 09:38 | 2014-01-30 09:25 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 28.3926 | [15 empty] | T
Project-A09 |  | 0.54531 | 1.5386 |  |  |  | 2014-01-01 |  | 15 | 2014-01-17 | 2014-04-16 20:35 |  | 0 | 2014-04-17 20:35 | 2014-06-12 18:05 |  | 0 | 2014-06-13 18:05 | 2014-07-05 07:39 |  | 0 | 2014-07-06 07:39 | 2014-07-27 21:14 |  | 0 | 2014-07-28 21:14 | 2014-08-19 10:49 |  | 0 | 2014-08-20 10:49 | 2014-09-11 00:24 |  | v003 |  | 0.083747 |  | 15 | 0 | 0 | 0 | 0 | 0 | 15 | 18.8431 |  | 237.0165 | [15 empty] | H
Project-A10 |  | 0.56261 | 1.6373 |  |  |  | 2014-01-01 |  | 27 | 2014-01-29 | 2014-04-02 23:43 |  | 0 | 2014-04-03 23:43 | 2014-05-27 02:58 |  | 0 | 2014-05-28 02:58 | 2014-06-12 11:32 |  | 0 | 2014-06-13 11:32 | 2014-06-28 20:06 |  | 0 | 2014-06-29 20:06 | 2014-07-15 04:41 |  | 0 | 2014-07-16 04:41 | 2014-07-31 13:15 |  | v001 |  | 0.076303 |  | 27 | 0 | 0 | 0 | 0 | 0 | 27 | 30.9026 |  | 183.5521 | [15 empty] | I
Project-A11 |  | 0.52829 | 1.5328 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-06-04 06:05 |  | 0 | 2014-06-05 06:05 | 2014-07-27 10:43 |  | 0 | 2014-07-28 10:43 | 2014-08-26 01:37 |  | 0 | 2014-08-27 01:37 | 2014-09-24 16:31 |  | 0 | 2014-09-25 16:31 | 2014-10-24 07:25 |  | 0 | 2014-10-25 07:25 | 2014-11-22 22:19 |  | v002 |  | 0.08871 |  | 34 | 0 | 0 | 0 | 0 | 0 | 34 | 45.2419 |  | 290.9299 | [15 empty] | S
Project-A12 |  | 0.50897 | 1.5559 |  |  |  | 2014-01-01 |  | 47 | 2014-02-18 | 2014-06-25 17:01 |  | 0 | 2014-06-26 17:01 | 2014-08-24 04:41 |  | 0 | 2014-08-25 04:41 | 2014-09-24 20:17 |  | 0 | 2014-09-25 20:17 | 2014-10-26 11:54 |  | 0 | 2014-10-27 11:54 | 2014-11-27 03:30 |  | 0 | 2014-11-28 03:30 | 2014-12-28 19:06 |  | v004 |  | 0.096774 |  | 47 | 0 | 0 | 0 | 0 | 0 | 47 | 68.2258 |  | 313.7961
Project-A13 |  | 0.52661 | 2.0136 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-09-08 07:11 |  | 0 | 2014-09-09 07:11 | 2014-10-23 01:14 |  | 0 | 2014-10-24 01:14 | 2014-12-06 19:17 |  | 6 | 2014-12-13 19:17 | 2015-01-26 13:20 |  | 0 | 2015-01-27 13:20 | 2015-03-12 07:22 |  | 0 | 2015-03-13 07:22 | 2015-04-26 01:25 |  | v007 |  | 0.084367 |  | 67 | 0 | 0 | 6 | 0 | 0 | 73 | 84.7891 |  | 412.0592 | [15 empty] | W
Project-A14 |  | 0.25028 | 1.9775 |  |  |  | 2014-01-01 |  | 71 | 2014-03-14 | 2014-08-16 19:53 |  | 0 | 2014-08-17 19:53 | 2014-09-24 05:27 |  | 0 | 2014-09-25 05:27 | 2014-11-01 15:02 |  | 0 | 2014-11-02 15:02 | 2014-12-10 00:36 |  | 0 | 2014-12-11 00:36 | 2015-01-17 10:10 |  | 0 | 2015-01-18 10:10 | 2015-02-24 19:45 |  | v006 |  | 0.057072 |  | 71 | 0 | 0 | 0 | 0 | 0 | 71 | 60.7816 |  | 347.8227 | [15 empty] | O
Project-A15 |  | 1.1303 | 0.26055 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-04-03 04:37 |  | 0 | 2014-04-04 04:37 | 2015-04-19 03:49 |  | 0 | 2015-04-20 03:49 | 2015-07-20 08:26 |  | 0 | 2015-07-21 08:26 | 2015-10-20 13:03 |  | 0 | 2015-10-21 13:03 | 2016-01-20 17:39 |  | 0 | 2016-01-21 17:39 | 2016-04-21 22:16 |  | v008 |  | 0.10608 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 840.9279 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 50.1333 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.4 |  |  |  | 0 |  |  |  | 0.46667 | [5 empty] | 0.066667 |  | 50.1333 | 0 | 0 | 0.4 | 0 | 0.46667 | 51 | 67.5813 | Average | 337.1084 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 752 |  |  |  | 0 |  |  |  | 0 |  |  |  | 6 |  |  |  | 0 |  |  |  | 7 | [5 empty] | 1 |  | 752 | 0 | 0 | 6 | 0 | 7 | 765 | 1013.719 | Total | 5056.6267 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 3
| Days: | 12.2516
E
N
SIT - Violation | Count: | 3 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 12.2516
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-12-03 23:58 | 2015-02-05 06:56 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2.8048 | 0 | 0
Project-A02 | 2014-03-05 15:07 | 2014-03-12 04:37 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-15 18:34 | 2014-02-23 06:35 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-03-29 05:07 | 2014-04-14 12:18 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2015-02-06 12:51 | 2015-04-15 23:05 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-02 22:20 | 2014-07-25 13:51 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-01-03 07:40 | 2016-03-14 00:38 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-19 10:16 | 2014-01-21 10:03 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-13 18:05 | 2014-07-05 07:39 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-05-28 02:58 | 2014-06-12 11:32 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-07-28 10:43 | 2014-08-26 01:37 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0.87208 | 0 | 0 | 0 | S
Project-A12 | 2014-08-25 04:41 | 2014-09-24 20:17 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-24 01:14 | 2014-12-06 19:17 | v007 |  | Count P-A14: 1; Count P-A15: 0 | [13 empty] | 8.5747 | 0 | E
Project-A14 | 2014-09-25 05:27 | 2014-11-01 15:02 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2015-04-20 03:49 | 2015-07-20 08:26 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-02-06 06:56 | 2015-04-10 13:53 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-13 04:37 | 2014-03-19 18:07 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-24 06:35 | 2014-03-03 18:36 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-04-15 12:18 | 2014-05-01 19:29 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-04-16 23:05 | 2015-06-24 09:19 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-07-26 13:51 | 2014-08-18 05:21 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-03-15 00:38 | 2016-05-24 17:37 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-22 10:03 | 2014-01-24 09:51 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-06 07:39 | 2014-07-27 21:14 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-13 11:32 | 2014-06-28 20:06 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-08-27 01:37 | 2014-09-24 16:31 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-25 20:17 | 2014-10-26 11:54 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-13 19:17 | 2015-01-26 13:20 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-11-02 15:02 | 2014-12-10 00:36 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-07-21 08:26 | 2015-10-20 13:03 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-04-11 13:53 | 2015-06-13 20:51 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-20 18:07 | 2014-03-27 07:37 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-04 18:36 | 2014-03-12 06:37 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-02 19:29 | 2014-05-19 02:41 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-06-25 09:19 | 2015-09-01 19:33 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-19 05:21 | 2014-09-10 20:52 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-05-25 17:37 | 2016-08-04 10:35 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-25 09:51 | 2014-01-27 09:38 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-28 21:14 | 2014-08-19 10:49 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-29 20:06 | 2014-07-15 04:41 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-25 16:31 | 2014-10-24 07:25 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-27 11:54 | 2014-11-27 03:30 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-27 13:20 | 2015-03-12 07:22 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-12-11 00:36 | 2015-01-17 10:10 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-10-21 13:03 | 2016-01-20 17:39 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-06-14 20:51 | 2015-08-17 03:49 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-03-28 07:37 | 2014-04-03 21:07 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-13 06:37 | 2014-03-20 18:38 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-20 02:41 | 2014-06-05 09:52 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-09-02 19:33 | 2015-11-10 05:47 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-18 20:52 | 2014-10-11 12:22 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-08-05 10:35 | 2016-10-15 03:33 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-28 09:38 | 2014-01-30 09:25 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-20 10:49 | 2014-09-11 00:24 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-16 04:41 | 2014-07-31 13:15 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-25 07:25 | 2014-11-22 22:19 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-28 03:30 | 2014-12-28 19:06 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-13 07:22 | 2015-04-26 01:25 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-01-18 10:10 | 2015-02-24 19:45 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2016-01-21 17:39 | 2016-04-21 22:16 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.96299 | 96.2985 | 96
0.76069 | 76.0685 | 76
0.85629 | 85.6287 | 85
0.070445 | 7.0445 | 7
0.78393 | 78.3927 | 78
0.38103 | 38.1033 | 38
0.1771 | 17.7102 | 17
0.10464 | 10.4635 | 10
0.4676 | 46.7598 | 46
0.80806 | 80.8059 | 80
0.34332 | 34.332 | 34
0.93779 | 93.7794 | 93
0.27646 | 27.6461 | 27
0.69351 | 69.3506 | 69
0.82004 | 82.0044 | 82
0.75614 | 75.614 | 75
0.55902 | 55.9019 | 55
0.53868 | 53.8676 | 53
0.85398 | 85.3982 | 85
0.57945 | 57.9452 | 57
0.32391 | 32.3911 | 32
0.38776 | 38.7759 | 38
0.13261 | 13.2607 | 13
0.086802 | 8.6802 | 8
0.060034 | 6.0034 | 6
0.63827 | 63.8272 | 63
0.0099818 | 0.99818 | 0
0.79502 | 79.5024 | 79
0.59473 | 59.4729 | 59
0.018404 | 1.8404 | 1
0.32423 | 32.4228 | 32
0.65028 | 65.0279 | 65
0.49036 | 49.0362 | 49
0.38059 | 38.0587 | 38
0.72053 | 72.0526 | 72
0.11925 | 11.9255 | 11
0.38549 | 38.5491 | 38
0.17629 | 17.6292 | 17
0.59657 | 59.6567 | 59

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 2034.4176 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 30 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH