## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.49246 | 1.5938 |  |  |  | 17 | 17.76 | 34.76 | 34.5205 |  | 4.08 | 74 | 78.08 | 46.4294 |  | 4.08 | 17.76 | 21.84 | 11.1431 |  | 4.08 | 17.76 | 21.84 | 11.1431 |  | 4.08 | 17.76 | 21.84 | 11.1431 |  | 4.08 | 17.76 | 21.84 | 11.1431 |  | 200.2 | 125.5222 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 75.9451 | 102.1448 | 102.1448
Project-A02 |  | v002 |  | 0.57013 | 1.5083 |  |  |  | 15 | 19.2 | 34.2 | 26.31 |  | 3.6 | 80 | 83.6 | 53.0381 |  | 3.6 | 19.2 | 22.8 | 12.7291 |  | 3.6 | 19.2 | 22.8 | 12.7291 |  | 3.6 | 19.2 | 22.8 | 12.7291 |  | 3.6 | 19.2 | 22.8 | 12.7291 |  | 209 | 130.2647 | 104500 |  | 0.058933 |  | 33 | 176 |  | 57.8819 | 116.6838 | 116.6838 | [12 empty] | E
Project-A03 |  | v003 |  | 0.46765 | 1.5331 |  |  |  | 16 | 6.48 | 22.48 | 34.2135 |  | 3.84 | 27 | 30.84 | 17.6114 |  | 3.84 | 6.48 | 10.32 | 8.2112 |  | 3.84 | 6.48 | 10.32 | 8.2112 |  | 3.84 | 6.48 | 10.32 | 8.2112 |  | 3.84 | 6.48 | 10.32 | 8.2112 |  | 94.6 | 84.6698 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 75.2697 | 38.745 | 75.2697 | [12 empty] | N
Project-A04 |  | v004 |  | 0.48143 | 1.5592 |  |  |  | 35 | 4.32 | 39.32 | 72.6997 |  | 8.4 | 18 | 26.4 | 17.4479 |  | 8.4 | 4.32 | 12.72 | 17.4479 |  | 8.4 | 4.32 | 12.72 | 17.4479 |  | 8.4 | 4.32 | 12.72 | 17.4479 |  | 8.4 | 4.32 | 12.72 | 17.4479 |  | 116.6 | 159.9393 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 159.9393 | 25.3982 | 159.9393 | [12 empty] | D
Project-A05 |  | v002 |  | 0.50175 | 1.5471 |  |  |  | 6 | 19.2 | 25.2 | 12.41 |  | 1.44 | 80 | 81.44 | 51.7083 |  | 1.44 | 19.2 | 20.64 | 12.41 |  | 1.44 | 19.2 | 20.64 | 12.41 |  | 1.44 | 19.2 | 20.64 | 12.41 |  | 1.44 | 19.2 | 20.64 | 12.41 |  | 189.2 | 113.7582 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 26.3078 | 113.7582 | 113.7582
Project-A06 |  | v003 |  | 0.50094 | 2.356 |  |  |  | 52 | 10.56 | 62.56 | 103.8043 |  | 12.48 | 44 | 56.48 | 24.913 |  | 12.48 | 10.56 | 23.04 | 24.913 |  | 12.48 | 10.56 | 23.04 | 24.913 |  | 12.48 | 10.56 | 23.04 | 24.913 |  | 12.48 | 10.56 | 23.04 | 24.913 |  | 211.2 | 228.3695 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 228.3695 | 41.0872 | 228.3695 | [12 empty] | O
Project-A07 |  | v005 |  | 0.26063 | 1.531 |  |  |  | 93 | 19.92 | 112.92 | 356.8261 |  | 22.32 | 83 | 105.32 | 85.6383 |  | 22.32 | 19.92 | 42.24 | 85.6383 |  | 22.32 | 19.92 | 42.24 | 85.6383 |  | 22.32 | 19.92 | 42.24 | 85.6383 |  | 22.32 | 19.92 | 42.24 | 85.6383 |  | 387.2 | 785.0174 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 785.0174 | 119.267 | 785.0174 | [12 empty] | F
Project-A08 |  | v006 |  | 0.49784 | 1.8715 |  |  |  | 5 | 2.64 | 7.64 | 10.0434 |  | 1.2 | 11 | 12.2 | 5.8778 |  | 1.2 | 2.64 | 3.84 | 2.4104 |  | 1.2 | 2.64 | 3.84 | 2.4104 |  | 1.2 | 2.64 | 3.84 | 2.4104 |  | 1.2 | 2.64 | 3.84 | 2.4104 |  | 35.2 | 25.5628 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 22.0955 | 12.9311 | 22.0955
Project-A09 |  | v003 |  | 0.55965 | 1.4597 |  |  |  | 49 | 20.64 | 69.64 | 87.5554 |  | 11.76 | 86 | 97.76 | 58.9153 |  | 11.76 | 20.64 | 32.4 | 21.0133 |  | 11.76 | 20.64 | 32.4 | 21.0133 |  | 11.76 | 20.64 | 32.4 | 21.0133 |  | 11.76 | 20.64 | 32.4 | 21.0133 |  | 297 | 230.5238 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 192.6219 | 129.6136 | 192.6219 | [12 empty] | T
Project-A10 |  | v001 |  | 0.54727 | 1.4856 |  |  |  | 36 | 20.88 | 56.88 | 65.7813 |  | 8.64 | 87 | 95.64 | 58.5613 |  | 8.64 | 20.88 | 29.52 | 15.7875 |  | 8.64 | 20.88 | 29.52 | 15.7875 |  | 8.64 | 20.88 | 29.52 | 15.7875 |  | 8.64 | 20.88 | 29.52 | 15.7875 |  | 270.6 | 187.4926 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 144.7188 | 128.8348 | 144.7188 | [12 empty] | H
Project-A11 |  | v002 |  | 0.52489 | 1.5334 |  |  |  | 63 | 19.2 | 82.2 | 120.0242 |  | 15.12 | 80 | 95.12 | 52.1699 |  | 15.12 | 19.2 | 34.32 | 28.8058 |  | 15.12 | 19.2 | 34.32 | 28.8058 |  | 15.12 | 19.2 | 34.32 | 28.8058 |  | 15.12 | 19.2 | 34.32 | 28.8058 |  | 314.6 | 287.4173 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 264.0532 | 114.7739 | 264.0532 | [12 empty] | I
Project-A12 |  | v004 |  | 0.51022 | 1.4879 |  |  |  | 65 | 21.84 | 86.84 | 127.3951 |  | 15.6 | 91 | 106.6 | 61.1602 |  | 15.6 | 21.84 | 37.44 | 30.5748 |  | 15.6 | 21.84 | 37.44 | 30.5748 |  | 15.6 | 21.84 | 37.44 | 30.5748 |  | 15.6 | 21.84 | 37.44 | 30.5748 |  | 343.2 | 310.8545 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 280.2691 | 134.5523 | 280.2691 | [12 empty] | S
Project-A13 |  | v007 |  | 0.50123 | 1.966 |  |  |  | 96 | 9.6 | 105.6 | 191.5297 |  | 23.04 | 40 | 63.04 | 45.9671 |  | 23.04 | 9.6 | 32.64 | 45.9671 |  | 23.04 | 9.6 | 32.64 | 45.9671 |  | 23.04 | 9.6 | 32.64 | 45.9671 |  | 23.04 | 9.6 | 32.64 | 45.9671 |  | 299.2 | 421.3654 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 421.3654 | 44.7608 | 421.3654
Project-A14 |  | v006 |  | 0.55542 | 0.42769 |  |  |  | 39 | 12.72 | 51.72 | 70.2168 |  | 9.36 | 53 | 62.36 | 123.9227 |  | 9.36 | 12.72 | 22.08 | 29.7415 |  | 9.36 | 12.72 | 22.08 | 29.7415 |  | 9.36 | 12.72 | 22.08 | 29.7415 |  | 9.36 | 12.72 | 22.08 | 29.7415 |  | 202.4 | 313.1053 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 154.4769 | 272.63 | 272.63 | [12 empty] | W
Project-A15 |  | v008 |  | 1.0285 | 2.1396 |  |  |  | 72 | 23.76 | 95.76 | 70.0062 |  | 17.28 | 99 | 116.28 | 46.2705 |  | 17.28 | 23.76 | 41.04 | 16.8015 |  | 17.28 | 23.76 | 41.04 | 16.8015 |  | 17.28 | 23.76 | 41.04 | 16.8015 |  | 17.28 | 23.76 | 41.04 | 16.8015 |  | 376.2 | 183.4826 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 154.0136 | 101.795 | 154.0136 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 92.2224 |  | 10.544 | 63.5333 | 74.0773 | 49.9754 |  | 10.544 | 15.248 | 25.792 | 24.2396 |  | 10.544 | 15.248 | 25.792 | 24.2396 |  | 10.544 | 15.248 | 25.792 | 24.2396 |  | 10.544 | 15.248 | 25.792 | 24.2396 |  | 236.4267 | 239.1564 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 202.823 | 99.7984 | 222.1967 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1383.336 |  | 158.16 | 953 | 1111.16 | 749.6311 |  | 158.16 | 228.72 | 386.88 | 363.5946 |  | 158.16 | 228.72 | 386.88 | 363.5946 |  | 158.16 | 228.72 | 386.88 | 363.5946 |  | 158.16 | 228.72 | 386.88 | 363.5946 |  | 3546.4 | 3587.3454 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 3042.3451 | 1496.9756 | 3332.9501 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 858.0174 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 321.1564 |  | <- To shorten average individual project span |  |  |  | <----------> | 222.1967
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 56.5577 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 297.8143 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1533.5458 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.49246 | 1.5938 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-05 12:30 |  | 0 | 2014-02-06 12:30 | 2014-03-24 22:48 |  | 0 | 2014-03-25 22:48 | 2014-04-06 02:14 |  | 0 | 2014-04-07 02:14 | 2014-04-18 05:40 |  | 3 | 2014-04-22 05:40 | 2014-05-03 09:06 |  | 365 | 2015-05-04 09:06 | 2015-05-15 12:32 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 3 | 365 | 368 | 0 |  | 498.5222 | 858.0174 | [14 empty] | E
Project-A02 |  | 0.57013 | 1.5083 |  |  |  | 2014-01-01 |  | 17 | 2014-01-19 | 2014-02-14 07:26 |  | 0 | 2014-02-15 07:26 | 2014-04-09 08:21 |  | 0 | 2014-04-10 08:21 | 2014-04-23 01:51 |  | 0 | 2014-04-24 01:51 | 2014-05-06 19:21 |  | 0 | 2014-05-07 19:21 | 2014-05-20 12:51 |  | 0 | 2014-05-21 12:51 | 2014-06-03 06:21 |  | v002 |  | 0.058933 |  | 17 | 0 | 0 | 0 | 0 | 0 | 17 | 15.0279 |  | 135.2647 | [15 empty] | N
Project-A03 |  | 0.46765 | 1.5331 |  |  |  | 2014-01-01 |  | 1 | 2014-01-03 | 2014-02-06 05:07 |  | 0 | 2014-02-07 05:07 | 2014-02-24 19:48 |  | 0 | 2014-02-25 19:48 | 2014-03-06 00:52 |  | 0 | 2014-03-07 00:52 | 2014-03-15 05:56 |  | 0 | 2014-03-16 05:56 | 2014-03-24 11:00 |  | 2 | 2014-03-27 11:00 | 2014-04-04 16:05 |  | v003 |  | 0.026675 |  | 1 | 0 | 0 | 0 | 0 | 2 | 3 | 0.40012 |  | 91.6698 | [15 empty] | D
Project-A04 |  | 0.48143 | 1.5592 |  |  |  | 2014-01-01 |  | 37 | 2014-02-08 | 2014-04-21 16:48 |  | 0 | 2014-04-22 16:48 | 2014-05-10 03:33 |  | 0 | 2014-05-11 03:33 | 2014-05-28 14:18 |  | 0 | 2014-05-29 14:18 | 2014-06-16 01:03 |  | 0 | 2014-06-17 01:03 | 2014-07-04 11:48 |  | 0 | 2014-07-05 11:48 | 2014-07-22 22:33 |  | v004 |  | 0.032878 |  | 37 | 0 | 0 | 0 | 0 | 0 | 37 | 18.2475 |  | 164.9393
Project-A05 |  | 0.50175 | 1.5471 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-14 09:50 |  | 0 | 2014-01-15 09:50 | 2014-03-08 02:50 |  | 0 | 2014-03-09 02:50 | 2014-03-21 12:41 |  | 2 | 2014-03-24 12:41 | 2014-04-05 22:31 |  | 1 | 2014-04-07 22:31 | 2014-04-20 08:21 |  | 1 | 2014-04-22 08:21 | 2014-05-04 18:12 |  | v002 |  | 0.05335 |  | 0 | 0 | 0 | 2 | 1 | 1 | 4 | 0 |  | 122.7582 | [15 empty] | O
Project-A06 |  | 0.50094 | 2.356 |  |  |  | 2014-01-01 |  | 330 | 2014-11-28 | 2015-03-11 19:18 |  | 0 | 2015-03-12 19:18 | 2015-04-06 17:13 |  | 0 | 2015-04-07 17:13 | 2015-05-02 15:08 |  | 0 | 2015-05-03 15:08 | 2015-05-28 13:03 |  | 3 | 2015-06-01 13:03 | 2015-06-26 10:57 |  | 0 | 2015-06-27 10:57 | 2015-07-22 08:52 |  | v003 |  | 0.059553 |  | 330 | 0 | 0 | 0 | 3 | 0 | 333 | 294.7891 |  | 236.3695 | [15 empty] | F
Project-A07 |  | 0.26063 | 1.531 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2015-03-01 19:50 |  | 0 | 2015-03-02 19:50 | 2015-05-27 11:09 |  | 0 | 2015-05-28 11:09 | 2015-08-22 02:28 |  | 1 | 2015-08-24 02:28 | 2015-11-17 17:47 |  | 0 | 2015-11-18 17:47 | 2016-02-12 09:06 |  | 0 | 2016-02-13 09:06 | 2016-05-09 00:25 |  | v005 |  | 0.10918 |  | 67 | 0 | 0 | 1 | 0 | 0 | 68 | 109.727 |  | 791.0174
Project-A08 |  | 0.49784 | 1.8715 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-01-12 01:02 |  | 0 | 2014-01-13 01:02 | 2014-01-18 22:06 |  | 0 | 2014-01-19 22:06 | 2014-01-22 07:57 |  | 0 | 2014-01-23 07:57 | 2014-01-25 17:48 |  | 6 | 2014-02-01 17:48 | 2014-02-04 03:39 |  | 2 | 2014-02-07 03:39 | 2014-02-09 13:30 |  | v006 |  | 0.0099256 |  | 0 | 0 | 0 | 0 | 6 | 2 | 8 | 0 |  | 38.5628 | [15 empty] | T
Project-A09 |  | 0.55965 | 1.4597 |  |  |  | 2014-01-01 |  | 16 | 2014-01-18 | 2014-04-15 13:20 |  | 0 | 2014-04-16 13:20 | 2014-06-14 11:18 |  | 0 | 2014-06-15 11:18 | 2014-07-06 11:37 |  | 1 | 2014-07-08 11:37 | 2014-07-29 11:56 |  | 2 | 2014-08-01 11:56 | 2014-08-22 12:15 |  | 0 | 2014-08-23 12:15 | 2014-09-13 12:34 |  | v003 |  | 0.083747 |  | 16 | 0 | 0 | 1 | 2 | 0 | 19 | 20.0993 |  | 238.5238 | [15 empty] | H
Project-A10 |  | 0.54727 | 1.4856 |  |  |  | 2014-01-01 |  | 20 | 2014-01-22 | 2014-03-28 18:45 |  | 0 | 2014-03-29 18:45 | 2014-05-27 08:13 |  | 0 | 2014-05-28 08:13 | 2014-06-13 03:07 |  | 3 | 2014-06-17 03:07 | 2014-07-02 22:01 |  | 3 | 2014-07-06 22:01 | 2014-07-22 16:55 |  | 1 | 2014-07-24 16:55 | 2014-08-09 11:49 |  | v001 |  | 0.076303 |  | 20 | 0 | 0 | 3 | 3 | 1 | 27 | 22.8908 |  | 199.4926 | [15 empty] | I
Project-A11 |  | 0.52489 | 1.5334 |  |  |  | 2014-01-01 |  | 36 | 2014-02-07 | 2014-06-07 00:35 |  | 0 | 2014-06-08 00:35 | 2014-07-30 04:40 |  | 0 | 2014-07-31 04:40 | 2014-08-29 |  | 0 | 2014-08-30 | 2014-09-27 19:20 |  | 1 | 2014-09-29 19:20 | 2014-10-28 14:41 |  | 0 | 2014-10-29 14:41 | 2014-11-27 10:01 |  | v002 |  | 0.08871 |  | 36 | 0 | 0 | 0 | 1 | 0 | 37 | 47.9032 |  | 293.4173 | [15 empty] | S
Project-A12 |  | 0.51022 | 1.4879 |  |  |  | 2014-01-01 |  | 48 | 2014-02-19 | 2014-06-26 09:29 |  | 0 | 2014-06-27 09:29 | 2014-08-27 13:20 |  | 0 | 2014-08-28 13:20 | 2014-09-28 03:07 |  | 4 | 2014-10-03 03:07 | 2014-11-02 16:55 |  | 0 | 2014-11-03 16:55 | 2014-12-04 06:43 |  | 0 | 2014-12-05 06:43 | 2015-01-04 20:30 |  | v004 |  | 0.096774 |  | 48 | 0 | 0 | 4 | 0 | 0 | 52 | 69.6774 |  | 319.8545
Project-A13 |  | 0.50123 | 1.966 |  |  |  | 2014-01-01 |  | 55 | 2014-02-26 | 2014-09-05 12:43 |  | 0 | 2014-09-06 12:43 | 2014-10-22 11:55 |  | 0 | 2014-10-23 11:55 | 2014-12-08 11:08 |  | 3 | 2014-12-12 11:08 | 2015-01-27 10:21 |  | 3 | 2015-01-31 10:21 | 2015-03-18 09:33 |  | 0 | 2015-03-19 09:33 | 2015-05-04 08:46 |  | v007 |  | 0.084367 |  | 55 | 0 | 0 | 3 | 3 | 0 | 61 | 69.603 |  | 432.3654 | [15 empty] | W
Project-A14 |  | 0.55542 | 0.42769 |  |  |  | 2014-01-01 |  | 69 | 2014-03-12 | 2014-05-21 05:12 |  | 0 | 2014-05-22 05:12 | 2014-09-23 03:21 |  | 0 | 2014-09-24 03:21 | 2014-10-23 21:09 |  | 14 | 2014-11-07 21:09 | 2014-12-07 14:56 |  | 3 | 2014-12-11 14:56 | 2015-01-10 08:44 |  | 365 | 2016-01-11 08:44 | 2016-02-10 02:32 |  | v006 |  | 0.057072 |  | 69 | 0 | 0 | 14 | 3 | 365 | 451 | 59.0695 |  | 700.1053 | [15 empty] | O
Project-A15 |  | 1.0285 | 2.1396 |  |  |  | 2014-01-01 |  | 76 | 2014-03-19 | 2014-05-28 00:09 |  | 0 | 2014-05-29 00:09 | 2014-07-14 06:38 |  | 0 | 2014-07-15 06:38 | 2014-08-01 01:52 |  | 1 | 2014-08-03 01:52 | 2014-08-19 21:07 |  | 365 | 2015-08-20 21:07 | 2015-09-06 16:21 |  | 0 | 2015-09-07 16:21 | 2015-09-24 11:35 |  | v008 |  | 0.10608 |  | 76 | 0 | 0 | 1 | 365 | 0 | 442 | 120.9305 |  | 554.4826 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 51.4667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 1.9333 |  |  |  | 26 |  |  |  | 49.0667 | [5 empty] | 0.066667 |  | 51.4667 | 0 | 0 | 1.9333 | 26 | 49.0667 | 128.4667 | 56.5577 | Average | 321.1564 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 772 |  |  |  | 0 |  |  |  | 0 |  |  |  | 29 |  |  |  | 390 |  |  |  | 736 | [5 empty] | 1 |  | 772 | 0 | 0 | 29 | 390 | 736 | 1927 | 848.3654 | Total | 4817.3454 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 5
| Days: | 5.9563
E
N
SIT - Violation | Count: | 5 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 5.9563
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-25 22:48 | 2014-04-06 02:14 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-10 08:21 | 2014-04-23 01:51 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-25 19:48 | 2014-03-06 00:52 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-11 03:33 | 2014-05-28 14:18 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0.25296 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-03-09 02:50 | 2014-03-21 12:41 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2015-04-07 17:13 | 2015-05-02 15:08 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-05-28 11:09 | 2015-08-22 02:28 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-19 22:06 | 2014-01-22 07:57 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-15 11:18 | 2014-07-06 11:37 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-05-28 08:13 | 2014-06-13 03:07 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-07-31 04:40 | 2014-08-29 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 1 | [11 empty] | 0.4447 | 0 | 0 | 0.884 | S
Project-A12 | 2014-08-28 13:20 | 2014-09-28 03:07 | v004 |  | Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [12 empty] | 0 | 3.9905 | 0 | H
Project-A13 | 2014-10-23 11:55 | 2014-12-08 11:08 | v007 |  | Count P-A14: 1; Count P-A15: 0 | [13 empty] | 0.38409 | 0 | E
Project-A14 | 2014-09-24 03:21 | 2014-10-23 21:09 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-15 06:38 | 2014-08-01 01:52 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-07 02:14 | 2014-04-18 05:40 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-24 01:51 | 2014-05-06 19:21 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-07 00:52 | 2014-03-15 05:56 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-29 14:18 | 2014-06-16 01:03 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-03-24 12:41 | 2014-04-05 22:31 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-05-03 15:08 | 2015-05-28 13:03 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-24 02:28 | 2015-11-17 17:47 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-23 07:57 | 2014-01-25 17:48 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-08 11:37 | 2014-07-29 11:56 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-17 03:07 | 2014-07-02 22:01 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-08-30 | 2014-09-27 19:20 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-03 03:07 | 2014-11-02 16:55 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-12 11:08 | 2015-01-27 10:21 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-11-07 21:09 | 2014-12-07 14:56 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-03 01:52 | 2014-08-19 21:07 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-22 05:40 | 2014-05-03 09:06 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-07 19:21 | 2014-05-20 12:51 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-16 05:56 | 2014-03-24 11:00 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-17 01:03 | 2014-07-04 11:48 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-07 22:31 | 2014-04-20 08:21 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-06-01 13:03 | 2015-06-26 10:57 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-11-18 17:47 | 2016-02-12 09:06 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-02-01 17:48 | 2014-02-04 03:39 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-01 11:56 | 2014-08-22 12:15 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-06 22:01 | 2014-07-22 16:55 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-29 19:20 | 2014-10-28 14:41 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-03 16:55 | 2014-12-04 06:43 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-31 10:21 | 2015-03-18 09:33 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-12-11 14:56 | 2015-01-10 08:44 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-08-20 21:07 | 2015-09-06 16:21 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-05-04 09:06 | 2015-05-15 12:32 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-21 12:51 | 2014-06-03 06:21 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-27 11:00 | 2014-04-04 16:05 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-07-05 11:48 | 2014-07-22 22:33 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-04-22 08:21 | 2014-05-04 18:12 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2015-06-27 10:57 | 2015-07-22 08:52 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2016-02-13 09:06 | 2016-05-09 00:25 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-02-07 03:39 | 2014-02-09 13:30 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-23 12:15 | 2014-09-13 12:34 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-24 16:55 | 2014-08-09 11:49 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-29 14:41 | 2014-11-27 10:01 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-12-05 06:43 | 2015-01-04 20:30 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-19 09:33 | 2015-05-04 08:46 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2016-01-11 08:44 | 2016-02-10 02:32 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2015-09-07 16:21 | 2015-09-24 11:35 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.60904 | 60.9044 | 60
0.12037 | 12.0368 | 12
0.59867 | 59.8675 | 59
0.78338 | 78.3382 | 78
0.51035 | 51.0353 | 51
0.38923 | 38.9234 | 38
0.88921 | 88.9208 | 88
0.39697 | 39.6968 | 39
0.93671 | 93.671 | 93
0.95042 | 95.0419 | 95
0.59979 | 59.9788 | 59
0.605 | 60.4995 | 60
0.10837 | 10.8367 | 10
0.86435 | 86.4353 | 86
0.12188 | 12.1882 | 12
0.15935 | 15.9349 | 15
0.060869 | 6.0869 | 6
0.42056 | 42.056 | 42
0.19385 | 19.3851 | 19
0.81422 | 81.4216 | 81
0.79701 | 79.7014 | 79
0.52322 | 52.3215 | 52
0.61418 | 61.4184 | 61
0.79411 | 79.4112 | 79
0.39371 | 39.3712 | 39
0.8081 | 80.8101 | 80
0.7949 | 79.4904 | 79
0.78585 | 78.5849 | 78
0.25195 | 25.1945 | 25
0.68506 | 68.5062 | 68
0.44206 | 44.2059 | 44
0.23728 | 23.7279 | 23
0.55808 | 55.8081 | 55
0.30927 | 30.9272 | 30
0.90537 | 90.5365 | 90
0.1813 | 18.1303 | 18
0.78206 | 78.2063 | 78
0.61533 | 61.5334 | 61
0.17604 | 17.6043 | 17

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1533.5458 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 40 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH