## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.51452 | 0.29668 |  |  |  | 17 | 17.76 | 34.76 | 59.8615 |  | 4.08 | 74 | 78.08 | 249.4231 |  | 4.08 | 17.76 | 21.84 | 59.8615 |  | 4.08 | 17.76 | 21.84 | 59.8615 |  | 4.08 | 17.76 | 21.84 | 59.8615 |  | 4.08 | 17.76 | 21.84 | 59.8615 |  | 200.2 | 548.7308 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 72.6894 | 548.7308 | 548.7308
Project-A02 |  | v002 |  | 0.48904 | 1.4556 |  |  |  | 15 | 19.2 | 34.2 | 30.6725 |  | 3.6 | 80 | 83.6 | 54.9588 |  | 3.6 | 19.2 | 22.8 | 13.1901 |  | 3.6 | 19.2 | 22.8 | 13.1901 |  | 3.6 | 19.2 | 22.8 | 13.1901 |  | 3.6 | 19.2 | 22.8 | 13.1901 |  | 209 | 138.3918 | 104500 |  | 0.058933 |  | 33 | 176 |  | 67.4796 | 120.9093 | 120.9093 | [12 empty] | E
Project-A03 |  | v003 |  | 0.57392 | 2.5592 |  |  |  | 16 | 6.48 | 22.48 | 27.8786 |  | 3.84 | 27 | 30.84 | 10.5501 |  | 3.84 | 6.48 | 10.32 | 6.6909 |  | 3.84 | 6.48 | 10.32 | 6.6909 |  | 3.84 | 6.48 | 10.32 | 6.6909 |  | 3.84 | 6.48 | 10.32 | 6.6909 |  | 94.6 | 65.1921 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 61.3329 | 23.2102 | 61.3329 | [12 empty] | N
Project-A04 |  | v004 |  | 0.4994 | 1.4361 |  |  |  | 35 | 4.32 | 39.32 | 70.0844 |  | 8.4 | 18 | 26.4 | 16.8203 |  | 8.4 | 4.32 | 12.72 | 16.8203 |  | 8.4 | 4.32 | 12.72 | 16.8203 |  | 8.4 | 4.32 | 12.72 | 16.8203 |  | 8.4 | 4.32 | 12.72 | 16.8203 |  | 116.6 | 154.1857 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 154.1857 | 27.5743 | 154.1857 | [12 empty] | D
Project-A05 |  | v002 |  | 0.59194 | 0.26927 |  |  |  | 6 | 19.2 | 25.2 | 71.3037 |  | 1.44 | 80 | 81.44 | 297.0987 |  | 1.44 | 19.2 | 20.64 | 71.3037 |  | 1.44 | 19.2 | 20.64 | 71.3037 |  | 1.44 | 19.2 | 20.64 | 71.3037 |  | 1.44 | 19.2 | 20.64 | 71.3037 |  | 189.2 | 653.6172 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 22.2996 | 653.6172 | 653.6172
Project-A06 |  | v003 |  | 0.4531 | 1.5203 |  |  |  | 52 | 10.56 | 62.56 | 114.7646 |  | 12.48 | 44 | 56.48 | 28.9415 |  | 12.48 | 10.56 | 23.04 | 27.5435 |  | 12.48 | 10.56 | 23.04 | 27.5435 |  | 12.48 | 10.56 | 23.04 | 27.5435 |  | 12.48 | 10.56 | 23.04 | 27.5435 |  | 211.2 | 253.8801 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 252.4821 | 63.6713 | 252.4821 | [12 empty] | O
Project-A07 |  | v005 |  | 0.53326 | 1.5448 |  |  |  | 93 | 19.92 | 112.92 | 174.3978 |  | 22.32 | 83 | 105.32 | 53.7269 |  | 22.32 | 19.92 | 42.24 | 41.8555 |  | 22.32 | 19.92 | 42.24 | 41.8555 |  | 22.32 | 19.92 | 42.24 | 41.8555 |  | 22.32 | 19.92 | 42.24 | 41.8555 |  | 387.2 | 395.5467 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 383.6753 | 118.1993 | 383.6753 | [12 empty] | F
Project-A08 |  | v006 |  | 0.50317 | 1.5683 |  |  |  | 5 | 2.64 | 7.64 | 9.9369 |  | 1.2 | 11 | 12.2 | 7.014 |  | 1.2 | 2.64 | 3.84 | 2.3849 |  | 1.2 | 2.64 | 3.84 | 2.3849 |  | 1.2 | 2.64 | 3.84 | 2.3849 |  | 1.2 | 2.64 | 3.84 | 2.3849 |  | 35.2 | 26.4903 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 21.8612 | 15.4307 | 21.8612
Project-A09 |  | v003 |  | 0.49001 | 2.4075 |  |  |  | 49 | 20.64 | 69.64 | 99.9972 |  | 11.76 | 86 | 97.76 | 35.7218 |  | 11.76 | 20.64 | 32.4 | 23.9993 |  | 11.76 | 20.64 | 32.4 | 23.9993 |  | 11.76 | 20.64 | 32.4 | 23.9993 |  | 11.76 | 20.64 | 32.4 | 23.9993 |  | 297 | 231.7163 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 219.9938 | 78.588 | 219.9938 | [12 empty] | T
Project-A10 |  | v001 |  | 0.58438 | 1.4635 |  |  |  | 36 | 20.88 | 56.88 | 61.6036 |  | 8.64 | 87 | 95.64 | 59.445 |  | 8.64 | 20.88 | 29.52 | 14.7849 |  | 8.64 | 20.88 | 29.52 | 14.7849 |  | 8.64 | 20.88 | 29.52 | 14.7849 |  | 8.64 | 20.88 | 29.52 | 14.7849 |  | 270.6 | 180.1881 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 135.528 | 130.7789 | 135.528 | [12 empty] | H
Project-A11 |  | v002 |  | 0.52895 | 0.30298 |  |  |  | 63 | 19.2 | 82.2 | 119.1029 |  | 15.12 | 80 | 95.12 | 264.0482 |  | 15.12 | 19.2 | 34.32 | 63.3716 |  | 15.12 | 19.2 | 34.32 | 63.3716 |  | 15.12 | 19.2 | 34.32 | 63.3716 |  | 15.12 | 19.2 | 34.32 | 63.3716 |  | 314.6 | 636.6373 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 262.0264 | 580.906 | 580.906 | [12 empty] | I
Project-A12 |  | v004 |  | 0.51102 | 1.5801 |  |  |  | 65 | 21.84 | 86.84 | 127.1974 |  | 15.6 | 91 | 106.6 | 57.5918 |  | 15.6 | 21.84 | 37.44 | 30.5274 |  | 15.6 | 21.84 | 37.44 | 30.5274 |  | 15.6 | 21.84 | 37.44 | 30.5274 |  | 15.6 | 21.84 | 37.44 | 30.5274 |  | 343.2 | 306.8988 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 279.8344 | 126.7019 | 279.8344 | [12 empty] | S
Project-A13 |  | v007 |  | 0.49413 | 2.0542 |  |  |  | 96 | 9.6 | 105.6 | 194.2791 |  | 23.04 | 40 | 63.04 | 46.627 |  | 23.04 | 9.6 | 32.64 | 46.627 |  | 23.04 | 9.6 | 32.64 | 46.627 |  | 23.04 | 9.6 | 32.64 | 46.627 |  | 23.04 | 9.6 | 32.64 | 46.627 |  | 299.2 | 427.4141 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 427.4141 | 42.84 | 427.4141
Project-A14 |  | v006 |  | 0.25872 | 1.9989 |  |  |  | 39 | 12.72 | 51.72 | 150.7428 |  | 9.36 | 53 | 62.36 | 36.1783 |  | 9.36 | 12.72 | 22.08 | 36.1783 |  | 9.36 | 12.72 | 22.08 | 36.1783 |  | 9.36 | 12.72 | 22.08 | 36.1783 |  | 9.36 | 12.72 | 22.08 | 36.1783 |  | 202.4 | 331.6342 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 331.6342 | 58.3331 | 331.6342 | [12 empty] | W
Project-A15 |  | v008 |  | 0.97443 | 3.5425 |  |  |  | 72 | 23.76 | 95.76 | 73.889 |  | 17.28 | 99 | 116.28 | 27.9464 |  | 17.28 | 23.76 | 41.04 | 17.7334 |  | 17.28 | 23.76 | 41.04 | 17.7334 |  | 17.28 | 23.76 | 41.04 | 17.7334 |  | 17.28 | 23.76 | 41.04 | 17.7334 |  | 376.2 | 172.769 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 162.5559 | 61.4822 | 162.5559 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 92.3808 |  | 10.544 | 63.5333 | 74.0773 | 83.0728 |  | 10.544 | 15.248 | 25.792 | 31.5248 |  | 10.544 | 15.248 | 25.792 | 31.5248 |  | 10.544 | 15.248 | 25.792 | 31.5248 |  | 10.544 | 15.248 | 25.792 | 31.5248 |  | 236.4267 | 301.5528 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 190.3328 | 176.7315 | 288.9774 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1385.7122 |  | 158.16 | 953 | 1111.16 | 1246.0917 |  | 158.16 | 228.72 | 386.88 | 472.8721 |  | 158.16 | 228.72 | 386.88 | 472.8721 |  | 158.16 | 228.72 | 386.88 | 472.8721 |  | 158.16 | 228.72 | 386.88 | 472.8721 |  | 3546.4 | 4523.2923 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2854.9924 | 2650.9731 | 4334.6607 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 895.7308 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 359.8862 |  | <- To shorten average individual project span |  |  |  | <----------> | 288.9774
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 96.3517 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 346.2362 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1698.2049 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.51452 | 0.29668 |  |  |  | 2014-01-01 |  | 352 | 2014-12-20 | 2015-02-17 20:41 |  | 0 | 2015-02-18 20:41 | 2015-10-26 06:50 |  | 0 | 2015-10-27 06:50 | 2015-12-26 03:30 |  | 0 | 2015-12-27 03:30 | 2016-02-25 00:11 |  | 0 | 2016-02-26 00:11 | 2016-04-25 20:52 |  | 1 | 2016-04-27 20:52 | 2016-06-26 17:32 |  | v001 |  | 0.056452 |  | 352 | 0 | 0 | 0 | 0 | 1 | 353 | 298.0645 |  | 554.7308 | 895.7308 | [14 empty] | E
Project-A02 |  | 0.48904 | 1.4556 |  |  |  | 2014-01-01 |  | 11 | 2014-01-13 | 2014-02-12 16:08 |  | 0 | 2014-02-13 16:08 | 2014-04-09 15:09 |  | 0 | 2014-04-10 15:09 | 2014-04-23 19:43 |  | 0 | 2014-04-24 19:43 | 2014-05-08 00:17 |  | 4 | 2014-05-13 00:17 | 2014-05-26 04:50 |  | 1 | 2014-05-28 04:50 | 2014-06-10 09:24 |  | v002 |  | 0.058933 |  | 11 | 0 | 0 | 0 | 4 | 1 | 16 | 9.7239 |  | 148.3918 | [15 empty] | N
Project-A03 |  | 0.57392 | 2.5592 |  |  |  | 2014-01-01 |  | 21 | 2014-01-23 | 2014-02-19 21:05 |  | 0 | 2014-02-20 21:05 | 2014-03-03 10:17 |  | 0 | 2014-03-04 10:17 | 2014-03-11 02:52 |  | 0 | 2014-03-12 02:52 | 2014-03-18 19:27 |  | 0 | 2014-03-19 19:27 | 2014-03-26 12:02 |  | 1 | 2014-03-28 12:02 | 2014-04-04 04:37 |  | v003 |  | 0.026675 |  | 21 | 0 | 0 | 0 | 0 | 1 | 22 | 8.4026 |  | 71.1921 | [15 empty] | D
Project-A04 |  | 0.4994 | 1.4361 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-04-16 02:02 |  | 0 | 2014-04-17 02:02 | 2014-05-03 21:43 |  | 0 | 2014-05-04 21:43 | 2014-05-21 17:24 |  | 0 | 2014-05-22 17:24 | 2014-06-08 13:05 |  | 0 | 2014-06-09 13:05 | 2014-06-26 08:46 |  | 3 | 2014-06-30 08:46 | 2014-07-17 04:27 |  | v004 |  | 0.032878 |  | 34 | 0 | 0 | 0 | 0 | 3 | 37 | 16.768 |  | 162.1857
Project-A05 |  | 0.59194 | 0.26927 |  |  |  | 2014-01-01 |  | 43 | 2014-02-14 | 2014-04-26 07:17 |  | 0 | 2014-04-27 07:17 | 2015-02-18 09:39 |  | 0 | 2015-02-19 09:39 | 2015-05-01 16:57 |  | 1 | 2015-05-03 16:57 | 2015-07-14 00:14 |  | 4 | 2015-07-19 00:14 | 2015-09-28 07:31 |  | 1 | 2015-09-30 07:31 | 2015-12-10 14:49 |  | v002 |  | 0.05335 |  | 43 | 0 | 0 | 1 | 4 | 1 | 49 | 34.4107 |  | 664.6172 | [15 empty] | O
Project-A06 |  | 0.4531 | 1.5203 |  |  |  | 2014-01-01 |  | 57 | 2014-02-28 | 2014-06-22 18:21 |  | 0 | 2014-06-23 18:21 | 2014-07-22 16:57 |  | 0 | 2014-07-23 16:57 | 2014-08-20 05:59 |  | 4 | 2014-08-25 05:59 | 2014-09-21 19:02 |  | 0 | 2014-09-22 19:02 | 2014-10-20 08:05 |  | 2 | 2014-10-23 08:05 | 2014-11-19 21:07 |  | v003 |  | 0.059553 |  | 57 | 0 | 0 | 4 | 0 | 2 | 63 | 50.9181 |  | 264.8801 | [15 empty] | F
Project-A07 |  | 0.53326 | 1.5448 |  |  |  | 2014-01-01 |  | 364 | 2015-01-01 | 2015-06-24 09:33 |  | 0 | 2015-06-25 09:33 | 2015-08-18 03:00 |  | 0 | 2015-08-19 03:00 | 2015-09-29 23:32 |  | 1 | 2015-10-01 23:32 | 2015-11-12 20:03 |  | 2 | 2015-11-15 20:03 | 2015-12-27 16:35 |  | 2 | 2015-12-30 16:35 | 2016-02-10 13:07 |  | v005 |  | 0.10918 |  | 364 | 0 | 0 | 1 | 2 | 2 | 369 | 596.129 |  | 405.5467
Project-A08 |  | 0.50317 | 1.5683 |  |  |  | 2014-01-01 |  | 74 | 2014-03-17 | 2014-03-26 22:29 |  | 0 | 2014-03-27 22:29 | 2014-04-03 22:49 |  | 0 | 2014-04-04 22:49 | 2014-04-07 08:03 |  | 1 | 2014-04-09 08:03 | 2014-04-11 17:18 |  | 1 | 2014-04-13 17:18 | 2014-04-16 02:32 |  | 0 | 2014-04-17 02:32 | 2014-04-19 11:46 |  | v006 |  | 0.0099256 |  | 74 | 0 | 0 | 1 | 1 | 0 | 76 | 11.0174 |  | 33.4903 | [15 empty] | T
Project-A09 |  | 0.49001 | 2.4075 |  |  |  | 2014-01-01 |  | 16 | 2014-01-18 | 2014-04-27 23:56 |  | 0 | 2014-04-28 23:56 | 2014-06-03 17:15 |  | 0 | 2014-06-04 17:15 | 2014-06-28 17:14 |  | 1 | 2014-06-30 17:14 | 2014-07-24 17:13 |  | 2 | 2014-07-27 17:13 | 2014-08-20 17:12 |  | 365 | 2015-08-21 17:12 | 2015-09-14 17:11 |  | v003 |  | 0.083747 |  | 16 | 0 | 0 | 1 | 2 | 365 | 384 | 20.0993 |  | 604.7163 | [15 empty] | H
Project-A10 |  | 0.58438 | 1.4635 |  |  |  | 2014-01-01 |  | 22 | 2014-01-24 | 2014-03-26 14:29 |  | 0 | 2014-03-27 14:29 | 2014-05-26 01:10 |  | 0 | 2014-05-27 01:10 | 2014-06-10 20:00 |  | 0 | 2014-06-11 20:00 | 2014-06-26 14:50 |  | 361 | 2015-06-23 14:50 | 2015-07-08 09:41 |  | 2 | 2015-07-11 09:41 | 2015-07-26 04:31 |  | v001 |  | 0.076303 |  | 22 | 0 | 0 | 0 | 361 | 2 | 385 | 25.1799 |  | 548.1881 | [15 empty] | I
Project-A11 |  | 0.52895 | 0.30298 |  |  |  | 2014-01-01 |  | 37 | 2014-02-08 | 2014-06-07 02:28 |  | 0 | 2014-06-08 02:28 | 2015-02-27 03:38 |  | 0 | 2015-02-28 03:38 | 2015-05-02 12:33 |  | 1 | 2015-05-04 12:33 | 2015-07-06 21:28 |  | 5 | 2015-07-12 21:28 | 2015-09-14 06:23 |  | 0 | 2015-09-15 06:23 | 2015-11-17 15:18 |  | v002 |  | 0.08871 |  | 37 | 0 | 0 | 1 | 5 | 0 | 43 | 49.2339 |  | 647.6373 | [15 empty] | S
Project-A12 |  | 0.51102 | 1.5801 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-06-23 04:44 |  | 0 | 2014-06-24 04:44 | 2014-08-20 18:56 |  | 0 | 2014-08-21 18:56 | 2014-09-21 07:36 |  | 0 | 2014-09-22 07:36 | 2014-10-22 20:15 |  | 0 | 2014-10-23 20:15 | 2014-11-23 08:55 |  | 2 | 2014-11-26 08:55 | 2014-12-26 21:34 |  | v004 |  | 0.096774 |  | 45 | 0 | 0 | 0 | 0 | 2 | 47 | 65.3226 |  | 313.8988
Project-A13 |  | 0.49413 | 2.0542 |  |  |  | 2014-01-01 |  | 58 | 2014-03-01 | 2014-09-11 06:42 |  | 0 | 2014-09-12 06:42 | 2014-10-28 21:45 |  | 0 | 2014-10-29 21:45 | 2014-12-15 12:48 |  | 18 | 2015-01-03 12:48 | 2015-02-19 03:51 |  | 0 | 2015-02-20 03:51 | 2015-04-07 18:53 |  | 1 | 2015-04-09 18:53 | 2015-05-26 09:56 |  | v007 |  | 0.084367 |  | 58 | 0 | 0 | 18 | 0 | 1 | 77 | 73.3995 |  | 451.4141 | [15 empty] | W
Project-A14 |  | 0.25872 | 1.9989 |  |  |  | 2014-01-01 |  | 73 | 2014-03-16 | 2014-08-13 17:50 |  | 0 | 2014-08-14 17:50 | 2014-09-19 22:06 |  | 0 | 2014-09-20 22:06 | 2014-10-27 02:23 |  | 1 | 2014-10-29 02:23 | 2014-12-04 06:40 |  | 0 | 2014-12-05 06:40 | 2015-01-10 10:57 |  | 1 | 2015-01-12 10:57 | 2015-02-17 15:13 |  | v006 |  | 0.057072 |  | 73 | 0 | 0 | 1 | 0 | 1 | 75 | 62.4938 |  | 338.6342 | [15 empty] | O
Project-A15 |  | 0.97443 | 3.5425 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-06-02 21:20 |  | 0 | 2014-06-03 21:20 | 2014-07-01 20:03 |  | 0 | 2014-07-02 20:03 | 2014-07-20 13:39 |  | 11 | 2014-08-01 13:39 | 2014-08-19 07:15 |  | 0 | 2014-08-20 07:15 | 2014-09-07 00:51 |  | 0 | 2014-09-08 00:51 | 2014-09-25 18:27 |  | v008 |  | 0.10608 |  | 78 | 0 | 0 | 11 | 0 | 0 | 89 | 124.1129 |  | 188.769 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 85.6667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 2.6 |  |  |  | 25.2667 |  |  |  | 25.4667 | [5 empty] | 0.066667 |  | 85.6667 | 0 | 0 | 2.6 | 25.2667 | 25.4667 | 139 | 96.3517 | Average | 359.8862 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 1285 |  |  |  | 0 |  |  |  | 0 |  |  |  | 39 |  |  |  | 379 |  |  |  | 382 | [5 empty] | 1 |  | 1285 | 0 | 0 | 39 | 379 | 382 | 2085 | 1445.2761 | Total | 5398.2923 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 3
| Days: | 6.9247
E
N
SIT - Violation | Count: | 2 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 6.51
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2015-10-27 06:50 | 2015-12-26 03:30 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-10 15:09 | 2014-04-23 19:43 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-03-04 10:17 | 2014-03-11 02:52 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-04 21:43 | 2014-05-21 17:24 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2015-02-19 09:39 | 2015-05-01 16:57 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-23 16:57 | 2014-08-20 05:59 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-19 03:00 | 2015-09-29 23:32 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-04-04 22:49 | 2014-04-07 08:03 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-04 17:15 | 2014-06-28 17:14 | v003 |  | Count P-A10: 1; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 6.1144 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-05-27 01:10 | 2014-06-10 20:00 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2015-02-28 03:38 | 2015-05-02 12:33 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-21 18:56 | 2014-09-21 07:36 | v004 |  | Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [12 empty] | 0 | 0.39552 | 0 | H
Project-A13 | 2014-10-29 21:45 | 2014-12-15 12:48 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-09-20 22:06 | 2014-10-27 02:23 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-02 20:03 | 2014-07-20 13:39 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2015-12-27 03:30 | 2016-02-25 00:11 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-24 19:43 | 2014-05-08 00:17 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-12 02:52 | 2014-03-18 19:27 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-22 17:24 | 2014-06-08 13:05 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-05-03 16:57 | 2015-07-14 00:14 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-25 05:59 | 2014-09-21 19:02 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-01 23:32 | 2015-11-12 20:03 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-04-09 08:03 | 2014-04-11 17:18 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-06-30 17:14 | 2014-07-24 17:13 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-11 20:00 | 2014-06-26 14:50 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-05-04 12:33 | 2015-07-06 21:28 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-22 07:36 | 2014-10-22 20:15 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-03 12:48 | 2015-02-19 03:51 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-10-29 02:23 | 2014-12-04 06:40 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-01 13:39 | 2014-08-19 07:15 | v008
NFT - Violation | Count: | 1 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0.41476
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-02-26 00:11 | 2016-04-25 20:52 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-13 00:17 | 2014-05-26 04:50 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-19 19:27 | 2014-03-26 12:02 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-09 13:05 | 2014-06-26 08:46 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-07-19 00:14 | 2015-09-28 07:31 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-22 19:02 | 2014-10-20 08:05 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-11-15 20:03 | 2015-12-27 16:35 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-04-13 17:18 | 2014-04-16 02:32 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-27 17:13 | 2014-08-20 17:12 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 1 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0.41476
Project-A10 | 2015-06-23 14:50 | 2015-07-08 09:41 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-07-12 21:28 | 2015-09-14 06:23 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-23 20:15 | 2014-11-23 08:55 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-02-20 03:51 | 2015-04-07 18:53 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-12-05 06:40 | 2015-01-10 10:57 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-20 07:15 | 2014-09-07 00:51 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2016-04-27 20:52 | 2016-06-26 17:32 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-28 04:50 | 2014-06-10 09:24 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-28 12:02 | 2014-04-04 04:37 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-30 08:46 | 2014-07-17 04:27 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2015-09-30 07:31 | 2015-12-10 14:49 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-10-23 08:05 | 2014-11-19 21:07 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-12-30 16:35 | 2016-02-10 13:07 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-04-17 02:32 | 2014-04-19 11:46 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-08-21 17:12 | 2015-09-14 17:11 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2015-07-11 09:41 | 2015-07-26 04:31 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-09-15 06:23 | 2015-11-17 15:18 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-26 08:55 | 2014-12-26 21:34 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-04-09 18:53 | 2015-05-26 09:56 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2015-01-12 10:57 | 2015-02-17 15:13 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-08 00:51 | 2014-09-25 18:27 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.72505 | 72.5055 | 72
0.56409 | 56.4085 | 56
0.28049 | 28.0493 | 28
0.36232 | 36.2317 | 36
0.14616 | 14.6162 | 14
0.64584 | 64.5843 | 64
0.53523 | 53.5233 | 53
0.22638 | 22.6381 | 22
0.36536 | 36.5358 | 36
0.80196 | 80.1962 | 80
0.98488 | 98.4883 | 98
0.33335 | 33.3349 | 33
0.63629 | 63.6291 | 63
0.065363 | 6.5363 | 6
0.86262 | 86.2618 | 86
0.54673 | 54.6735 | 54
0.69974 | 69.974 | 69
0.59217 | 59.2167 | 59
0.16647 | 16.6468 | 16
0.89939 | 89.9386 | 89
0.37123 | 37.1232 | 37
0.77378 | 77.3781 | 77
0.52993 | 52.9935 | 52
0.29943 | 29.9425 | 29
0.44516 | 44.5161 | 44
0.31611 | 31.6107 | 31
0.89476 | 89.4758 | 89
0.75398 | 75.3981 | 75
0.91429 | 91.4287 | 91
0.98195 | 98.1952 | 98
0.33247 | 33.2473 | 33
0.98357 | 98.3567 | 98
0.68091 | 68.0912 | 68
0.51559 | 51.5585 | 51
0.80667 | 80.6666 | 80
0.3219 | 32.1899 | 32
0.47309 | 47.3086 | 47
0.045822 | 4.5822 | 4
0.53986 | 53.9861 | 53

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1698.2049 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 50 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH