## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.53681 | 1.5026 |  |  |  | 17 | 17.76 | 34.76 | 31.6687 |  | 4.08 | 74 | 78.08 | 49.2483 |  | 4.08 | 17.76 | 21.84 | 11.8196 |  | 4.08 | 17.76 | 21.84 | 11.8196 |  | 4.08 | 17.76 | 21.84 | 11.8196 |  | 4.08 | 17.76 | 21.84 | 11.8196 |  | 200.2 | 128.1953 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 69.6711 | 108.3463 | 108.3463
Project-A02 |  | v002 |  | 0.51545 | 1.5293 |  |  |  | 15 | 19.2 | 34.2 | 29.1007 |  | 3.6 | 80 | 83.6 | 52.3117 |  | 3.6 | 19.2 | 22.8 | 12.5548 |  | 3.6 | 19.2 | 22.8 | 12.5548 |  | 3.6 | 19.2 | 22.8 | 12.5548 |  | 3.6 | 19.2 | 22.8 | 12.5548 |  | 209 | 131.6316 | 104500 |  | 0.058933 |  | 33 | 176 |  | 64.0215 | 115.0858 | 115.0858 | [12 empty] | E
Project-A03 |  | v003 |  | 0.5133 | 3.2763 |  |  |  | 16 | 6.48 | 22.48 | 31.1709 |  | 3.84 | 27 | 30.84 | 8.241 |  | 3.84 | 6.48 | 10.32 | 7.481 |  | 3.84 | 6.48 | 10.32 | 7.481 |  | 3.84 | 6.48 | 10.32 | 7.481 |  | 3.84 | 6.48 | 10.32 | 7.481 |  | 94.6 | 69.3359 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 68.576 | 18.1301 | 68.576 | [12 empty] | N
Project-A04 |  | v004 |  | 0.50919 | 1.567 |  |  |  | 35 | 4.32 | 39.32 | 68.7366 |  | 8.4 | 18 | 26.4 | 16.4968 |  | 8.4 | 4.32 | 12.72 | 16.4968 |  | 8.4 | 4.32 | 12.72 | 16.4968 |  | 8.4 | 4.32 | 12.72 | 16.4968 |  | 8.4 | 4.32 | 12.72 | 16.4968 |  | 116.6 | 151.2206 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 151.2206 | 25.2719 | 151.2206 | [12 empty] | D
Project-A05 |  | v002 |  | 0.46825 | 1.5058 |  |  |  | 6 | 19.2 | 25.2 | 12.8138 |  | 1.44 | 80 | 81.44 | 53.1288 |  | 1.44 | 19.2 | 20.64 | 12.7509 |  | 1.44 | 19.2 | 20.64 | 12.7509 |  | 1.44 | 19.2 | 20.64 | 12.7509 |  | 1.44 | 19.2 | 20.64 | 12.7509 |  | 189.2 | 116.9461 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 28.1903 | 116.8833 | 116.8833
Project-A06 |  | v003 |  | 0.56363 | 1.4745 |  |  |  | 52 | 10.56 | 62.56 | 92.259 |  | 12.48 | 44 | 56.48 | 29.841 |  | 12.48 | 10.56 | 23.04 | 22.1422 |  | 12.48 | 10.56 | 23.04 | 22.1422 |  | 12.48 | 10.56 | 23.04 | 22.1422 |  | 12.48 | 10.56 | 23.04 | 22.1422 |  | 211.2 | 210.6686 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 202.9698 | 65.6501 | 202.9698 | [12 empty] | O
Project-A07 |  | v005 |  | 0.54777 | 0.30366 |  |  |  | 93 | 19.92 | 112.92 | 169.7785 |  | 22.32 | 83 | 105.32 | 273.3362 |  | 22.32 | 19.92 | 42.24 | 65.6007 |  | 22.32 | 19.92 | 42.24 | 65.6007 |  | 22.32 | 19.92 | 42.24 | 65.6007 |  | 22.32 | 19.92 | 42.24 | 65.6007 |  | 387.2 | 705.5175 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 373.5127 | 601.3397 | 601.3397 | [12 empty] | F
Project-A08 |  | v006 |  | 0.46757 | 1.9394 |  |  |  | 5 | 2.64 | 7.64 | 10.6935 |  | 1.2 | 11 | 12.2 | 5.6718 |  | 1.2 | 2.64 | 3.84 | 2.5665 |  | 1.2 | 2.64 | 3.84 | 2.5665 |  | 1.2 | 2.64 | 3.84 | 2.5665 |  | 1.2 | 2.64 | 3.84 | 2.5665 |  | 35.2 | 26.6312 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 23.5258 | 12.478 | 23.5258
Project-A09 |  | v003 |  | 0.52379 | 0.28624 |  |  |  | 49 | 20.64 | 69.64 | 93.5495 |  | 11.76 | 86 | 97.76 | 300.4499 |  | 11.76 | 20.64 | 32.4 | 72.108 |  | 11.76 | 20.64 | 32.4 | 72.108 |  | 11.76 | 20.64 | 32.4 | 72.108 |  | 11.76 | 20.64 | 32.4 | 72.108 |  | 297 | 682.4313 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 205.8089 | 660.9898 | 660.9898 | [12 empty] | T
Project-A10 |  | v001 |  | 0.51802 | 1.5261 |  |  |  | 36 | 20.88 | 56.88 | 69.4948 |  | 8.64 | 87 | 95.64 | 57.0091 |  | 8.64 | 20.88 | 29.52 | 16.6787 |  | 8.64 | 20.88 | 29.52 | 16.6787 |  | 8.64 | 20.88 | 29.52 | 16.6787 |  | 8.64 | 20.88 | 29.52 | 16.6787 |  | 270.6 | 193.2188 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 152.8885 | 125.42 | 152.8885 | [12 empty] | H
Project-A11 |  | v002 |  | 0.25954 | 1.5252 |  |  |  | 63 | 19.2 | 82.2 | 242.7336 |  | 15.12 | 80 | 95.12 | 58.2561 |  | 15.12 | 19.2 | 34.32 | 58.2561 |  | 15.12 | 19.2 | 34.32 | 58.2561 |  | 15.12 | 19.2 | 34.32 | 58.2561 |  | 15.12 | 19.2 | 34.32 | 58.2561 |  | 314.6 | 534.0138 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 534.0138 | 115.3928 | 534.0138 | [12 empty] | I
Project-A12 |  | v004 |  | 0.51415 | 1.495 |  |  |  | 65 | 21.84 | 86.84 | 126.4227 |  | 15.6 | 91 | 106.6 | 60.8704 |  | 15.6 | 21.84 | 37.44 | 30.3414 |  | 15.6 | 21.84 | 37.44 | 30.3414 |  | 15.6 | 21.84 | 37.44 | 30.3414 |  | 15.6 | 21.84 | 37.44 | 30.3414 |  | 343.2 | 308.6588 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 278.1299 | 133.9149 | 278.1299 | [12 empty] | S
Project-A13 |  | v007 |  | 0.51153 | 2.0428 |  |  |  | 96 | 9.6 | 105.6 | 187.6731 |  | 23.04 | 40 | 63.04 | 45.0415 |  | 23.04 | 9.6 | 32.64 | 45.0415 |  | 23.04 | 9.6 | 32.64 | 45.0415 |  | 23.04 | 9.6 | 32.64 | 45.0415 |  | 23.04 | 9.6 | 32.64 | 45.0415 |  | 299.2 | 412.8808 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 412.8808 | 43.0776 | 412.8808
Project-A14 |  | v006 |  | 0.52604 | 2.0412 |  |  |  | 39 | 12.72 | 51.72 | 74.139 |  | 9.36 | 53 | 62.36 | 25.9651 |  | 9.36 | 12.72 | 22.08 | 17.7933 |  | 9.36 | 12.72 | 22.08 | 17.7933 |  | 9.36 | 12.72 | 22.08 | 17.7933 |  | 9.36 | 12.72 | 22.08 | 17.7933 |  | 202.4 | 171.2774 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 163.1057 | 57.1232 | 163.1057 | [12 empty] | W
Project-A15 |  | v008 |  | 1.025 | 1.985 |  |  |  | 72 | 23.76 | 95.76 | 70.2467 |  | 17.28 | 99 | 116.28 | 49.8747 |  | 17.28 | 23.76 | 41.04 | 16.8592 |  | 17.28 | 23.76 | 41.04 | 16.8592 |  | 17.28 | 23.76 | 41.04 | 16.8592 |  | 17.28 | 23.76 | 41.04 | 16.8592 |  | 376.2 | 187.5583 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 154.5428 | 109.7244 | 154.5428 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 87.3654 |  | 10.544 | 63.5333 | 74.0773 | 72.3828 |  | 10.544 | 15.248 | 25.792 | 27.2327 |  | 10.544 | 15.248 | 25.792 | 27.2327 |  | 10.544 | 15.248 | 25.792 | 27.2327 |  | 10.544 | 15.248 | 25.792 | 27.2327 |  | 236.4267 | 268.6791 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 192.2039 | 153.9219 | 249.6332 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1310.481 |  | 158.16 | 953 | 1111.16 | 1085.7424 |  | 158.16 | 228.72 | 386.88 | 408.4907 |  | 158.16 | 228.72 | 386.88 | 408.4907 |  | 158.16 | 228.72 | 386.88 | 408.4907 |  | 158.16 | 228.72 | 386.88 | 408.4907 |  | 3546.4 | 4030.1863 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2883.0581 | 2308.8278 | 3744.4985 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 943.6686 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 299.8124 |  | <- To shorten average individual project span |  |  |  | <----------> | 249.6332
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 60.84 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 0 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 1304.3209 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | TRUE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.53681 | 1.5026 |  |  |  | 2014-01-01 |  | 2 | 2014-01-04 | 2014-02-04 16:03 |  | 0 | 2014-02-05 16:03 | 2014-03-26 22:00 |  | 0 | 2014-03-27 22:00 | 2014-04-08 17:41 |  | 1 | 2014-04-10 17:41 | 2014-04-22 13:21 |  | 1 | 2014-04-24 13:21 | 2014-05-06 09:01 |  | 2 | 2014-05-09 09:01 | 2014-05-21 04:41 |  | v001 |  | 0.056452 |  | 2 | 0 | 0 | 1 | 1 | 2 | 6 | 1.6935 |  | 137.1953 | 943.6686 | [14 empty] | E
Project-A02 |  | 0.51545 | 1.5293 |  |  |  | 2014-01-01 |  | 14 | 2014-01-16 | 2014-02-14 02:25 |  | 0 | 2014-02-15 02:25 | 2014-04-08 09:54 |  | 0 | 2014-04-09 09:54 | 2014-04-21 23:13 |  | 0 | 2014-04-22 23:13 | 2014-05-05 12:32 |  | 2 | 2014-05-08 12:32 | 2014-05-21 01:51 |  | 0 | 2014-05-22 01:51 | 2014-06-03 15:10 |  | v002 |  | 0.058933 |  | 14 | 0 | 0 | 0 | 2 | 0 | 16 | 12.3759 |  | 138.6316 | [15 empty] | N
Project-A03 |  | 0.5133 | 3.2763 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-02 04:06 |  | 0 | 2014-02-03 04:06 | 2014-02-11 09:53 |  | 0 | 2014-02-12 09:53 | 2014-02-19 21:26 |  | 1 | 2014-02-21 21:26 | 2014-03-01 08:58 |  | 1 | 2014-03-03 08:58 | 2014-03-10 20:31 |  | 1 | 2014-03-12 20:31 | 2014-03-20 08:04 |  | v003 |  | 0.026675 |  | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 0 |  | 77.3359 | [15 empty] | D
Project-A04 |  | 0.50919 | 1.567 |  |  |  | 2014-01-01 |  | 40 | 2014-02-11 | 2014-04-20 17:41 |  | 0 | 2014-04-21 17:41 | 2014-05-08 05:36 |  | 0 | 2014-05-09 05:36 | 2014-05-25 17:32 |  | 1 | 2014-05-27 17:32 | 2014-06-13 05:27 |  | 0 | 2014-06-14 05:27 | 2014-06-30 17:22 |  | 0 | 2014-07-01 17:22 | 2014-07-18 05:18 |  | v004 |  | 0.032878 |  | 40 | 0 | 0 | 1 | 0 | 0 | 41 | 19.727 |  | 157.2206
Project-A05 |  | 0.46825 | 1.5058 |  |  |  | 2014-01-01 |  | 46 | 2014-02-17 | 2014-03-01 19:32 |  | 0 | 2014-03-02 19:32 | 2014-04-24 22:37 |  | 0 | 2014-04-25 22:37 | 2014-05-08 16:39 |  | 0 | 2014-05-09 16:39 | 2014-05-22 10:40 |  | 0 | 2014-05-23 10:40 | 2014-06-05 04:41 |  | 1 | 2014-06-07 04:41 | 2014-06-19 22:42 |  | v002 |  | 0.05335 |  | 46 | 0 | 0 | 0 | 0 | 1 | 47 | 36.8114 |  | 122.9461 | [15 empty] | O
Project-A06 |  | 0.56363 | 1.4745 |  |  |  | 2014-01-01 |  | 363 | 2014-12-31 | 2015-04-02 06:13 |  | 0 | 2015-04-03 06:13 | 2015-05-03 02:24 |  | 0 | 2015-05-04 02:24 | 2015-05-26 05:49 |  | 364 | 2016-05-25 05:49 | 2016-06-16 09:13 |  | 0 | 2016-06-17 09:13 | 2016-07-09 12:38 |  | 1 | 2016-07-11 12:38 | 2016-08-02 16:03 |  | v003 |  | 0.059553 |  | 363 | 0 | 0 | 364 | 0 | 1 | 728 | 324.268 |  | 580.6686 | [15 empty] | F
Project-A07 |  | 0.54777 | 0.30366 |  |  |  | 2014-01-01 |  | 69 | 2014-03-12 | 2014-08-28 18:41 |  | 0 | 2014-08-29 18:41 | 2015-05-30 02:45 |  | 0 | 2015-05-31 02:45 | 2015-08-04 17:10 |  | 3 | 2015-08-08 17:10 | 2015-10-13 07:35 |  | 1 | 2015-10-15 07:35 | 2015-12-19 22:00 |  | 1 | 2015-12-21 22:00 | 2016-02-25 12:25 |  | v005 |  | 0.10918 |  | 69 | 0 | 0 | 3 | 1 | 1 | 74 | 113.0025 |  | 715.5175
Project-A08 |  | 0.46757 | 1.9394 |  |  |  | 2014-01-01 |  | 1 | 2014-01-03 | 2014-01-13 16:39 |  | 0 | 2014-01-14 16:39 | 2014-01-20 08:46 |  | 0 | 2014-01-21 08:46 | 2014-01-23 22:22 |  | 0 | 2014-01-24 22:22 | 2014-01-27 11:58 |  | 0 | 2014-01-28 11:58 | 2014-01-31 01:33 |  | 1 | 2014-02-02 01:33 | 2014-02-04 15:09 |  | v006 |  | 0.0099256 |  | 1 | 0 | 0 | 0 | 0 | 1 | 2 | 0.14888 |  | 32.6312 | [15 empty] | T
Project-A09 |  | 0.52379 | 0.28624 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-04-17 13:11 |  | 0 | 2014-04-18 13:11 | 2015-02-12 23:59 |  | 0 | 2015-02-13 23:59 | 2015-04-27 02:35 |  | 0 | 2015-04-28 02:35 | 2015-07-09 05:10 |  | 0 | 2015-07-10 05:10 | 2015-09-20 07:46 |  | 0 | 2015-09-21 07:46 | 2015-12-02 10:21 |  | v003 |  | 0.083747 |  | 12 | 0 | 0 | 0 | 0 | 0 | 12 | 15.0744 |  | 687.4313 | [15 empty] | H
Project-A10 |  | 0.51802 | 1.5261 |  |  |  | 2014-01-01 |  | 22 | 2014-01-24 | 2014-04-03 11:52 |  | 0 | 2014-04-04 11:52 | 2014-05-31 12:06 |  | 0 | 2014-06-01 12:06 | 2014-06-18 04:23 |  | 1 | 2014-06-20 04:23 | 2014-07-06 20:40 |  | 0 | 2014-07-07 20:40 | 2014-07-24 12:58 |  | 3 | 2014-07-28 12:58 | 2014-08-14 05:15 |  | v001 |  | 0.076303 |  | 22 | 0 | 0 | 1 | 0 | 3 | 26 | 25.1799 |  | 202.2188 | [15 empty] | I
Project-A11 |  | 0.25954 | 1.5252 |  |  |  | 2014-01-01 |  | 35 | 2014-02-06 | 2014-10-06 17:36 |  | 0 | 2014-10-07 17:36 | 2014-12-04 23:45 |  | 0 | 2014-12-05 23:45 | 2015-02-02 05:54 |  | 0 | 2015-02-03 05:54 | 2015-04-02 12:02 |  | 1 | 2015-04-04 12:02 | 2015-06-01 18:11 |  | 2 | 2015-06-04 18:11 | 2015-08-02 00:20 |  | v002 |  | 0.08871 |  | 35 | 0 | 0 | 0 | 1 | 2 | 38 | 46.5726 |  | 542.0138 | [15 empty] | S
Project-A12 |  | 0.51415 | 1.495 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-06-22 10:09 |  | 0 | 2014-06-23 10:09 | 2014-08-23 07:02 |  | 0 | 2014-08-24 07:02 | 2014-09-23 15:14 |  | 0 | 2014-09-24 15:14 | 2014-10-24 23:25 |  | 0 | 2014-10-25 23:25 | 2014-11-25 07:37 |  | 0 | 2014-11-26 07:37 | 2014-12-26 15:49 |  | v004 |  | 0.096774 |  | 45 | 0 | 0 | 0 | 0 | 0 | 45 | 65.3226 |  | 313.6588
Project-A13 |  | 0.51153 | 2.0428 |  |  |  | 2014-01-01 |  | 58 | 2014-03-01 | 2014-09-04 16:09 |  | 0 | 2014-09-05 16:09 | 2014-10-20 17:09 |  | 0 | 2014-10-21 17:09 | 2014-12-05 18:09 |  | 0 | 2014-12-06 18:09 | 2015-01-20 19:09 |  | 1 | 2015-01-22 19:09 | 2015-03-08 20:09 |  | 0 | 2015-03-09 20:09 | 2015-04-23 21:08 |  | v007 |  | 0.084367 |  | 58 | 0 | 0 | 0 | 1 | 0 | 59 | 73.3995 |  | 418.8808 | [15 empty] | W
Project-A14 |  | 0.52604 | 2.0412 |  |  |  | 2014-01-01 |  | 66 | 2014-03-09 | 2014-05-22 03:20 |  | 0 | 2014-05-23 03:20 | 2014-06-18 02:30 |  | 0 | 2014-06-19 02:30 | 2014-07-06 21:32 |  | 0 | 2014-07-07 21:32 | 2014-07-25 16:35 |  | 1 | 2014-07-27 16:35 | 2014-08-14 11:37 |  | 0 | 2014-08-15 11:37 | 2014-09-02 06:39 |  | v006 |  | 0.057072 |  | 66 | 0 | 0 | 0 | 1 | 0 | 67 | 56.5012 |  | 177.2774 | [15 empty] | O
Project-A15 |  | 1.025 | 1.985 |  |  |  | 2014-01-01 |  | 77 | 2014-03-20 | 2014-05-29 05:55 |  | 0 | 2014-05-30 05:55 | 2014-07-19 02:55 |  | 0 | 2014-07-20 02:55 | 2014-08-05 23:32 |  | 0 | 2014-08-06 23:32 | 2014-08-23 20:09 |  | 0 | 2014-08-24 20:09 | 2014-09-10 16:47 |  | 1 | 2014-09-12 16:47 | 2014-09-29 13:24 |  | v008 |  | 0.10608 |  | 77 | 0 | 0 | 0 | 0 | 1 | 78 | 122.5217 |  | 193.5583 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 56.6667 |  |  |  | 0 |  |  |  | 0 |  |  |  | 24.7333 |  |  |  | 0.53333 |  |  |  | 0.86667 | [5 empty] | 0.066667 |  | 56.6667 | 0 | 0 | 24.7333 | 0.53333 | 0.86667 | 82.8 | 60.84 | Average | 299.8124 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 850 |  |  |  | 0 |  |  |  | 0 |  |  |  | 371 |  |  |  | 8 |  |  |  | 13 | [5 empty] | 1 |  | 850 | 0 | 0 | 371 | 8 | 13 | 1242 | 912.5993 | Total | 4497.1863 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 0
| Days: | 0
E
N
SIT - Violation | Count: | 0 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 0
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-27 22:00 | 2014-04-08 17:41 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-09 09:54 | 2014-04-21 23:13 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-02-12 09:53 | 2014-02-19 21:26 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-09 05:36 | 2014-05-25 17:32 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-04-25 22:37 | 2014-05-08 16:39 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2015-05-04 02:24 | 2015-05-26 05:49 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-05-31 02:45 | 2015-08-04 17:10 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | W
Project-A08 | 2014-01-21 08:46 | 2014-01-23 22:22 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2015-02-13 23:59 | 2015-04-27 02:35 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | R
Project-A10 | 2014-06-01 12:06 | 2014-06-18 04:23 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-12-05 23:45 | 2015-02-02 05:54 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0 | S
Project-A12 | 2014-08-24 07:02 | 2014-09-23 15:14 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-21 17:09 | 2014-12-05 18:09 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-19 02:30 | 2014-07-06 21:32 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-20 02:55 | 2014-08-05 23:32 | v008 | [31 empty] | T
UAT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-10 17:41 | 2014-04-22 13:21 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-22 23:13 | 2014-05-05 12:32 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-02-21 21:26 | 2014-03-01 08:58 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-27 17:32 | 2014-06-13 05:27 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-09 16:39 | 2014-05-22 10:40 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2016-05-25 05:49 | 2016-06-16 09:13 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-08-08 17:10 | 2015-10-13 07:35 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-24 22:22 | 2014-01-27 11:58 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-04-28 02:35 | 2015-07-09 05:10 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-06-20 04:23 | 2014-07-06 20:40 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-02-03 05:54 | 2015-04-02 12:02 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-09-24 15:14 | 2014-10-24 23:25 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-06 18:09 | 2015-01-20 19:09 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-07 21:32 | 2014-07-25 16:35 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-06 23:32 | 2014-08-23 20:09 | v008
NFT - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-24 13:21 | 2014-05-06 09:01 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-08 12:32 | 2014-05-21 01:51 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-03 08:58 | 2014-03-10 20:31 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-14 05:27 | 2014-06-30 17:22 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-23 10:40 | 2014-06-05 04:41 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2016-06-17 09:13 | 2016-07-09 12:38 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-10-15 07:35 | 2015-12-19 22:00 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-01-28 11:58 | 2014-01-31 01:33 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-07-10 05:10 | 2015-09-20 07:46 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-07 20:40 | 2014-07-24 12:58 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-04-04 12:02 | 2015-06-01 18:11 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-10-25 23:25 | 2014-11-25 07:37 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-22 19:09 | 2015-03-08 20:09 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-27 16:35 | 2014-08-14 11:37 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-24 20:09 | 2014-09-10 16:47 | v008
Prod - Violation | Count: | 0 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 0
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-05-09 09:01 | 2014-05-21 04:41 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-22 01:51 | 2014-06-03 15:10 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-12 20:31 | 2014-03-20 08:04 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-07-01 17:22 | 2014-07-18 05:18 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-06-07 04:41 | 2014-06-19 22:42 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2016-07-11 12:38 | 2016-08-02 16:03 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A07 | 2015-12-21 22:00 | 2016-02-25 12:25 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A08 | 2014-02-02 01:33 | 2014-02-04 15:09 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2015-09-21 07:46 | 2015-12-02 10:21 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0
Project-A10 | 2014-07-28 12:58 | 2014-08-14 05:15 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2015-06-04 18:11 | 2015-08-02 00:20 | v002 |  | Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 0 | 0 | 0 | 0
Project-A12 | 2014-11-26 07:37 | 2014-12-26 15:49 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-09 20:09 | 2015-04-23 21:08 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-15 11:37 | 2014-09-02 06:39 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-12 16:47 | 2014-09-29 13:24 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.85517 | 85.5167 | 85
0.36575 | 36.5746 | 36
0.64704 | 64.7042 | 64
0.79273 | 79.2726 | 79
0.84656 | 84.6556 | 84
0.9751 | 97.5096 | 97
0.22148 | 22.1479 | 22
0.48947 | 48.9466 | 48
0.97106 | 97.1062 | 97
0.84504 | 84.5041 | 84
0.084312 | 8.4312 | 8
0.42349 | 42.3493 | 42
0.79184 | 79.1836 | 79
0.09585 | 9.585 | 9
0.10003 | 10.0025 | 10
0.54092 | 54.0918 | 54
0.16995 | 16.9948 | 16
0.34172 | 34.1716 | 34
0.98232 | 98.2315 | 98
0.54813 | 54.8131 | 54
0.83855 | 83.8552 | 83
0.020139 | 2.0139 | 2
0.88454 | 88.4538 | 88
0.11809 | 11.8095 | 11
0.20215 | 20.2152 | 20
0.49795 | 49.7951 | 49
0.18341 | 18.3405 | 18
0.08853 | 8.853 | 8
0.91885 | 91.8853 | 91
0.75344 | 75.3437 | 75
0.87271 | 87.2712 | 87
0.38508 | 38.508 | 38
0.058119 | 5.8119 | 5
0.84054 | 84.0544 | 84
0.58232 | 58.2318 | 58
0.36523 | 36.5228 | 36
0.71224 | 71.2238 | 71
0.81015 | 81.0152 | 81
0.58496 | 58.4955 | 58

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 1304.3209 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 60 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH