## Project Facts (User Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62 | 63
[9 empty] | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day) |  |  |  |  | Required Effort (Person-Day)
|  |  |  | Resource Allocation / Full Time Employee (FTEs) |  |  |  |  | Plan Phase | Plan Phase | Plan Total (Person-Day) | Plan Total (Calendar-Day) |  | Development Phase | Development Phase | Development Total (Person-Day) | Development Total (Calendar-Day) |  | SIT Phase | SIT Phase | SIT Total (Person-Day) | SIT Total (Calendar-Day) |  | UAT Phase | UAT Phase | UAT Total (Person-Day) | UAT Total (Calendar-Day) |  | NFT Phase | NFT Phase | NFT Total (Person-Day) | NFT Total (Calendar-Day) |  | Production Phase | Production Phase | Production Total (Person-Day) | Production Total (Calendar-Day) | [10 empty] | Benchmark Reference (Theoretically Perfect Project Make-Span without constraints)
Project Name |  | Code Base Version |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Knowledge Engineer | Software Engineer |  |  |  | Total Project Effort (Person-Days) | Total Project Span (Calendar-Days) | Project Cost (Total Project Effort x $500/Person-Day) |  | Project Priority |  | Total Project Effort - KE (Person-Days) | Total Project Effort - SE (Person-Days) |  | Perfect Project Span - KE (Calendar-Days) | Perfect Project Span - SE (Calendar-Days) | Perfect Project Span (Calendar-Days)
Project-A01 |  | v001 |  | 0.5 | 1.5 |  |  |  | 17 | 17.76 | 34.76 | 34 |  | 4.08 | 74 | 78.08 | 49.3333 |  | 4.08 | 17.76 | 21.84 | 11.84 |  | 4.08 | 17.76 | 21.84 | 11.84 |  | 4.08 | 17.76 | 21.84 | 11.84 |  | 4.08 | 17.76 | 21.84 | 11.84 |  | 200.2 | 130.6933 | 100100 |  | 0.056452 |  | 37.4 | 162.8 |  | 74.8 | 108.5333 | 108.5333
Project-A02 |  | v002 |  | 0.5 | 1.5 |  |  |  | 15 | 19.2 | 34.2 | 30 |  | 3.6 | 80 | 83.6 | 53.3333 |  | 3.6 | 19.2 | 22.8 | 12.8 |  | 3.6 | 19.2 | 22.8 | 12.8 |  | 3.6 | 19.2 | 22.8 | 12.8 |  | 3.6 | 19.2 | 22.8 | 12.8 |  | 209 | 134.5333 | 104500 |  | 0.058933 |  | 33 | 176 |  | 66 | 117.3333 | 117.3333 | [12 empty] | E
Project-A03 |  | v003 |  | 0.5 | 1.5 |  |  |  | 16 | 6.48 | 22.48 | 32 |  | 3.84 | 27 | 30.84 | 18 |  | 3.84 | 6.48 | 10.32 | 7.68 |  | 3.84 | 6.48 | 10.32 | 7.68 |  | 3.84 | 6.48 | 10.32 | 7.68 |  | 3.84 | 6.48 | 10.32 | 7.68 |  | 94.6 | 80.72 | 47300 |  | 0.026675 |  | 35.2 | 59.4 |  | 70.4 | 39.6 | 70.4 | [12 empty] | N
Project-A04 |  | v004 |  | 0.5 | 1.5 |  |  |  | 35 | 4.32 | 39.32 | 70 |  | 8.4 | 18 | 26.4 | 16.8 |  | 8.4 | 4.32 | 12.72 | 16.8 |  | 8.4 | 4.32 | 12.72 | 16.8 |  | 8.4 | 4.32 | 12.72 | 16.8 |  | 8.4 | 4.32 | 12.72 | 16.8 |  | 116.6 | 154 | 58300 |  | 0.032878 |  | 77 | 39.6 |  | 154 | 26.4 | 154 | [12 empty] | D
Project-A05 |  | v002 |  | 0.5 | 1.5 |  |  |  | 6 | 19.2 | 25.2 | 12.8 |  | 1.44 | 80 | 81.44 | 53.3333 |  | 1.44 | 19.2 | 20.64 | 12.8 |  | 1.44 | 19.2 | 20.64 | 12.8 |  | 1.44 | 19.2 | 20.64 | 12.8 |  | 1.44 | 19.2 | 20.64 | 12.8 |  | 189.2 | 117.3333 | 94600 |  | 0.05335 |  | 13.2 | 176 |  | 26.4 | 117.3333 | 117.3333
Project-A06 |  | v003 |  | 0.5 | 1.5 |  |  |  | 52 | 10.56 | 62.56 | 104 |  | 12.48 | 44 | 56.48 | 29.3333 |  | 12.48 | 10.56 | 23.04 | 24.96 |  | 12.48 | 10.56 | 23.04 | 24.96 |  | 12.48 | 10.56 | 23.04 | 24.96 |  | 12.48 | 10.56 | 23.04 | 24.96 |  | 211.2 | 233.1733 | 105600 |  | 0.059553 |  | 114.4 | 96.8 |  | 228.8 | 64.5333 | 228.8 | [12 empty] | O
Project-A07 |  | v005 |  | 0.5 | 1.5 |  |  |  | 93 | 19.92 | 112.92 | 186 |  | 22.32 | 83 | 105.32 | 55.3333 |  | 22.32 | 19.92 | 42.24 | 44.64 |  | 22.32 | 19.92 | 42.24 | 44.64 |  | 22.32 | 19.92 | 42.24 | 44.64 |  | 22.32 | 19.92 | 42.24 | 44.64 |  | 387.2 | 419.8933 | 193600 |  | 0.10918 |  | 204.6 | 182.6 |  | 409.2 | 121.7333 | 409.2 | [12 empty] | F
Project-A08 |  | v006 |  | 0.5 | 1.5 |  |  |  | 5 | 2.64 | 7.64 | 10 |  | 1.2 | 11 | 12.2 | 7.3333 |  | 1.2 | 2.64 | 3.84 | 2.4 |  | 1.2 | 2.64 | 3.84 | 2.4 |  | 1.2 | 2.64 | 3.84 | 2.4 |  | 1.2 | 2.64 | 3.84 | 2.4 |  | 35.2 | 26.9333 | 17600 |  | 0.0099256 |  | 11 | 24.2 |  | 22 | 16.1333 | 22
Project-A09 |  | v003 |  | 0.5 | 1.5 |  |  |  | 49 | 20.64 | 69.64 | 98 |  | 11.76 | 86 | 97.76 | 57.3333 |  | 11.76 | 20.64 | 32.4 | 23.52 |  | 11.76 | 20.64 | 32.4 | 23.52 |  | 11.76 | 20.64 | 32.4 | 23.52 |  | 11.76 | 20.64 | 32.4 | 23.52 |  | 297 | 249.4133 | 148500 |  | 0.083747 |  | 107.8 | 189.2 |  | 215.6 | 126.1333 | 215.6 | [12 empty] | T
Project-A10 |  | v001 |  | 0.5 | 1.5 |  |  |  | 36 | 20.88 | 56.88 | 72 |  | 8.64 | 87 | 95.64 | 58 |  | 8.64 | 20.88 | 29.52 | 17.28 |  | 8.64 | 20.88 | 29.52 | 17.28 |  | 8.64 | 20.88 | 29.52 | 17.28 |  | 8.64 | 20.88 | 29.52 | 17.28 |  | 270.6 | 199.12 | 135300 |  | 0.076303 |  | 79.2 | 191.4 |  | 158.4 | 127.6 | 158.4 | [12 empty] | H
Project-A11 |  | v002 |  | 0.5 | 1.5 |  |  |  | 63 | 19.2 | 82.2 | 126 |  | 15.12 | 80 | 95.12 | 53.3333 |  | 15.12 | 19.2 | 34.32 | 30.24 |  | 15.12 | 19.2 | 34.32 | 30.24 |  | 15.12 | 19.2 | 34.32 | 30.24 |  | 15.12 | 19.2 | 34.32 | 30.24 |  | 314.6 | 300.2933 | 157300 |  | 0.08871 |  | 138.6 | 176 |  | 277.2 | 117.3333 | 277.2 | [12 empty] | I
Project-A12 |  | v004 |  | 0.5 | 1.5 |  |  |  | 65 | 21.84 | 86.84 | 130 |  | 15.6 | 91 | 106.6 | 60.6667 |  | 15.6 | 21.84 | 37.44 | 31.2 |  | 15.6 | 21.84 | 37.44 | 31.2 |  | 15.6 | 21.84 | 37.44 | 31.2 |  | 15.6 | 21.84 | 37.44 | 31.2 |  | 343.2 | 315.4667 | 171600 |  | 0.096774 |  | 143 | 200.2 |  | 286 | 133.4667 | 286 | [12 empty] | S
Project-A13 |  | v007 |  | 0.5 | 2 |  |  |  | 96 | 9.6 | 105.6 | 192 |  | 23.04 | 40 | 63.04 | 46.08 |  | 23.04 | 9.6 | 32.64 | 46.08 |  | 23.04 | 9.6 | 32.64 | 46.08 |  | 23.04 | 9.6 | 32.64 | 46.08 |  | 23.04 | 9.6 | 32.64 | 46.08 |  | 299.2 | 422.4 | 149600 |  | 0.084367 |  | 211.2 | 88 |  | 422.4 | 44 | 422.4
Project-A14 |  | v006 |  | 0.5 | 2 |  |  |  | 39 | 12.72 | 51.72 | 78 |  | 9.36 | 53 | 62.36 | 26.5 |  | 9.36 | 12.72 | 22.08 | 18.72 |  | 9.36 | 12.72 | 22.08 | 18.72 |  | 9.36 | 12.72 | 22.08 | 18.72 |  | 9.36 | 12.72 | 22.08 | 18.72 |  | 202.4 | 179.38 | 101200 |  | 0.057072 |  | 85.8 | 116.6 |  | 171.6 | 58.3 | 171.6 | [12 empty] | W
Project-A15 |  | v008 |  | 1 | 2 |  |  |  | 72 | 23.76 | 95.76 | 72 |  | 17.28 | 99 | 116.28 | 49.5 |  | 17.28 | 23.76 | 41.04 | 17.28 |  | 17.28 | 23.76 | 41.04 | 17.28 |  | 17.28 | 23.76 | 41.04 | 17.28 |  | 17.28 | 23.76 | 41.04 | 17.28 |  | 376.2 | 190.62 | 188100 |  | 0.10608 |  | 158.4 | 217.8 |  | 158.4 | 108.9 | 158.4 | [12 empty] | O
R
K
|  | Average |  | 0.53333 | 1.6 |  |  |  | 43.9333 | 15.248 | 59.1813 | 83.12 |  | 10.544 | 63.5333 | 74.0773 | 42.2809 |  | 10.544 | 15.248 | 25.792 | 21.216 |  | 10.544 | 15.248 | 25.792 | 21.216 |  | 10.544 | 15.248 | 25.792 | 21.216 |  | 10.544 | 15.248 | 25.792 | 21.216 |  | 236.4267 | 210.2649 | 118213.3333 |  | 0.066667 |  | 96.6533 | 139.7733 | Average | 182.7467 | 88.4889 | 194.48 | [12 empty] | S
|  | Total |  | 8 | 24 |  |  |  | 659 | 228.72 | 887.72 | 1246.8 |  | 158.16 | 953 | 1111.16 | 634.2133 |  | 158.16 | 228.72 | 386.88 | 318.24 |  | 158.16 | 228.72 | 386.88 | 318.24 |  | 158.16 | 228.72 | 386.88 | 318.24 |  | 158.16 | 228.72 | 386.88 | 318.24 |  | 3546.4 | 3153.9733 | 1773200 |  | 1 |  | 1449.8 | 2096.6 | Total | 2741.2 | 1327.3333 | 2917.2 | [12 empty] | H
E
|  | Available FTE |  | 8 | 24 | [57 empty] | E
T
|  | END | OF | THIS | WORKSHEET
Note on N11: KE and SE can work in paralled. Thus use MAX()
Note on AS12: Priority = Individual Project Cost / Total Project Cost

## Project Release Optimizer (GA)
Legend: |  | Fitness Control Dashboard
Chromosome |  | Fitness Breakdown |  | Fitness Priority | Formula |  | Value | [6 empty] | Benchmark
Constraint (Hard) |  | Proj Make-Span (Overall) |  | Medium | =AW15 |  | 492.8933 |  | <- To shorten entire projects span (ALL projects) |  |  |  |  | Perfect AVG Project Span
Constraint (Soft) |  | Average Proj Make-Span (Individual) |  | Medium | =AV32 |  | 216.7316 |  | <- To shorten average individual project span |  |  |  | <----------> | 194.48
Fitness |  | Priority-Weighted Plan-Lead |  | Low | =AT32 |  | 43.2171 |  | <- To schedule important projects to start earlier
User Inputs |  | Code-Base Violation x Weight |  | High | ='Code Base Violation Constraint'!E13*20 |  | 15195.3333 |  | <- Heuristic Weight (Hard -> Soft constraint): |  |  | 50
Formula |  | Integrated Fitness - To Min() |  | N.A. | =SUM(I4:I7) |  | 15948.1753 |  | <- To Minimize
|  | Code-Base constraint satisfied ? |  | FALSE
Vlookup Index | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 38 | 39 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60 | 61 | 62
|  | Resource Allocation / Full Time Employee (FTEs) | [7 empty] | Plan Phase (Calendar-Day) |  |  |  | Development Phase (Calendar-Day) |  |  |  | SIT Phase (Calendar-Day) |  |  |  | UAT Phase (Calendar-Day) |  |  |  | NFT Phase (Calendar-Day) |  |  |  | Prod Phase (Calendar-Day) | [6 empty] | Fitness - Lead / Idle Time (Days) prior to: | [8 empty] | Fitness - Project Make-Sapn (Days) (Without Plan-Lead) |  |  | Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name |  | Knowledge Engineer | Software Engineer | Project Manager (Future work) | Admin (Future work) |  | Initial Date |  | Lead prior to Plan (Calendar-Day) | Start Date | End Date |  | Lead prior to Development (Calendar-Day) | Start Date | End Date |  | Lead prior to SIT (Calendar-Day) | Start Date | End Date |  | Lead prior to UAT (Calendar-Day) | Start Date | End Date |  | Lead prior to NFT (Calendar-Day) | Start Date | End Date |  | Lead prior to Prod (Calendar-Day) | Start Date | End Date |  | Code Base Version |  | Project Priority |  | Plan | Development | SIT | UAT | NFT | Prod | Total | Priority-Weighted Plan-Lead |  | Individual | Overall |  | Refer to worksheet: Code Base Violation Constraint
Project-A01 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 0 | 2014-01-02 | 2014-02-05 |  | 0 | 2014-02-06 | 2014-03-27 08:00 |  | 0 | 2014-03-28 08:00 | 2014-04-09 04:10 |  | 0 | 2014-04-10 04:10 | 2014-04-22 00:19 |  | 1 | 2014-04-24 00:19 | 2014-05-05 20:29 |  | 0 | 2014-05-06 20:29 | 2014-05-18 16:38 |  | v001 |  | 0.056452 |  | 0 | 0 | 0 | 0 | 1 | 0 | 1 | 0 |  | 136.6933 | 492.8933 | [14 empty] | E
Project-A02 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-02-13 |  | 0 | 2014-02-14 | 2014-04-08 08:00 |  | 0 | 2014-04-09 08:00 | 2014-04-22 03:12 |  | 1 | 2014-04-24 03:12 | 2014-05-06 22:24 |  | 0 | 2014-05-07 22:24 | 2014-05-20 17:36 |  | 1 | 2014-05-22 17:36 | 2014-06-04 12:48 |  | v002 |  | 0.058933 |  | 12 | 0 | 0 | 1 | 0 | 1 | 14 | 10.6079 |  | 141.5333 | [15 empty] | N
Project-A03 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-02-26 |  | 0 | 2014-02-27 | 2014-03-17 |  | 0 | 2014-03-18 | 2014-03-25 16:19 |  | 0 | 2014-03-26 16:19 | 2014-04-03 08:38 |  | 1 | 2014-04-05 08:38 | 2014-04-13 00:58 |  | 0 | 2014-04-14 00:58 | 2014-04-21 17:17 |  | v003 |  | 0.026675 |  | 23 | 0 | 0 | 0 | 1 | 0 | 24 | 9.2029 |  | 86.72 | [15 empty] | D
Project-A04 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-04-16 |  | 0 | 2014-04-17 | 2014-05-03 19:12 |  | 0 | 2014-05-04 19:12 | 2014-05-21 14:24 |  | 1 | 2014-05-23 14:24 | 2014-06-09 09:36 |  | 0 | 2014-06-10 09:36 | 2014-06-27 04:48 |  | 1 | 2014-06-29 04:48 | 2014-07-16 |  | v004 |  | 0.032878 |  | 34 | 0 | 0 | 1 | 0 | 1 | 36 | 16.768 |  | 161
Project-A05 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-02-28 19:12 |  | 0 | 2014-03-01 19:12 | 2014-04-24 03:12 |  | 0 | 2014-04-25 03:12 | 2014-05-07 22:24 |  | 0 | 2014-05-08 22:24 | 2014-05-21 17:36 |  | 1 | 2014-05-23 17:36 | 2014-06-05 12:48 |  | 0 | 2014-06-06 12:48 | 2014-06-19 08:00 |  | v002 |  | 0.05335 |  | 45 | 0 | 0 | 0 | 1 | 0 | 46 | 36.0112 |  | 123.3333 | [15 empty] | O
Project-A06 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-06-11 |  | 0 | 2014-06-12 | 2014-07-11 08:00 |  | 0 | 2014-07-12 08:00 | 2014-08-06 07:02 |  | 1 | 2014-08-08 07:02 | 2014-09-02 06:05 |  | 0 | 2014-09-03 06:05 | 2014-09-28 05:07 |  | 1 | 2014-09-30 05:07 | 2014-10-25 04:10 |  | v003 |  | 0.059553 |  | 56 | 0 | 0 | 1 | 0 | 1 | 58 | 50.0248 |  | 240.1733 | [15 empty] | F
Project-A07 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-09-12 |  | 0 | 2014-09-13 | 2014-11-07 08:00 |  | 0 | 2014-11-08 08:00 | 2014-12-22 23:22 |  | 0 | 2014-12-23 23:22 | 2015-02-06 14:43 |  | 1 | 2015-02-08 14:43 | 2015-03-25 06:05 |  | 0 | 2015-03-26 06:05 | 2015-05-09 21:26 |  | v005 |  | 0.10918 |  | 67 | 0 | 0 | 0 | 1 | 0 | 68 | 109.727 |  | 425.8933
Project-A08 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-03-31 |  | 0 | 2014-04-01 | 2014-04-08 08:00 |  | 0 | 2014-04-09 08:00 | 2014-04-11 17:36 |  | 1 | 2014-04-13 17:36 | 2014-04-16 03:12 |  | 0 | 2014-04-17 03:12 | 2014-04-19 12:48 |  | 1 | 2014-04-21 12:48 | 2014-04-23 22:24 |  | v006 |  | 0.0099256 |  | 78 | 0 | 0 | 1 | 0 | 1 | 80 | 11.6129 |  | 33.9333 | [15 empty] | T
Project-A09 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 12 | 2014-01-14 | 2014-04-22 |  | 0 | 2014-04-23 | 2014-06-19 08:00 |  | 0 | 2014-06-20 08:00 | 2014-07-13 20:29 |  | 0 | 2014-07-14 20:29 | 2014-08-07 08:58 |  | 1 | 2014-08-09 08:58 | 2014-09-01 21:26 |  | 0 | 2014-09-02 21:26 | 2014-09-26 09:55 |  | v003 |  | 0.083747 |  | 12 | 0 | 0 | 0 | 1 | 0 | 13 | 15.0744 |  | 255.4133 | [15 empty] | H
Project-A10 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 23 | 2014-01-25 | 2014-04-07 |  | 0 | 2014-04-08 | 2014-06-05 |  | 0 | 2014-06-06 | 2014-06-23 06:43 |  | 1 | 2014-06-25 06:43 | 2014-07-12 13:26 |  | 0 | 2014-07-13 13:26 | 2014-07-30 20:10 |  | 1 | 2014-08-01 20:10 | 2014-08-19 02:53 |  | v001 |  | 0.076303 |  | 23 | 0 | 0 | 1 | 0 | 1 | 25 | 26.3244 |  | 206.12 | [15 empty] | I
Project-A11 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 34 | 2014-02-05 | 2014-06-11 |  | 0 | 2014-06-12 | 2014-08-04 08:00 |  | 0 | 2014-08-05 08:00 | 2014-09-04 13:46 |  | 0 | 2014-09-05 13:46 | 2014-10-05 19:31 |  | 1 | 2014-10-07 19:31 | 2014-11-07 01:17 |  | 0 | 2014-11-08 01:17 | 2014-12-08 07:02 |  | v002 |  | 0.08871 |  | 34 | 0 | 0 | 0 | 1 | 0 | 35 | 45.2419 |  | 306.2933 | [15 empty] | S
Project-A12 |  | 0.5 | 1.5 |  |  |  | 2014-01-01 |  | 45 | 2014-02-16 | 2014-06-26 |  | 0 | 2014-06-27 | 2014-08-26 16:00 |  | 0 | 2014-08-27 16:00 | 2014-09-27 20:48 |  | 1 | 2014-09-29 20:48 | 2014-10-31 01:36 |  | 0 | 2014-11-01 01:36 | 2014-12-02 06:24 |  | 1 | 2014-12-04 06:24 | 2015-01-04 11:12 |  | v004 |  | 0.096774 |  | 45 | 0 | 0 | 1 | 0 | 1 | 47 | 65.3226 |  | 322.4667
Project-A13 |  | 0.5 | 2 |  |  |  | 2014-01-01 |  | 56 | 2014-02-27 | 2014-09-07 |  | 0 | 2014-09-08 | 2014-10-24 01:55 |  | 0 | 2014-10-25 01:55 | 2014-12-10 03:50 |  | 0 | 2014-12-11 03:50 | 2015-01-26 05:46 |  | 1 | 2015-01-28 05:46 | 2015-03-15 07:41 |  | 0 | 2015-03-16 07:41 | 2015-05-01 09:36 |  | v007 |  | 0.084367 |  | 56 | 0 | 0 | 0 | 1 | 0 | 57 | 70.8685 |  | 428.4 | [15 empty] | W
Project-A14 |  | 0.5 | 2 |  |  |  | 2014-01-01 |  | 67 | 2014-03-10 | 2014-05-27 |  | 0 | 2014-05-28 | 2014-06-23 12:00 |  | 0 | 2014-06-24 12:00 | 2014-07-13 05:17 |  | 1 | 2014-07-15 05:17 | 2014-08-02 22:34 |  | 0 | 2014-08-03 22:34 | 2014-08-22 15:50 |  | 1 | 2014-08-24 15:50 | 2014-09-12 09:07 |  | v006 |  | 0.057072 |  | 67 | 0 | 0 | 1 | 0 | 1 | 69 | 57.3573 |  | 186.38 | [15 empty] | O
Project-A15 |  | 1 | 2 |  |  |  | 2014-01-01 |  | 78 | 2014-03-21 | 2014-06-01 |  | 0 | 2014-06-02 | 2014-07-21 12:00 |  | 0 | 2014-07-22 12:00 | 2014-08-08 18:43 |  | 0 | 2014-08-09 18:43 | 2014-08-27 01:26 |  | 1 | 2014-08-29 01:26 | 2014-09-15 08:10 |  | 0 | 2014-09-16 08:10 | 2014-10-03 14:53 |  | v008 |  | 0.10608 |  | 78 | 0 | 0 | 0 | 1 | 0 | 79 | 124.1129 |  | 196.62 | [15 empty] | R
K
S
Average |  | 0.53333 | 1.6 | [5 empty] | 42 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0.46667 |  |  |  | 0.53333 |  |  |  | 0.46667 | [5 empty] | 0.066667 |  | 42 | 0 | 0 | 0.46667 | 0.53333 | 0.46667 | 43.4667 | 43.2171 | Average | 216.7316 | [15 empty] | H
Total |  | 8 | 24 | [5 empty] | 630 |  |  |  | 0 |  |  |  | 0 |  |  |  | 7 |  |  |  | 8 |  |  |  | 7 | [5 empty] | 1 |  | 630 | 0 | 0 | 7 | 8 | 7 | 652 | 648.2568 | Total | 3250.9733 | [15 empty] | E
|  | <= | <= | [58 empty] | E
Available FTE |  | 8 | 24 | [31 empty] | Priority Factor | [26 empty] | T
15
|  | END | OF | THIS | WORKSHEET
Note on O14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on S14: Fixed to '0', because Code-Base Violation is not possible prior to this project phase.
Note on AT14: Value = Project Priority x Plan-Lead x Priority Factor To Min() This is for scheduling important Project to start earlier.
Note on E15: GA setting: 0.25 <= FTE <= 5 One resource can be assigned to max 4 projects. Any project can be assigned max 5 FTE for each type of recourse.
Note on K15: GA setting: 0 <= Lead <= 365 Integer

## Code Base Violation Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula
Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.
Total - Violation (SIT/UAT/NFT/Prod) | Count: | 26
| Days: | 303.9067
E
N
SIT - Violation | Count: | 10 |  |  | Compare Roll Project against Column Project, to check violation. | [29 empty] | D
| Days: | 87.6533
[5 empty] | Count | [14 empty] | Days (Overlap) simplified rough formula | [14 empty] | O
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | F
Project-A01 | 2014-03-28 08:00 | 2014-04-09 04:10 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-09 08:00 | 2014-04-22 03:12 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 2.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | T
Project-A03 | 2014-03-18 | 2014-03-25 16:19 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | H
Project-A04 | 2014-05-04 19:12 | 2014-05-21 14:24 | v004 | [5 empty] | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 3.1333 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | I
Project-A05 | 2014-04-25 03:12 | 2014-05-07 22:24 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | S
Project-A06 | 2014-07-12 08:00 | 2014-08-06 07:02 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0.96 | 0 | 0 | 0.88667 | 14.7933
Project-A07 | 2014-11-08 08:00 | 2014-12-22 23:22 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 1; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 31.8267 | 0 | 0 | W
Project-A08 | 2014-04-09 08:00 | 2014-04-11 17:36 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | O
Project-A09 | 2014-06-20 08:00 | 2014-07-13 20:29 | v003 |  | Count P-A10: 1; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [9 empty] | 2.9467 | 0 | 0 | 0 | 19.3533 | 0 | R
Project-A10 | 2014-06-06 | 2014-06-23 06:43 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0 | K
Project-A11 | 2014-08-05 08:00 | 2014-09-04 13:46 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 1 | [11 empty] | 7.9067 | 0 | 0 | 3.4467 | S
Project-A12 | 2014-08-27 16:00 | 2014-09-27 20:48 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0 | H
Project-A13 | 2014-10-25 01:55 | 2014-12-10 03:50 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0 | E
Project-A14 | 2014-06-24 12:00 | 2014-07-13 05:17 | v006 |  | Count P-A15: 0 | [14 empty] | 0 | E
Project-A15 | 2014-07-22 12:00 | 2014-08-08 18:43 | v008 | [31 empty] | T
UAT - Violation | Count: | 5 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 83.0267
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-10 04:10 | 2014-04-22 00:19 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 5.96 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-04-24 03:12 | 2014-05-06 22:24 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-03-26 16:19 | 2014-04-03 08:38 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-05-23 14:24 | 2014-06-09 09:36 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-08 22:24 | 2014-05-21 17:36 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-08-08 07:02 | 2014-09-02 06:05 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 18.7667
Project-A07 | 2014-12-23 23:22 | 2015-02-06 14:43 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 1; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 33.2667 | 0 | 0
Project-A08 | 2014-04-13 17:36 | 2014-04-16 03:12 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-07-14 20:29 | 2014-08-07 08:58 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 0 | [9 empty] | 0 | 0 | 0 | 0 | 19.0867 | 0
Project-A10 | 2014-06-25 06:43 | 2014-07-12 13:26 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-09-05 13:46 | 2014-10-05 19:31 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 5.9467 | 0 | 0 | 0
Project-A12 | 2014-09-29 20:48 | 2014-10-31 01:36 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2014-12-11 03:50 | 2015-01-26 05:46 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-07-15 05:17 | 2014-08-02 22:34 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-09 18:43 | 2014-08-27 01:26 | v008
NFT - Violation | Count: | 5 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 69.9
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-04-24 00:19 | 2014-05-05 20:29 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-07 22:24 | 2014-05-20 17:36 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-04-05 08:38 | 2014-04-13 00:58 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-10 09:36 | 2014-06-27 04:48 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-05-23 17:36 | 2014-06-05 12:48 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-03 06:05 | 2014-09-28 05:07 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.0867
Project-A07 | 2015-02-08 14:43 | 2015-03-25 06:05 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 1; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 34.7067 | 0 | 0
Project-A08 | 2014-04-17 03:12 | 2014-04-19 12:48 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-08-09 08:58 | 2014-09-01 21:26 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 1 | [9 empty] | 0 | 0 | 0 | 0 | 13.2867 | 3.8333
Project-A10 | 2014-07-13 13:26 | 2014-07-30 20:10 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-10-07 19:31 | 2014-11-07 01:17 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 5.9867 | 0 | 0 | 0
Project-A12 | 2014-11-01 01:36 | 2014-12-02 06:24 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-01-28 05:46 | 2015-03-15 07:41 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-03 22:34 | 2014-08-22 15:50 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-08-29 01:26 | 2014-09-15 08:10 | v008
Prod - Violation | Count: | 6 |  |  | Count P-A01: Compare Roll Project against Column Project, to check violation.
| Days: | 63.3267
[5 empty] | Count P-A01: Count | Days (Overlap) simplified rough formula
Project Name | Start Date | End Date | Code Base Version |  | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15 | P-A01 | P-A02 | P-A03 | P-A04 | P-A05 | P-A06 | P-A07 | P-A08 | P-A09 | P-A10 | P-A11 | P-A12 | P-A13 | P-A14 | P-A15
Project-A01 | 2014-05-06 20:29 | 2014-05-18 16:38 | v001 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A02 | 2014-05-22 17:36 | 2014-06-04 12:48 | v002 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A03 | 2014-04-14 00:58 | 2014-04-21 17:17 | v003 |  |  |  |  | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0.18667 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A04 | 2014-06-29 04:48 | 2014-07-16 | v004 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A05 | 2014-06-06 12:48 | 2014-06-19 08:00 | v002 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A06 | 2014-09-30 05:07 | 2014-10-25 04:10 | v003 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | [6 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3.4067
Project-A07 | 2015-03-26 06:05 | 2015-05-09 21:26 | v005 |  | Count P-A08: 0; Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 1; Count P-A14: 0; Count P-A15: 0 | [7 empty] | 0 | 0 | 0 | 0 | 0 | 36.1467 | 0 | 0
Project-A08 | 2014-04-21 12:48 | 2014-04-23 22:24 | v006 |  | Count P-A09: 0; Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0
Project-A09 | 2014-09-02 21:26 | 2014-09-26 09:55 | v003 |  | Count P-A10: 0; Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 1; Count P-A15: 1 | [9 empty] | 0 | 0 | 0 | 0 | 9.4867 | 10.0733
Project-A10 | 2014-08-01 20:10 | 2014-08-19 02:53 | v001 |  | Count P-A11: 0; Count P-A12: 0; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [10 empty] | 0 | 0 | 0 | 0 | 0
Project-A11 | 2014-11-08 01:17 | 2014-12-08 07:02 | v002 |  | Count P-A12: 1; Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [11 empty] | 4.0267 | 0 | 0 | 0
Project-A12 | 2014-12-04 06:24 | 2015-01-04 11:12 | v004 |  | Count P-A13: 0; Count P-A14: 0; Count P-A15: 0 | [12 empty] | 0 | 0 | 0
Project-A13 | 2015-03-16 07:41 | 2015-05-01 09:36 | v007 |  | Count P-A14: 0; Count P-A15: 0 | [13 empty] | 0 | 0
Project-A14 | 2014-08-24 15:50 | 2014-09-12 09:07 | v006 |  | Count P-A15: 0 | [14 empty] | 0
Project-A15 | 2014-09-16 08:10 | 2014-10-03 14:53 | v008
| END | OF | THIS | WORKSHEET

## Random Number
Random | x100 | Interger
0.014696 | 1.4696 | 1
0.20005 | 20.0051 | 20
0.84112 | 84.1117 | 84
0.31243 | 31.2431 | 31
0.74579 | 74.5788 | 74
0.0020077 | 0.20077 | 0
0.038637 | 3.8637 | 3
0.17749 | 17.7488 | 17
0.89913 | 89.9132 | 89
0.2879 | 28.7896 | 28
0.20415 | 20.4149 | 20
0.67462 | 67.4616 | 67
0.0016092 | 0.16092 | 0
0.93623 | 93.6232 | 93
0.55896 | 55.8963 | 55
0.67748 | 67.7481 | 67
0.37844 | 37.8442 | 37
0.97583 | 97.5829 | 97
0.3013 | 30.1299 | 30
0.33446 | 33.4461 | 33
0.94533 | 94.5329 | 94
0.54711 | 54.7109 | 54
0.41839 | 41.8386 | 41
0.7183 | 71.8301 | 71
0.38818 | 38.8183 | 38
0.92958 | 92.9583 | 92
0.0047333 | 0.47333 | 0
0.5776 | 57.7601 | 57
0.30714 | 30.7139 | 30
0.19077 | 19.0774 | 19
0.45325 | 45.3246 | 45
0.76771 | 76.7708 | 76
0.45528 | 45.5281 | 45
0.42547 | 42.5474 | 42
0.18395 | 18.3949 | 18
0.47147 | 47.1466 | 47
0.71536 | 71.5355 | 71
0.35448 | 35.4484 | 35
0.0059069 | 0.59069 | 0

## _PalUtilTempWorksheet (hidden)
0

## ev_HiddenInfo (hidden)
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize | 15948.1753 |  |  |  | MACROS |  |  | Compatibility with Old Versions (4 trips pre-v5 versions) | 4 |  | RISKOpt Tag | TRUE | Out. Stats
Goal (Type, Target Value) | 1 | 0 |  |  | Start (enabled, macro) | FALSE |  | Formula Conversion Cell (not used in v5) |  |  | #Iterations (Sim Stopping) |  | Mean | Creation Version | 5.5.0 | Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count) | FALSE | 5000000000000 |  |  | Before Recalc (enabled, macro) | FALSE |  | Number Formatting Cell (introduced in v5) | 365 |  | Sim. Stopping Mode, Tolerance |  | Std. Dev. | Required Version | 5.0.0 | Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count) | TRUE | 10 | 2 |  | After Recalc (enabled, macro) | FALSE |  |  |  |  | Same Seed Each Simulation |  | Min | Recommended Version | 4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent) | FALSE | 1000000000 | 1e-10 | TRUE | After Storage (enabled, macro) | FALSE |  |  |  |  | Sampling Type |  | Max | Last Modified by Version | 5.5.0
Formula Stopping (enabled, formula) | FALSE | 0 |  |  | Finish (enabled, macro) | FALSE |  |  |  |  | Macro Before Simulation (enabled, macro)
Population Size | 500 | [9 empty] | Macro After Simulation (enabled, macro)
UNUSED | UNUSED |  |  |  | Seed (Is Auto, Value) | TRUE | 1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5) | 3 |  |  |  | Minimize Excel on Startup | FALSE
Stop on Errors (before v5: Pause on Errors) | FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting) | FALSE
Ev4/RO1: Graph Progress | FALSE |  |  |  | Show Excel Recalcs (replaces "Update Display" used before v5) | 2
# Chromosomes | 1 | [21 empty] | # Constraints | 2
Method + #Operators | Mutation Rate | Crossover Rate | Description | # Time Blocks/All Groups Must Be Present | Constraint Range | #Ranges | Adj. Range | Min Val or Range | Max Val Or Range | Flags | [6 empty] | HARD CONSTRAINT DEV | CONSTRAINT SOLVER | ROFUNC | RISKOPT | SOFT CONSTRAINT DEV | EVAL (True/False or penalty) | Type (Hard/Soft) | Entry Mode | Formula | Description | Left Val Or Range | Left Operator | Constrained Cells | Right Operator | Right Val Or Range | Penalty Function | RO Eval Time (Iter/Sim) | RO Statistic to Constrain | RO Statistic Parameter
RECIPE11 | 0.5 | 0.5 |  |  |  | 2 | #VALUE! | 0.25 | 5 | False,False,False | [12 empty] | 2 | 1 |  | Max 8 KE FTEs | 0 | 6 | 8 | 2 | 8
DEFAULT PARENT SELECTION | [6 empty] | #VALUE! | 0 | 365 | True,False,False | [12 empty] | 2 | 1 |  | Max 24 SE FTEs | 0 | 6 | 24 | 2 | 24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH