## Read_Me
GU Zhan (Sam)
17 March 2019
Convert to NLP-Solver to support iss-vm

## Project_Facts_(User_Inputs)
Legend:
Chromosome
Constraint-Hard
Constraint-Soft
Fitness
User Inputs
Formula

Vlookup Index	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	47	48	49	50	51	52	53	54	55	56	57	58	59	60	61	62	63
					Required Effort (Person-Day)					Required Effort (Person-Day)					Required Effort (Person-Day)					Required Effort (Person-Day)					Required Effort (Person-Day)					Required Effort (Person-Day)
				Resource Allocation / Full Time Employee (FTEs)					Plan Phase	Plan Phase	Plan Total / (Person-Day)	Plan Total / (Calendar-Day)		Development Phase	Development Phase	Development Total / (Person-Day)	Development Total / (Calendar-Day)		SIT Phase	SIT Phase	SIT Total / (Person-Day)	SIT Total / (Calendar-Day)		UAT Phase	UAT Phase	UAT Total / (Person-Day)	UAT Total / (Calendar-Day)		NFT Phase	NFT Phase	NFT Total / (Person-Day)	NFT Total / (Calendar-Day)		Production Phase	Production Phase	Production Total / (Person-Day)	Production Total / (Calendar-Day)					Benchmark Reference / (Theoretically Perfect Project Make-Span without constraints)
Project Name		Code Base Version		Knowledge / Engineer	Software / Engineer	Project Manager / (Future work)	Admin / (Future work)		Knowledge / Engineer	Software / Engineer				Knowledge / Engineer	Software / Engineer				Knowledge / Engineer	Software / Engineer				Knowledge / Engineer	Software / Engineer				Knowledge / Engineer	Software / Engineer				Knowledge / Engineer	Software / Engineer				Total Project Effort / (Person-Days)	Total Project Span / (Calendar-Days)	Project Cost / (Total Project Effort x $500/Person-Day)		Project Priority		Total Project Effort - KE / (Person-Days)	Total Project Effort - SE / (Person-Days)		Perfect Project Span - KE / (Calendar-Days)	Perfect Project Span - SE / (Calendar-Days)	Perfect Project Span / (Calendar-Days)
Project-A01		v001		0.33	1.22				17.00	17.76	34.76	51.92		4.08	74.00	78.08	60.58		4.08	17.76	21.84	14.54		4.08	17.76	21.84	14.54		4.08	17.76	21.84	14.54		4.08	17.76	21.84	14.54		200.20	170.65	$100,100		0.06		37.40	162.80		114.22	133.28	133.28
Project-A02		v002		0.30	3.08				15.00	19.20	34.20	50.11		3.60	80.00	83.60	25.98		3.60	19.20	22.80	12.03		3.60	19.20	22.80	12.03		3.60	19.20	22.80	12.03		3.60	19.20	22.80	12.03		209.00	124.19	$104,500		0.06		33.00	176.00		110.24	57.16	110.24					E
Project-A03		v003		0.20	0.62				16.00	6.48	22.48	80.37		3.84	27.00	30.84	43.81		3.84	6.48	10.32	19.29		3.84	6.48	10.32	19.29		3.84	6.48	10.32	19.29		3.84	6.48	10.32	19.29		94.60	201.33	$47,300		0.03		35.20	59.40		176.81	96.38	176.81					N
Project-A04		v004		0.52	0.27				35.00	4.32	39.32	67.92		8.40	18.00	26.40	66.99		8.40	4.32	12.72	16.30		8.40	4.32	12.72	16.30		8.40	4.32	12.72	16.30		8.40	4.32	12.72	16.30		116.60	200.12	$58,300		0.03		77.00	39.60		149.43	147.37	149.43					D
Project-A05		v002		0.13	2.93				6.00	19.20	25.20	46.10		1.44	80.00	81.44	27.31		1.44	19.20	20.64	11.07		1.44	19.20	20.64	11.07		1.44	19.20	20.64	11.07		1.44	19.20	20.64	11.07		189.20	117.67	$94,600		0.05		13.20	176.00		101.43	60.08	101.43
Project-A06		v003		0.25	0.97				52.00	10.56	62.56	206.11		12.48	44.00	56.48	49.47		12.48	10.56	23.04	49.47		12.48	10.56	23.04	49.47		12.48	10.56	23.04	49.47		12.48	10.56	23.04	49.47		211.20	453.44	$105,600		0.06		114.40	96.80		453.44	100.22	453.44					O
Project-A07		v005		1.22	3.40				93.00	19.92	112.92	76.50		22.32	83.00	105.32	24.38		22.32	19.92	42.24	18.36		22.32	19.92	42.24	18.36		22.32	19.92	42.24	18.36		22.32	19.92	42.24	18.36		387.20	174.32	$193,600		0.11		204.60	182.60		168.30	53.64	168.30					F
Project-A08		v006		0.61	0.91				5.00	2.64	7.64	8.15		1.20	11.00	12.20	12.14		1.20	2.64	3.84	2.91		1.20	2.64	3.84	2.91		1.20	2.64	3.84	2.91		1.20	2.64	3.84	2.91		35.20	31.95	$17,600		0.01		11.00	24.20		17.93	26.71	26.71
Project-A09		v003		0.47	0.75				49.00	20.64	69.64	103.48		11.76	86.00	97.76	115.34		11.76	20.64	32.40	27.68		11.76	20.64	32.40	27.68		11.76	20.64	32.40	27.68		11.76	20.64	32.40	27.68		297.00	329.54	$148,500		0.08		107.80	189.20		227.65	253.75	253.75					T
Project-A10		v001		0.73	2.00				36.00	20.88	56.88	49.10		8.64	87.00	95.64	43.41		8.64	20.88	29.52	11.78		8.64	20.88	29.52	11.78		8.64	20.88	29.52	11.78		8.64	20.88	29.52	11.78		270.60	139.66	$135,300		0.08		79.20	191.40		108.03	95.51	108.03					H
Project-A11		v002		0.72	2.20				63.00	19.20	82.20	87.88		15.12	80.00	95.12	36.31		15.12	19.20	34.32	21.09		15.12	19.20	34.32	21.09		15.12	19.20	34.32	21.09		15.12	19.20	34.32	21.09		314.60	208.57	$157,300		0.09		138.60	176.00		193.35	79.88	193.35					I
Project-A12		v004		0.86	3.80				65.00	21.84	86.84	75.37		15.60	91.00	106.60	23.93		15.60	21.84	37.44	18.09		15.60	21.84	37.44	18.09		15.60	21.84	37.44	18.09		15.60	21.84	37.44	18.09		343.20	171.65	$171,600		0.10		143.00	200.20		165.81	52.64	165.81					S
Project-A13		v007		0.34	0.31				96.00	9.60	105.60	279.50		23.04	40.00	63.04	129.25		23.04	9.60	32.64	67.08		23.04	9.60	32.64	67.08		23.04	9.60	32.64	67.08		23.04	9.60	32.64	67.08		299.20	677.07	$149,600		0.08		211.20	88.00		614.89	284.35	614.89
Project-A14		v006		0.42	0.28				39.00	12.72	51.72	93.84		9.36	53.00	62.36	191.14		9.36	12.72	22.08	45.87		9.36	12.72	22.08	45.87		9.36	12.72	22.08	45.87		9.36	12.72	22.08	45.87		202.40	468.47	$101,200		0.06		85.80	116.60		206.45	420.50	420.50					W
Project-A15		v008		0.90	1.27				72.00	23.76	95.76	79.81		17.28	99.00	116.28	78.19		17.28	23.76	41.04	19.16		17.28	23.76	41.04	19.16		17.28	23.76	41.04	19.16		17.28	23.76	41.04	19.16		376.20	234.63	$188,100		0.11		158.40	217.80		175.59	172.03	175.59					O
					R
					K
		Average		0.53	1.60				43.93	15.25	59.18	90.41		10.54	63.53	74.08	61.88		10.54	15.25	25.79	23.65		10.54	15.25	25.79	23.65		10.54	15.25	25.79	23.65		10.54	15.25	25.79	23.65		236.43	246.88	$118,213		0.07		96.65	139.77	Average	198.90	135.57	216.77					S
		Total		8.00	24.00				659.00	228.72	887.72	1356.16		158.16	953.00	1111.16	928.23		158.16	228.72	386.88	354.71		158.16	228.72	386.88	354.71		158.16	228.72	386.88	354.71		158.16	228.72	386.88	354.71		3546.40	3703.25	$1,773,200		1.00		1449.80	2096.60	Total	2983.55	2033.50	3251.55					H
					E
		Available FTE		8	24					E
					T

		END	OF	THIS	WORKSHEET

## Project_Release_Optimizer_(GA)
Legend:		Fitness Control Dashboard
Chromosome		Fitness Breakdown		Fitness Priority	Formula		Value					Benchmark
Constraint (Hard)		Proj Make-Span (Overall)		Medium	=AW15		1200.47		<- To shorten entire projects span (ALL projects)					Perfect AVG Project Span
Constraint (Soft)		Average Proj Make-Span (Individual)		Medium	=AV32		557.68		<- To shorten average individual project span				<---------->	216.7699676114
Fitness		Priority-Weighted Plan-Lead		Low	=AT32		169.59		<- To schedule important projects to start earlier
User Inputs		Code-Base Violation x Weight		High	='Code Base Violation Constraint'!E13*20		0.00		<- Heuristic Weight (Hard -> Soft constraint):			50
Formula		Integrated Fitness - To Min()		N.A.	=SUM(I4:I7)		1927.74		<- To Minimize
		Code-Base constraint satisfied ?		TRUE

Vlookup Index	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	38	39	49	50	51	52	53	54	55	56	57	58	59	60	61	62

		Resource Allocation / Full Time Employee (FTEs)					Plan Phase (Calendar-Day)				Development Phase (Calendar-Day)				SIT Phase (Calendar-Day)				UAT Phase (Calendar-Day)				NFT Phase (Calendar-Day)				Prod Phase (Calendar-Day)					Fitness - Lead / Idle Time (Days) prior to:					Fitness - Project Make-Sapn (Days) / (Without Plan-Lead)			Constraint (Hard -> Soft) - Code-Base Version violation detection (SIT/UAT/NFT/Prod only)
Project Name		Knowledge / Engineer	Software / Engineer	Project Manager / (Future work)	Admin / (Future work)		Initial Date		Lead prior to Plan / (Calendar-Day)	Start Date	End Date		Lead prior to Development / (Calendar-Day)	Start Date	End Date		Lead prior to SIT / (Calendar-Day)	Start Date	End Date		Lead prior to UAT / (Calendar-Day)	Start Date	End Date		Lead prior to NFT / (Calendar-Day)	Start Date	End Date		Lead prior to Prod / (Calendar-Day)	Start Date	End Date		Code Base Version		Project Priority		Plan	Development	SIT	UAT	NFT	Prod	Total	Priority-Weighted Plan-Lead		Individual	Overall		Refer to worksheet: Code Base Violation Constraint
Project-A01		0.33	1.22				01-Jan-2014		312	10-Nov-2014	31-Dec-2014		0	01-Jan-2015	03-Mar-2015		0	04-Mar-2015	19-Mar-2015		81	09-Jun-2015	23-Jun-2015		15	09-Jul-2015	24-Jul-2015		8	02-Aug-2015	16-Aug-2015		v001		0.06		312	0	0	81	15	8	416	264.19		279.65	1200.47					E
Project-A02		0.30	3.08				01-Jan-2014		0	02-Jan-2014	21-Feb-2014		0	22-Feb-2014	20-Mar-2014		0	21-Mar-2014	02-Apr-2014		7	10-Apr-2014	22-Apr-2014		11	04-May-2014	16-May-2014		21	07-Jun-2014	19-Jun-2014		v002		0.06		0	0	0	7	11	21	39	0.00		168.19					N
Project-A03		0.20	0.62				01-Jan-2014		140	22-May-2014	10-Aug-2014		0	11-Aug-2014	24-Sep-2014		0	25-Sep-2014	14-Oct-2014		2	17-Oct-2014	05-Nov-2014		2	08-Nov-2014	28-Nov-2014		2	01-Dec-2014	20-Dec-2014		v003		0.03		140	0	0	2	2	2	146	56.02		212.33					D
Project-A04		0.52	0.27				01-Jan-2014		58	01-Mar-2014	07-May-2014		0	08-May-2014	14-Jul-2014		0	15-Jul-2014	01-Aug-2014		6	08-Aug-2014	24-Aug-2014		776	09-Oct-2016	25-Oct-2016		24	19-Nov-2016	06-Dec-2016		v004		0.03		58	0	0	6	776	24	864	28.60		1011.12
Project-A05		0.13	2.93				01-Jan-2014		1	03-Jan-2014	18-Feb-2014		0	19-Feb-2014	18-Mar-2014		0	19-Mar-2014	30-Mar-2014		395	30-Apr-2015	11-May-2015		5	17-May-2015	28-May-2015		24	22-Jun-2015	03-Jul-2015		v002		0.05		1	0	0	395	5	24	425	0.80		546.67					O
Project-A06		0.25	0.97				01-Jan-2014		7	09-Jan-2014	03-Aug-2014		0	04-Aug-2014	22-Sep-2014		0	23-Sep-2014	12-Nov-2014		11	24-Nov-2014	12-Jan-2015		17	30-Jan-2015	20-Mar-2015		3	24-Mar-2015	13-May-2015		v003		0.06		7	0	0	11	17	3	38	6.25		489.44					F
Project-A07		1.22	3.40				01-Jan-2014		544	30-Jun-2015	14-Sep-2015		0	15-Sep-2015	09-Oct-2015		0	10-Oct-2015	29-Oct-2015		259	15-Jul-2016	02-Aug-2016		2	05-Aug-2016	23-Aug-2016		27	20-Sep-2016	09-Oct-2016		v005		0.11		544	0	0	259	2	27	832	890.92		467.32
Project-A08		0.61	0.91				01-Jan-2014		101	13-Apr-2014	21-Apr-2014		0	22-Apr-2014	04-May-2014		0	05-May-2014	08-May-2014		4	13-May-2014	16-May-2014		215	18-Dec-2014	21-Dec-2014		30	21-Jan-2015	23-Jan-2015		v006		0.01		101	0	0	4	215	30	350	15.04		285.95					T
Project-A09		0.47	0.75				01-Jan-2014		7	09-Jan-2014	22-Apr-2014		0	23-Apr-2014	16-Aug-2014		0	17-Aug-2014	14-Sep-2014		41	26-Oct-2014	23-Nov-2014		29	23-Dec-2014	19-Jan-2015		9	29-Jan-2015	26-Feb-2015		v003		0.08		7	0	0	41	29	9	86	8.79		413.54					H
Project-A10		0.73	2.00				01-Jan-2014		4	06-Jan-2014	24-Feb-2014		0	25-Feb-2014	09-Apr-2014		0	10-Apr-2014	22-Apr-2014		4	27-Apr-2014	09-May-2014		22	01-Jun-2014	12-Jun-2014		10	23-Jun-2014	05-Jul-2014		v001		0.08		4	0	0	4	22	10	40	4.58		180.66					I
Project-A11		0.72	2.20				01-Jan-2014		230	20-Aug-2014	15-Nov-2014		0	16-Nov-2014	23-Dec-2014		0	24-Dec-2014	14-Jan-2015		520	18-Jun-2016	09-Jul-2016		45	24-Aug-2016	14-Sep-2016		143	05-Feb-2017	26-Feb-2017		v002		0.09		230	0	0	520	45	143	938	306.05		921.57					S
Project-A12		0.86	3.80				01-Jan-2014		518	04-Jun-2015	18-Aug-2015		0	19-Aug-2015	12-Sep-2015		0	13-Sep-2015	01-Oct-2015		2	04-Oct-2015	22-Oct-2015		106	06-Feb-2016	24-Feb-2016		12	08-Mar-2016	26-Mar-2016		v004		0.10		518	0	0	2	106	12	638	751.94		296.65
Project-A13		0.34	0.31				01-Jan-2014		103	15-Apr-2014	19-Jan-2015		0	20-Jan-2015	29-May-2015		0	30-May-2015	05-Aug-2015		156	09-Jan-2016	16-Mar-2016		6	23-Mar-2016	29-May-2016		21	20-Jun-2016	27-Aug-2016		v007		0.08		103	0	0	156	6	21	286	130.35		865.07					W
Project-A14		0.42	0.28				01-Jan-2014		92	04-Apr-2014	06-Jul-2014		0	07-Jul-2014	14-Jan-2015		0	15-Jan-2015	02-Mar-2015		0	03-Mar-2015	18-Apr-2015		618	27-Dec-2016	11-Feb-2017		17	01-Mar-2017	16-Apr-2017		v006		0.06		92	0	0	0	618	17	727	78.76		1108.47					O
Project-A15		0.90	1.27				01-Jan-2014		1	03-Jan-2014	23-Mar-2014		0	24-Mar-2014	11-Jun-2014		0	12-Jun-2014	01-Jul-2014		686	18-May-2016	06-Jun-2016		3	10-Jun-2016	29-Jun-2016		190	06-Jan-2017	25-Jan-2017		v008		0.11		1	0	0	686	3	190	880	1.59		1118.63					R
							K
							S
Average		0.53	1.60					141				0				0				145				125				36					0.07		141	0	0	145	125	36	447	169.59	Average	557.68					H
Total		8.00	24.00					2118				0				0				2174				1872				541					1.00		2118	0	0	2174	1872	541	6705	2543.88	Total	8365.25					E
		<=	<=					E
Available FTE		8	24					Priority Factor					T
							15.00

		END	OF	THIS	WORKSHEET

## Code_Base_Violation_Constraint
Legend:
Chromosome
Constraint (Hard)
Constraint (Soft)
Fitness
User Inputs
Formula

Constraint (Hard -> Soft) - Code-Base Version violation detection (applicable to SIT/UAT/NFT/Prod only) / Projects with different Code-Base versions cannot co-eixit in the same testing environment, say SIT, at the same time.

Total - Violation / (SIT/UAT/NFT/Prod)	Count:	0
	Days:	0.00

					E
					N
SIT - Violation	Count:	0			Compare Roll Project against Column Project, to check violation.					D
	Days:	0.00
					Count					Days (Overlap) simplified rough formula					O
Project Name	Start Date	End Date	Code Base Version		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15					F
Project-A01	04-Mar-2015	19-Mar-2015	v001			0	0	0	0	0	0	0	0	0	0	0	0	0	0			0	0	0	0	0	0	0	0	0	0	0	0	0	0
Project-A02	21-Mar-2014	02-Apr-2014	v002				0	0	0	0	0	0	0	0	0	0	0	0	0				0	0	0	0	0	0	0	0	0	0	0	0	0					T
Project-A03	25-Sep-2014	14-Oct-2014	v003					0	0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0	0					H
Project-A04	15-Jul-2014	01-Aug-2014	v004					0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0					I
Project-A05	19-Mar-2014	30-Mar-2014	v002					0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0					S
Project-A06	23-Sep-2014	12-Nov-2014	v003					0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0
Project-A07	10-Oct-2015	29-Oct-2015	v005					0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0					W
Project-A08	05-May-2014	08-May-2014	v006					0	0	0	0	0	0	0					0	0	0	0	0	0	0					O
Project-A09	17-Aug-2014	14-Sep-2014	v003					0	0	0	0	0	0					0	0	0	0	0	0					R
Project-A10	10-Apr-2014	22-Apr-2014	v001					0	0	0	0	0					0	0	0	0	0					K
Project-A11	24-Dec-2014	14-Jan-2015	v002					0	0	0	0					0	0	0	0					S
Project-A12	13-Sep-2015	01-Oct-2015	v004					0	0	0					0	0	0					H
Project-A13	30-May-2015	05-Aug-2015	v007					0	0					0	0					E
Project-A14	15-Jan-2015	02-Mar-2015	v006					0					0					E
Project-A15	12-Jun-2014	01-Jul-2014	v008					T

UAT - Violation	Count:	0			Compare Roll Project against Column Project, to check violation.
	Days:	0.00
					Count					Days (Overlap) simplified rough formula
Project Name	Start Date	End Date	Code Base Version		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15
Project-A01	09-Jun-2015	23-Jun-2015	v001			0	0	0	0	0	0	0	0	0	0	0	0	0	0			0	0	0	0	0	0	0	0	0	0	0	0	0	0
Project-A02	10-Apr-2014	22-Apr-2014	v002				0	0	0	0	0	0	0	0	0	0	0	0	0				0	0	0	0	0	0	0	0	0	0	0	0	0
Project-A03	17-Oct-2014	05-Nov-2014	v003					0	0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0	0
Project-A04	08-Aug-2014	24-Aug-2014	v004					0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0
Project-A05	30-Apr-2015	11-May-2015	v002					0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0
Project-A06	24-Nov-2014	12-Jan-2015	v003					0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0
Project-A07	15-Jul-2016	02-Aug-2016	v005					0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0
Project-A08	13-May-2014	16-May-2014	v006					0	0	0	0	0	0	0					0	0	0	0	0	0	0
Project-A09	26-Oct-2014	23-Nov-2014	v003					0	0	0	0	0	0					0	0	0	0	0	0
Project-A10	27-Apr-2014	09-May-2014	v001					0	0	0	0	0					0	0	0	0	0
Project-A11	18-Jun-2016	09-Jul-2016	v002					0	0	0	0					0	0	0	0
Project-A12	04-Oct-2015	22-Oct-2015	v004					0	0	0					0	0	0
Project-A13	09-Jan-2016	16-Mar-2016	v007					0	0					0	0
Project-A14	03-Mar-2015	18-Apr-2015	v006					0					0
Project-A15	18-May-2016	06-Jun-2016	v008

NFT - Violation	Count:	0			Compare Roll Project against Column Project, to check violation.
	Days:	0.00
					Count					Days (Overlap) simplified rough formula
Project Name	Start Date	End Date	Code Base Version		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15
Project-A01	09-Jul-2015	24-Jul-2015	v001			0	0	0	0	0	0	0	0	0	0	0	0	0	0			0	0	0	0	0	0	0	0	0	0	0	0	0	0
Project-A02	04-May-2014	16-May-2014	v002				0	0	0	0	0	0	0	0	0	0	0	0	0				0	0	0	0	0	0	0	0	0	0	0	0	0
Project-A03	08-Nov-2014	28-Nov-2014	v003					0	0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0	0
Project-A04	09-Oct-2016	25-Oct-2016	v004					0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0
Project-A05	17-May-2015	28-May-2015	v002					0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0
Project-A06	30-Jan-2015	20-Mar-2015	v003					0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0
Project-A07	05-Aug-2016	23-Aug-2016	v005					0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0
Project-A08	18-Dec-2014	21-Dec-2014	v006					0	0	0	0	0	0	0					0	0	0	0	0	0	0
Project-A09	23-Dec-2014	19-Jan-2015	v003					0	0	0	0	0	0					0	0	0	0	0	0
Project-A10	01-Jun-2014	12-Jun-2014	v001					0	0	0	0	0					0	0	0	0	0
Project-A11	24-Aug-2016	14-Sep-2016	v002					0	0	0	0					0	0	0	0
Project-A12	06-Feb-2016	24-Feb-2016	v004					0	0	0					0	0	0
Project-A13	23-Mar-2016	29-May-2016	v007					0	0					0	0
Project-A14	27-Dec-2016	11-Feb-2017	v006					0					0
Project-A15	10-Jun-2016	29-Jun-2016	v008

Prod - Violation	Count:	0			Compare Roll Project against Column Project, to check violation.
	Days:	0.00
					Count					Days (Overlap) simplified rough formula
Project Name	Start Date	End Date	Code Base Version		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15		P-A01	P-A02	P-A03	P-A04	P-A05	P-A06	P-A07	P-A08	P-A09	P-A10	P-A11	P-A12	P-A13	P-A14	P-A15
Project-A01	02-Aug-2015	16-Aug-2015	v001			0	0	0	0	0	0	0	0	0	0	0	0	0	0			0	0	0	0	0	0	0	0	0	0	0	0	0	0
Project-A02	07-Jun-2014	19-Jun-2014	v002				0	0	0	0	0	0	0	0	0	0	0	0	0				0	0	0	0	0	0	0	0	0	0	0	0	0
Project-A03	01-Dec-2014	20-Dec-2014	v003					0	0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0	0
Project-A04	19-Nov-2016	06-Dec-2016	v004					0	0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0	0
Project-A05	22-Jun-2015	03-Jul-2015	v002					0	0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0	0
Project-A06	24-Mar-2015	13-May-2015	v003					0	0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0	0
Project-A07	20-Sep-2016	09-Oct-2016	v005					0	0	0	0	0	0	0	0					0	0	0	0	0	0	0	0
Project-A08	21-Jan-2015	23-Jan-2015	v006					0	0	0	0	0	0	0					0	0	0	0	0	0	0
Project-A09	29-Jan-2015	26-Feb-2015	v003					0	0	0	0	0	0					0	0	0	0	0	0
Project-A10	23-Jun-2014	05-Jul-2014	v001					0	0	0	0	0					0	0	0	0	0
Project-A11	05-Feb-2017	26-Feb-2017	v002					0	0	0	0					0	0	0	0
Project-A12	08-Mar-2016	26-Mar-2016	v004					0	0	0					0	0	0
Project-A13	20-Jun-2016	27-Aug-2016	v007					0	0					0	0
Project-A14	01-Mar-2017	16-Apr-2017	v006					0					0
Project-A15	06-Jan-2017	25-Jan-2017	v008

	END	OF	THIS	WORKSHEET

## Random_Number
Random	x100	Interger
0.0766821471	7.668214713	7
0.3176545454	31.765454537	31
0.6817685865	68.1768586521	68
0.1235684901	12.3568490118	12
0.1718540429	17.1854042881	17
0.5312699046	53.1269904572	53
0.9362513511	93.6251351107	93
0.9052406809	90.524068092	90
0.2842555045	28.4255504516	28
0.1754800845	17.548008448	17
0.6828028648	68.2802864785	68
0.4518844874	45.1884487422	45
0.3194566504	31.9456650411	31
0.330752873	33.0752873028	33
0.3470385483	34.7038548264	34
0.1771307136	17.7130713582	17
0.905162077	90.5162077049	90
0.5966726295	59.667262955	59
0.3019386108	30.1938610772	30
0.7859045389	78.5904538931	78
0.7734086192	77.3408619226	77
0.4077489548	40.7748954756	40
0.1791259358	17.9125935767	17
0.4649179	46.4917900001	46
0.5284471215	52.8447121528	52
0.5785519812	57.8551981221	57
0.3268706665	32.6870666517	32
0.5558839606	55.588396062	55
0.628189968	62.8189968035	62
0.8813788842	88.1378884241	88
0.9992876705	99.9287670459	99
0.4066462786	40.664627858	40
0.0399017461	3.9901746081	3
0.7130976044	71.3097604449	71
0.9511690772	95.1169077166	95
0.149541715	14.9541714954	14
0.0112389566	1.123895656	1
0.8765412755	87.6541275474	87
0.6658338691	66.5833869128	66

## _PalUtilTempWorksheet
0

## ev_HiddenInfo
Goal (Cell, Statistic, Parameter), E1: RO Formula to Optimize	1927.74				MACROS			Compatibility with Old Versions (4 trips pre-v5 versions)	4		RISKOpt Tag	TRUE		Out. Stats
Goal (Type, Target Value)	1	0			Start (enabled, macro)	FALSE		Formula Conversion Cell (not used in v5)			#Iterations (Sim Stopping)			Mean			Creation Version	5.5.0		Constraint Solver, number of Latin Hypercube stratifications, for reproducing results with Actual Convergence
Trial Count Stopping (enabled, trial count)	FALSE	5000000000000			Before Recalc (enabled, macro)	FALSE		Number Formatting Cell (introduced in v5)	365		Sim. Stopping Mode, Tolerance			Std. Dev.			Required Version	5.0.0		Constraint Solver, total of adjustable cell values, to only pass number of stratifications if model hasn't changed
Timespan Stopping (enabled, trial count)	TRUE	10	2		After Recalc (enabled, macro)	FALSE					Same Seed Each Simulation			Min			Recommended Version	4.0.0
Progress Stopping (enabled, trial count, max % change, change is percent)	FALSE	1000000000	1E-10	TRUE	After Storage (enabled, macro)	FALSE					Sampling Type			Max			Last Modified by Version	5.5.0
Formula Stopping (enabled, formula)	FALSE	0			Finish (enabled, macro)	FALSE					Macro Before Simulation (enabled, macro)
Population Size	500										Macro After Simulation (enabled, macro)
UNUSED	UNUSED				Seed (Is Auto, Value)	TRUE	1
Ev4/RO1: Update Display (replaced by Show Excel Recalcs in v5)	3				Minimize Excel on Startup	FALSE
Stop on Errors (before v5: Pause on Errors)	FALSE
Keep Trial-by-Trial Log (if cell has anything other than False consider True, since Evolver 4 didn't have this setting)	FALSE
Ev4/RO1: Graph Progress	FALSE				Show Excel Recalcs (replaces "Update Display" used before v5)	2

# Chromosomes	1																		# Constraints	2
Method + #Operators	Mutation Rate	Crossover Rate	Description	# Time Blocks/All Groups Must Be Present	Constraint Range	#Ranges	Adj. Range	Min Val or Range	Max Val Or Range	Flags									HARD CONSTRAINT DEV	CONSTRAINT SOLVER	ROFUNC	RISKOPT	SOFT CONSTRAINT DEV	EVAL (True/False or penalty)	Type (Hard/Soft)	Entry Mode	Formula	Description	Left Val Or Range	Left Operator	Constrained Cells	Right Operator	Right Val Or Range	Penalty Function	RO Eval Time (Iter/Sim)	RO Statistic to Constrain	RO Statistic Parameter
RECIPE11	0.5	0.5				2	#VALUE!	0.25	5	False,False,False									2	1		Max 8 KE FTEs	0	6	8.00	2	8
DEFAULT PARENT SELECTION							Err:509	0	365	True,False,False									2	1		Max 24 SE FTEs	0	6	24.00	2	24
DEFAULT MUTATION
DEFAULT CROSSOVER
DEFAULT BACKTRACK
ARITHMETIC CROSSOVER
HEURISTIC CROSSOVER
CAUCHY MUTATION
BOUNDARY MUTATION
NON-UNIFORM MUTATION
LINEAR
LOCAL SEARCH

## Project_Release_Optimizer_(NLP-Solver)
Legend:		Fitness Control Dashboard
Chromosome		Fitness Breakdown		Fitness Priority	Formula		Value					Benchmark
Constraint (Hard)		Proj Make-Span (Overall)		Medium	'=Project_Release_Optimizer_(GA).AW15		1200.47		<- To shorten entire projects span (ALL projects)					Perfect AVG Project Span
Constraint (Soft)		Average Proj Make-Span (Individual)		Medium	'=Project_Release_Optimizer_(GA).AV32		557.68		<- To shorten average individual project span				<---------->	216.77
Fitness		Priority-Weighted Plan-Lead		Low	'=Project_Release_Optimizer_(GA).AT32		169.59		<- To schedule important projects to start earlier
User Inputs		Code-Base Violation x Weight		High	'='Code Base Violation Constraint'!E13*20		0.00		<- Heuristic Weight (Hard -> Soft constraint):			50
Formula		Integrated Fitness - To Min()		N.A.	'=Project_Release_Optimizer_(GA).SUM(I4:I7) + F36		1928.15		<- To Minimize
		Code-Base constraint satisfied ?		TRUE

Vlookup Index	2	3	4	5	6	7	8	9	10	11	12	13	14	15	16	17	18	19	20	21	22	23	24	25	26	27	28	29	30	31	32	33	34	35	36	37	38	39	40	41	42	43	44	45	46	38	39	49	50	51	52	53	54	55	56	57	58	59	60	61	62

		Resource Allocation / Full Time Employee (FTEs)
Project Name		Knowledge / Engineer	Software Engineer	Lead prior to Plan / (Calendar-Day)	Lead prior to UAT / (Calendar-Day)	Lead prior to NFT / (Calendar-Day)	Lead prior to Prod / (Calendar-Day)
Project-A01		0.33	1.22	312	81	15	8
Project-A02		0.30	3.08	0	7	11	21
Project-A03		0.20	0.62	140	2	2	2
Project-A04		0.52	0.27	58	6	776	24
Project-A05		0.13	2.93	1	395	5	24
Project-A06		0.25	0.97	7	11	17	3
Project-A07		1.22	3.40	544	259	2	27
Project-A08		0.61	0.91	101	4	215	30
Project-A09		0.47	0.75	7	41	29	9
Project-A10		0.73	2.00	4	4	22	10
Project-A11		0.72	2.20	230	520	45	143
Project-A12		0.86	3.80	518	2	106	12
Project-A13		0.34	0.31	103	156	6	21
Project-A14		0.42	0.28	92	0	618	17
Project-A15		0.90	1.27	1	686	3	190

Average		0.53	1.60	141	145	125	36
Total		8.00	24.00	2118	2174	1872	541
		<=	<=
Available FTE		8	24
		9.99844965452468E-05	0.0003105275	0.4105120431

		END	OF	THIS	WORKSHEET